## pivot
Sum of Contract Value | Column Labels
Row Labels | BB | S | (blank) | Grand Total
Mobilisation | 22600000 | 22600000 |  | 45200000
NR Imm |  | 3000000 |  | 3000000
Off Street - Other | 37658464.3266 | 29101316.7198 |  | 66759781.0464
Off Street Depot | 9013373.7954 | 3953691.5408 |  | 12967065.3362
On Street - Other | 19208894.1143 | 15451911.2198 |  | 34660805.3341
On Street - Princes St | 1529441.7678 | 2137776.2849 |  | 3667218.0527
Prelims | 30774220.5241 | 13533246.0568 |  | 44307466.5808
SDS Interface |  | 3800000 |  | 3800000
Sectional Completion | 2400000 | 2400000 |  | 4800000
(blank) |  |  | 0 | 0
Grand Total | 123184394.5282 | 95977941.8221 | 0 | 219162336.3503

## Data
[5 empty] | 123184394 | BB |  | 123184394.5282
[5 empty] | 95977942 | S |  | 95977941.8221
[5 empty] | 219162336 | Total |  | 219162336.3503
[8 empty] | 219162336.3503 | 87291002.7749
L4 | L5 | Activity ID | Activity Name | Type iii | Type i | Type ii | Contractor | Contract Value | COWD to P11
0
0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
Mobilisation | [7 empty] | 0 | 0
Mobilisation | Mobilisation | [6 empty] | 0 | 0
Mobilisation | Mobilisation | 00A | Contract Award | Mobilisation | Prelims | Mobilisation | BB | 19100000 | 19100000
Mobilisation | Mobilisation | 00A | Contract Award | Mobilisation | Prelims | Mobilisation | S | 19100000 | 19100000
Mobilisation | Mobilisation | 00B | Period 1 Payment | Mobilisation | Prelims | Mobilisation | BB | 3500000 | 3500000
Mobilisation | Mobilisation | 00C | Period 2 Payment | Mobilisation | Prelims | Mobilisation | S | 3500000 | 3500000
Preliminaries | Preliminaries | [6 empty] | 0 | 0
Preliminaries | Preliminaries | Mth 1 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 539898.6029 | 539898.6029
Preliminaries | Preliminaries | Mth 2 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 539898.6029 | 539898.6029
Preliminaries | Preliminaries | Mth 3 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 539898.6029 | 539898.6029
Preliminaries | Preliminaries | Mth 4 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 539898.6029 | 539898.6029
Preliminaries | Preliminaries | Mth 5 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 539898.6029 | 539898.6029
Preliminaries | Preliminaries | Mth 6 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 539898.6029 | 539898.6029
Preliminaries | Preliminaries | Mth 7 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 1027883.703 | 1027883.703
Preliminaries | Preliminaries | Mth 8 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 1027883.703 | 1027883.703
Preliminaries | Preliminaries | Mth 9 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 1027883.703 | 1027883.703
Preliminaries | Preliminaries | Mth 10 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 1027883.703 | 1027883.703
Preliminaries | Preliminaries | Mth 11 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 1027883.703 | 1027883.703
Preliminaries | Preliminaries | Mth 12 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 1027883.703 | 1027883.703
Preliminaries | Preliminaries | Mth 13 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 1027883.703 | 1027883.703
Preliminaries | Preliminaries | Mth 14 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 1027883.703 | 1027883.703
Preliminaries | Preliminaries | Mth 15 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 1027883.703 | 1027883.703
Preliminaries | Preliminaries | Mth 16 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 1027883.703 | 1027883.703
Preliminaries | Preliminaries | Mth 17 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 1027883.703 | 1027883.703
Preliminaries | Preliminaries | Mth 18 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 1027883.703 | 1027883.703
Preliminaries | Preliminaries | Mth 19 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 1027883.703 | 1027883.703
Preliminaries | Preliminaries | Mth 20 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 1027883.703 | 1027883.703
Preliminaries | Preliminaries | Mth 21 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 1027883.703 | 1027883.703
Preliminaries | Preliminaries | Mth 22 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 1027883.703 | 1027883.703
Preliminaries | Preliminaries | Mth 23 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 1027883.703 | 1027883.703
Preliminaries | Preliminaries | Mth 24 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 1027883.703 | 0
Preliminaries | Preliminaries | Mth 25 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 1027883.703 | 0
Preliminaries | Preliminaries | Mth 26 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 1027883.703 | 0
Preliminaries | Preliminaries | Mth 27 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 1027883.703 | 0
Preliminaries | Preliminaries | Mth 28 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 1027883.703 | 0
Preliminaries | Preliminaries | Mth 29 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 487985.1052 | 0
Preliminaries | Preliminaries | Mth 30 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 487985.1052 | 0
Preliminaries | Preliminaries | Mth 31 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 487985.1052 | 0
Preliminaries | Preliminaries | Mth 32 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 487985.1052 | 0
Preliminaries | Preliminaries | Mth 33 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 296944.7019 | 0
Preliminaries | Preliminaries | Mth 34 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 296944.7019 | 0
Preliminaries | Preliminaries | Mth 35 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 296944.7019 | 0
Preliminaries | Preliminaries | Mth 36 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 296944.7019 | 0
Preliminaries | Preliminaries | Mth 37 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 296944.7019 | 0
Preliminaries | Preliminaries | Mth 38 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 296944.7019 | 0
Preliminaries | Preliminaries | Mth 39 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 296944.7019 | 0
Preliminaries | Preliminaries | Mth 40 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 296944.7019 | 0
Preliminaries | Preliminaries | Mth 41 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 296944.7019 | 0
Preliminaries | Preliminaries | Mth 42 | Preliminaries - Bilfinger Berger | Prelims | Prelims | Prelims | BB | 296944.7019 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
Preliminaries | [7 empty] | 0 | 0
Preliminaries | Preliminaries | [6 empty] | 0 | 0
Preliminaries | Preliminaries | Mth 1 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 232162.2065 | 232162.2065
Preliminaries | Preliminaries | Mth 2 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 232162.2065 | 232162.2065
Preliminaries | Preliminaries | Mth 3 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 232162.2065 | 232162.2065
Preliminaries | Preliminaries | Mth 4 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 232162.2065 | 232162.2065
Preliminaries | Preliminaries | Mth 5 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 232162.2065 | 232162.2065
Preliminaries | Preliminaries | Mth 6 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 232162.2065 | 232162.2065
Preliminaries | Preliminaries | Mth 7 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 442001.4606 | 442001.4606
Preliminaries | Preliminaries | Mth 8 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 442001.4606 | 442001.4606
Preliminaries | Preliminaries | Mth 9 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 442001.4606 | 442001.4606
Preliminaries | Preliminaries | Mth 10 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 442001.4606 | 442001.4606
Preliminaries | Preliminaries | Mth 11 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 442001.4606 | 442001.4606
Preliminaries | Preliminaries | Mth 12 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 442001.4606 | 442001.4606
Preliminaries | Preliminaries | Mth 13 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 442001.4606 | 442001.4606
Preliminaries | Preliminaries | Mth 14 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 442001.4606 | 442001.4606
Preliminaries | Preliminaries | Mth 15 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 442001.4606 | 442001.4606
Preliminaries | Preliminaries | Mth 16 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 442001.4606 | 442001.4606
Preliminaries | Preliminaries | Mth 17 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 442001.4606 | 442001.4606
Preliminaries | Preliminaries | Mth 18 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 442001.4606 | 442001.4606
Preliminaries | Preliminaries | Mth 19 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 442001.4606 | 442001.4606
Preliminaries | Preliminaries | Mth 20 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 442001.4606 | 442001.4606
Preliminaries | Preliminaries | Mth 21 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 442001.4606 | 442001.4606
Preliminaries | Preliminaries | Mth 22 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 442001.4606 | 442001.4606
Preliminaries | Preliminaries | Mth 23 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 442001.4606 | 442001.4606
Preliminaries | Preliminaries | Mth 24 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 442001.4606 | 0
Preliminaries | Preliminaries | Mth 25 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 442001.4606 | 0
Preliminaries | Preliminaries | Mth 26 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 442001.4606 | 0
Preliminaries | Preliminaries | Mth 27 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 442001.4606 | 0
Preliminaries | Preliminaries | Mth 28 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 442001.4606 | 0
Preliminaries | Preliminaries | Mth 29 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 209839.2541 | 0
Preliminaries | Preliminaries | Mth 30 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 209839.2541 | 0
Preliminaries | Preliminaries | Mth 31 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 209839.2541 | 0
Preliminaries | Preliminaries | Mth 32 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 209839.2541 | 0
Preliminaries | Preliminaries | Mth 33 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 157688.367 | 0
Preliminaries | Preliminaries | Mth 34 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 157688.367 | 0
Preliminaries | Preliminaries | Mth 35 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 157688.367 | 0
Preliminaries | Preliminaries | Mth 36 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 157688.367 | 0
Preliminaries | Preliminaries | Mth 37 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 157688.367 | 0
Preliminaries | Preliminaries | Mth 38 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 157688.367 | 0
Preliminaries | Preliminaries | Mth 39 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 157688.367 | 0
Preliminaries | Preliminaries | Mth 40 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 157688.367 | 0
Preliminaries | Preliminaries | Mth 41 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 157688.367 | 0
Preliminaries | Preliminaries | Mth 42 | Preliminaries - Siemens | Prelims | Prelims | Prelims | S | 157688.367 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
Network Rail Immunisation | [7 empty] | 0 | 0
Network Rail Immunisation | Network Rail Immunisation | [6 empty] | 0 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 1 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 0 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 2 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 0 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 3 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 0 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 4 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 184615 | 184615
Network Rail Immunisation | Network Rail Immunisation | Mth 5 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 70000 | 70000
Network Rail Immunisation | Network Rail Immunisation | Mth 6 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 44623 | 44622.7179
Network Rail Immunisation | Network Rail Immunisation | Mth 7 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 44623 | 20615.3846
Network Rail Immunisation | Network Rail Immunisation | Mth 8 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 24007 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 9 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 24007 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 10 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 24007 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 11 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 24007 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 12 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 24007 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 13 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 24007 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 1 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 24007 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 2 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 24007 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 3 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 24007 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 4 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 24007 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 5 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 24007 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 6 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 24007 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 7 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 24007 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 8 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 24007 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 9 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 24007 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 10 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 24007 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 11 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 24007 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 12 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 24007 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 13 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 24013 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 1 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 0 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 2 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 0 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 3 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 0 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 4 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 100000 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 5 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 100000 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 6 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 100000 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 7 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 100000 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 8 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 100000 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 9 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 0 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 10 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 0 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 11 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 200000 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 12 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 200000 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 13 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 200000 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 14 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 200000 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 15 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 200000 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 16 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 200000 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 17 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 200000 | 0
Network Rail Immunisation | Network Rail Immunisation | Mth 18 | Network Rail Immunisation | NR Imm | NR Immun | NR Imm | S | 300000 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
SDS Interface | [7 empty] | 0 | 0
SDS Interface | SDS Interface | [6 empty] | 0 | 0
SDS Interface | SDS Interface | Mth 1 | SDS Interface | SDS Interface | Prelims | SDS Interface | S | 292307.6923 | 292307.6923
SDS Interface | SDS Interface | Mth 2 | SDS Interface | SDS Interface | Prelims | SDS Interface | S | 292307.6923 | 292307.6923
SDS Interface | SDS Interface | Mth 3 | SDS Interface | SDS Interface | Prelims | SDS Interface | S | 292307.6923 | 292307.6923
SDS Interface | SDS Interface | Mth 4 | SDS Interface | SDS Interface | Prelims | SDS Interface | S | 292307.6923 | 292307.6923
SDS Interface | SDS Interface | Mth 5 | SDS Interface | SDS Interface | Prelims | SDS Interface | S | 292307.6923 | 292307.6923
SDS Interface | SDS Interface | Mth 6 | SDS Interface | SDS Interface | Prelims | SDS Interface | S | 292307.6923 | 292307.6923
SDS Interface | SDS Interface | Mth 7 | SDS Interface | SDS Interface | Prelims | SDS Interface | S | 292307.6923 | 292307.6923
SDS Interface | SDS Interface | Mth 8 | SDS Interface | SDS Interface | Prelims | SDS Interface | S | 292307.6923 | 292307.6923
SDS Interface | SDS Interface | Mth 9 | SDS Interface | SDS Interface | Prelims | SDS Interface | S | 292307.6923 | 292307.6923
SDS Interface | SDS Interface | Mth 10 | SDS Interface | SDS Interface | Prelims | SDS Interface | S | 292307.6923 | 292307.6923
SDS Interface | SDS Interface | Mth 11 | SDS Interface | SDS Interface | Prelims | SDS Interface | S | 292307.6923 | 292307.6923
SDS Interface | SDS Interface | Mth 12 | SDS Interface | SDS Interface | Prelims | SDS Interface | S | 292307.6923 | 292307.6923
SDS Interface | SDS Interface | Mth 13 | SDS Interface | SDS Interface | Prelims | SDS Interface | S | 292307.6923 | 292307.6923
[8 empty] | 0 | 0
[8 empty] | 0 | 0
Incentivisation | [7 empty] | 0 | 0
Incentivisation | Incentivisation | [6 empty] | 0 | 0
Incentivisation | Incentivisation | Section A | Incentivisation | Sectional Completion | Prelims | Sectional Completion | BB | 1200000 | 0
Incentivisation | Incentivisation | Section B | Incentivisation | Sectional Completion | Prelims | Sectional Completion | BB | 1200000 | 0
Incentivisation | Incentivisation | Section C | Incentivisation | Sectional Completion | Prelims | Sectional Completion | S | 1200000 | 0
Incentivisation | Incentivisation | Section D | Incentivisation | Sectional Completion | Prelims | Sectional Completion | S | 1200000 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
Trackwork Ch 0 - 265 | [7 empty] | 0 | 0
Trackwork Ch 0 - 265 | Trackwork | [6 empty] | 0 | 0
Trackwork Ch 0 - 265 | Trackwork | A15970 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1A | BB | 18295.8 | 0
Trackwork Ch 0 - 265 | Trackwork | A15980 | Excavate box | On Street - Other | Track | 1A | BB |  | 0
Trackwork Ch 0 - 265 | Trackwork | A15990 | Excavate, lay and concrete ducts | On Street - Other | Track | 1A | BB |  | 0
Trackwork Ch 0 - 265 | Trackwork | A16000 | Excavate and construct OLE bases | On Street - Other | Track | 1A | BB | 73183.2 | 0
Trackwork Ch 0 - 265 | Trackwork | A16010 | Set Track (265m) - 60% | On Street - Other | Track | 1A | S | 228473.4502 | 0
Trackwork Ch 0 - 265 | Trackwork | A16010 | Set Track (265m) - 40% | On Street - Other | Track | 1A | S | 152315.6334 | 0
Trackwork Ch 0 - 265 | Trackwork | A16020 | Place upper concrete and cure | On Street - Other | Track | 1A | BB |  | 0
Trackwork Ch 0 - 265 | Trackwork | A16030 | Street Surface finishes | On Street - Other | Track | 1A | BB |  | 0
Trackwork Ch 0 - 265 | Trackwork | A16040 | Remove fencing and Traffic Management | On Street - Other | Track | 1A | BB | 98672 | 0
Trackwork Ch 0 - 265 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1A | BB | 5767.0664 | 0
Trackwork Ch 265 - 425 | [7 empty] | 0 | 0
Trackwork Ch 265 - 425 | Trackwork | [6 empty] | 0 | 0
Trackwork Ch 265 - 425 | Trackwork | A15890 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1A | BB | 11046.5 | 0
Trackwork Ch 265 - 425 | Trackwork | A15900 | Excavate box | On Street - Other | Track | 1A | BB |  | 0
Trackwork Ch 265 - 425 | Trackwork | A15910 | Excavate, lay and concrete ducts | On Street - Other | Track | 1A | BB | 44186 | 0
Trackwork Ch 265 - 425 | Trackwork | A15920 | Excavate and construct OLE bases | On Street - Other | Track | 1A | BB | 11046.5 | 0
Trackwork Ch 265 - 425 | Trackwork | A15930 | Set Track (160m) | On Street - Other | Track | 1A | S | 229910.2448 | 0
Trackwork Ch 265 - 425 | Trackwork | A15940 | Place upper concrete and cure | On Street - Other | Track | 1A | BB |  | 0
Trackwork Ch 265 - 425 | Trackwork | A15950 | Street Surface finishes | On Street - Other | Track | 1A | BB |  | 0
Trackwork Ch 265 - 425 | Trackwork | A15960 | Remove fencing and Traffic Management | On Street - Other | Track | 1A | BB | 48529 | 0
Trackwork Ch 265 - 425 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1A | BB | 3482 | 0
Trackwork Ch 425 - 475 | [7 empty] | 0 | 0
Trackwork Ch 425 - 475 | Trackwork | [6 empty] | 0 | 0
Trackwork Ch 425 - 475 | Trackwork | A15810 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1A | BB | 6904 | 0
Trackwork Ch 425 - 475 | Trackwork | A15820 | Excavate box | On Street - Other | Track | 1A | BB |  | 0
Trackwork Ch 425 - 475 | Trackwork | A15830 | Excavate, lay and concrete ducts | On Street - Other | Track | 1A | BB | 10356 | 0
Trackwork Ch 425 - 475 | Trackwork | A15840 | Excavate and construct OLE bases | On Street - Other | Track | 1A | BB | 6904 | 0
Trackwork Ch 425 - 475 | Trackwork | A15850 | Set Track (50m) | On Street - Other | Track | 1A | S |  | 0
Trackwork Ch 425 - 475 | Trackwork | A15860 | Place upper concrete and cure | On Street - Other | Track | 1A | S | 71846.7456 | 0
Trackwork Ch 425 - 475 | Trackwork | A15870 | Street Surface finishes | On Street - Other | Track | 1A | BB |  | 0
Trackwork Ch 425 - 475 | Trackwork | A15880 | Remove fencing and Traffic Management | On Street - Other | Track | 1A | BB | 11713 | 0
Trackwork Ch 425 - 475 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1A | BB | 1088.1257 | 0
Trackwork Ch 475 - 600 | [7 empty] | 0 | 0
Trackwork Ch 475 - 600 | Trackwork | [6 empty] | 0 | 0
Trackwork Ch 475 - 600 | Trackwork | A15730 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1A | BB | 8630.1 | 0
Trackwork Ch 475 - 600 | Trackwork | A15740 | Excavate box | On Street - Other | Track | 1A | BB |  | 0
Trackwork Ch 475 - 600 | Trackwork | A15750 | Excavate, lay and concrete ducts | On Street - Other | Track | 1A | BB | 34520.4 | 0
Trackwork Ch 475 - 600 | Trackwork | A15760 | Excavate and construct OLE bases | On Street - Other | Track | 1A | BB | 17260.2 | 0
Trackwork Ch 475 - 600 | Trackwork | A15770 | Set Track (125m) | On Street - Other | Track | 1A | S |  | 0
Trackwork Ch 475 - 600 | Trackwork | A15780 | Place upper concrete and cure | On Street - Other | Track | 1A | S | 179617.5244 | 0
Trackwork Ch 475 - 600 | Trackwork | A15790 | Street Surface finishes | On Street - Other | Track | 1A | BB |  | 0
Trackwork Ch 475 - 600 | Trackwork | A15800 | Remove fencing and Traffic Management | On Street - Other | Track | 1A | BB | 29283.3 | 0
Trackwork Ch 475 - 600 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1A | BB | 2720.3143 | 0
Trackwork Ch 600 - 700 | [7 empty] | 0 | 0
Trackwork Ch 600 - 700 | Trackwork | [6 empty] | 0 | 0
Trackwork Ch 600 - 700 | Trackwork | A15650 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1A | BB | 6832.5 | 0
Trackwork Ch 600 - 700 | Trackwork | A15660 | Excavate box | On Street - Other | Track | 1A | BB |  | 0
Trackwork Ch 600 - 700 | Trackwork | A15670 | Excavate, lay and concrete ducts | On Street - Other | Track | 1A | BB |  | 0
Trackwork Ch 600 - 700 | Trackwork | A15680 | Excavate and construct OLE bases | On Street - Other | Track | 1A | BB | 40995 | 0
Trackwork Ch 600 - 700 | Trackwork | A15690 | Set Track (100m) | On Street - Other | Track | 1A | S |  | 0
Trackwork Ch 600 - 700 | Trackwork | A15700 | Place upper concrete and cure | On Street - Other | Track | 1A | S | 142204.9369 | 0
Trackwork Ch 600 - 700 | Trackwork | A15710 | Street Surface finishes | On Street - Other | Track | 1A | BB |  | 0
Trackwork Ch 600 - 700 | Trackwork | A15720 | Remove fencing and Traffic Management | On Street - Other | Track | 1A | BB | 23183.5 | 0
Trackwork Ch 600 - 700 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1A | BB | 2153.7042 | 0
Trackwork Ch 700 - 850 | [7 empty] | 0 | 0
Trackwork Ch 700 - 850 | Trackwork | [6 empty] | 0 | 0
Trackwork Ch 700 - 850 | Trackwork | A15570 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1A | BB | 10356.1 | 0
Trackwork Ch 700 - 850 | Trackwork | A15580 | Excavate box | On Street - Other | Track | 1A | BB |  | 0
Trackwork Ch 700 - 850 | Trackwork | A15590 | Excavate, lay and concrete ducts | On Street - Other | Track | 1A | BB | 62136.6 | 0
Trackwork Ch 700 - 850 | Trackwork | A15600 | Excavate and construct OLE bases | On Street - Other | Track | 1A | BB | 10356.1 | 0
Trackwork Ch 700 - 850 | Trackwork | A15610 | Set Track (150m) | On Street - Other | Track | 1A | S |  | 0
Trackwork Ch 700 - 850 | Trackwork | A15620 | Place upper concrete and cure | On Street - Other | Track | 1A | S | 215540.8972 | 0
Trackwork Ch 700 - 850 | Trackwork | A15630 | Street Surface finishes | On Street - Other | Track | 1A | BB |  | 0
Trackwork Ch 700 - 850 | Trackwork | A15640 | Remove fencing and Traffic Management | On Street - Other | Track | 1A | BB | 24784.2 | 0
Trackwork Ch 700 - 850 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1A | BB | 3264.3772 | 0
[8 empty] | 0 | 0
Ocean Terminal Ch 850 - 1080 | [7 empty] | 0 | 0
Ocean Terminal Ch 850 - 1080 | Trackwork | [6 empty] | 0 | 0
Ocean Terminal Ch 850 - 1080 | Trackwork | A15310 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1A | BB | 15879.3 | 0
Ocean Terminal Ch 850 - 1080 | Trackwork | A15320 | Excavate box | On Street - Other | Track | 1A | BB |  | 0
Ocean Terminal Ch 850 - 1080 | Trackwork | A15330 | Excavate, lay and concrete ducts | On Street - Other | Track | 1A | BB |  | 0
Ocean Terminal Ch 850 - 1080 | Trackwork | A15340 | Excavate and construct OLE bases | On Street - Other | Track | 1A | BB | 95275.8 | 0
Ocean Terminal Ch 850 - 1080 | Trackwork | A15350 | Set Track (280m) - 50% | On Street - Other | Track | 1A | S | 165247.8451 | 0
Ocean Terminal Ch 850 - 1080 | Trackwork | A15350 | Set Track (280m) - 50% | On Street - Other | Track | 1A | S | 165247.8451 | 0
Ocean Terminal Ch 850 - 1080 | Trackwork | A15360 | Place upper concrete and cure | On Street - Other | Track | 1A | BB |  | 0
Ocean Terminal Ch 850 - 1080 | Trackwork | A15370 | Street Surface finishes | On Street - Other | Track | 1A | BB |  | 0
Ocean Terminal Ch 850 - 1080 | Trackwork | A15380 | Remove fencing and Traffic Management | On Street - Other | Track | 1A | BB | 53880.9 | 0
Ocean Terminal Ch 850 - 1080 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1A | BB | 5005.3783 | 0
Ocean Terminal to Rennies Isle Ch 1080 - 1410 | [7 empty] | 0 | 0
Ocean Terminal to Rennies Isle Ch 1080 - 1410 | Trackwork | [6 empty] | 0 | 0
Ocean Terminal to Rennies Isle Ch 1080 - 1410 | Trackwork | A15230 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1A | BB | 22783.4 | 0
Ocean Terminal to Rennies Isle Ch 1080 - 1410 | Trackwork | A15240 | Excavate box | On Street - Other | Track | 1A | BB |  | 0
Ocean Terminal to Rennies Isle Ch 1080 - 1410 | Trackwork | A15250 | Excavate, lay and concrete ducts | On Street - Other | Track | 1A | BB | 136700.4 | 0
Ocean Terminal to Rennies Isle Ch 1080 - 1410 | Trackwork | A15260 | Excavate and construct OLE bases | On Street - Other | Track | 1A | BB | 22783.4 | 0
Ocean Terminal to Rennies Isle Ch 1080 - 1410 | Trackwork | A15270 | Set Track (330m) - 50% | On Street - Other | Track | 1A | S | 237094.9209 | 0
Ocean Terminal to Rennies Isle Ch 1080 - 1410 | Trackwork | A15270 | Set Track (330m) - 50% | On Street - Other | Track | 1A | S | 237094.9209 | 0
Ocean Terminal to Rennies Isle Ch 1080 - 1410 | Trackwork | A15280 | Place upper concrete and cure | On Street - Other | Track | 1A | BB |  | 0
Ocean Terminal to Rennies Isle Ch 1080 - 1410 | Trackwork | A15290 | Street Surface finishes | On Street - Other | Track | 1A | BB |  | 0
Ocean Terminal to Rennies Isle Ch 1080 - 1410 | Trackwork | A15300 | Remove fencing and Traffic Management | On Street - Other | Track | 1A | BB | 54524.8 | 0
Ocean Terminal to Rennies Isle Ch 1080 - 1410 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1A | BB | 7181.6298 | 0
Rennies Isle to Casino Square Ch 1410 - 1880 | [7 empty] | 0 | 0
Rennies Isle to Casino Square Ch 1410 - 1880 | Trackwork | [6 empty] | 0 | 0
Rennies Isle to Casino Square Ch 1410 - 1880 | Trackwork | A15150 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1A | BB | 32449.1 | 0
Rennies Isle to Casino Square Ch 1410 - 1880 | Trackwork | A15160 | Excavate box | On Street - Other | Track | 1A | BB |  | 0
Rennies Isle to Casino Square Ch 1410 - 1880 | Trackwork | A15170 | Excavate, lay and concrete ducts | On Street - Other | Track | 1A | BB | 194694.6 | 0
Rennies Isle to Casino Square Ch 1410 - 1880 | Trackwork | A15180 | Excavate and construct OLE bases | On Street - Other | Track | 1A | BB | 32449.1 | 0
Rennies Isle to Casino Square Ch 1410 - 1880 | Trackwork | A15190 | Set Track (470m) - 50% | On Street - Other | Track | 1A | S | 337680.695 | 0
Rennies Isle to Casino Square Ch 1410 - 1880 | Trackwork | A15190 | Set Track (470m) - 50% | On Street - Other | Track | 1A | S | 337680.695 | 0
Rennies Isle to Casino Square Ch 1410 - 1880 | Trackwork | A15200 | Place upper concrete and cure | On Street - Other | Track | 1A | BB |  | 0
Rennies Isle to Casino Square Ch 1410 - 1880 | Trackwork | A15210 | Street Surface finishes | On Street - Other | Track | 1A | BB |  | 0
Rennies Isle to Casino Square Ch 1410 - 1880 | Trackwork | A15220 | Remove fencing and Traffic Management | On Street - Other | Track | 1A | BB | 77656.2 | 0
Rennies Isle to Casino Square Ch 1410 - 1880 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1A | BB | 10228.3818 | 0
[8 empty] | 0 | 0
Casino Square to Baltic Street Ch 1850 - 1880 | [7 empty] | 0 | 0
Casino Square to Baltic Street Ch 1850 - 1880 | Trackwork | [6 empty] | 0 | 0
Casino Square to Baltic Street Ch 1850 - 1880 | Trackwork | A16110 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1A | BB | 2071.2 | 0
Casino Square to Baltic Street Ch 1850 - 1880 | Trackwork | A16120 | Excavate box | On Street - Other | Track | 1A | BB |  | 0
Casino Square to Baltic Street Ch 1850 - 1880 | Trackwork | A16130 | Excavate, lay and concrete ducts | On Street - Other | Track | 1A | BB |  | 0
Casino Square to Baltic Street Ch 1850 - 1880 | Trackwork | A16140 | Excavate and construct OLE bases | On Street - Other | Track | 1A | BB | 12427.2 | 0
Casino Square to Baltic Street Ch 1850 - 1880 | Trackwork | A16150 | Set Track (30m) | On Street - Other | Track | 1A | S |  | 0
Casino Square to Baltic Street Ch 1850 - 1880 | Trackwork | A16160 | Place upper concrete and cure | On Street - Other | Track | 1A | S | 43108.0474 | 0
Casino Square to Baltic Street Ch 1850 - 1880 | Trackwork | A16170 | Street Surface finishes | On Street - Other | Track | 1A | BB |  | 0
Casino Square to Baltic Street Ch 1850 - 1880 | Trackwork | A16180 | Remove fencing and Traffic Management | On Street - Other | Track | 1A | BB | 7027.6 | 0
Casino Square to Baltic Street Ch 1850 - 1880 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1A | BB | 652.8754 | 0
Casino Square to Baltic Street Ch 1880 - 2110 | [7 empty] | 0 | 0
Casino Square to Baltic Street Ch 1880 - 2110 | Trackwork | [6 empty] | 0 | 0
Casino Square to Baltic Street Ch 1880 - 2110 | Trackwork | A15010 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1A | BB | 15879.3 | 0
Casino Square to Baltic Street Ch 1880 - 2110 | Trackwork | A15020 | Excavate box | On Street - Other | Track | 1A | BB | 63517.2 | 0
Casino Square to Baltic Street Ch 1880 - 2110 | Trackwork | A15030 | Excavate, lay and concrete ducts | On Street - Other | Track | 1A | BB |  | 0
Casino Square to Baltic Street Ch 1880 - 2110 | Trackwork | A15040 | Excavate and construct OLE bases | On Street - Other | Track | 1A | BB | 15879.3 | 0
Casino Square to Baltic Street Ch 1880 - 2110 | Trackwork | A15050 | Set Track (230m) - 50% | On Street - Other | Track | 1A | S | 165247.8451 | 0
Casino Square to Baltic Street Ch 1880 - 2110 | Trackwork | A15050 | Set Track (230m) - 50% | On Street - Other | Track | 1A | S | 165247.8451 | 0
Casino Square to Baltic Street Ch 1880 - 2110 | Trackwork | A15060 | Place upper concrete and cure | On Street - Other | Track | 1A | BB | 47637.9 | 0
Casino Square to Baltic Street Ch 1880 - 2110 | Trackwork | A15070 | Street Surface finishes | On Street - Other | Track | 1A | BB |  | 0
Casino Square to Baltic Street Ch 1880 - 2110 | Trackwork | A15080 | Remove fencing and Traffic Management | On Street - Other | Track | 1A | BB | 22122.3 | 0
Casino Square to Baltic Street Ch 1880 - 2110 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1A | BB | 5005.3783 | 0
[8 empty] | 0 | 0
Baltic to Queen Charlotte Ch 2110 - 2340 | [7 empty] | 0 | 0
Baltic to Queen Charlotte Ch 2110 - 2340 | Trackwork | [6 empty] | 0 | 0
Baltic to Queen Charlotte Ch 2110 - 2340 | Trackwork | A14870 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1A | BB | 15879.3 | 0
Baltic to Queen Charlotte Ch 2110 - 2340 | Trackwork | A14880 | Excavate box | On Street - Other | Track | 1A | BB |  | 0
Baltic to Queen Charlotte Ch 2110 - 2340 | Trackwork | A14890 | Excavate, lay and concrete ducts | On Street - Other | Track | 1A | BB |  | 0
Baltic to Queen Charlotte Ch 2110 - 2340 | Trackwork | A14900 | Excavate and construct OLE bases | On Street - Other | Track | 1A | BB | 15879.3 | 0
Baltic to Queen Charlotte Ch 2110 - 2340 | Trackwork | A14910 | Set Track (230m) - 50% | On Street - Other | Track | 1A | S | 165247.8451 | 0
Baltic to Queen Charlotte Ch 2110 - 2340 | Trackwork | A14910 | Set Track (230m) - 50% | On Street - Other | Track | 1A | S | 165247.8451 | 0
Baltic to Queen Charlotte Ch 2110 - 2340 | Trackwork | A14920 | Place upper concrete and cure | On Street - Other | Track | 1A | BB | 95275.8 | 0
Baltic to Queen Charlotte Ch 2110 - 2340 | Trackwork | A14930 | Street Surface finishes | On Street - Other | Track | 1A | BB |  | 0
Baltic to Queen Charlotte Ch 2110 - 2340 | Trackwork | A14940 | Remove fencing and Traffic Management | On Street - Other | Track | 1A | BB | 38001.6 | 0
Baltic to Queen Charlotte Ch 2110 - 2340 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1A | BB | 5005.3783 | 0
Queen Charlotte to Foot/Walk Ch 2340 - 2730 | [7 empty] | 0 | 0
Queen Charlotte to Foot/Walk Ch 2340 - 2730 | Trackwork | [6 empty] | 0 | 0
Queen Charlotte to Foot/Walk Ch 2340 - 2730 | Trackwork | A14630 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1A | BB | 26925.8 | 0
Queen Charlotte to Foot/Walk Ch 2340 - 2730 | Trackwork | A14640 | Excavate box | On Street - Other | Track | 1A | BB | 80777.4 | 0
Queen Charlotte to Foot/Walk Ch 2340 - 2730 | Trackwork | A14650 | Excavate, lay and concrete ducts | On Street - Other | Track | 1A | BB |  | 0
Queen Charlotte to Foot/Walk Ch 2340 - 2730 | Trackwork | A14660 | Excavate and construct OLE bases | On Street - Other | Track | 1A | BB | 26925.8 | 0
Queen Charlotte to Foot/Walk Ch 2340 - 2730 | Trackwork | A14680 | Set Track (390m) - 50% | On Street - Other | Track | 1A | S | 280202.9683 | 0
Queen Charlotte to Foot/Walk Ch 2340 - 2730 | Trackwork | A14680 | Set Track (390m) - 50% | On Street - Other | Track | 1A | S | 280202.9683 | 0
Queen Charlotte to Foot/Walk Ch 2340 - 2730 | Trackwork | A14690 | Place upper concrete and cure | On Street - Other | Track | 1A | BB | 80777.4 | 0
Queen Charlotte to Foot/Walk Ch 2340 - 2730 | Trackwork | A14700 | Street Surface finishes | On Street - Other | Track | 1A | BB |  | 0
Queen Charlotte to Foot/Walk Ch 2340 - 2730 | Trackwork | A14710 | Remove fencing and Traffic Management | On Street - Other | Track | 1A | BB | 64437.6 | 0
Queen Charlotte to Foot/Walk Ch 2340 - 2730 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1A | BB | 8487.3807 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
Foot of the Walk Ch 0 - 100 | [7 empty] | 0 | 0
Foot of the Walk Ch 0 - 100 | Trackwork | [6 empty] | 0 | 0
Foot of the Walk Ch 0 - 100 | Trackwork | Phase 1 | [5 empty] | 0 | 0
Foot of the Walk Ch 0 - 100 | Trackwork | A12450 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1B | BB | 2396.8 | 0
Foot of the Walk Ch 0 - 100 | Trackwork | A12460 | Excavate box | On Street - Other | Track | 1B | BB |  | 0
Foot of the Walk Ch 0 - 100 | Trackwork | A12470 | Excavate, lay and concrete ducts | On Street - Other | Track | 1B | BB |  | 0
Foot of the Walk Ch 0 - 100 | Trackwork | A12480 | Excavate and construct OLE bases | On Street - Other | Track | 1B | BB | 9587.2 | 0
Foot of the Walk Ch 0 - 100 | Trackwork | A12500 | Set Track (50m) | On Street - Other | Track | 1B | S |  | 0
Foot of the Walk Ch 0 - 100 | Trackwork | A12510 | Place upper concrete and cure | On Street - Other | Track | 1B | S | 49884.2613 | 0
Foot of the Walk Ch 0 - 100 | Trackwork | A12520 | Street Surface finishes | On Street - Other | Track | 1B | BB |  | 0
Foot of the Walk Ch 0 - 100 | Trackwork | A13510 | Remove fencing and Traffic Management | On Street - Other | Track | 1B | BB | 12926 | 0
Foot of the Walk Ch 0 - 100 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1B | BB | 755.4981 | 0
Foot of the Walk Ch 0 - 100 | Trackwork | Phase 2 | [5 empty] | 0 | 0
Foot of the Walk Ch 0 - 100 | Trackwork | A12530 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1B | BB | 2396.8 | 0
Foot of the Walk Ch 0 - 100 | Trackwork | A12540 | Excavate box | On Street - Other | Track | 1B | BB |  | 0
Foot of the Walk Ch 0 - 100 | Trackwork | A12550 | Excavate, lay and concrete ducts | On Street - Other | Track | 1B | BB |  | 0
Foot of the Walk Ch 0 - 100 | Trackwork | A12560 | Excavate and construct OLE bases | On Street - Other | Track | 1B | BB | 9587.2 | 0
Foot of the Walk Ch 0 - 100 | Trackwork | A12580 | Set Track (50m) | On Street - Other | Track | 1B | S |  | 0
Foot of the Walk Ch 0 - 100 | Trackwork | A12590 | Place upper concrete and cure | On Street - Other | Track | 1B | S | 49884.2613 | 0
Foot of the Walk Ch 0 - 100 | Trackwork | A12600 | Street Surface finishes | On Street - Other | Track | 1B | BB |  | 0
Foot of the Walk Ch 0 - 100 | Trackwork | A13500 | Remove fencing and Traffic Management | On Street - Other | Track | 1B | BB | 12926 | 0
Foot of the Walk Ch 0 - 100 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1B | BB | 755.4981 | 0
Foot of the Walk Ch 0 - 100 | Trackwork | Phase 3 | [5 empty] | 0 | 0
Foot of the Walk Ch 0 - 100 | Trackwork | A12610 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1B | BB | 2396.8 | 0
Foot of the Walk Ch 0 - 100 | Trackwork | A12620 | Excavate box | On Street - Other | Track | 1B | BB |  | 0
Foot of the Walk Ch 0 - 100 | Trackwork | A12630 | Excavate, lay and concrete ducts | On Street - Other | Track | 1B | BB |  | 0
Foot of the Walk Ch 0 - 100 | Trackwork | A12640 | Excavate and construct OLE bases | On Street - Other | Track | 1B | BB | 11984 | 0
Foot of the Walk Ch 0 - 100 | Trackwork | A12660 | Set Track (50m) | On Street - Other | Track | 1B | S |  | 0
Foot of the Walk Ch 0 - 100 | Trackwork | A12670 | Place upper concrete and cure | On Street - Other | Track | 1B | S | 49884.2624 | 0
Foot of the Walk Ch 0 - 100 | Trackwork | A12680 | Street Surface finishes | On Street - Other | Track | 1B | BB |  | 0
Foot of the Walk Ch 0 - 100 | Trackwork | A13490 | Remove fencing and Traffic Management | On Street - Other | Track | 1B | BB | 10529.2 | 0
Foot of the Walk Ch 0 - 100 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1B | BB | 0 | 0
Leith Walk Ch 100 - 350 | [7 empty] | 0 | 0
Leith Walk Ch 100 - 350 | Trackwork | [6 empty] | 0 | 0
Leith Walk Ch 100 - 350 | Trackwork | 1st half | [5 empty] | 0 | 0
Leith Walk Ch 100 - 350 | Trackwork | A12690 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1B | BB | 9555.5 | 0
Leith Walk Ch 100 - 350 | Trackwork | A12700 | Excavate box | On Street - Other | Track | 1B | BB |  | 0
Leith Walk Ch 100 - 350 | Trackwork | A12710 | Excavate, lay and concrete ducts | On Street - Other | Track | 1B | BB |  | 0
Leith Walk Ch 100 - 350 | Trackwork | A12720 | Excavate and construct OLE bases | On Street - Other | Track | 1B | BB | 28666.5 | 0
Leith Walk Ch 100 - 350 | Trackwork | A12740 | Set Track (250m) | On Street - Other | Track | 1B | S | 198590.4299 | 0
Leith Walk Ch 100 - 350 | Trackwork | A12750 | Place upper concrete and cure | On Street - Other | Track | 1B | BB | 38222 | 0
Leith Walk Ch 100 - 350 | Trackwork | A12760 | Street Surface finishes | On Street - Other | Track | 1B | BB | 22863 | 0
Leith Walk Ch 100 - 350 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1B | BB | 2869.2126 | 0
Trackwork | Trackwork | 2nd half | [5 empty] | 0 | 0
Leith Walk Ch 100 - 350 | Trackwork | A13090 | Excavate box | On Street - Other | Track | 1B | BB |  | 0
Leith Walk Ch 100 - 350 | Trackwork | A13100 | Excavate, lay and concrete ducts | On Street - Other | Track | 1B | BB |  | 0
Leith Walk Ch 100 - 350 | Trackwork | A13130 | Set Track | On Street - Other | Track | 1B | S | 175540.8699 | 0
Leith Walk Ch 100 - 350 | Trackwork | A13140 | Place upper concrete and cure | On Street - Other | Track | 1B | BB | 67363.2 | 0
Leith Walk Ch 100 - 350 | Trackwork | A13150 | Street Surface finishes | On Street - Other | Track | 1B | BB |  | 0
Leith Walk Ch 100 - 350 | Trackwork | A13160 | Remove fencing and Traffic Management | On Street - Other | Track | 1B | BB | 20156.8 | 0
Leith Walk Ch 100 - 350 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1B | BB | 2797.0235 | 0
Leith Walk Ch 350 - 600 | [7 empty] | 0 | 0
Trackwork | Trackwork | [6 empty] | 0 | 0
Trackwork | Trackwork | 1st half | [5 empty] | 0 | 0
Leith Walk Ch 350 - 600 | Trackwork | A12770 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1B | BB | 9555.5 | 0
Leith Walk Ch 350 - 600 | Trackwork | A12780 | Excavate box | On Street - Other | Track | 1B | BB |  | 0
Leith Walk Ch 350 - 600 | Trackwork | A12790 | Excavate, lay and concrete ducts | On Street - Other | Track | 1B | BB |  | 0
Leith Walk Ch 350 - 600 | Trackwork | A12800 | Excavate and construct OLE bases | On Street - Other | Track | 1B | BB | 28666.5 | 0
Leith Walk Ch 350 - 600 | Trackwork | A12820 | Set Track (250m) | On Street - Other | Track | 1B | S | 198590.4299 | 0
Leith Walk Ch 350 - 600 | Trackwork | A12830 | Place upper concrete and cure | On Street - Other | Track | 1B | BB | 47777.5 | 0
Leith Walk Ch 350 - 600 | Trackwork | A12840 | Street Surface finishes | On Street - Other | Track | 1B | BB | 13307.5 | 0
Leith Walk Ch 350 - 600 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1B | BB | 2869.2126 | 0
Trackwork | Trackwork | 2nd half | [5 empty] | 0 | 0
Leith Walk Ch 350 - 600 | Trackwork | A13170 | Excavate box | On Street - Other | Track | 1B | BB |  | 0
Leith Walk Ch 350 - 600 | Trackwork | A13180 | Excavate, lay and concrete ducts | On Street - Other | Track | 1B | BB |  | 0
Leith Walk Ch 350 - 600 | Trackwork | A131210 | Set Track | On Street - Other | Track | 1B | S | 175540.8699 | 0
Leith Walk Ch 350 - 600 | Trackwork | A13220 | Place upper concrete and cure | On Street - Other | Track | 1B | BB | 67363.2 | 0
Leith Walk Ch 350 - 600 | Trackwork | A13230 | Street Surface finishes | On Street - Other | Track | 1B | BB |  | 0
Leith Walk Ch 350 - 600 | Trackwork | A13240 | Remove fencing and Traffic Management | On Street - Other | Track | 1B | BB | 20156.8 | 0
Leith Walk Ch 350 - 600 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1B | BB | 2797.0235 | 0
[8 empty] | 0 | 0
Balfour Street Ch 600 - 850 | [7 empty] | 0 | 0
Balfour Street Ch 600 - 850 | Trackwork | [6 empty] | 0 | 0
Balfour Street Ch 600 - 850 | Trackwork | 1st half | [5 empty] | 0 | 0
Balfour Street Ch 600 - 850 | Trackwork | A12850 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1B | BB | 9555.5 | 0
Balfour Street Ch 600 - 850 | Trackwork | A12860 | Excavate box | On Street - Other | Track | 1B | BB |  | 0
Balfour Street Ch 600 - 850 | Trackwork | A12870 | Excavate, lay and concrete ducts | On Street - Other | Track | 1B | BB |  | 0
Balfour Street Ch 600 - 850 | Trackwork | A12880 | Excavate and construct OLE bases | On Street - Other | Track | 1B | BB | 28666.5 | 0
Balfour Street Ch 600 - 850 | Trackwork | A12900 | Set Track (250m) | On Street - Other | Track | 1B | S | 198590.4299 | 0
Balfour Street Ch 600 - 850 | Trackwork | A12910 | Place upper concrete and cure | On Street - Other | Track | 1B | BB | 47777.5 | 0
Balfour Street Ch 600 - 850 | Trackwork | A12920 | Street Surface finishes | On Street - Other | Track | 1B | BB | 13307.5 | 0
Balfour Street Ch 600 - 850 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1B | BB | 2869.2126 | 0
Balfour Street Ch 600 - 850 | Trackwork | 2nd half | [5 empty] | 0 | 0
Balfour Street Ch 600 - 850 | Trackwork | A13250 | Excavate box | On Street - Other | Track | 1B | BB |  | 0
Balfour Street Ch 600 - 850 | Trackwork | A13260 | Excavate, lay and concrete ducts | On Street - Other | Track | 1B | BB |  | 0
Balfour Street Ch 600 - 850 | Trackwork | A13290 | Set Track | On Street - Other | Track | 1B | S | 175540.8699 | 0
Balfour Street Ch 600 - 850 | Trackwork | A13300 | Place upper concrete and cure | On Street - Other | Track | 1B | BB | 67363.2 | 0
Balfour Street Ch 600 - 850 | Trackwork | A13310 | Street Surface finishes | On Street - Other | Track | 1B | BB |  | 0
Balfour Street Ch 600 - 850 | Trackwork | A13320 | Remove fencing and Traffic Management | On Street - Other | Track | 1B | BB | 20156.8 | 0
Balfour Street Ch 600 - 850 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1B | BB | 2797.0235 | 0
Pilrig / Iona Street Ch 850 - 950 | [7 empty] | 0 | 0
Pilrig / Iona Street Ch 850 - 950 | Trackwork | [6 empty] | 0 | 0
Pilrig / Iona Street Ch 850 - 950 | Trackwork | 1st half | [5 empty] | 0 | 0
Pilrig / Iona Street Ch 850 - 950 | Trackwork | A12930 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1B | BB | 3822.2 | 0
Pilrig / Iona Street Ch 850 - 950 | Trackwork | A12940 | Excavate box | On Street - Other | Track | 1B | BB |  | 0
Pilrig / Iona Street Ch 850 - 950 | Trackwork | A12950 | Excavate, lay and concrete ducts | On Street - Other | Track | 1B | BB |  | 0
Pilrig / Iona Street Ch 850 - 950 | Trackwork | A12960 | Excavate and construct OLE bases | On Street - Other | Track | 1B | BB | 19111 | 0
Pilrig / Iona Street Ch 850 - 950 | Trackwork | A12980 | Set Track (100m) | On Street - Other | Track | 1B | S | 79436.172 | 0
Pilrig / Iona Street Ch 850 - 950 | Trackwork | A12990 | Place upper concrete and cure | On Street - Other | Track | 1B | BB | 11466.6 | 0
Pilrig / Iona Street Ch 850 - 950 | Trackwork | A13000 | Street Surface finishes | On Street - Other | Track | 1B | BB | 5323.2 | 0
Pilrig / Iona Street Ch 850 - 950 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1B | BB | 1147.6851 | 0
Trackwork | Trackwork | 2nd half | [5 empty] | 0 | 0
Pilrig / Iona Street Ch 850 - 950 | Trackwork | A13330 | Excavate box | On Street - Other | Track | 1B | BB |  | 0
Pilrig / Iona Street Ch 850 - 950 | Trackwork | A13340 | Excavate, lay and concrete ducts | On Street - Other | Track | 1B | BB |  | 0
Pilrig / Iona Street Ch 850 - 950 | Trackwork | A13370 | Set Track | On Street - Other | Track | 1B | S | 70215.9518 | 0
Pilrig / Iona Street Ch 850 - 950 | Trackwork | A13380 | Place upper concrete and cure | On Street - Other | Track | 1B | BB | 26944.8 | 0
Pilrig / Iona Street Ch 850 - 950 | Trackwork | A13390 | Street Surface finishes | On Street - Other | Track | 1B | BB |  | 0
Pilrig / Iona Street Ch 850 - 950 | Trackwork | A13400 | Remove fencing and Traffic Management | On Street - Other | Track | 1B | BB | 8063.2 | 0
Pilrig / Iona Street Ch 850 - 950 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1B | BB | 1118.8094 | 0
McDonald / Brunswick Road Ch 950 - 1250 | [7 empty] | 0 | 0
McDonald / Brunswick Road Ch 950 - 1250 | Trackwork | [6 empty] | 0 | 0
McDonald / Brunswick Road Ch 950 - 1250 | Trackwork | 1st half | [5 empty] | 0 | 0
McDonald / Brunswick Road Ch 950 - 1250 | Trackwork | A13010 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1B | BB | 11466.6 | 0
McDonald / Brunswick Road Ch 950 - 1250 | Trackwork | A13020 | Excavate box | On Street - Other | Track | 1B | BB |  | 0
McDonald / Brunswick Road Ch 950 - 1250 | Trackwork | A13030 | Excavate, lay and concrete ducts | On Street - Other | Track | 1B | BB |  | 0
McDonald / Brunswick Road Ch 950 - 1250 | Trackwork | A13040 | Excavate and construct OLE bases | On Street - Other | Track | 1B | BB | 34399.8 | 0
McDonald / Brunswick Road Ch 950 - 1250 | Trackwork | A13060 | Set Track (300m) | On Street - Other | Track | 1B | S | 238308.5159 | 0
McDonald / Brunswick Road Ch 950 - 1250 | Trackwork | A13070 | Place upper concrete and cure | On Street - Other | Track | 1B | BB | 45866.4 | 0
McDonald / Brunswick Road Ch 950 - 1250 | Trackwork | A13080 | Street Surface finishes | On Street - Other | Track | 1B | BB | 27435.2 | 0
McDonald / Brunswick Road Ch 950 - 1250 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1B | BB | 3443.0552 | 0
Trackwork | Trackwork | 2nd half | [5 empty] | 0 | 0
McDonald / Brunswick Road Ch 950 - 1250 | Trackwork | A13410 | Excavate box | On Street - Other | Track | 1B | BB |  | 0
McDonald / Brunswick Road Ch 950 - 1250 | Trackwork | A13420 | Excavate, lay and concrete ducts | On Street - Other | Track | 1B | BB |  | 0
McDonald / Brunswick Road Ch 950 - 1250 | Trackwork | A13450 | Set Track | On Street - Other | Track | 1B | S | 210648.5156 | 0
McDonald / Brunswick Road Ch 950 - 1250 | Trackwork | A13460 | Place upper concrete and cure | On Street - Other | Track | 1B | BB | 70730.8 | 0
McDonald / Brunswick Road Ch 950 - 1250 | Trackwork | A13470 | Street Surface finishes | On Street - Other | Track | 1B | BB |  | 0
McDonald / Brunswick Road Ch 950 - 1250 | Trackwork | A13480 | Remove fencing and Traffic Management | On Street - Other | Track | 1B | BB | 34292.2 | 0
McDonald / Brunswick Road Ch 950 - 1250 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1B | BB | 3356.4281 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
McDonald Road Tramstop | [7 empty] | 0 | 0
Leith Walk Ch 0 - 375 | [7 empty] | 0 | 0
Leith Walk Ch 0 - 375 | Trackwork | [6 empty] | 0 | 0
Leith Walk Ch 0 - 375 | Trackwork | 1st Half (Dummy) | [5 empty] | 0 | 0
Leith Walk Ch 0 - 375 | Trackwork | A16190 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1C | BB | 18798.8 | 0
Leith Walk Ch 0 - 375 | Trackwork | A16200 | Excavate box | On Street - Other | Track | 1C | BB |  | 0
Leith Walk Ch 0 - 375 | Trackwork | A16210 | Excavate, lay and concrete ducts | On Street - Other | Track | 1C | BB | 56396.4 | 0
Leith Walk Ch 0 - 375 | Trackwork | A16220 | Excavate and construct OLE bases | On Street - Other | Track | 1C | BB | 18798.8 | 0
Leith Walk Ch 0 - 375 | Trackwork | A16230 | Set Track (300m) - 50% | On Street - Other | Track | 1C | S | 195346.1162 | 0
Leith Walk Ch 0 - 375 | Trackwork | A16230 | Set Track (300m) - 50% | On Street - Other | Track | 1C | S | 195346.1162 | 0
Leith Walk Ch 0 - 375 | Trackwork | A16240 | Place upper concrete and cure | On Street - Other | Track | 1C | BB | 56396.4 | 0
Leith Walk Ch 0 - 375 | Trackwork | A16250 | Street Surface finishes | On Street - Other | Track | 1C | BB | 44977.6 | 0
Leith Walk Ch 0 - 375 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1C | BB | 5645.1361 | 0
Trackwork | Trackwork | 2nd Half (Dummy) | [5 empty] | 0 | 0
Leith Walk Ch 0 - 375 | Trackwork | A16330 | Excavate box | On Street - Other | Track | 1C | BB |  | 0
Leith Walk Ch 0 - 375 | Trackwork | A16340 | Excavate, lay and concrete ducts | On Street - Other | Track | 1C | BB | 82686 | 0
Leith Walk Ch 0 - 375 | Trackwork | A16350 | Set Track | On Street - Other | Track | 1C | S |  | 0
Leith Walk Ch 0 - 375 | Trackwork | A16360 | Place upper concrete and cure | On Street - Other | Track | 1C | S | 344754.3335 | 0
Leith Walk Ch 0 - 375 | Trackwork | A16370 | Street Surface finishes | On Street - Other | Track | 1C | BB |  | 0
Leith Walk Ch 0 - 375 | Trackwork | A16380 | Remove fencing and Traffic Management | On Street - Other | Track | 1C | BB | 89199 | 0
Leith Walk Ch 0 - 375 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1C | BB | 5493.2407 | 0
London Road Ch 375 - 450 | [7 empty] | 0 | 0
London Road Ch 375 - 450 | Trackwork | [6 empty] | 0 | 0
London Road Ch 375 - 450 | Trackwork | 1st Half (Dummy) | [5 empty] | 0 | 0
London Road Ch 375 - 450 | Trackwork | A16260 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1C | BB | 3835.7 | 0
London Road Ch 375 - 450 | Trackwork | A16270 | Excavate box | On Street - Other | Track | 1C | BB |  | 0
London Road Ch 375 - 450 | Trackwork | A16280 | Excavate, lay and concrete ducts | On Street - Other | Track | 1C | BB |  | 0
London Road Ch 375 - 450 | Trackwork | A16290 | Excavate and construct OLE bases | On Street - Other | Track | 1C | BB | 15342.8 | 0
London Road Ch 375 - 450 | Trackwork | A16300 | Set Track (300m) | On Street - Other | Track | 1C | S |  | 0
London Road Ch 375 - 450 | Trackwork | A16310 | Place upper concrete and cure | On Street - Other | Track | 1C | S | 78630.5264 | 0
London Road Ch 375 - 450 | Trackwork | A16320 | Street Surface finishes | On Street - Other | Track | 1C | BB | 20148.5 | 0
London Road Ch 375 - 450 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1C | BB | 1129.0272 | 0
London Road Ch 375 - 450 | Trackwork | 2nd Half (Dummy) | [5 empty] | 0 | 0
London Road Ch 375 - 450 | Trackwork | A16390 | Excavate box | On Street - Other | Track | 1C | BB |  | 0
London Road Ch 375 - 450 | Trackwork | A16400 | Excavate, lay and concrete ducts | On Street - Other | Track | 1C | BB |  | 0
London Road Ch 375 - 450 | Trackwork | A16410 | Set Track | On Street - Other | Track | 1C | S |  | 0
London Road Ch 375 - 450 | Trackwork | A16420 | Place upper concrete and cure | On Street - Other | Track | 1C | S | 68950.6026 | 0
London Road Ch 375 - 450 | Trackwork | A16430 | Street Surface finishes | On Street - Other | Track | 1C | BB |  | 0
London Road Ch 375 - 450 | Trackwork | A16440 | Remove fencing and Traffic Management | On Street - Other | Track | 1C | BB | 34377 | 0
London Road Ch 375 - 450 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1C | BB | 1098.6481 | 0
[8 empty] | 0 | 0
Picardy Place Ch 450 - 700 | [7 empty] | 0 | 0
Picardy Place Ch 450 - 700 | Trackwork | [6 empty] | 0 | 0
Picardy Place Ch 450 - 700 | Trackwork | Phase 3 - 1st Half (Dummy) | [5 empty] | 0 | 0
Picardy Place Ch 450 - 700 | Trackwork | A16450 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1C | BB | 5109.4 | 0
Picardy Place Ch 450 - 700 | Trackwork | A16460 | Excavate box | On Street - Other | Track | 1C | BB |  | 0
Picardy Place Ch 450 - 700 | Trackwork | A16470 | Excavate, lay and concrete ducts | On Street - Other | Track | 1C | BB |  | 0
Picardy Place Ch 450 - 700 | Trackwork | A16480 | Excavate and construct OLE bases | On Street - Other | Track | 1C | BB | 25547 | 0
Picardy Place Ch 450 - 700 | Trackwork | A16490 | Set Track (100m) - Picardy Place | On Street - Other | Track | 1C | S |  | 0
Picardy Place Ch 450 - 700 | Trackwork | A16500 | Place upper concrete and cure | On Street - Other | Track | 1C | S | 106190.5386 | 0
Picardy Place Ch 450 - 700 | Trackwork | A16510 | Street Surface finishes | On Street - Other | Track | 1C | BB | 22443.6 | 0
Picardy Place Ch 450 - 700 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1C | BB | 1535.7487 | 0
Trackwork | Trackwork | Phase 3 - 2nd Half (Dummy) | [5 empty] | 0 | 0
Picardy Place Ch 450 - 700 | Trackwork | A16520 | Excavate box | On Street - Other | Track | 1C | BB |  | 0
Picardy Place Ch 450 - 700 | Trackwork | A16530 | Excavate, lay and concrete ducts | On Street - Other | Track | 1C | BB |  | 0
Picardy Place Ch 450 - 700 | Trackwork | A16540 | Set Track | On Street - Other | Track | 1C | S |  | 0
Picardy Place Ch 450 - 700 | Trackwork | A16550 | Place upper concrete and cure | On Street - Other | Track | 1C | BB |  | 0
Picardy Place Ch 450 - 700 | Trackwork | A16560 | Street Surface finishes | On Street - Other | Track | 1C | S | 91934.3569 | 0
Picardy Place Ch 450 - 700 | Trackwork | A16570 | Remove fencing and Traffic Management | On Street - Other | Track | 1C | BB | 45836 | 0
Picardy Place Ch 450 - 700 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1C | BB | 1464.8642 | 0
Trackwork | Trackwork | Phase 4 | [5 empty] | 0 | 0
Picardy Place Ch 450 - 700 | Trackwork | A16580 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1C | BB |  | 0
Picardy Place Ch 450 - 700 | Trackwork | A16590 | Excavate box | On Street - Other | Track | 1C | BB |  | 0
Picardy Place Ch 450 - 700 | Trackwork | A16600 | Excavate, lay and concrete ducts | On Street - Other | Track | 1C | BB |  | 0
Picardy Place Ch 450 - 700 | Trackwork | A16610 | Excavate and construct OLE bases | On Street - Other | Track | 1C | BB | 14166.5 | 0
Picardy Place Ch 450 - 700 | Trackwork | A16620 | Set Track (150m) | On Street - Other | Track | 1C | S | 69519.2655 | 0
Picardy Place Ch 450 - 700 | Trackwork | A16630 | Place upper concrete and cure | On Street - Other | Track | 1C | S | 294847.0834 | 0
Picardy Place Ch 450 - 700 | Trackwork | A16640 | Street Surface finishes | On Street - Other | Track | 1C | BB |  | 0
Picardy Place Ch 450 - 700 | Trackwork | A16650 | Remove fencing and Traffic Management | On Street - Other | Track | 1C | BB | 63549 | 0
Picardy Place Ch 450 - 700 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1C | BB | 4465.4771 | 0
York Place Ch 700 - 850 | [7 empty] | 0 | 0
York Place Ch 700 - 850 | Trackwork | [6 empty] | 0 | 0
York Place Ch 700 - 850 | Trackwork | A13660 | Dummy | On Street - Other | Track | 1C | BB |  | 0
York Place Ch 700 - 850 | Trackwork | A16660 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1C | BB | 14134.4 | 0
York Place Ch 700 - 850 | Trackwork | A16670 | Excavate box | On Street - Other | Track | 1C | BB |  | 0
York Place Ch 700 - 850 | Trackwork | A16680 | Excavate, lay and concrete ducts | On Street - Other | Track | 1C | BB | 56537.6 | 0
York Place Ch 700 - 850 | Trackwork | A16690 | Excavate and construct OLE bases | On Street - Other | Track | 1C | BB | 14134.4 | 0
York Place Ch 700 - 850 | Trackwork | A16700 | Set Track (150m) | On Street - Other | Track | 1C | S |  | 0
York Place Ch 700 - 850 | Trackwork | A16710 | Place upper concrete and cure | On Street - Other | Track | 1C | S | 294178.6263 | 0
York Place Ch 700 - 850 | Trackwork | A16720 | Street Surface finishes | On Street - Other | Track | 1C | BB |  | 0
York Place Ch 700 - 850 | Trackwork | A16730 | Remove fencing and Traffic Management | On Street - Other | Track | 1C | BB | 62094.6 | 0
York Place Ch 700 - 850 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1C | BB | 4455.3507 | 0
York Place Ch 850 - 1000 | [7 empty] | 0 | 0
York Place Ch 850 - 1000 | Trackwork | [6 empty] | 0 | 0
York Place Ch 850 - 1000 | Trackwork | A13670 | Dummy | On Street - Other | Track | 1C | BB |  | 0
York Place Ch 850 - 1000 | Trackwork | A16740 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1C | BB | 14134.4 | 0
York Place Ch 850 - 1000 | Trackwork | A16750 | Excavate box | On Street - Other | Track | 1C | BB |  | 0
York Place Ch 850 - 1000 | Trackwork | A16760 | Excavate, lay and concrete ducts | On Street - Other | Track | 1C | BB | 56537.6 | 0
York Place Ch 850 - 1000 | Trackwork | A16770 | Excavate and construct OLE bases | On Street - Other | Track | 1C | BB | 14134.4 | 0
York Place Ch 850 - 1000 | Trackwork | A16780 | Set Track (150m) | On Street - Other | Track | 1C | S |  | 0
York Place Ch 850 - 1000 | Trackwork | A16790 | Place upper concrete and cure | On Street - Other | Track | 1C | S | 294178.6263 | 0
York Place Ch 850 - 1000 | Trackwork | A16800 | Street Surface finishes | On Street - Other | Track | 1C | BB |  | 0
York Place Ch 850 - 1000 | Trackwork | A16810 | Remove fencing and Traffic Management | On Street - Other | Track | 1C | BB | 62094.6 | 0
York Place Ch 850 - 1000 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1C | BB | 4455.3507 | 0
[8 empty] | 0 | 0
St Andrews Square to Waverley Bridge Ch 1000 - 1360 | [7 empty] | 0 | 0
St Andrews Square to Waverley Bridge Ch 1000 - 1360 | Trackwork | [6 empty] | 0 | 0
St Andrews Square to Waverley Bridge Ch 1000 - 1360 | Trackwork | A13530 | Dummy | On Street - Other | Track | 1C | BB |  | 0
St Andrews Square to Waverley Bridge Ch 1000 - 1360 | Trackwork | A16820 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1C | BB | 33922.6 | 0
St Andrews Square to Waverley Bridge Ch 1000 - 1360 | Trackwork | A16830 | Excavate box | On Street - Other | Track | 1C | BB |  | 0
St Andrews Square to Waverley Bridge Ch 1000 - 1360 | Trackwork | A16840 | Excavate, lay and concrete ducts | On Street - Other | Track | 1C | BB | 135690.4 | 0
St Andrews Square to Waverley Bridge Ch 1000 - 1360 | Trackwork | A16850 | Excavate and construct OLE bases | On Street - Other | Track | 1C | BB | 33922.6 | 0
St Andrews Square to Waverley Bridge Ch 1000 - 1360 | Trackwork | A16860 | Set Track (360m) | On Street - Other | Track | 1C | S | 706028.9673 | 0
St Andrews Square to Waverley Bridge Ch 1000 - 1360 | Trackwork | A16870 | Place upper concrete and cure | On Street - Other | Track | 1C | BB | 101767.8 | 0
St Andrews Square to Waverley Bridge Ch 1000 - 1360 | Trackwork | A16880 | Street Surface finishes | On Street - Other | Track | 1C | BB |  | 0
St Andrews Square to Waverley Bridge Ch 1000 - 1360 | Trackwork | A16890 | Remove fencing and Traffic Management | On Street - Other | Track | 1C | BB | 46513.6 | 0
St Andrews Square to Waverley Bridge Ch 1000 - 1360 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1C | BB | 10692.8417 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
Lothian Road Junction Ch 440 - 280 | [7 empty] | 0 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | [6 empty] | 0 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | Phase 2 - 1st Half | [5 empty] | 0 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8320 | Establish Traffic Management & Temp. Fencing | On Street - Princes St | Track | 1D | BB | 2413.8 | 2413.8
Lothian Road Junction Ch 440 - 280 | Trackwork | A8330 | Excavate box | On Street - Other | Track | 1D | BB |  | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8340 | Excavate, lay and concrete ducts | On Street - Other | Track | 1D | BB |  | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8350 | Excavate and construct OLE bases | On Street - Princes St | Track | 1D | BB | 12069 | 12069
Lothian Road Junction Ch 440 - 280 | Trackwork | A8370 | Set Track (100m) | On Street - Other | Track | 1D | S |  | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8380 | Place upper concrete and cure | On Street - Other | Track | 1D | S | 50165.1345 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8390 | Street Surface finishes | On Street - Other | Track | 1D | BB | 10603.2 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1D | BB | 724.7165 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | Phase 2 - 2nd Half | [5 empty] | 0 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8410 | Excavate box | On Street - Other | Track | 1D | BB |  | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8420 | Excavate, lay and concrete ducts | On Street - Other | Track | 1D | BB |  | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8450 | Set Track | On Street - Other | Track | 1D | S |  | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8460 | Place upper concrete and cure | On Street - Other | Track | 1D | BB |  | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8470 | Street Surface finishes | On Street - Other | Track | 1D | S | 44420.5787 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8480 | Remove fencing and Traffic Management | On Street - Other | Track | 1D | BB | 22147 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1D | BB | 707.7831 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | Phase 3a - 1st Half | [5 empty] | 0 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8680 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1D | BB |  | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8690 | Excavate box | On Street - Other | Track | 1D | BB |  | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8700 | Excavate, lay and concrete ducts | On Street - Other | Track | 1D | BB | 3448.5 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8710 | Excavate and construct OLE bases | On Street - Other | Track | 1D | BB | 689.7 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8730 | Set Track (30m) | On Street - Other | Track | 1D | S |  | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8740 | Place upper concrete and cure | On Street - Other | Track | 1D | S | 14355.2516 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8750 | Street Surface finishes | On Street - Other | Track | 1D | BB | 3029.8 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1D | BB | 217.415 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | Phase 3a - 2nd Half | [5 empty] | 0 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8760 | Excavate box | On Street - Other | Track | 1D | BB |  | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8770 | Excavate, lay and concrete ducts | On Street - Other | Track | 1D | BB |  | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8800 | Set Track | On Street - Other | Track | 1D | S |  | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8810 | Place upper concrete and cure | On Street - Other | Track | 1D | BB |  | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8820 | Street Surface finishes | On Street - Other | Track | 1D | S | 14019.9341 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8830 | Remove fencing and Traffic Management | On Street - Other | Track | 1D | BB | 7001 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1D | BB | 212.3349 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | Phase 4 - 1st Half | [5 empty] | 0 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8840 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1D | BB |  | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8850 | Excavate box | On Street - Other | Track | 1D | BB |  | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8860 | Excavate, lay and concrete ducts | On Street - Other | Track | 1D | BB | 3448.5 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8870 | Excavate and construct OLE bases | On Street - Other | Track | 1D | BB | 689.7 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8890 | Set Track (30m) | On Street - Other | Track | 1D | S | 14355.2516 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8900 | Place upper concrete and cure | On Street - Other | Track | 1D | BB |  | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8910 | Street Surface finishes | On Street - Other | Track | 1D | BB | 3029.8 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1D | BB | 217.415 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | Phase 4 - 2nd half | [5 empty] | 0 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8920 | Excavate box | On Street - Other | Track | 1D | BB |  | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8930 | Excavate, lay and concrete ducts | On Street - Other | Track | 1D | BB |  | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8960 | Set Track | On Street - Other | Track | 1D | S |  | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8970 | Place upper concrete and cure | On Street - Other | Track | 1D | S | 14019.9341 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8980 | Street Surface finishes | On Street - Other | Track | 1D | BB |  | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | A8990 | Remove fencing and Traffic Management | On Street - Other | Track | 1D | BB | 7001 | 0
Lothian Road Junction Ch 440 - 280 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1D | BB | 212.3349 | 0
Princes Street Ch 280 - 0, 1980 - 1360 | [7 empty] | 0 | 0
Princes Street Ch 280 - 0, 1980 - 1360 | Trackwork | [6 empty] | 0 | 0
Princes Street Ch 280 - 0, 1980 - 1360 | Trackwork | Phase 1 | [5 empty] | 0 | 0
Princes Street Ch 280 - 0, 1980 - 1360 | Trackwork | A13760 | Establish Traffic Management & Temp. Fencing | On Street - Princes St | Track | 1D | BB |  | 0
Princes Street Ch 280 - 0, 1980 - 1360 | Trackwork | A13770 | Excavate box | On Street - Princes St | Track | 1D | BB | 163603.6 | 163603.6
Princes Street Ch 280 - 0, 1980 - 1360 | Trackwork | A13780 | Excavate, lay and concrete ducts | On Street - Princes St | Track | 1D | BB |  | 0
Princes Street Ch 280 - 0, 1980 - 1360 | Trackwork | A13790 | Excavate and construct OLE bases | On Street - Princes St | Track | 1D | BB | 40900.9 | 40900.9
Princes Street Ch 280 - 0, 1980 - 1360 | Trackwork | A13810 | Set Track (950m) - 1st Half | On Street - Princes St | Track | 1D | S | 383070.6528 | 383070.6528
Princes Street Ch 280 - 0, 1980 - 1360 | Trackwork | A13810 | Set Track (950m) | On Street - Princes St | Track | 1D | S | 468197.4645 | 468197.4645
Princes Street Ch 280 - 0, 1980 - 1360 | Trackwork | A13830 | Street Surface finishes | On Street - Princes St | Track | 1D | BB | 81801.8 | 81801.8
Princes Street Ch 280 - 0, 1980 - 1360 | Trackwork | A13820 | Place Upper Concrete and Cure | On Street - Princes St | Track | 1D | BB | 138782.7 | 138782.7
Princes Street Ch 280 - 0, 1980 - 1360 | Trackwork | Snagging | Snagging | On Street - Princes St | Track | 1D | BB | 12892.497 | 0
[8 empty] | 0 | 0
Haymarket Ch 1250 - 1125 | [7 empty] | 0 | 0
Haymarket Ch 1250 - 1125 | Trackwork | [6 empty] | 0 | 0
Haymarket Ch 1250 - 1125 | Trackwork | Phase 3 - 1st Half | [5 empty] | 0 | 0
Haymarket Ch 1250 - 1125 | Trackwork | A6570 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1D | BB |  | 0
Haymarket Ch 1250 - 1125 | Trackwork | A6580 | Excavate box | On Street - Other | Track | 1D | BB |  | 0
Haymarket Ch 1250 - 1125 | Trackwork | A6590 | Excavate, lay and concrete ducts | On Street - Other | Track | 1D | BB |  | 0
Haymarket Ch 1250 - 1125 | Trackwork | A6600 | Excavate and construct OLE bases | On Street - Other | Track | 1D | BB | 4790 | 0
Haymarket Ch 1250 - 1125 | Trackwork | A6620 | Set Track (54m) | On Street - Other | Track | 1D | S |  | 0
Haymarket Ch 1250 - 1125 | Trackwork | A6630 | Place upper concrete and cure | On Street - Other | Track | 1D | S | 19938.3997 | 0
Haymarket Ch 1250 - 1125 | Trackwork | A6640 | Street Surface finishes | On Street - Other | Track | 1D | BB | 5166 | 0
Haymarket Ch 1250 - 1125 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1D | BB | 301.9652 | 0
Haymarket Ch 1250 - 1125 | Trackwork | Phase 3 - 2nd half | [5 empty] | 0 | 0
Haymarket Ch 1250 - 1125 | Trackwork | A6650 | Excavate box | On Street - Other | Track | 1D | BB |  | 0
Haymarket Ch 1250 - 1125 | Trackwork | A6660 | Excavate, lay and concrete ducts | On Street - Other | Track | 1D | BB |  | 0
Haymarket Ch 1250 - 1125 | Trackwork | A6690 | Set Track | On Street - Other | Track | 1D | S |  | 0
Haymarket Ch 1250 - 1125 | Trackwork | A6700 | Place upper concrete and cure | On Street - Other | Track | 1D | BB |  | 0
Haymarket Ch 1250 - 1125 | Trackwork | A6710 | Street Surface finishes | On Street - Other | Track | 1D | S | 18965.096 | 0
Haymarket Ch 1250 - 1125 | Trackwork | A6720 | Remove fencing and Traffic Management | On Street - Other | Track | 1D | BB | 9470 | 0
Haymarket Ch 1250 - 1125 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1D | BB | 287.2297 | 0
Haymarket Ch 1250 - 1125 | Trackwork | Phase 5 - 1st half | [5 empty] | 0 | 0
Haymarket Ch 1250 - 1125 | Trackwork | A6920 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1D | BB |  | 0
Haymarket Ch 1250 - 1125 | Trackwork | A6940 | Excavate box | On Street - Other | Track | 1D | BB |  | 0
Haymarket Ch 1250 - 1125 | Trackwork | A6950 | Excavate, lay and concrete ducts | On Street - Other | Track | 1D | BB |  | 0
Haymarket Ch 1250 - 1125 | Trackwork | A6960 | Excavate and construct OLE bases | On Street - Other | Track | 1D | BB | 4790 | 0
Haymarket Ch 1250 - 1125 | Trackwork | A6980 | Set Track (54m) | On Street - Other | Track | 1D | S |  | 0
Haymarket Ch 1250 - 1125 | Trackwork | A6990 | Place upper concrete and cure | On Street - Other | Track | 1D | S | 19938.3997 | 0
Haymarket Ch 1250 - 1125 | Trackwork | A7000 | Street Surface finishes | On Street - Other | Track | 1D | BB | 5166 | 0
Haymarket Ch 1250 - 1125 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1D | BB | 301.9652 | 0
Haymarket Ch 1250 - 1125 | Trackwork | Phase 5 - 2nd half | [5 empty] | 0 | 0
Haymarket Ch 1250 - 1125 | Trackwork | A7075 | Remove fencing and Traffic Management | On Street - Other | Track | 1D | BB |  | 0
Haymarket Ch 1250 - 1125 | Trackwork | A7010 | Excavate box | On Street - Other | Track | 1D | BB |  | 0
Haymarket Ch 1250 - 1125 | Trackwork | A7020 | Excavate, lay and concrete ducts | On Street - Other | Track | 1D | BB |  | 0
Haymarket Ch 1250 - 1125 | Trackwork | A7050 | Set Track | On Street - Other | Track | 1D | S |  | 0
Haymarket Ch 1250 - 1125 | Trackwork | A7060 | Place upper concrete and cure | On Street - Other | Track | 1D | S | 19472.4242 | 0
Haymarket Ch 1250 - 1125 | Trackwork | A7070 | Street Surface finishes | On Street - Other | Track | 1D | BB | 9724 | 0
Haymarket Ch 1250 - 1125 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1D | BB | 294.9096 | 0
Haymarket Ch 1250 - 1125 | Trackwork | Phase 6a - 1st Half | [5 empty] | 0 | 0
Haymarket Ch 1250 - 1125 | Trackwork | A7080 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1D | BB |  | 0
Haymarket Ch 1250 - 1125 | Trackwork | A7100 | Excavate box | On Street - Other | Track | 1D | BB |  | 0
Haymarket Ch 1250 - 1125 | Trackwork | A7110 | Excavate, lay and concrete ducts | On Street - Other | Track | 1D | BB |  | 0
Haymarket Ch 1250 - 1125 | Trackwork | A7120 | Excavate and construct OLE bases | On Street - Other | Track | 1D | BB | 4790 | 0
Haymarket Ch 1250 - 1125 | Trackwork | A7140 | Set Track (54m) | On Street - Other | Track | 1D | S |  | 0
Haymarket Ch 1250 - 1125 | Trackwork | A7150 | Place upper concrete and cure | On Street - Other | Track | 1D | S | 19938.3997 | 0
Haymarket Ch 1250 - 1125 | Trackwork | A7160 | Street Surface finishes | On Street - Other | Track | 1D | BB | 5166 | 0
Haymarket Ch 1250 - 1125 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1D | BB | 301.9652 | 0
Haymarket Ch 1250 - 1125 | Trackwork | Phase 6a - 2nd Half | [5 empty] | 0 | 0
Haymarket Ch 1250 - 1125 | Trackwork | A7235 | Remove fencing and Traffic Management | On Street - Other | Track | 1D | BB |  | 0
Haymarket Ch 1250 - 1125 | Trackwork | A7170 | Excavate box | On Street - Other | Track | 1D | BB |  | 0
Haymarket Ch 1250 - 1125 | Trackwork | A7180 | Excavate, lay and concrete ducts | On Street - Other | Track | 1D | BB |  | 0
Haymarket Ch 1250 - 1125 | Trackwork | A7210 | Set Track | On Street - Other | Track | 1D | S |  | 0
Haymarket Ch 1250 - 1125 | Trackwork | A7220 | Place upper concrete and cure | On Street - Other | Track | 1D | S | 19472.4242 | 0
Haymarket Ch 1250 - 1125 | Trackwork | A7230 | Street Surface finishes | On Street - Other | Track | 1D | BB | 9724 | 0
Haymarket Ch 1250 - 1125 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1D | BB | 294.9096 | 0
Torphicen Ch 1125 - 940 | [7 empty] | 0 | 0
Torphicen Ch 1125 - 940 | Trackwork | [6 empty] | 0 | 0
Torphicen Ch 1125 - 940 | Trackwork | Phase 1 - 1st Half | [5 empty] | 0 | 0
Torphicen Ch 1125 - 940 | Trackwork | A7360 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1D | BB |  | 0
Torphicen Ch 1125 - 940 | Trackwork | A7380 | Excavate box | On Street - Other | Track | 1D | BB |  | 0
Torphicen Ch 1125 - 940 | Trackwork | A7390 | Excavate, lay and concrete ducts | On Street - Other | Track | 1D | BB | 20002.2 | 0
Torphicen Ch 1125 - 940 | Trackwork | A7400 | Excavate and construct OLE bases | On Street - Other | Track | 1D | BB | 6667.4 | 0
Torphicen Ch 1125 - 940 | Trackwork | A7420 | Set Track (145m) | On Street - Other | Track | 1D | S |  | 0
Torphicen Ch 1125 - 940 | Trackwork | A7430 | Place upper concrete and cure | On Street - Other | Track | 1D | S | 69384.7065 | 0
Torphicen Ch 1125 - 940 | Trackwork | A7440 | Street Surface finishes | On Street - Other | Track | 1D | BB | 7978.4 | 0
Torphicen Ch 1125 - 940 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1D | BB | 1050.839 | 0
Torphicen Ch 1125 - 940 | Trackwork | Phase 1 - 2nd Half | [5 empty] | 0 | 0
Torphicen Ch 1125 - 940 | Trackwork | A7515 | Remove fencing and Traffic Management | On Street - Other | Track | 1D | BB |  | 0
Torphicen Ch 1125 - 940 | Trackwork | A7450 | Excavate box | On Street - Other | Track | 1D | BB |  | 0
Torphicen Ch 1125 - 940 | Trackwork | A7460 | Excavate, lay and concrete ducts | On Street - Other | Track | 1D | BB |  | 0
Torphicen Ch 1125 - 940 | Trackwork | A7490 | Set Track | On Street - Other | Track | 1D | S | 67763.4552 | 0
Torphicen Ch 1125 - 940 | Trackwork | A7500 | Place upper concrete and cure | On Street - Other | Track | 1D | BB | 19534.8 | 0
Torphicen Ch 1125 - 940 | Trackwork | A7510 | Street Surface finishes | On Street - Other | Track | 1D | BB | 14303.2 | 0
Torphicen Ch 1125 - 940 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1D | BB | 1026.2856 | 0
Torphicen Ch 1125 - 940 | Trackwork | Phase 2 - 1st Half | [5 empty] | 0 | 0
Torphicen Ch 1125 - 940 | Trackwork | A7520 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1D | BB |  | 0
Torphicen Ch 1125 - 940 | Trackwork | A7540 | Excavate box | On Street - Other | Track | 1D | BB |  | 0
Torphicen Ch 1125 - 940 | Trackwork | A7550 | Excavate, lay and concrete ducts | On Street - Other | Track | 1D | BB |  | 0
Torphicen Ch 1125 - 940 | Trackwork | A7560 | Excavate and construct OLE bases | On Street - Other | Track | 1D | BB | 4598.5 | 0
Torphicen Ch 1125 - 940 | Trackwork | A7580 | Set Track (40m) | On Street - Other | Track | 1D | S |  | 0
Torphicen Ch 1125 - 940 | Trackwork | A7590 | Place upper concrete and cure | On Street - Other | Track | 1D | S | 19140.9957 | 0
Torphicen Ch 1125 - 940 | Trackwork | A7600 | Street Surface finishes | On Street - Other | Track | 1D | BB | 4959.5 | 0
Torphicen Ch 1125 - 940 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1D | BB | 289.8866 | 0
Torphicen Ch 1125 - 940 | Trackwork | Phase 2 - 2nd Half | [5 empty] | 0 | 0
Torphicen Ch 1125 - 940 | Trackwork | A7675 | Remove fencing and Traffic Management | On Street - Other | Track | 1D | BB |  | 0
Torphicen Ch 1125 - 940 | Trackwork | A7610 | Excavate box | On Street - Other | Track | 1D | BB |  | 0
Torphicen Ch 1125 - 940 | Trackwork | A7620 | Excavate, lay and concrete ducts | On Street - Other | Track | 1D | BB |  | 0
Torphicen Ch 1125 - 940 | Trackwork | A7650 | Set Track | On Street - Other | Track | 1D | S |  | 0
Torphicen Ch 1125 - 940 | Trackwork | A7660 | Place upper concrete and cure | On Street - Other | Track | 1D | S | 18693.6857 | 0
Torphicen Ch 1125 - 940 | Trackwork | A7670 | Street Surface finishes | On Street - Other | Track | 1D | BB | 9335 | 0
Torphicen Ch 1125 - 940 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1D | BB | 283.1133 | 0
West Mailtland Ch 940 - 850 | [7 empty] | 0 | 0
West Mailtland Ch 940 - 850 | Trackwork | [6 empty] | 0 | 0
West Mailtland Ch 940 - 850 | Trackwork | Phases 2 & 3 - 1st Half | [5 empty] | 0 | 0
West Maitland Ch 940 - 850 | Trackwork | A7940 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1D | BB |  | 0
West Maitland Ch 940 - 850 | Trackwork | A7960 | Excavate box | On Street - Other | Track | 1D | BB |  | 0
West Maitland Ch 940 - 850 | Trackwork | A7970 | Excavate, lay and concrete ducts | On Street - Other | Track | 1D | BB |  | 0
West Maitland Ch 940 - 850 | Trackwork | A7980 | Excavate and construct OLE bases | On Street - Other | Track | 1D | BB | 12415.2 | 0
West Maitland Ch 940 - 850 | Trackwork | A8000 | Set Track (90m) | On Street - Other | Track | 1D | S |  | 0
West Maitland Ch 940 - 850 | Trackwork | A8010 | Place upper concrete and cure | On Street - Other | Track | 1D | S | 43066.4151 | 0
West Maitland Ch 940 - 850 | Trackwork | A8020 | Street Surface finishes | On Street - Other | Track | 1D | BB | 9090.8 | 0
West Maitland Ch 940 - 850 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1D | BB | 652.2449 | 0
West Mailtland Ch 940 - 850 | Trackwork | Phases 2 & 3 - 2nd Half | [5 empty] | 0 | 0
West Maitland Ch 940 - 850 | Trackwork | A8095 | Remove fencing and Traffic Management | On Street - Other | Track | 1D | BB |  | 0
West Maitland Ch 940 - 850 | Trackwork | A8030 | Excavate box | On Street - Other | Track | 1D | BB |  | 0
West Maitland Ch 940 - 850 | Trackwork | A8040 | Excavate, lay and concrete ducts | On Street - Other | Track | 1D | BB |  | 0
West Maitland Ch 940 - 850 | Trackwork | A8070 | Set Track | On Street - Other | Track | 1D | S |  | 0
West Maitland Ch 940 - 850 | Trackwork | A8080 | Place upper concrete and cure | On Street - Other | Track | 1D | S | 42060.4627 | 0
West Maitland Ch 940 - 850 | Trackwork | A8090 | Street Surface finishes | On Street - Other | Track | 1D | BB | 21003 | 0
West Maitland Ch 940 - 850 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1D | BB | 637.0048 | 0
Shandwick Place Ch 850 - 440 | [7 empty] | 0 | 0
Shandwick Place Ch 850 - 440 | Trackwork | [6 empty] | 0 | 0
Shandwick Place Ch 850 - 440 | Trackwork | Phase 1 | [5 empty] | 0 | 0
Shandwick Place Ch 850 - 440 | Trackwork | A8100 | Establish Traffic Management & Temp. Fencing | On Street - Other | Track | 1D | BB |  | 0
Shandwick Place Ch 850 - 440 | Trackwork | A8110 | Excavate box | On Street - Other | Track | 1D | BB |  | 0
Shandwick Place Ch 850 - 440 | Trackwork | A8120 | Excavate, lay and concrete ducts | On Street - Other | Track | 1D | BB | 74530.4 | 0
Shandwick Place Ch 850 - 440 | Trackwork | A8130 | Excavate and construct OLE bases | On Street - Other | Track | 1D | BB | 18632.6 | 0
Shandwick Place Ch 850 - 440 | Trackwork | A8150 | Set Track (410m) | On Street - Other | Track | 1D | S | 387799.7073 | 0
Shandwick Place Ch 850 - 440 | Trackwork | A8170 | Street Surface finishes | On Street - Other | Track | 1D | BB |  | 0
Shandwick Place Ch 850 - 440 | Trackwork | A8175 | Remove fencing and Traffic Management | On Street - Other | Track | 1D | BB | 55897.8 | 0
Shandwick Place Ch 850 - 440 | Trackwork | A8160 | Place Upper Concrete and Cure | On Street - Other | Track | 1D | BB | 44591.2 | 0
Shandwick Place Ch 850 - 440 | Trackwork | Snagging | Snagging | On Street - Other | Track | 1D | BB | 5873.2486 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
Haymarket to Roseburn Junction | [7 empty] | 0 | 0
Haymarket to Roseburn Junction | Trackwork | [6 empty] | 0 | 0
Haymarket to Roseburn Junction | Trackwork | 550 | Fencing | Off Street - Other | Track | 2A | BB | 151909.2 | 0
Haymarket to Roseburn Junction | Trackwork | 263 | Track Finishes | Off Street - Other | Track | 2A | BB |  | 0
Haymarket to Roseburn Junction | Trackwork | 1119 | CBM- Ducts | Off Street - Other | Track | 2A | BB |  | 0
Haymarket to Roseburn Junction | Trackwork | 1129 | Track Laying - 1 Third | Off Street - Other | Track | 2A | S | 632336.0495 | 0
Haymarket to Roseburn Junction | Trackwork | 1129 | Track Laying - 1 Third | Off Street - Other | Track | 2A | S | 632336.0495 | 0
Haymarket to Roseburn Junction | Trackwork | 1129 | Track Laying | Off Street - Other | Track | 2A | S | 316168.0247 | 0
Haymarket to Roseburn Junction | Trackwork | 1099 | Bulk Excavation - Sub Base | Off Street - Other | Track | 2A | BB | 379773 | 0
Haymarket to Roseburn Junction | Trackwork | 1109 | OLE Foundations - Drainage | Off Street - Other | Track | 2A | BB | 257726.8 | 0
Haymarket to Roseburn Junction | Trackwork | Snagging | Snagging | Off Street - Other | Track | 2A | BB | 23941.9099 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
Roseburn Junction to Murrayfield Trackwork (470m) | [7 empty] | 0 | 0
Roseburn Junction to Murrayfield Trackwork (470m) | Trackwork | [6 empty] | 0 | 0
Roseburn Junction to Murrayfield Trackwork (470m) | Trackwork | 540 | Fencing | Off Street - Other | Track | 5A | BB | 107137.5 | 0
Roseburn Junction to Murrayfield Trackwork (470m) | Trackwork | 253 | Track Finishes | Off Street - Other | Track | 5A | BB |  | 0
Roseburn Junction to Murrayfield Trackwork (470m) | Trackwork | 1049 | CBM- Ducts | Off Street - Other | Track | 5A | BB | 107137.5 | 0
Roseburn Junction to Murrayfield Trackwork (470m) | Trackwork | 1059 | Track Laying ROJ - MUR - 1 Half | Off Street - Other | Track | 5A | S | 408805.3707 | 0
Roseburn Junction to Murrayfield Trackwork (470m) | Trackwork | 1059 | Track Laying ROJ - MUR | Off Street - Other | Track | 5A | S | 334477.1215 | 0
Roseburn Junction to Murrayfield Trackwork (470m) | Trackwork | 1029 | Bulk Excavation - Sub Base | Off Street - Other | Track | 5A | BB |  | 0
Roseburn Junction to Murrayfield Trackwork (470m) | Trackwork | 1039 | OLE Foundations - Drainage | Off Street - Other | Track | 5A | BB | 156891 | 0
Roseburn Junction to Murrayfield Trackwork (470m) | Trackwork | Snagging | Snagging | Off Street - Other | Track | 5A | BB | 11257.0512 | 0
[8 empty] | 0 | 0
Murrayfield to Balgreen Road Trackwork (1006m) | [7 empty] | 0 | 0
Murrayfield to Balgreen Road Trackwork (1006m) | Trackwork | [6 empty] | 0 | 0
Murrayfield to Balgreen Road Trackwork (1006m) | Trackwork | 530 | Tracklaying | Off Street - Other | Track | 5A | S | 1610977.276 | 0
Murrayfield to Balgreen Road Trackwork (1006m) | Trackwork | 243 | CBM - Ducts | Off Street - Other | Track | 5A | BB | 299000 | 0
Murrayfield to Balgreen Road Trackwork (1006m) | Trackwork | 989 | Track Finishes | Off Street - Other | Track | 5A | BB |  | 0
Murrayfield to Balgreen Road Trackwork (1006m) | Trackwork | 999 | Fencing | Off Street - Other | Track | 5A | BB | 74750 | 0
Murrayfield to Balgreen Road Trackwork (1006m) | Trackwork | 1009 | Bulk Excavation - Sub Base | Off Street - Other | Track | 5A | BB | 265185 | 0
Murrayfield to Balgreen Road Trackwork (1006m) | Trackwork | 1019 | OLE Foundations - Drainage | Off Street - Other | Track | 5A | BB | 74750 | 0
Murrayfield to Balgreen Road Trackwork (1006m) | Trackwork | Snagging | Snagging | Off Street - Other | Track | 5A | BB | 84824.8799 | 0
Murrayfield to Balgreen Road Trackwork (1006m) | Trackwork | 3rd Party | Third Party Sign-off | Off Street - Other | Track | 5A | BB | 25000 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
Ballasted Track 1160m | [7 empty] | 0 | 0
Ballasted Track 1160m | Trackwork | [6 empty] | 0 | 0
Ballasted Track 1160m | Trackwork | 1534 | OLE Foundations - Drainage | Off Street - Other | Track | 5B | BB | 77360.4 | 0
Ballasted Track 1160m | Trackwork | 1533 | Earthworks - Subbase | Off Street - Other | Track | 5B | BB | 386802 | 0
Ballasted Track 1160m | Trackwork | 1609 | Bottom Ballast - Ducts | Off Street - Other | Track | 5B | BB | 77360.4 | 0
Ballasted Track 1160m | Trackwork | 1619 | Track laying - 50% | Off Street - Other | Track | 5B | S | 805048.9266 | 0
Ballasted Track 1160m | Trackwork | 1619 | Track laying | Off Street - Other | Track | 5B | S | 805048.9266 | 0
Ballasted Track 1160m | Trackwork | 1629 | Top Ballast | Off Street - Other | Track | 5B | BB | 154720.8 | 0
Ballasted Track 1160m | Trackwork | 1639 | Fencing & Trackside Finishes | Off Street - Other | Track | 5B | BB | 107775.4 | 0
Ballasted Track 1160m | Trackwork | Snagging | Snagging | Off Street - Other | Track | 5B | BB | 24385.0119 | 0
Concrete Slab Track 590m | [7 empty] | 0 | 0
Concrete Slab Track 590m | Trackwork | [6 empty] | 0 | 0
Guided Busway | Trackwork | 1544 | OLE Foundations - Drainage - Ducts | Off Street - Other | Track | 5B | BB | 124431 | 0
Guided Busway | Trackwork | 1543 | Piling | Off Street - Other | Track | 5B | BB | 82954 | 82954
Guided Busway | Trackwork | 1543 | Earthworks- Subbase | Off Street - Other | Track | 5B | BB | 124430.7 | 0
Guided Busway | Trackwork | 1659 | Track laying - 50% | Off Street - Other | Track | 5B | S | 431628.3115 | 0
Guided Busway | Trackwork | 1659 | Track laying - 50% | Off Street - Other | Track | 5B | S | 431628.3115 | 0
Guided Busway | Trackwork | 1679 | Fencing & Finishes | Off Street - Other | Track | 5B | BB | 99260.8 | 0
Guided Busway | Trackwork | Snagging | Snagging | Off Street - Other | Track | 5B | BB | 13074.0653 | 0
[8 empty] | 0 | 0
Saughton Road North to South Gyle Access Trackwork (1260m) | [7 empty] | 0 | 0
Saughton Road North to South Gyle Access Trackwork (1260m) | Trackwork | [6 empty] | 0 | 0
Saughton Road North to South Gyle Access Trackwork (1260m) | Trackwork | 510 | OLE Foundations - Drainage - Ducts | Off Street - Other | Track | 5B | BB | 177155.6 | 0
Saughton Road North to South Gyle Access Trackwork (1260m) | Trackwork | 223 | Earthworks and Subbase | Off Street - Other | Track | 5B | BB | 442889 | 0
Saughton Road North to South Gyle Access Trackwork (1260m) | Trackwork | 919 | Track laying - 25% | Off Street - Other | Track | 5B | S | 460891.2702 | 0
Saughton Road North to South Gyle Access Trackwork (1260m) | Trackwork | 919 | Track laying - 25% | Off Street - Other | Track | 5B | S | 460891.2702 | 0
Saughton Road North to South Gyle Access Trackwork (1260m) | Trackwork | 919 | Track laying - 25% | Off Street - Other | Track | 5B | S | 460891.2702 | 0
Saughton Road North to South Gyle Access Trackwork (1260m) | Trackwork | 919 | Track laying | Off Street - Other | Track | 5B | S | 460891.2702 | 0
Saughton Road North to South Gyle Access Trackwork (1260m) | Trackwork | 939 | Fencing & Trackside Finishes | Off Street - Other | Track | 5B | BB | 300558.4 | 0
Saughton Road North to South Gyle Access Trackwork (1260m) | Trackwork | 13000 | Delay Start to Maintain Guided Busway | Off Street - Other | Track | 5B | BB |  | 0
Saughton Road North to South Gyle Access Trackwork (1260m) | Trackwork | Snagging | Snagging | Off Street - Other | Track | 5B | BB | 27920.8852 | 0
[8 empty] | 0 | 0
South Gyle Access to Edinburgh Park Station Trackwork (790m) | [7 empty] | 0 | 0
South Gyle Access to Edinburgh Park Station Trackwork (790m) | Trackwork | [6 empty] | 0 | 0
South Gyle Access to Edinburgh Park Station Trackwork (790m) | Trackwork | 500 | OLE Foundations - Drainage | Off Street - Other | Track | 5B | BB | 55536.8 | 0
South Gyle Access to Edinburgh Park Station Trackwork (790m) | Trackwork | 213 | Earthworks and Subbase | Off Street - Other | Track | 5B | BB | 222147.2 | 0
South Gyle Access to Edinburgh Park Station Trackwork (790m) | Trackwork | 859 | Ducts and Bottom Ballast | Off Street - Other | Track | 5B | BB | 111073.6 | 0
South Gyle Access to Edinburgh Park Station Trackwork (790m) | Trackwork | 879 | Track laying | Off Street - Other | Track | 5B | S | 1155885.5502 | 0
South Gyle Access to Edinburgh Park Station Trackwork (790m) | Trackwork | 889 | Top Ballast | Off Street - Other | Track | 5B | BB | 111073.6 | 0
South Gyle Access to Edinburgh Park Station Trackwork (790m) | Trackwork | 899 | Fencing and Trackside finishes | Off Street - Other | Track | 5B | BB | 77371.8 | 0
South Gyle Access to Edinburgh Park Station Trackwork (790m) | Trackwork | Snagging | Snagging | Off Street - Other | Track | 5B | BB | 17505.9518 | 0
[8 empty] | 0 | 0
Edinburgh Park Station to Edinburgh Park Trackwork (854m) | [7 empty] | 0 | 0
Edinburgh Park Station to Edinburgh Park Trackwork (854m) | Trackwork | [6 empty] | 0 | 0
Edinburgh Park Station to Edinburgh Park Trackwork (854m) | Trackwork | 490 | OLE Foundations - Drainage | Off Street - Other | Track | 5B | BB | 61309.2 | 0
Edinburgh Park Station to Edinburgh Park Trackwork (854m) | Trackwork | 203 | Earthworks- Subbase | Off Street - Other | Track | 5B | BB | 245236.8 | 0
Edinburgh Park Station to Edinburgh Park Trackwork (854m) | Trackwork | 829 | Track Formation - Ducts | Off Street - Other | Track | 5B | BB | 122618.4 | 0
Edinburgh Park Station to Edinburgh Park Trackwork (854m) | Trackwork | 839 | Track laying | Off Street - Other | Track | 5B | S | 618516.1005 | 0
Edinburgh Park Station to Edinburgh Park Trackwork (854m) | Trackwork | 839 | Track laying | Off Street - Other | Track | 5B | S | 618516.1005 | 0
Edinburgh Park Station to Edinburgh Park Trackwork (854m) | Trackwork | 849 | Track Finishes | Off Street - Other | Track | 5B | BB |  | 0
Edinburgh Park Station to Edinburgh Park Trackwork (854m) | Trackwork | 869 | Fencing | Off Street - Other | Track | 5B | BB | 207295.6 | 0
Edinburgh Park Station to Edinburgh Park Trackwork (854m) | Trackwork | Snagging | Snagging | Off Street - Other | Track | 5B | BB | 18924.1555 | 0
Edinburgh Park Station Bridge (S27) Disruptive Possessions | [7 empty] | 0 | 0
Bridges | Trackwork | [6 empty] | 0 | 0
Edinburgh Park Station Bridge (S27) Disruptive Possessions | Bridge | 258 | Trackwork | Off Street - Other | Structures | 5B | BB |  | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
Edinburgh Park to Gyle Trackwork (760m) | [7 empty] | 0 | 0
Edinburgh Park to Gyle Trackwork (760m) | Trackwork | [6 empty] | 0 | 0
Edinburgh Park to Gyle Trackwork (760m) | Trackwork | 140 | Earthworks and Subbase | Off Street - Other | Track | 5C | BB | 195142.8 | 29271.42
Edinburgh Park to Gyle Trackwork (760m) | Trackwork | 183 | OLE Foundations - Drainage | Off Street - Other | Track | 5C | BB | 57510.6 | 0
Edinburgh Park to Gyle Trackwork (760m) | Trackwork | 779 | Track Formation and Ducts | Off Street - Other | Track | 5C | BB | 57510.6 | 0
Edinburgh Park to Gyle Trackwork (760m) | Trackwork | 789 | Track laying sub-section 06 Edin Park Central to Gyle - 40% | Off Street - Other | Track | 5C | S | 478786.2499 | 0
Edinburgh Park to Gyle Trackwork (760m) | Trackwork | 789 | Track laying sub-section 06 Edin Park Central to Gyle - 60% | Off Street - Other | Track | 5C | S | 718179.3748 | 0
Edinburgh Park to Gyle Trackwork (760m) | Trackwork | 799 | Track Finishes | Off Street - Other | Track | 5C | BB | 115021.2 | 0
Edinburgh Park to Gyle Trackwork (760m) | Trackwork | 809 | Road Crossings | Off Street - Other | Track | 5C | BB | 57510.6 | 0
Edinburgh Park to Gyle Trackwork (760m) | Trackwork | 819 | Fencing | Off Street - Other | Track | 5C | BB | 115021.2 | 0
Edinburgh Park to Gyle Trackwork (760m) | Trackwork | Snagging | Snagging | Off Street - Other | Track | 5C | BB | 18128.1079 | 0
[8 empty] | 0 | 0
Gyle to Depot Stop Trackwork (562m) | [7 empty] | 0 | 0
Gyle to Depot Stop Trackwork (562m) | Trackwork | [6 empty] | 0 | 0
Gyle to Depot Stop Trackwork (562m) | Trackwork | 478 | Track Laying | Off Street - Other | Track | 5C | S | 885124.7437 | 0
Gyle to Depot Stop Trackwork (562m) | Trackwork | A2380 | Track Finishes | Off Street - Other | Track | 5C | BB |  | 0
Gyle to Depot Stop Trackwork (562m) | Trackwork | A2390 | Fencing and Reinstatements | Off Street - Other | Track | 5C | BB | 85055.2 | 0
Gyle to Depot Stop Trackwork (562m) | Trackwork | 1069 | Bulk Excavation | Off Street - Other | Track | 5C | BB | 127582.8 | 0
Gyle to Depot Stop Trackwork (562m) | Trackwork | 1079 | Drainage and OLE Foundations | Off Street - Other | Track | 5C | BB | 85055.2 | 0
Gyle to Depot Stop Trackwork (562m) | Trackwork | 1089 | Track Formation and Ducts | Off Street - Other | Track | 5C | BB | 144302.8 | 0
Gyle to Depot Stop Trackwork (562m) | Trackwork | Snagging | Snagging | Off Street - Other | Track | 5C | BB | 13405.2588 | 0
[8 empty] | 0 | 0
Depot Stop to Gogarburn Trackwork (562m) | [7 empty] | 0 | 0
Depot Stop to Gogarburn Trackwork (562m) | Trackwork | [6 empty] | 0 | 0
Depot Stop to Gogarburn Trackwork (562m) | Trackwork | 148 | Ramp Wall out of depot (details unknown) | Off Street - Other | Track | 5C | BB | 85055.2 | 0
Depot Stop to Gogarburn Trackwork (562m) | Trackwork | A2330 | Track Finishes | Off Street - Other | Track | 5C | BB |  | 0
Depot Stop to Gogarburn Trackwork (562m) | Trackwork | A2340 | Fencing and Reinstatements | Off Street - Other | Track | 5C | BB | 85055.2 | 0
Depot Stop to Gogarburn Trackwork (562m) | Trackwork | 749 | Drainage and OLE Foundations | Off Street - Other | Track | 5C | BB | 42527.6 | 0
Depot Stop to Gogarburn Trackwork (562m) | Trackwork | 759 | Track Formation and Ducts | Off Street - Other | Track | 5C | BB | 85055.2 | 0
Depot Stop to Gogarburn Trackwork (562m) | Trackwork | 769 | Track Laying - 50% | Off Street - Other | Track | 5C | S | 442562.3719 | 0
Depot Stop to Gogarburn Trackwork (562m) | Trackwork | 769 | Track Laying | Off Street - Other | Track | 5C | S | 442562.3719 | 0
Depot Stop to Gogarburn Trackwork (562m) | Trackwork | 288 | Earthworks and Subbase | Off Street - Other | Track | 5C | BB | 144302.8 | 0
Depot Stop to Gogarburn Trackwork (562m) | Trackwork | Snagging | Snagging | Off Street - Other | Track | 5C | BB | 13405.2588 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
Depot | [7 empty] | 0 | 0
Depot Trackwork | Trackwork | 154 | Trackwork Depot | Off Street Depot | Track | 6A | BB | 62977.6 | 0
Depot Trackwork | Trackwork | 154 | Trackwork Depot | Off Street Depot | Track | 6A | BB | 62977.6 | 0
Depot Trackwork | Trackwork | 154 | Trackwork Depot | Off Street Depot | Track | 6A | BB | 62977.6 | 0
Depot Trackwork | Trackwork | 154 | Trackwork Depot | Off Street Depot | Track | 6A | BB | 62977.6 | 0
Depot Trackwork | Trackwork | 154 | Trackwork Depot | Off Street Depot | Track | 6A | BB | 75357.6 | 0
Depot Trackwork | Trackwork | 204 | Track Laying Depot | Off Street Depot | Track | 6A | S | 218458.0932 | 0
Depot Trackwork | Trackwork | 204 | Track Laying Depot | Off Street Depot | Track | 6A | S | 218458.0932 | 0
Depot Trackwork | Trackwork | 204 | Track Laying Depot | Off Street Depot | Track | 6A | S | 218458.0932 | 0
Depot Trackwork | Trackwork | Snagging | Snagging | Off Street Depot | Track | 6A | BB | 9925.673 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
Gogarburn to Inglishton Park & Ride Trackwork (1750m) | [7 empty] | 0 | 0
Gogarburn to Inglishton Park & Ride Trackwork (1750m) | Trackwork | [6 empty] | 0 | 0
Gogarburn to Inglishton Park & Ride Trackwork (1750m) | Trackwork | 162 | Earthworks and Subbase | Off Street - Other | Track | 7A | BB | 259494 | 0
Gogarburn to Inglishton Park & Ride Trackwork (1750m) | Trackwork | A1990 | Top Ballast | Off Street - Other | Track | 7A | BB | 86498 | 0
Gogarburn to Inglishton Park & Ride Trackwork (1750m) | Trackwork | A2020 | Fencing & Trackside Finishes | Off Street - Other | Track | 7A | BB | 86498 | 0
Gogarburn to Inglishton Park & Ride Trackwork (1750m) | Trackwork | 399 | Drainage and OLE Foundations - 50% | Off Street - Other | Track | 7A | BB | 86498 | 0
Gogarburn to Inglishton Park & Ride Trackwork (1750m) | Trackwork | 399 | Drainage and OLE Foundations - 50% | Off Street - Other | Track | 7A | BB | 157362 | 0
Gogarburn to Inglishton Park & Ride Trackwork (1750m) | Trackwork | 409 | Bottom Balast and Ducts - 30% | Off Street - Other | Track | 7A | BB | 87735 | 0
Gogarburn to Inglishton Park & Ride Trackwork (1750m) | Trackwork | 409 | Bottom Balast and Ducts - 70% | Off Street - Other | Track | 7A | BB | 172996 | 0
Gogarburn to Inglishton Park & Ride Trackwork (1750m) | Trackwork | 419 | Track Laying - 60% | Off Street - Other | Track | 7A | S | 1874471.7114 | 0
Gogarburn to Inglishton Park & Ride Trackwork (1750m) | Trackwork | 419 | Track Laying - 40% | Off Street - Other | Track | 7A | S | 1875688.7114 | 0
Gogarburn to Inglishton Park & Ride Trackwork (1750m) | Trackwork | Snagging | Snagging | Off Street - Other | Track | 7A | BB | 47345.6721 | 0
[8 empty] | 0 | 0
Inglishton Park & Ride to Edinburgh Airport Trackwork (833m) | [7 empty] | 0 | 0
Inglishton Park & Ride to Edinburgh Airport Trackwork (833m) | Trackwork | [6 empty] | 0 | 0
Inglishton Park & Ride to Edinburgh Airport Trackwork (833m) | Trackwork | 168 | Earthworks and Subbase | Off Street - Other | Track | 7A | BB | 214488.6 | 0
Inglishton Park & Ride to Edinburgh Airport Trackwork (833m) | Trackwork | A1910 | Top Ballast | Off Street - Other | Track | 7A | BB | 142992.4 | 0
Inglishton Park & Ride to Edinburgh Airport Trackwork (833m) | Trackwork | 369 | Drainage and OLE Foundations | Off Street - Other | Track | 7A | BB | 99605.2 | 0
Inglishton Park & Ride to Edinburgh Airport Trackwork (833m) | Trackwork | 379 | Bottom Ballast and Ducts | Off Street - Other | Track | 7A | BB | 142992.4 | 0
Inglishton Park & Ride to Edinburgh Airport Trackwork (833m) | Trackwork | 389 | Track Laying IPR to AIR - 50% | Off Street - Other | Track | 7A | S | 744023.3035 | 0
Inglishton Park & Ride to Edinburgh Airport Trackwork (833m) | Trackwork | 389 | Track Laying IPR to AIR - 50% | Off Street - Other | Track | 7A | S | 744023.3035 | 0
Inglishton Park & Ride to Edinburgh Airport Trackwork (833m) | Trackwork | A2350 | Fencing & Trackside Finishes | Off Street - Other | Track | 7A | BB | 142992.4 | 0
Inglishton Park & Ride to Edinburgh Airport Trackwork (833m) | Trackwork | Snagging | Snagging | Off Street - Other | Track | 7A | BB | 22536.5399 | 0
0
0
0
0
Newhaven to Ocean Terminal | [8 empty] | 0
Newhaven to Ocean Terminal | E & M Installations | [7 empty] | 0
Newhaven to Ocean Terminal | E & M Installations | A17000 | Access for E&M wayside installation (01A) | On Street - Other | SCC | 1A | S | 0 | 0
Newhaven to Ocean Terminal | E & M Installations | A16990 | Access for visual inspection for E&M wayside installation (01A) | On Street - Other | SCC | 1A | S | 0 | 0
Newhaven to Ocean Terminal | E & M Installations | A17030 | Access for visual inspection to cable pits for cable laying (01A) | On Street - Other | SCC | 1A | S | 0 | 0
Newhaven to Ocean Terminal | E & M Installations | A17040 | Access to cable pits for cable laying (01A) | On Street - Other | SCC | 1A | S | 0 | 0
Newhaven to Ocean Terminal | E & M Installations | A17050 | Install Electrical Cables | On Street - Other | SCC | 1A | S | 0 | 0
Newhaven to Ocean Terminal | E & M Installations | A17060 | Install Fibre Optic Cables | On Street - Other | SCC | 1A | S | 222504.7228 | 0
Newhaven to Ocean Terminal | E & M Installations | A17070 | Install Signalling Wayside Equipment | On Street - Other | SCC | 1A | S | 5993.569 | 0
Newhaven to Ocean Terminal | E & M Installations | A17050 | Install Electrical Cables | On Street - Other | SCC | 1A | S | 0 | 0
Newhaven Road Tramstop | [8 empty] | 0
Newhaven Road Tramstop | Tramstop | [7 empty] | 0
Newhaven Road Tramstop | Tramstop | 98 | Order REC Supply | On Street - Other | SCC | 1A | S | 0 | 0
Newhaven Road Tramstop | Tramstop | A4288 | Access for visual inspection for E&M Tram Stop installation (01A Newhaven Road) | On Street - Other | SCC | 1A | S | 0 | 0
Newhaven Road Tramstop | Tramstop | A4289 | Access for E&M Tram Stop installation (01A Newhaven Road) | On Street - Other | SCC | 1A | S | 0 | 0
Newhaven Road Tramstop | Tramstop | A4290 | Install LV Power Supply and LV Power Equipment | On Street - Other | SCC | 1A | S | 0 | 0
Newhaven Road Tramstop | Tramstop | A4300 | Install Telecon Equipment | On Street - Other | SCC | 1A | S | 0 | 0
Newhaven Road Tramstop | Tramstop | A4310 | Install Station Control Equipment + AFC Equipment | On Street - Other | SCC | 1A | S | 0 | 0
Newhaven Road Tramstop | Tramstop | A4315 | Package Test Tramstop | On Street - Other | SCC | 1A | S | 34132.23 | 0
Newhaven Road Tramstop | Tramstop | Snagging | Snagging | On Street - Other | SCC | 1A | S | 341.3223 | 0
0
Ocean Terminal to Foot of the Walk | [8 empty] | 0
Ocean Terminal to Foot of the Walk | E & M Installations | [7 empty] | 0
Ocean Terminal to Foot of the Walk | E & M Installations | A3883 | Access for visual inspection for E&M wayside installation (01A) | On Street - Other | SCC | 1A | S | 0 | 0
Ocean Terminal to Foot of the Walk | E & M Installations | A3884 | Access for E&M wayside installation (01A) | On Street - Other | SCC | 1A | S | 0 | 0
Ocean Terminal to Foot of the Walk | E & M Installations | A3885 | Installation of poles and building fixings | On Street - Other | SCC | 1A | S | 0 | 0
Ocean Terminal to Foot of the Walk | E & M Installations | A3898 | Access for visual inspection to cable pits for cable laying (01A) | On Street - Other | SCC | 1A | S | 0 | 0
Ocean Terminal to Foot of the Walk | E & M Installations | A3899 | Access to cable pits for cable laying (01A) | On Street - Other | SCC | 1A | S | 0 | 0
Ocean Terminal to Foot of the Walk | E & M Installations | A3900 | Install Electrical Cables | On Street - Other | SCC | 1A | S | 0 | 0
Ocean Terminal to Foot of the Walk | E & M Installations | A3910 | Install Fibre Optic Cables | On Street - Other | SCC | 1A | S | 382708.1232 | 0
Ocean Terminal to Foot of the Walk | E & M Installations | A3920 | Install Signalling Wayside Equipment | On Street - Other | SCC | 1A | S | 10308.9387 | 0
0
Ocean Terminal Tram Stop | [8 empty] | 0
Ocean Terminal Tram Stop | Tramstop | [7 empty] | 0
Ocean Terminal Tram Stop | Tramstop | 178 | Order REC Supply | On Street - Other | SCC | 1A | S | 0 | 0
Ocean Terminal Tram Stop | Tramstop | A4318 | Access for visual insepction for E&M Tram Stop installation (01A Ocean Terminal) | On Street - Other | SCC | 1A | S | 0 | 0
Ocean Terminal Tram Stop | Tramstop | A4319 | Access for E&M Tram Stop installation (01A Ocean Terminal) | On Street - Other | SCC | 1A | S | 0 | 0
Ocean Terminal Tram Stop | Tramstop | A4320 | Install LV Power Supply and LV Power Equipment | On Street - Other | SCC | 1A | S | 0 | 0
Ocean Terminal Tram Stop | Tramstop | A6090 | Installation of SIG-interlocking cubicle (2) | On Street - Other | SCC | 1A | S | 0 | 0
Ocean Terminal Tram Stop | Tramstop | A6100 | Commissioning of SIG -interlocking cubicle | On Street - Other | SCC | 1A | S | 0 | 0
Ocean Terminal Tram Stop | Tramstop | A4330 | Install Telecon Equipment | On Street - Other | SCC | 1A | S | 0 | 0
Ocean Terminal Tram Stop | Tramstop | A4340 | Install Station Control Equipment + AFC Equipment | On Street - Other | SCC | 1A | S | 0 | 0
Ocean Terminal Tram Stop | Tramstop | A4350 | Package Test Tramstop | On Street - Other | SCC | 1A | S | 34132.23 | 0
Ocean Terminal Tram Stop | Tramstop | Snagging | Snagging | On Street - Other | SCC | 1A | S | 341.3223 | 0
0
Ocean Drive Tram Stop | [8 empty] | 0
Ocean Drive Tram Stop | Tramstop | [7 empty] | 0
Ocean Drive Tram Stop | Tramstop | 188 | Order REC Supply | On Street - Other | SCC | 1A | S | 0 | 0
Ocean Drive Tram Stop | Tramstop | A4358 | Access for visual inspection for E&M Tram Stop installation (01A Ocean Drive) | On Street - Other | SCC | 1A | S | 0 | 0
Ocean Drive Tram Stop | Tramstop | A4359 | Access for E&M Tram Stop installation (01A Ocean Drive) | On Street - Other | SCC | 1A | S | 0 | 0
Ocean Drive Tram Stop | Tramstop | A4360 | Install LV Power Supply and LV Power Equipment | On Street - Other | SCC | 1A | S | 0 | 0
Ocean Drive Tram Stop | Tramstop | A4370 | Install Telecon Equipment | On Street - Other | SCC | 1A | S | 0 | 0
Ocean Drive Tram Stop | Tramstop | A4380 | Install Station Control Equipment + AFC Equipment | On Street - Other | SCC | 1A | S | 0 | 0
Ocean Drive Tram Stop | Tramstop | A4390 | Package Test Tramstop | On Street - Other | SCC | 1A | S | 34132.23 | 0
Ocean Drive Tram Stop | Tramstop | Snagging | Snagging | On Street - Other | SCC | 1A | S | 341.3223 | 0
0
Constitution Street Tram Stop | [8 empty] | 0
Constitution Street Tram Stop | Tramstop | [7 empty] | 0
Constitution Street Tram Stop | Tramstop | 198 | Order REC Supply | On Street - Other | SCC | 1A | S | 0 | 0
Constitution Street Tram Stop | Tramstop | A4398 | Access for visual insepction for E&M Tram Stop installation (01A Constitution Street) | On Street - Other | SCC | 1A | S | 0 | 0
Constitution Street Tram Stop | Tramstop | A4399 | Access for E&M Tram Stop installation (01A Constitution Street) | On Street - Other | SCC | 1A | S | 0 | 0
Constitution Street Tram Stop | Tramstop | A4400 | Install LV Power Supply and LV Power Equipment | On Street - Other | SCC | 1A | S | 0 | 0
Constitution Street Tram Stop | Tramstop | A4410 | Install Telecon Equipment | On Street - Other | SCC | 1A | S | 0 | 0
Constitution Street Tram Stop | Tramstop | A4420 | Install Station Control Equipment + AFC Equipment | On Street - Other | SCC | 1A | S | 0 | 0
Constitution Street Tram Stop | Tramstop | A4430 | Package Test Tramstop | On Street - Other | SCC | 1A | S | 34132.23 | 0
Constitution Street Tram Stop | Tramstop | Snagging | Snagging | On Street - Other | SCC | 1A | S | 341.3223 | 0
0
0
Foot of the Walk to McDonald Road | [8 empty] | 0
Foot of the Walk to McDonald Road | E & M Installations | [7 empty] | 0
Foot of the Walk to McDonald Road | E & M Installations | A3780 | Install Electrical Cables | On Street - Other | SCC | 1B | S | 151303.2115 | 0
Foot of the Walk to McDonald Road | E & M Installations | A3790 | Install Fibre Optic Cables | On Street - Other | SCC | 1B | S | 151303.2115 | 0
Foot of the Walk to McDonald Road | E & M Installations | A3800 | Install Signalling Wayside Equipment | On Street - Other | SCC | 1B | S | 151303.2115 | 0
Foot of the Walk to McDonald Road | E & M Installations | A3765 | Installation of poles and building fixings | On Street - Other | SCC | 1B | S | 151303.2115 | 0
Foot of the Walk to McDonald Road | E & M Installations | A3764 | Access for E&M wayside installation (01B) | On Street - Other | SCC | 1B | S | 0 | 0
Foot of the Walk to McDonald Road | E & M Installations | A3779 | Access to cable pits for cable laying (01B) | On Street - Other | SCC | 1B | S | 0 | 0
Foot of the Walk to McDonald Road | E & M Installations | A3779 | Access to cable pits for cable laying (01B) | On Street - Other | SCC | 1B | S | 0 | 0
Foot of the Walk to McDonald Road | E & M Installations | A3779 | Access to cable pits for cable laying (01B) | On Street - Other | SCC | 1B | S | 0 | 0
Foot of the Walk to McDonald Road | E & M Installations | Snagging | Snagging | On Street - Other | SCC | 1B | S | 6113.2611 | 0
0
Foot of the Walk Tram Stop | [8 empty] | 0
Foot of the Walk Tram Stop | Tramstop | [7 empty] | 0
Foot of the Walk Tram Stop | Tramstop | 528 | Order REC Supply | On Street - Other | SCC | 1B | S | 0 | 0
Foot of the Walk Tram Stop | Tramstop | Construction |  | On Street - Other | SCC | 1B | S | 0 | 0
Foot of the Walk Tram Stop | Tramstop | A4470 | Package Test Tramstop | On Street - Other | SCC | 1B | S | 34132.23 | 0
Foot of the Walk Tram Stop | Tramstop | A4440 | Install LV Power Supply and LV Power Equipment | On Street - Other | SCC | 1B | S | 0 | 0
Foot of the Walk Tram Stop | Tramstop | A4450 | Install Telecon Equipment | On Street - Other | SCC | 1B | S | 0 | 0
Foot of the Walk Tram Stop | Tramstop | A4460 | Install Station Control Equipment + AFC Equipment | On Street - Other | SCC | 1B | S | 0 | 0
Foot of the Walk Tram Stop | Tramstop | A4439 | Access for E&M Tram Stop installation (01B Foot of the Walk) | On Street - Other | SCC | 1B | S | 0 | 0
Foot of the Walk Tram Stop | Tramstop | A4438 | Access for visual inspection for E&M Tram Stop installation (01B Foot of the Walk) | On Street - Other | SCC | 1B | S | 0 | 0
Foot of the Walk Tram Stop | Tramstop | Snagging | Snagging | On Street - Other | SCC | 1B | S | 341.3223 | 0
0
Balfour Street Tram Stop | [8 empty] | 0
Balfour Street Tram Stop | Tramstop | [7 empty] | 0
Balfour Street Tram Stop | Tramstop | 538 | Order REC Supply | On Street - Other | SCC | 1B | S | 0 | 0
Balfour Street Tram Stop | Tramstop | Construction |  | On Street - Other | SCC | 1B | S | 0 | 0
Balfour Street Tram Stop | Tramstop | A4510 | Package Test Tramstop | On Street - Other | SCC | 1B | S | 34132.23 | 0
Balfour Street Tram Stop | Tramstop | A4480 | Install LV Power Supply and LV Power Equipment | On Street - Other | SCC | 1B | S | 0 | 0
Balfour Street Tram Stop | Tramstop | A4490 | Install Telecon Equipment | On Street - Other | SCC | 1B | S | 0 | 0
Balfour Street Tram Stop | Tramstop | A4500 | Install Station Control Equipment + AFC Equipment | On Street - Other | SCC | 1B | S | 0 | 0
Balfour Street Tram Stop | Tramstop | A4479 | Access for E&M Tram Stop installation (01B Balfour Street) | On Street - Other | SCC | 1B | S | 0 | 0
Balfour Street Tram Stop | Tramstop | A4478 | Access for visual inspection for E&M Tram Stop installation (01B Balfour Street) | On Street - Other | SCC | 1B | S | 0 | 0
Balfour Street Tram Stop | Tramstop | Snagging | Snagging | On Street - Other | SCC | 1B | S | 341.3223 | 0
0
0
McDonald Road to Princess Street West | [8 empty] | 0
McDonald Road to Princess Street West | E & M Installations | [7 empty] | 0
McDonald Road to Princess Street West | E & M Installations | A3860 | Install Electrical Cables | On Street - Other | SCC | 1C | S | 151303.2115 | 0
McDonald Road to Princess Street West | E & M Installations | A3870 | Install Fibre Optic Cables | On Street - Other | SCC | 1C | S | 151303.2115 | 0
McDonald Road to Princess Street West | E & M Installations | A3880 | Install Signalling Wayside Equipment | On Street - Other | SCC | 1C | S | 151303.2115 | 0
McDonald Road to Princess Street West | E & M Installations | A3845 | Installation of poles and building fixings | On Street - Other | SCC | 1C | S | 151303.2115 | 0
McDonald Road to Princess Street West | E & M Installations | A3844 | Access for E&M wayside installation (01C) | On Street - Other | SCC | 1C | S | 0 | 0
McDonald Road to Princess Street West | E & M Installations | A3859 | Access to cable pits for cable laying (01C) | On Street - Other | SCC | 1C | S | 0 | 0
McDonald Road to Princess Street West | E & M Installations | A3843 | Access for visual inspection for E&M wayside installation (01C) | On Street - Other | SCC | 1C | S | 0 | 0
McDonald Road to Princess Street West | E & M Installations | A3858 | Access for visual inspection to cable pits for cable laying (01C) | On Street - Other | SCC | 1C | S | 0 | 0
McDonald Road to Princess Street West | E & M Installations | Snagging | Snagging | On Street - Other | SCC | 1C | S | 6113.2611 | 0
0
McDonald Road Tramstop | [8 empty] | 0
McDonald Road Tramstop | Tramstop | [7 empty] | 0
McDonald Road Tramstop | Tramstop | 548 | Order REC Supply | On Street - Other | SCC | 1C | S | 0 | 0
McDonald Road Tramstop | Tramstop | A2670 | Install LV Power Supply and LV Power Equipment | On Street - Other | SCC | 1C | S | 0 | 0
McDonald Road Tramstop | Tramstop | A2680 | Package Test Tramstop | On Street - Other | SCC | 1C | S | 16905.9825 | 0
McDonald Road Tramstop | Tramstop | A2673 | Install Telecon Equipment | On Street - Other | SCC | 1C | S | 0 | 0
McDonald Road Tramstop | Tramstop | A2675 | Install Station Control Equipment + AFC Equipment | On Street - Other | SCC | 1C | S | 0 | 0
McDonald Road Tramstop | Tramstop | A2669 | Access for E&M Tram Stop installation (01C McDonald Road) | On Street - Other | SCC | 1C | S | 0 | 0
McDonald Road Tramstop | Tramstop | A2668 | Access for visual inspection for E&M Tram Stop installation (01C McDonald Road) | On Street - Other | SCC | 1C | S | 0 | 0
McDonald Road Tramstop | Tramstop | Snagging | Snagging | On Street - Other | SCC | 1C | S | 170.7675 | 0
0
Picardy Place Tram Stop | [8 empty] | 0
Picardy Place Tram Stop | Tramstop | [7 empty] | 0
Picardy Place Tram Stop | Tramstop | 558 | Order REC Supply | On Street - Other | SCC | 1C | S | 0 | 0
Picardy Place Tram Stop | Tramstop | A4550 | Package Test Tramstop | On Street - Other | SCC | 1C | S | 16905.9825 | 0
Picardy Place Tram Stop | Tramstop | A4520 | Install LV Power Supply and LV Power Equipment | On Street - Other | SCC | 1C | S | 0 | 0
Picardy Place Tram Stop | Tramstop | A4530 | Install Telecon Equipment | On Street - Other | SCC | 1C | S | 0 | 0
Picardy Place Tram Stop | Tramstop | A4540 | Install Station Control Equipment + AFC Equipment | On Street - Other | SCC | 1C | S | 0 | 0
Picardy Place Tram Stop | Tramstop | A4519 | Access for E&M Tram Stop installation (01C Picardy Place) | On Street - Other | SCC | 1C | S | 0 | 0
Picardy Place Tram Stop | Tramstop | A4518 | Access for visual inspection for E&M Tram Stop installation (01C Picardy Place) | On Street - Other | SCC | 1C | S | 0 | 0
Picardy Place Tram Stop | Tramstop | Snagging | Snagging | On Street - Other | SCC | 1C | S | 170.7675 | 0
0
Princes Street West Tram Stop | [8 empty] | 0
Princes Street West Tram Stop | Tramstop | [7 empty] | 0
Princes Street West Tram Stop | Tramstop | 578 | Order REC Supply | On Street - Princes St | SCC | 1C | S | 0 | 0
Princes Street West Tram Stop | Tramstop | A4630 | Package Test Tramstop | On Street - Princes St | SCC | 1C | S | 16905.9825 | 0
Princes Street West Tram Stop | Tramstop | A4600 | Install LV Power Supply and LV Power Equipment | On Street - Princes St | SCC | 1C | S | 0 | 0
Princes Street West Tram Stop | Tramstop | A4610 | Install Telecon Equipment | On Street - Princes St | SCC | 1C | S | 0 | 0
Princes Street West Tram Stop | Tramstop | A4620 | Install Station Control Equipment + AFC Equipment | On Street - Princes St | SCC | 1C | S | 0 | 0
Princes Street West Tram Stop | Tramstop | A4599 | Access for E&M Tram Stop installation (01D Princess Street West) | On Street - Princes St | SCC | 1C | S | 0 | 0
Princes Street West Tram Stop | Tramstop | A4598 | Access for visual inspection for E&M Tram Stop installation (01D Princess Street West) | On Street - Princes St | SCC | 1C | S | 0 | 0
Princes Street West Tram Stop | Tramstop | Snagging | Snagging | On Street - Princes St | SCC | 1C | S | 170.7675 | 0
St Andrews Square Tram Stop | [8 empty] | 0
St Andrews Square Tram Stop | Tramstop | [7 empty] | 0
St Andrews Square Tram Stop | Tramstop | 568 | Order REC Supply | On Street - Other | SCC | 1C | S | 0 | 0
St Andrews Square Tram Stop | Tramstop | A4590 | Package Test Tramstop | On Street - Other | SCC | 1C | S | 16905.9825 | 0
St Andrews Square Tram Stop | Tramstop | A4560 | Install LV Power Supply and LV Power Equipment | On Street - Other | SCC | 1C | S | 0 | 0
St Andrews Square Tram Stop | Tramstop | A4570 | Install Telecon Equipment | On Street - Other | SCC | 1C | S | 0 | 0
St Andrews Square Tram Stop | Tramstop | A4580 | Install Station Control Equipment + AFC Equipment | On Street - Other | SCC | 1C | S | 0 | 0
St Andrews Square Tram Stop | Tramstop | A6150 | Installation of SIG-interlocking cubicle | On Street - Other | SCC | 1C | S | 0 | 0
St Andrews Square Tram Stop | Tramstop | A6160 | Commissioning of SIG -interlocking cubicle | On Street - Other | SCC | 1C | S | 0 | 0
St Andrews Square Tram Stop | Tramstop | A4559 | Access for E&M Tram Stop installation (01C St. Andrews Square) | On Street - Other | SCC | 1C | S | 0 | 0
St Andrews Square Tram Stop | Tramstop | A4558 | Access for visual inspection for E&M Tram Stop installation (01C St. Andrews Square) | On Street - Other | SCC | 1C | S | 0 | 0
St Andrews Square Tram Stop | Tramstop | Snagging | Snagging | On Street - Other | SCC | 1C | S | 170.7675 | 0
0
0
Princes Street (inc.) to Haymarket (exc.) | [8 empty] | 0
Princes Street (inc.) to Haymarket (exc.) | E & M Installations | [7 empty] | 0
Princes Street (inc.) to Haymarket (exc.) | E & M Installations | A3820 | Install Electrical Cables | On Street - Princes St | SCC | 1D | S | 151303.2115 | 0
Princes Street (inc.) to Haymarket (exc.) | E & M Installations | A3830 | Install Fibre Optic Cables | On Street - Princes St | SCC | 1D | S | 151303.2115 | 0
Princes Street (inc.) to Haymarket (exc.) | E & M Installations | A3840 | Install Signalling Wayside Equipment | On Street - Princes St | SCC | 1D | S | 151303.2115 | 0
Princes Street (inc.) to Haymarket (exc.) | E & M Installations | A3805 | Installation of poles and building fixings | On Street - Princes St | SCC | 1D | S | 151303.2115 | 0
Princes Street (inc.) to Haymarket (exc.) | E & M Installations | A3804 | Access for E&M wayside installation (01D) | On Street - Princes St | SCC | 1D | S | 0 | 0
Princes Street (inc.) to Haymarket (exc.) | E & M Installations | A3819 | Access to cable pits for cable laying (01D) | On Street - Princes St | SCC | 1D | S | 0 | 0
Princes Street (inc.) to Haymarket (exc.) | E & M Installations | A3803 | Access for visual inspection for E&M wayside installation (01D) | On Street - Princes St | SCC | 1D | S | 0 | 0
Princes Street (inc.) to Haymarket (exc.) | E & M Installations | A3818 | Access for visual inspection to cable pits for cable laying (01D) | On Street - Princes St | SCC | 1D | S | 0 | 0
Princes Street (inc.) to Haymarket (exc.) | E & M Installations | Snagging | Snagging | On Street - Princes St | SCC | 1D | S | 6113.2611 | 0
0
Shandwick Place Tram Stop | [8 empty] | 0
Shandwick Place Tram Stop | Tramstop | [7 empty] | 0
Shandwick Place Tram Stop | Tramstop | 588 | Order REC Supply | On Street - Other | SCC | 1D | S | 0 | 0
Shandwick Place Tram Stop | Tramstop | A4670 | Package Test Tramstop | On Street - Other | SCC | 1D | S | 103037.22 | 0
Shandwick Place Tram Stop | Tramstop | A4640 | Install LV Power Supply and LV Power Equipment | On Street - Other | SCC | 1D | S | 0 | 0
Shandwick Place Tram Stop | Tramstop | A4650 | Install Telecon Equipment | On Street - Other | SCC | 1D | S | 0 | 0
Shandwick Place Tram Stop | Tramstop | A4660 | Install Station Control Equipment + AFC Equipment | On Street - Other | SCC | 1D | S | 0 | 0
Shandwick Place Tram Stop | Tramstop | A4639 | Access for E&M Tram Stop installation (01D Shadwick Place) | On Street - Other | SCC | 1D | S | 0 | 0
Shandwick Place Tram Stop | Tramstop | A4638 | Access for visual inspection for E&M Tram Stop installation (01D Shadwick Place) | On Street - Other | SCC | 1D | S | 0 | 0
Shandwick Place Tram Stop | Tramstop | Snagging | Snagging | On Street - Other | SCC | 1D | S | 1040.78 | 0
0
0
0
Haymarket Corridor | [8 empty] | 0
Haymarket Corridor | E & M Installations | [7 empty] | 0
Haymarket Corridor | E & M Installations | A4060 | Install Electrical Cables | Off Street - Other | SCC | 2A | S | 133667.5805 | 0
Haymarket Corridor | E & M Installations | A4070 | Install Fibre Optic Cables | Off Street - Other | SCC | 2A | S | 133667.5805 | 0
Haymarket Corridor | E & M Installations | A4080 | Install Signalling Wayside Equipment | Off Street - Other | SCC | 2A | S | 133667.5805 | 0
Haymarket Corridor | E & M Installations | A4045 | Installation of poles and building fixings | Off Street - Other | SCC | 2A | S | 133667.5805 | 0
Haymarket Corridor | E & M Installations | A4044 | Access for E&M wayside installation (02A) | Off Street - Other | SCC | 2A | S | 0 | 0
Haymarket Corridor | E & M Installations | A4059 | Access to cable pits for cable laying (02A) | Off Street - Other | SCC | 2A | S | 0 | 0
Haymarket Corridor | E & M Installations | A4043 | Access for visual inspection for E&M wayside installation (02A) | Off Street - Other | SCC | 2A | S | 0 | 0
Haymarket Corridor | E & M Installations | A4058 | Access visual inspection to cable pits for cable laying (02A) | Off Street - Other | SCC | 2A | S | 0 | 0
Haymarket Corridor | E & M Installations | Snagging | Snagging | Off Street - Other | SCC | 2A | S | 5400.7103 | 0
0
Haymarket Station Tram Stop | [8 empty] | 0
Haymarket Station Tram Stop | Tramstop | [7 empty] | 0
Haymarket Station Tram Stop | Tramstop | 3rd Party | Third Party Sign-off | Off Street - Other | SCC | 2A | S | 25000 | 0
Haymarket Station Tram Stop | Tramstop | 488 | Order REC Supply | Off Street - Other | SCC | 2A | S | 0 | 0
Haymarket Station Tram Stop | Tramstop | A4710 | Package Test Tramstop | Off Street - Other | SCC | 2A | S | 40499.91 | 0
Haymarket Station Tram Stop | Tramstop | A4680 | Install LV Power Supply and LV Power Equipment | Off Street - Other | SCC | 2A | S | 0 | 0
Haymarket Station Tram Stop | Tramstop | A4690 | Install Telecon Equipment | Off Street - Other | SCC | 2A | S | 0 | 0
Haymarket Station Tram Stop | Tramstop | A4700 | Install Station Control Equipment + AFC Equipment | Off Street - Other | SCC | 2A | S | 0 | 0
Haymarket Station Tram Stop | Tramstop | A6170 | Installation of SIG-interlocking cubicle | Off Street - Other | SCC | 2A | S | 0 | 0
Haymarket Station Tram Stop | Tramstop | A6180 | Commissioning of SIG -interlocking cubicle | Off Street - Other | SCC | 2A | S | 0 | 0
Haymarket Station Tram Stop | Tramstop | A4679 | Access for E&M Tram Stop installation (02A Haymarket Station) | Off Street - Other | SCC | 2A | S | 0 | 0
Haymarket Station Tram Stop | Tramstop | A4678 | Access for visual inspection for E&M Tram Stop installation (02A Haymarket Station) | Off Street - Other | SCC | 2A | S | 0 | 0
Haymarket Station Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | SCC | 2A | S | 409.09 | 0
0
0
0
Roseburn Junction (exc.) to Balgreen Road (inc.) | [8 empty] | 0
Roseburn Junction (exc.) to Balgreen Road (inc.) | E & M Installations | [7 empty] | 0
Roseburn Junction (exc.) to Balgreen Road (inc.) | E & M Installations | A4100 | Install Electrical Cables | Off Street - Other | SCC | 5A | S | 133667.5805 | 0
Roseburn Junction (exc.) to Balgreen Road (inc.) | E & M Installations | A4110 | Install Fibre Optic Cables | Off Street - Other | SCC | 5A | S | 133667.5805 | 0
Roseburn Junction (exc.) to Balgreen Road (inc.) | E & M Installations | A4120 | Install Signalling Wayside Equipment | Off Street - Other | SCC | 5A | S | 133667.5805 | 0
Roseburn Junction (exc.) to Balgreen Road (inc.) | E & M Installations | A4085 | Installation of poles and building fixings | Off Street - Other | SCC | 5A | S | 133667.5805 | 0
Roseburn Junction (exc.) to Balgreen Road (inc.) | E & M Installations | A4084 | Access for E&M wayside installation (05A) | Off Street - Other | SCC | 5A | S | 0 | 0
Roseburn Junction (exc.) to Balgreen Road (inc.) | E & M Installations | A4099 | Access to cable pits for cable laying (05A) | Off Street - Other | SCC | 5A | S | 0 | 0
Roseburn Junction (exc.) to Balgreen Road (inc.) | E & M Installations | A4083 | Access for visual inspection for E&M wayside installation (05A) | Off Street - Other | SCC | 5A | S | 0 | 0
Roseburn Junction (exc.) to Balgreen Road (inc.) | E & M Installations | A4098 | Access for visual inspection to cable pits for cable laying (05A) | Off Street - Other | SCC | 5A | S | 0 | 0
Roseburn Junction (exc.) to Balgreen Road (inc.) | E & M Installations | Snagging | Snagging | Off Street - Other | SCC | 5A | S | 5400.7103 | 0
0
Murrayfield Tram Stop | [8 empty] | 0
Murrayfield Tram Stop | Tramstop | [7 empty] | 0
Murrayfield Tram Stop | Tramstop | 3rd Party | Third Party Sign-off | Off Street - Other | SCC | 5A | S | 25000 | 0
Murrayfield Tram Stop | Tramstop | 228 | Order REC Supply | Off Street - Other | SCC | 5A | S | 0 | 0
Murrayfield Tram Stop | Tramstop | A5110 | Package Test Tramstop | Off Street - Other | SCC | 5A | S | 8099.982 | 0
Murrayfield Tram Stop | Tramstop | A5080 | Install LV Power Supply and LV Power Equipment | Off Street - Other | SCC | 5A | S | 8099.982 | 0
Murrayfield Tram Stop | Tramstop | A5090 | Install Telecon Equipment | Off Street - Other | SCC | 5A | S | 8099.982 | 0
Murrayfield Tram Stop | Tramstop | A5100 | Install Station Control Equipment + AFC Equipment | Off Street - Other | SCC | 5A | S | 8099.982 | 0
Murrayfield Tram Stop | Tramstop | A6270 | Installation of SIG-interlocking cubicle | Off Street - Other | SCC | 5A | S | 8099.982 | 0
Murrayfield Tram Stop | Tramstop | A6280 | Commissioning of SIG -interlocking cubicle | Off Street - Other | SCC | 5A | S | 0 | 0
Murrayfield Tram Stop | Tramstop | A5079 | Access for E&M Tram Stop installation (05A Murrayfield) | Off Street - Other | SCC | 5A | S | 0 | 0
Murrayfield Tram Stop | Tramstop | A5078 | Access for visual inspection for E&M Tram Stop installation (05A Murrayfield) | Off Street - Other | SCC | 5A | S | 0 | 0
Murrayfield Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | SCC | 5A | S | 409.09 | 0
0
Balgreen Road Tram Stop | [8 empty] | 0
Balgreen Road Tram Stop | Tramstop | [7 empty] | 0
Balgreen Road Tram Stop | Tramstop | 3rd Party | Third Party Sign-off | Off Street - Other | SCC | 5A | S | 25000 | 0
Balgreen Road Tram Stop | Tramstop | 328 | Order REC Supply | Off Street - Other | SCC | 5A | S | 0 | 0
Balgreen Road Tram Stop | Tramstop | A5150 | Package Test Tramstop | Off Street - Other | SCC | 5A | S | 10124.9775 | 0
Balgreen Road Tram Stop | Tramstop | A5120 | Install LV Power Supply and LV Power Equipment | Off Street - Other | SCC | 5A | S | 10124.9775 | 0
Balgreen Road Tram Stop | Tramstop | A5130 | Install Telecon Equipment | Off Street - Other | SCC | 5A | S | 10124.9775 | 0
Balgreen Road Tram Stop | Tramstop | A5140 | Install Station Control Equipment + AFC Equipment | Off Street - Other | SCC | 5A | S | 10124.9775 | 0
Balgreen Road Tram Stop | Tramstop | A5119 | Access for E&M Tram Stop installation (05A Balgreen Road) | Off Street - Other | SCC | 5A | S | 0 | 0
Balgreen Road Tram Stop | Tramstop | A5118 | Access for visual inspection for E&M Tram Stop installation (05A Balgreen Road) | Off Street - Other | SCC | 5A | S | 0 | 0
Balgreen Road Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | SCC | 5A | S | 409.09 | 0
0
0
Balgreen Road to Edinburgh Park | [8 empty] | 0
Balgreen Road to Edinburgh Park | E & M Installations | [7 empty] | 0
Balgreen Road to Edinburgh Park | E & M Installations | A4140 | Install Electrical Cables | Off Street - Other | SCC | 5B | S | 133667.5805 | 0
Balgreen Road to Edinburgh Park | E & M Installations | A4150 | Install Fibre Optic Cables | Off Street - Other | SCC | 5B | S | 133667.5805 | 0
Balgreen Road to Edinburgh Park | E & M Installations | A4160 | Install Signalling Wayside Equipment | Off Street - Other | SCC | 5B | S | 133667.5805 | 0
Balgreen Road to Edinburgh Park | E & M Installations | A4125 | Installation of poles and building fixings | Off Street - Other | SCC | 5B | S | 133667.5805 | 0
Balgreen Road to Edinburgh Park | E & M Installations | A4124 | Access for E&M wayside installation (05B) | Off Street - Other | SCC | 5B | S | 0 | 0
Balgreen Road to Edinburgh Park | E & M Installations | A4139 | Access to cable pits for cable laying (05B) | Off Street - Other | SCC | 5B | S | 0 | 0
Balgreen Road to Edinburgh Park | E & M Installations | A4123 | Access for visual inspection for E&M wayside installation (05B) | Off Street - Other | SCC | 5B | S | 0 | 0
Balgreen Road to Edinburgh Park | E & M Installations | A4138 | Access for visual inspection to cable pits for cable laying (05B) | Off Street - Other | SCC | 5B | S | 0 | 0
Balgreen Road to Edinburgh Park | E & M Installations | Snagging | Snagging | Off Street - Other | SCC | 5B | S | 5400.7103 | 0
0
Saughton Road North Tram Stop | [8 empty] | 0
Saughton Road North Tram Stop | Tramstop | [7 empty] | 0
Saughton Road North Tram Stop | Tramstop | 248 | Order REC Supply | Off Street - Other | SCC | 5B | S | 0 | 0
Saughton Road North Tram Stop | Tramstop | A5190 | Package Test Tramstop | Off Street - Other | SCC | 5B | S | 10124.9775 | 0
Saughton Road North Tram Stop | Tramstop | A5160 | Install LV Power Supply and LV Power Equipment | Off Street - Other | SCC | 5B | S | 10124.9775 | 0
Saughton Road North Tram Stop | Tramstop | A5170 | Install Telecon Equipment | Off Street - Other | SCC | 5B | S | 10124.9775 | 0
Saughton Road North Tram Stop | Tramstop | A5180 | Install Station Control Equipment + AFC Equipment | Off Street - Other | SCC | 5B | S | 10124.9775 | 0
Saughton Road North Tram Stop | Tramstop | A5159 | Access for E&M Tram Stop installation (05B Saughton Road North) | Off Street - Other | SCC | 5B | S | 0 | 0
Saughton Road North Tram Stop | Tramstop | A5158 | Access for visual inspection for E&M Tram Stop installation (05B Saughton Road North) | Off Street - Other | SCC | 5B | S | 0 | 0
Saughton Road North Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | SCC | 5B | S | 409.09 | 0
0
South Gyle Access Tram Stop | [8 empty] | 0
South Gyle Access Tram Stop | Tramstop | [7 empty] | 0
South Gyle Access Tram Stop | Tramstop | 318 | Order REC Supply | Off Street - Other | SCC | 5B | S | 0 | 0
South Gyle Access Tram Stop | Tramstop | A5230 | Package Test Tramstop | Off Street - Other | SCC | 5B | S | 10124.9775 | 0
South Gyle Access Tram Stop | Tramstop | A5200 | Install LV Power Supply and LV Power Equipment | Off Street - Other | SCC | 5B | S | 10124.9775 | 0
South Gyle Access Tram Stop | Tramstop | A5210 | Install Telecon Equipment | Off Street - Other | SCC | 5B | S | 10124.9775 | 0
South Gyle Access Tram Stop | Tramstop | A5220 | Install Station Control Equipment + AFC Equipment | Off Street - Other | SCC | 5B | S | 10124.9775 | 0
South Gyle Access Tram Stop | Tramstop | A5199 | Access for E&M Tram Stop installation (05B South Gyle) | Off Street - Other | SCC | 5B | S | 0 | 0
South Gyle Access Tram Stop | Tramstop | A5198 | Access for visual inspection for E&M Tram Stop installation (05B South Gyle) | Off Street - Other | SCC | 5B | S | 0 | 0
South Gyle Access Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | SCC | 5B | S | 409.09 | 0
0
Edinburgh Park Station Tram Stop | [8 empty] | 0
Edinburgh Park Station Tram Stop | Tramstop | [7 empty] | 0
Edinburgh Park Station Tram Stop | Tramstop | 278 | Order REC Supply | Off Street - Other | SCC | 5B | S | 0 | 0
Edinburgh Park Station Tram Stop | Tramstop | A5270 | Package Test Tramstop | Off Street - Other | SCC | 5B | S | 8099.982 | 0
Edinburgh Park Station Tram Stop | Tramstop | A5240 | Install LV Power Supply and LV Power Equipment | Off Street - Other | SCC | 5B | S | 8099.982 | 0
Edinburgh Park Station Tram Stop | Tramstop | A5250 | Install Telecon Equipment | Off Street - Other | SCC | 5B | S | 8099.982 | 0
Edinburgh Park Station Tram Stop | Tramstop | A5260 | Install Station Control Equipment + AFC Equipment | Off Street - Other | SCC | 5B | S | 8099.982 | 0
Edinburgh Park Station Tram Stop | Tramstop | A6290 | Installation of SIG-interlocking cubicle | Off Street - Other | SCC | 5B | S | 8099.982 | 0
Edinburgh Park Station Tram Stop | Tramstop | A6300 | Commissioning of SIG -interlocking cubicle | Off Street - Other | SCC | 5B | S | 0 | 0
Edinburgh Park Station Tram Stop | Tramstop | A5239 | Access for E&M Tram Stop installation (05B Edinburgh Park Station) | Off Street - Other | SCC | 5B | S | 0 | 0
Edinburgh Park Station Tram Stop | Tramstop | A5238 | Access for visual inspection for E&M Tram Stop installation (05B Edinburgh Park Station) | Off Street - Other | SCC | 5B | S | 0 | 0
Edinburgh Park Station Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | SCC | 5B | S | 409.09 | 0
0
Edinburgh Park Tram Stop | [8 empty] | 0
Edinburgh Park Tram Stop | Tramstop | [7 empty] | 0
Edinburgh Park Tram Stop | Tramstop | 268 | Order REC Supply | Off Street - Other | SCC | 5B | S | 0 | 0
Edinburgh Park Tram Stop | Tramstop | A5310 | Package Test Tramstop | Off Street - Other | SCC | 5B | S | 10124.9775 | 0
Edinburgh Park Tram Stop | Tramstop | A5280 | Install LV Power Supply and LV Power Equipment | Off Street - Other | SCC | 5B | S | 10124.9775 | 0
Edinburgh Park Tram Stop | Tramstop | A5290 | Install Telecon Equipment | Off Street - Other | SCC | 5B | S | 10124.9775 | 0
Edinburgh Park Tram Stop | Tramstop | A5300 | Install Station Control Equipment + AFC Equipment | Off Street - Other | SCC | 5B | S | 10124.9775 | 0
Edinburgh Park Tram Stop | Tramstop | A5279 | Access for E&M Tram Stop installation (05B Edinburgh Park) | Off Street - Other | SCC | 5B | S | 0 | 0
Edinburgh Park Tram Stop | Tramstop | A5278 | Access for visual inspection for E&M Tram Stop installation (05B Edinburgh Park) | Off Street - Other | SCC | 5B | S | 0 | 0
Edinburgh Park Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | SCC | 5B | S | 409.09 | 0
Edinburgh Park Station Bridge (S27) Disruptive Possessions | [8 empty] | 0
Edinburgh Park Station Bridge (S27) Disruptive Possessions | E & M Installations | [7 empty] | 0
Edinburgh Park Station Bridge (S27) Disruptive Possessions | E & M Installations | 51 | M & E Works | Off Street - Other | SCC | 5B | S | 133272.58 | 0
Edinburgh Park Station Bridge (S27) Disruptive Possessions | E & M Installations | A14140 | Possession 5 (12hrs) | Off Street - Other | OLE | 5B | S | 0 | 0
0
0
Edinburgh Park to Depot | [8 empty] | 0
Edinburgh Park to Depot | E & M Installations | [7 empty] | 0
Edinburgh Park to Depot | E & M Installations | A4180 | Install Electrical Cables | Off Street - Other | SCC | 5C | S | 0 | 0
Edinburgh Park to Depot | E & M Installations | A4190 | Install Fibre Optic Cables | Off Street - Other | SCC | 5C | S | 0 | 0
Edinburgh Park to Depot | E & M Installations | A4200 | Install Signalling Wayside Equipment | Off Street - Other | SCC | 5C | S | 267335.1609 | 0
Edinburgh Park to Depot | E & M Installations | A4165 | Installation of poles and building fixings | Off Street - Other | SCC | 5C | S | 0 | 0
Edinburgh Park to Depot | E & M Installations | A4164 | Access for E&M wayside installation (05C) | Off Street - Other | SCC | 5C | S | 0 | 0
Edinburgh Park to Depot | E & M Installations | A4179 | Access to cable pits for cable laying (05C) | Off Street - Other | SCC | 5C | S | 0 | 0
Edinburgh Park to Depot | E & M Installations | A4163 | Access for visual inspection for E&M wayside installation (05C) | Off Street - Other | SCC | 5C | S | 0 | 0
Edinburgh Park to Depot | E & M Installations | A4178 | Access for visual inspection to cable pits for cable laying (05C) | Off Street - Other | SCC | 5C | S | 0 | 0
Edinburgh Park to Depot | E & M Installations | Snagging | Snagging | Off Street - Other | SCC | 5C | S | 2700.3552 | 0
Depot to Gogarburn | [8 empty] | 0
Depot to Gogarburn | E & M Installations | [7 empty] | 0
Depot to Gogarburn | E & M Installations | A16960 | Install Electrical Cables | Off Street - Other | SCC | 5C | S | 0 | 0
Depot to Gogarburn | E & M Installations | A16970 | Install Fibre Optic Cables | Off Street - Other | SCC | 5C | S | 0 | 0
Depot to Gogarburn | E & M Installations | A16980 | Install Signalling Wayside Equipment | Off Street - Other | SCC | 5C | S | 267335.1609 | 0
Depot to Gogarburn | E & M Installations | A16920 | Installation of poles and building fixings Section 5c Edin.Park Central to Gogarburn | Off Street - Other | SCC | 5C | S | 0 | 0
Depot to Gogarburn | E & M Installations | A16910 | Access for E&M wayside installation (05C) | Off Street - Other | SCC | 5C | S | 0 | 0
Depot to Gogarburn | E & M Installations | A16950 | Access to cable pits for cable laying (05C) | Off Street - Other | SCC | 5C | S | 0 | 0
Depot to Gogarburn | E & M Installations | A16900 | Access for visual inspection for E&M wayside installation (05C) | Off Street - Other | SCC | 5C | S | 0 | 0
Depot to Gogarburn | E & M Installations | A16940 | Access for visual inspection to cable pits for cable laying (05C) | Off Street - Other | SCC | 5C | S | 0 | 0
Depot to Gogarburn | E & M Installations | Snagging | Snagging | Off Street - Other | SCC | 5C | S | 2700.3552 | 0
0
Gyle Tram Stop | [8 empty] | 0
Tramstop | Tramstop | [7 empty] | 0
Gyle Tram Stop | Tramstop | 298 | Order REC Supply | Off Street - Other | SCC | 5C | S | 0 | 0
Gyle Tram Stop | Tramstop | A5350 | Package Test Tramstop | Off Street - Other | SCC | 5C | S | 10124.9775 | 0
Gyle Tram Stop | Tramstop | A5320 | Install LV Power Supply and LV Power Equipment | Off Street - Other | SCC | 5C | S | 10124.9775 | 0
Gyle Tram Stop | Tramstop | A5330 | Install Telecon Equipment | Off Street - Other | SCC | 5C | S | 10124.9775 | 0
Gyle Tram Stop | Tramstop | A5340 | Install Station Control Equipment + AFC Equipment | Off Street - Other | SCC | 5C | S | 10124.9775 | 0
Gyle Tram Stop | Tramstop | A5319 | Access for E&M Tram Stop installation (05C Gyle) | Off Street - Other | SCC | 5C | S | 0 | 0
Gyle Tram Stop | Tramstop | A5318 | Access for visual inspection for E&M Tram Stop installation (05C Gyle) | Off Street - Other | SCC | 5C | S | 0 | 0
Gyle Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | SCC | 5C | S | 409.09 | 0
0
Gogarburn Tram Stop | [8 empty] | 0
Gogarburn Tram Stop | Tramstop | [7 empty] | 0
Gogarburn Tram Stop | Tramstop | 308 | Order REC Supply | Off Street - Other | SCC | 5C | S | 0 | 0
Gogarburn Tram Stop | Tramstop | A5390 | Package Test Tramstop | Off Street - Other | SCC | 5C | S | 10124.9775 | 0
Gogarburn Tram Stop | Tramstop | A5360 | Install LV Power Supply and LV Power Equipment | Off Street - Other | SCC | 5C | S | 10124.9775 | 0
Gogarburn Tram Stop | Tramstop | A5370 | Install Telecon Equipment | Off Street - Other | SCC | 5C | S | 10124.9775 | 0
Gogarburn Tram Stop | Tramstop | A5380 | Install Station Control Equipment + AFC Equipment | Off Street - Other | SCC | 5C | S | 10124.9775 | 0
Gogarburn Tram Stop | Tramstop | A5359 | Access for E&M Tram Stop installation (05C Gogarburn) | Off Street - Other | SCC | 5C | S | 0 | 0
Gogarburn Tram Stop | Tramstop | A5358 | Access for visual inspection for E&M Tram Stop installation (05C Gogarburn) | Off Street - Other | SCC | 5C | S | 0 | 0
Gogarburn Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | SCC | 5C | S | 409.09 | 0
0
0
0
Depot | [8 empty] | 0
Depot | E & M Workshop Equipment Installation | [7 empty] | 0
Depot | E & M Workshop Equipment Installation | A2545 | Installation of workshop equipment | Off Street Depot | SCC | 6A | S | 375985.005 | 0
Depot | E & M Workshop Equipment Installation | A2544 | Access for E&M workshop equipment | Off Street Depot | SCC | 6A | S | 0 | 0
Depot | E & M Workshop Equipment Installation | A2542 | Access for visual inspection forE&M workshop equipment | Off Street Depot | SCC | 6A | S | 0 | 0
Depot | E & M Workshop Equipment Installation | A4220 | Install Electrical Cables | Off Street Depot | SCC | 6A | S | 375985.005 | 0
Depot | E & M Workshop Equipment Installation | A4230 | Install Fibre Optic Cables | Off Street Depot | SCC | 6A | S | 375985.005 | 0
Depot | E & M Workshop Equipment Installation | A4240 | Install Signalling Wayside Equipment | Off Street Depot | SCC | 6A | S | 375985.005 | 0
Depot | E & M Workshop Equipment Installation | A4205 | Installation of poles and building fixings - 50% | Off Street Depot | SCC | 6A | S | 375985.005 | 0
Depot | E & M Workshop Equipment Installation | A4205 | Installation of poles and building fixingsb - 50% | Off Street Depot | SCC | 6A | S | 375985.005 | 0
Depot | E & M Workshop Equipment Installation | A4204 | Access for E&M Depot installation | Off Street Depot | SCC | 6A | S | 0 | 0
Depot | E & M Workshop Equipment Installation | A4219 | Access to cable pits for cable laying (Depot) | Off Street Depot | SCC | 6A | S | 0 | 0
Depot | E & M Workshop Equipment Installation | A4203 | Access for visual inspection for E&M Depot installation | Off Street Depot | SCC | 6A | S | 0 | 0
Depot | E & M Workshop Equipment Installation | A4218 | Access for visual inspection to cable pits for cable laying (Depot) | Off Street Depot | SCC | 6A | S | 0 | 0
Depot | E & M Workshop Equipment Installation | Snagging | Snagging | Off Street Depot | SCC | 6A | S | 22786.97 | 0
Depot | Inspection & Handover | [7 empty] | 0
Depot | Inspection & Handover | A2550 | Inspection and Testing | Off Street Depot | SCC | 6A | S | 256530.8776 | 0
0
0
0
Gogarburn to Edinburgh Airport E & M Installations | [8 empty] | 0
Gogarburn to Edinburgh Airport E & M Installations | E & M Installations | [7 empty] | 0
Gogarburn to Edinburgh Airport E & M Installations | E & M Installations | A4260 | Install Electrical Cables | Off Street - Other | SCC | 7A | S | 133667.5805 | 0
Gogarburn to Edinburgh Airport E & M Installations | E & M Installations | A4270 | Install Fibre Optic Cables | Off Street - Other | SCC | 7A | S | 133667.5805 | 0
Gogarburn to Edinburgh Airport E & M Installations | E & M Installations | A4280 | Install Signalling Wayside Equipment | Off Street - Other | SCC | 7A | S | 133667.5805 | 0
Gogarburn to Edinburgh Airport E & M Installations | E & M Installations | A4245 | Installation of poles and building fixings | Off Street - Other | SCC | 7A | S | 133667.5805 | 0
Gogarburn to Edinburgh Airport E & M Installations | E & M Installations | A4244 | Access for E&M wayside installation (07A) | Off Street - Other | SCC | 7A | S | 0 | 0
Gogarburn to Edinburgh Airport E & M Installations | E & M Installations | A4259 | Access to cable pits for cable laying (07A) | Off Street - Other | SCC | 7A | S | 0 | 0
Gogarburn to Edinburgh Airport E & M Installations | E & M Installations | A4243 | Access for visual inspection for E&M wayside installation (07A) | Off Street - Other | SCC | 7A | S | 0 | 0
Gogarburn to Edinburgh Airport E & M Installations | E & M Installations | A4258 | Access for visual inspection to cable pits for cable laying (07A) | Off Street - Other | SCC | 7A | S | 0 | 0
Gogarburn to Edinburgh Airport E & M Installations | E & M Installations | Snagging | Snagging | Off Street - Other | SCC | 7A | S | 5400.7103 | 0
0
Inglishton Park and Ride Tram Stop | [8 empty] | 0
Inglishton Park and Ride Tram Stop | Tramstop | [7 empty] | 0
Inglishton Park and Ride Tram Stop | Tramstop | 218 | Order REC Supply | Off Street - Other | SCC | 7A | S | 0 | 0
Inglishton Park and Ride Tram Stop | Tramstop | A5430 | Package Test Tramstop | Off Street - Other | SCC | 7A | S | 10124.9775 | 0
Inglishton Park and Ride Tram Stop | Tramstop | A5400 | Install LV Power Supply and LV Power Equipment | Off Street - Other | SCC | 7A | S | 10124.9775 | 0
Inglishton Park and Ride Tram Stop | Tramstop | A5410 | Install Telecon Equipment | Off Street - Other | SCC | 7A | S | 10124.9775 | 0
Inglishton Park and Ride Tram Stop | Tramstop | A5420 | Install Station Control Equipment + AFC Equipment | Off Street - Other | SCC | 7A | S | 10124.9775 | 0
Inglishton Park and Ride Tram Stop | Tramstop | A5399 | Access for E&M Tram Stop installation (07A Ingliston Park+Ride) | Off Street - Other | SCC | 7A | S | 0 | 0
Inglishton Park and Ride Tram Stop | Tramstop | A5398 | Access for visual inspection for E&M Tram Stop installation (07A Ingliston Park+Ride) | Off Street - Other | SCC | 7A | S | 0 | 0
Inglishton Park and Ride Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | SCC | 7A | S | 409.09 | 0
0
Edinburgh Airport Tram Stop | [8 empty] | 0
Edinburgh Airport Tram Stop | Tramstop | [7 empty] | 0
Edinburgh Airport Tram Stop | Tramstop | 208 | Order REC Supply | Off Street - Other | SCC | 7A | S | 0 | 0
Edinburgh Airport Tram Stop | Tramstop | A5470 | Package Test Tramstop | Off Street - Other | SCC | 7A | S | 8099.982 | 0
Edinburgh Airport Tram Stop | Tramstop | A5440 | Install LV Power Supply and LV Power Equipment | Off Street - Other | SCC | 7A | S | 8099.982 | 0
Edinburgh Airport Tram Stop | Tramstop | A5450 | Install Telecon Equipment | Off Street - Other | SCC | 7A | S | 8099.982 | 0
Edinburgh Airport Tram Stop | Tramstop | A5460 | Install Station Control Equipment + AFC Equipment | Off Street - Other | SCC | 7A | S | 8099.982 | 0
Edinburgh Airport Tram Stop | Tramstop | A6360 | Installation of SIG-interlocking cubicle | Off Street - Other | SCC | 7A | S | 8099.982 | 0
Edinburgh Airport Tram Stop | Tramstop | A6370 | Commissioning of SIG -interlocking cubicle | Off Street - Other | SCC | 7A | S | 0 | 0
Edinburgh Airport Tram Stop | Tramstop | A5439 | Access for E&M Tram Stop installation (07A Edingburgh Airport) | Off Street - Other | SCC | 7A | S | 0 | 0
Edinburgh Airport Tram Stop | Tramstop | A5438 | Access for visual inspection for E&M Tram Stop installation (07A Edingburgh Airport) | Off Street - Other | SCC | 7A | S | 0 | 0
Edinburgh Airport Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | SCC | 7A | S | 409.09 | 0
0
0
0
0
Newhaven to Ocean Terminal | [8 empty] | 0
Newhaven to Ocean Terminal | E & M Installations | [7 empty] | 0
Newhaven to Ocean Terminal | E & M Installations | A17020 | Overhead Catenary Line | On Street - Other | OLE | 1A | S | 185429.3034 | 0
Newhaven to Ocean Terminal | E & M Installations | A17020 | Overhead Catenary Line | On Street - Other | OLE | 1A | S | 185429.3034 | 0
Leith Sands Substation | [8 empty] | 0
Leith Sands Substation | Substation | [7 empty] | 0
Leith Sands Substation | Substation | 36 | Order REC supply from Scottish Power | On Street - Other | OLE | 1A | S | 0 | 0
Leith Sands Substation | Substation | A5483 | Access for visual inspection for E&M Substation installation (01A Leith Sands) | On Street - Other | OLE | 1A | S | 0 | 0
Leith Sands Substation | Substation | A5480 | Power Infeed from Public Net available inc HV cable | On Street - Other | OLE | 1A | S | 0 | 0
Leith Sands Substation | Substation | A5484 | Access for E&M Substation installation (01A Leith Sands) | On Street - Other | OLE | 1A | S | 0 | 0
Leith Sands Substation | Substation | A5490 | Install LV Power Supply and LV Power Equipment | On Street - Other | OLE | 1A | S | 0 | 0
Leith Sands Substation | Substation | A5500 | Installation of TPS Equipment | On Street - Other | OLE | 1A | S | 0 | 0
Leith Sands Substation | Substation | A5510 | Install Telecom and Scada | On Street - Other | OLE | 1A | S | 0 | 0
Leith Sands Substation | Substation | A5520 | Testing and Commissioning | On Street - Other | OLE | 1A | S | 284225.9017 | 0
Leith Sands Substation | Substation | Snagging | Snagging | On Street - Other | OLE | 1A | S | 2870.9687 | 0
0
Ocean Terminal to Foot of the Walk | [8 empty] | 0
Ocean Terminal to Foot of the Walk | E & M Installations | [7 empty] | 0
Ocean Terminal to Foot of the Walk | E & M Installations | A3890 | Overhead Catenary Line | On Street - Other | OLE | 1A | S | 318938.4019 | 0
Ocean Terminal to Foot of the Walk | E & M Installations | A3890 | Overhead Catenary Line | On Street - Other | OLE | 1A | S | 318938.4019 | 0
0
Foot of the Walk to McDonald Road | [8 empty] | 0
Foot of the Walk to McDonald Road | E & M Installations | [7 empty] | 0
Foot of the Walk to McDonald Road | E & M Installations | A3770 | Overhead Catenary Line - One Half | On Street - Other | OLE | 1B | S | 254260.8217 | 0
Foot of the Walk to McDonald Road | E & M Installations | A3770 | Overhead Catenary Line | On Street - Other | OLE | 1B | S | 381391.2326 | 0
Foot of the Walk to McDonald Road | E & M Installations | Snagging | Snagging | On Street - Other | OLE | 1B | S | 6420.7278 | 0
0
Leith Walk Substation | [8 empty] | 0
Leith Walk Substation | Substation | [7 empty] | 0
Leith Walk Substation | Substation | 146 | Order REC supply from Scottish Power | On Street - Other | OLE | 1B | S | 0 | 0
Leith Walk Substation | Substation | A5530 | Power Infeed from Public Net available inc HV cable | On Street - Other | OLE | 1B | S | 0 | 0
Leith Walk Substation | Substation | A5550 | Installation of TPS Equipment | On Street - Other | OLE | 1B | S | 0 | 0
Leith Walk Substation | Substation | A5540 | Install LV Power Supply and LV Power Equipment | On Street - Other | OLE | 1B | S | 0 | 0
Leith Walk Substation | Substation | A5570 | Testing and Commissioning | On Street - Other | OLE | 1B | S | 284225.9017 | 0
Leith Walk Substation | Substation | A5560 | Install Telecom and Scada | On Street - Other | OLE | 1B | S | 0 | 0
Leith Walk Substation | Substation | A2639 | Access for E&M Substation installation (01B Leith Walk) | On Street - Other | OLE | 1B | S | 0 | 0
Leith Walk Substation | Substation | A2638 | Access for visual inspection for E&M Substation installation (01B Leith Walk) | On Street - Other | OLE | 1B | S | 0 | 0
Leith Walk Substation | Substation | Snagging | Snagging | On Street - Other | OLE | 1B | S | 2870.9687 | 0
0
0
McDonald Road to Princess Street West | [8 empty] | 0
McDonald Road to Princess Street West | E & M Installations | [7 empty] | 0
McDonald Road to Princess Street West | E & M Installations | A3850 | Overhead Catenary Line - One Half | On Street - Other | OLE | 1C | S | 528815.5747 | 0
McDonald Road to Princess Street West | E & M Installations | A3850 | Overhead Catenary Line | On Street - Other | OLE | 1C | S | 352543.7165 | 0
McDonald Road to Princess Street West | E & M Installations | Snagging | Snagging | On Street - Other | OLE | 1C | S | 8902.6191 | 0
0
Cathedral SubStation | [8 empty] | 0
Cathedral SubStation | Substation | [7 empty] | 0
Cathedral SubStation | Substation | 346 | Order REC supply from Scottish Power | On Street - Other | OLE | 1C | S | 0 | 0
Cathedral SubStation | Substation | A5580 | Power Infeed from Public Net available inc HV cable | On Street - Other | OLE | 1C | S | 0 | 0
Cathedral SubStation | Substation | A5600 | Installation of TPS Equipment | On Street - Other | OLE | 1C | S | 56845.1803 | 0
Cathedral SubStation | Substation | A5590 | Install LV Power Supply and LV Power Equipment | On Street - Other | OLE | 1C | S | 56845.1803 | 0
Cathedral SubStation | Substation | A5620 | Testing and Commissioning | On Street - Other | OLE | 1C | S | 0 | 0
Cathedral SubStation | Substation | A5610 | Install Telecom and Scada | On Street - Other | OLE | 1C | S | 56845.1803 | 0
Cathedral SubStation | Substation | A6120 | Installation of SIG-interlocking cubicle | On Street - Other | OLE | 1C | S | 56845.1803 | 0
Cathedral SubStation | Substation | A6130 | Commissioning of SIG -interlocking cubicle | On Street - Other | OLE | 1C | S | 56845.1803 | 0
Cathedral SubStation | Substation | A2839 | Access for E&M substation installation (01C Cathredral) | On Street - Other | OLE | 1C | S | 0 | 0
Cathedral SubStation | Substation | A2838 | Access for visual inspection forE&M substation installation (01C Cathredral) | On Street - Other | OLE | 1C | S | 0 | 0
Cathedral SubStation | Substation | Snagging | Snagging | On Street - Other | OLE | 1C | S | 2870.9687 | 0
0
0
Princes Street (inc.) to Haymarket (exc.) | [8 empty] | 0
Princes Street (inc.) to Haymarket (exc.) | E & M Installations | [7 empty] | 0
Princes Street (inc.) to Haymarket (exc.) | E & M Installations | A3810 | Overhead Catenary Line - 20% | On Street - Princes St | OLE | 1D | S | 123350.2995 | 0
Princes Street (inc.) to Haymarket (exc.) | E & M Installations | A3810 | Overhead Catenary Line | On Street - Princes St | OLE | 1D | S | 493401.1981 | 0
Princes Street (inc.) to Haymarket (exc.) | E & M Installations | Snagging | Snagging | On Street - Princes St | OLE | 1D | S | 6229.8131 | 0
0
0
0
Haymarket Corridor | [8 empty] | 0
Haymarket Corridor | E & M Installations | [7 empty] | 0
Haymarket Corridor | E & M Installations | A4050 | Overhead Catenary Line | Off Street - Other | OLE | 2A | S | 317965.7661 | 0
Haymarket Corridor | E & M Installations | Snagging | Snagging | Off Street - Other | OLE | 2A | S | 3211.7754 | 0
0
Haymarket Terrace Substation | [8 empty] | 0
Haymarket Terrace Substation | Substation | [7 empty] | 0
Haymarket Terrace Substation | Substation | 326 | Order REC supply from Scottish Power | Off Street - Other | OLE | 2A | S | 0 | 0
Haymarket Terrace Substation | Substation | A5630 | Power Infeed from Public Net available inc HV cable | Off Street - Other | OLE | 2A | S | 0 | 0
Haymarket Terrace Substation | Substation | A5650 | Installation of TPS Equipment | Off Street - Other | OLE | 2A | S | 71056.4754 | 0
Haymarket Terrace Substation | Substation | A5640 | Install LV Power Supply and LV Power Equipment | Off Street - Other | OLE | 2A | S | 71056.4754 | 0
Haymarket Terrace Substation | Substation | A5670 | Testing and Commissioning | Off Street - Other | OLE | 2A | S | 71056.4754 | 0
Haymarket Terrace Substation | Substation | A5660 | Install Telecom and Scada | Off Street - Other | OLE | 2A | S | 71056.4754 | 0
Haymarket Terrace Substation | Substation | A2699 | Access for E&M Substation installation (02A Haymarket Terrace) | Off Street - Other | OLE | 2A | S | 0 | 0
Haymarket Terrace Substation | Substation | A2698 | Access for visual inspection for E&M Substation installation (02A Haymarket Terrace) | Off Street - Other | OLE | 2A | S | 0 | 0
Haymarket Terrace Substation | Substation | Snagging | Snagging | Off Street - Other | OLE | 2A | S | 2870.9687 | 0
0
0
0
Roseburn Junction (exc.) to Balgreen Road (inc.) | [8 empty] | 0
Roseburn Junction (exc.) to Balgreen Road (inc.) | E & M Installations | [7 empty] | 0
Roseburn Junction (exc.) to Balgreen Road (inc.) | E & M Installations | A4090 | Overhead Catenary Line - One Half | Off Street - Other | OLE | 5A | S | 363956.63 | 0
Roseburn Junction (exc.) to Balgreen Road (inc.) | E & M Installations | A4090 | Overhead Catenary Line | Off Street - Other | OLE | 5A | S | 242637.7533 | 0
Roseburn Junction (exc.) to Balgreen Road (inc.) | E & M Installations | Snagging | Snagging | Off Street - Other | OLE | 5A | S | 2450.8864 | 0
Jenners Depository Substation | [8 empty] | 0
Jenners Depository Substation | Substation | [7 empty] | 0
Jenners Depository Substation | Substation | 286 | Order REC supply from Scottish Power | Off Street - Other | OLE | 5A | S | 0 | 0
Jenners Depository Substation | Substation | A5830 | Power Infeed from Public Net available inc HV cable | Off Street - Other | OLE | 5A | S | 0 | 0
Jenners Depository Substation | Substation | A5850 | Installation of TPS Equipment | Off Street - Other | OLE | 5A | S | 71056.4754 | 0
Jenners Depository Substation | Substation | A5840 | Install LV Power Supply and LV Power Equipment | Off Street - Other | OLE | 5A | S | 71056.4754 | 0
Jenners Depository Substation | Substation | A5870 | Testing and Commissioning | Off Street - Other | OLE | 5A | S | 71056.4754 | 0
Jenners Depository Substation | Substation | A5860 | Install Telecom and Scada | Off Street - Other | OLE | 5A | S | 71056.4754 | 0
Jenners Depository Substation | Substation | A2279 | Access for E&M Substation installation (05A Jenners Depository) | Off Street - Other | OLE | 5A | S | 0 | 0
Jenners Depository Substation | Substation | A2278 | Access for visual inspection for E&M Substation installation (05A Jenners Depository) | Off Street - Other | OLE | 5A | S | 0 | 0
Jenners Depository Substation | Substation | Snagging | Snagging | Off Street - Other | OLE | 5A | S | 2870.9687 | 0
0
0
Balgreen Road to Edinburgh Park | [8 empty] | 0
Balgreen Road to Edinburgh Park | E & M Installations | [7 empty] | 0
Balgreen Road to Edinburgh Park | E & M Installations | A4130 | Overhead Catenary Line - One Sixth | Off Street - Other | OLE | 5B | S | 282721.039 | 0
Balgreen Road to Edinburgh Park | E & M Installations | A4130 | Overhead Catenary Line - One Sixth | Off Street - Other | OLE | 5B | S | 282721.039 | 0
Balgreen Road to Edinburgh Park | E & M Installations | A4130 | Overhead Catenary Line - One Sixth | Off Street - Other | OLE | 5B | S | 282721.039 | 0
Balgreen Road to Edinburgh Park | E & M Installations | A4130 | Overhead Catenary Line - One Sixth | Off Street - Other | OLE | 5B | S | 282721.039 | 0
Balgreen Road to Edinburgh Park | E & M Installations | A4130 | Overhead Catenary Line - One Sixth | Off Street - Other | OLE | 5B | S | 282721.039 | 0
Balgreen Road to Edinburgh Park | E & M Installations | A4130 | Overhead Catenary Line | Off Street - Other | OLE | 5B | S | 471201.7316 | 0
Balgreen Road to Edinburgh Park | E & M Installations | Snagging | Snagging | Off Street - Other | OLE | 5B | S | 19038.4538 | 0
0
Carrick Knowe Bridge (S23) | [8 empty] | 0
Bridges | E & M Installations | [7 empty] | 0
Bridges | Carrick Knowe Disruptive Possessions | 64 | OLE Supports | Off Street - Other | OLE | 5B | S | 32259.3386 | 0
Bridges | Carrick Knowe Disruptive Possessions | 75 | Catenary Cables | Off Street - Other | OLE | 5B | S | 32259.3386 | 0
Bridges | Carrick Knowe Disruptive Possessions | 265 | OLE Supports and Catenary over Tracks | Off Street - Other | OLE | 5B | S | 32259.3386 | 0
Bridges | Carrick Knowe Disruptive Possessions | 94 | Possessions 4 (12hrs) | Off Street - Other | OLE | 5B | S | 0 | 0
Bridges | Carrick Knowe Disruptive Possessions | Snagging | Snagging | Off Street - Other | OLE | 5B | S | 6842.89 | 0
Carrick Knowe Bridge (S23) | Carrick Knowe Disruptive Possessions | 3rd Party | Third Party Sign-off | Off Street - Other | Structures | 5B | BB | 25000 | 0
|  | Crit. Milestone | Completion of Construct Carricknowe Bridge (S23) (3) | Off Street - Other | Structures | 5B | BB | 0 | 0
0
Bankhead Drive Substation | [8 empty] | 0
Bankhead Drive Substation | Substation | [7 empty] | 0
Bankhead Drive Substation | Substation | 256 | Order REC supply from Scottish Power | Off Street - Other | OLE | 5B | S | 0 | 0
Bankhead Drive Substation | Substation | A5880 | Power Infeed from Public Net available inc HV cable | Off Street - Other | OLE | 5B | S | 0 | 0
Bankhead Drive Substation | Substation | A5900 | Installation of TPS Equipment | Off Street - Other | OLE | 5B | S | 71056.4754 | 0
Bankhead Drive Substation | Substation | A5890 | Install LV Power Supply and LV Power Equipment | Off Street - Other | OLE | 5B | S | 71056.4754 | 0
Bankhead Drive Substation | Substation | A5920 | Testing and Commissioning | Off Street - Other | OLE | 5B | S | 71056.4754 | 0
Bankhead Drive Substation | Substation | A5910 | Install Telecom and Scada | Off Street - Other | OLE | 5B | S | 71056.4754 | 0
Bankhead Drive Substation | Substation | A2259 | Access for E&M Substation installation (05B Bankhead Drive) | Off Street - Other | OLE | 5B | S | 0 | 0
Bankhead Drive Substation | Substation | A2258 | Access for visual inspection for E&M Substation installation (05B Bankhead Drive) | Off Street - Other | OLE | 5B | S | 0 | 0
Bankhead Drive Substation | Substation | Snagging | Snagging | Off Street - Other | OLE | 5B | S | 2870.9687 | 0
Edinburgh Park Station Bridge (S27) Disruptive Possessions | [8 empty] | 0
Edinburgh Park Station Bridge (S27) Disruptive Possessions | E & M Installations | [7 empty] | 0
Edinburgh Park Station Bridge (S27) Disruptive Possessions | E & M Installations | 52 | OLE Supports | Off Street - Other | OLE | 5B | S | 133272.58 | 0
Edinburgh Park Station Bridge (S27) Disruptive Possessions | E & M Installations | 373 | Catenary Cables | Off Street - Other | OLE | 5B | S | 133272.58 | 0
Edinburgh Park Station Bridge (S27) Disruptive Possessions | E & M Installations | A14150 | OLE Supports and Catenary over Tracks | Off Street - Other | OLE | 5B | S | 133272.58 | 0
Edinburgh Park Station Bridge (S27) Disruptive Possessions | E & M Installations | Snagging | Snagging | Off Street - Other | OLE | 5B | S | 35000.88 | 0
|  | Crit. Milestone | Completion of Edinburgh Park Station Bridge (2) |  |  |  |  | 0 | 0
0
0
Edinburgh Park to Depot | [8 empty] | 0
Edinburgh Park to Depot | E & M Installations | [7 empty] | 0
Edinburgh Park to Depot | E & M Installations | A4170 | Overhead Catenary Line | Off Street - Other | OLE | 5C | S | 365146.2289 | 0
Edinburgh Park to Depot | E & M Installations | Snagging | Snagging | Off Street - Other | OLE | 5C | S | 3688.3457 | 0
Depot to Gogarburn | [8 empty] | 0
Depot to Gogarburn | E & M Installations | [7 empty] | 0
Depot to Gogarburn | E & M Installations | A16930 | Overhead Catenary Line | Off Street - Other | OLE | 5C | S | 365146.2289 | 0
Depot to Gogarburn | E & M Installations | Snagging | Snagging | Off Street - Other | OLE | 5C | S | 3688.3457 | 0
0
0
0
Depot | Substation | [7 empty] | 0
Depot | Substation | 306 | Order REC supply from Scottish Power | Off Street Depot | OLE | 6A | S | 0 | 0
Depot | Substation | A5930 | Power Infeed from Public Net available inc HV cable | Off Street Depot | OLE | 6A | S | 0 | 0
Depot | Substation | A5950 | Installation of TPS Equipment | Off Street Depot | OLE | 6A | S | 134092.8484 | 0
Depot | Substation | A5940 | Install LV Power Supply and LV Power Equipment | Off Street Depot | OLE | 6A | S | 134092.8484 | 0
Depot | Substation | A5970 | Testing and Commissioning | Off Street Depot | OLE | 6A | S | 134092.8484 | 0
Depot | Substation | A5960 | Install Telecom and Scada | Off Street Depot | OLE | 6A | S | 134092.8484 | 0
Depot | Substation | A6330 | Installation of SIG-interlocking cubicle | Off Street Depot | OLE | 6A | S | 134092.8484 | 0
Depot | Substation | A6340 | Commissioning of SIG -interlocking cubicle | Off Street Depot | OLE | 6A | S | 0 | 0
Depot | Substation | A2519 | Access for E&M Substation installation (06A Depot) | Off Street Depot | OLE | 6A | S | 0 | 0
Depot | Substation | A2518 | Access for visual inspection for E&M Substation installation (06A Depot) | Off Street Depot | OLE | 6A | S | 0 | 0
Depot | Substation | Snagging | Snagging | Off Street Depot | OLE | 6A | S | 6772.3661 | 0
Gogar Deport E & M Installations | [8 empty] | 0
Gogar Deport E & M Installations | E & M Installations | [7 empty] | 0
Gogar Deport E & M Installations | E & M Installations | A4210 | Overhead Catenary Line | Off Street Depot | OLE | 6A | S | 84994.2479 | 0
Gogar Deport E & M Installations | E & M Installations | Snagging | Snagging | Off Street Depot | OLE | 6A | S | 858.5278 | 0
0
0
0
Gogarburn to Edinburgh Airport E & M Installations | [8 empty] | 0
Gogarburn to Edinburgh Airport E & M Installations | E & M Installations | [7 empty] | 0
Gogarburn to Edinburgh Airport E & M Installations | E & M Installations | A4250 | Overhead Catenary Line - One Third | Off Street - Other | OLE | 7A | S | 424061.4173 | 0
Gogarburn to Edinburgh Airport E & M Installations | E & M Installations | A4250 | Overhead Catenary Line - One Third | Off Street - Other | OLE | 7A | S | 318046.063 | 0
Gogarburn to Edinburgh Airport E & M Installations | E & M Installations | A4250 | Overhead Catenary Line | Off Street - Other | OLE | 7A | S | 318046.063 | 0
Gogarburn to Edinburgh Airport E & M Installations | E & M Installations | Snagging | Snagging | Off Street - Other | OLE | 7A | S | 10708.6217 | 0
0
Ingliston Park and Ride Substation | [8 empty] | 0
Ingliston Park and Ride Substation | Substation | [7 empty] | 0
Ingliston Park and Ride Substation | Substation | 216 | Order REC supply from Scottish Power | Off Street - Other | OLE | 7A | S | 0 | 0
Ingliston Park and Ride Substation | Substation | A5980 | Power Infeed from Public Net available inc HV cable | Off Street - Other | OLE | 7A | S | 0 | 0
Ingliston Park and Ride Substation | Substation | A6000 | Installation of TPS Equipment | Off Street - Other | OLE | 7A | S | 73781.0061 | 0
Ingliston Park and Ride Substation | Substation | A5990 | Install LV Power Supply and LV Power Equipment | Off Street - Other | OLE | 7A | S | 73781.0061 | 0
Ingliston Park and Ride Substation | Substation | A6020 | Testing and Commissioning | Off Street - Other | OLE | 7A | S | 73781.0061 | 0
Ingliston Park and Ride Substation | Substation | A6010 | Install Telecom and Scada | Off Street - Other | OLE | 7A | S | 73781.0061 | 0
Ingliston Park and Ride Substation | Substation | A1969 | Access for E&M Substation installation (07A Inglistion Park and Ride) | Off Street - Other | OLE | 7A | S | 0 | 0
Ingliston Park and Ride Substation | Substation | A1968 | Access for visual inspection for E&M Substation installation (07A Inglistion Park and Ride) | Off Street - Other | OLE | 7A | S | 0 | 0
Ingliston Park and Ride Substation | Substation | Snagging | Snagging | Off Street - Other | OLE | 7A | S | 2981.0508 | 0
0
0
0
0
Lindsay Road Retaining Walls (W1) | [8 empty] | 0
Lindsay Road Retaining Walls (W1) | Retaining Wall | [7 empty] | 0
Lindsay Road Retaining Walls (W1) | Retaining Wall | 5 | Wall B Contiguous Bored Piles | On Street - Other | Structures | 1A | BB | 145364.769 | 0
Lindsay Road Retaining Walls (W1) | Retaining Wall | 5 | Wall B Contiguous Bored Piles | On Street - Other | Structures | 1A | BB | 145364.769 | 0
Lindsay Road Retaining Walls (W1) | Retaining Wall | 5 | Wall B Contiguous Bored Piles | On Street - Other | Structures | 1A | BB | 145364.769 | 0
Lindsay Road Retaining Walls (W1) | Retaining Wall | 5 | Wall B Contiguous Bored Piles | On Street - Other | Structures | 1A | BB | 145364.769 | 0
Lindsay Road Retaining Walls (W1) | Retaining Wall | 5 | Wall B Contiguous Bored Piles | On Street - Other | Structures | 1A | BB | 145364.769 | 0
Lindsay Road Retaining Walls (W1) | Retaining Wall | A1710 | Wall A Reinforced Earth | On Street - Other | Structures | 1A | BB | 436094.307 | 0
Lindsay Road Retaining Walls (W1) | Retaining Wall | A1710 | Wall A Parapet Wall | On Street - Other | Structures | 1A | BB | 290729.538 | 0
Lindsay Road Retaining Walls (W1) | Retaining Wall | Snagging | Snagging | On Street - Other | Structures | 1A | BB | 14683.31 | 0
Newhaven Road Tramstop | [8 empty] | 0
Newhaven Road Tramstop | Tramstop | [7 empty] | 0
Newhaven Road Tramstop | Tramstop | 8 | Civil and Building Works | On Street - Other | Structures | 1A | BB | 127940.67 | 0
Newhaven Road Tramstop | Tramstop | 8 | Civil and Building Works | On Street - Other | Structures | 1A | BB | 127940.67 | 0
Newhaven Road Tramstop | Tramstop | Snagging | Snagging | On Street - Other | Structures | 1A | BB | 2584.66 | 0
Newhaven Road Tramstop | Tramstop | A1680 | Deliver and Install Shelter | On Street - Other | Structures | 1A | S | 34772.76 | 0
Newhaven Road Tramstop | Tramstop | Snagging | Snagging | On Street - Other | Structures | 1A | S | 351.24 | 0
Leith Sands Substation | [8 empty] | 0
Leith Sands Substation | Substation | [7 empty] | 0
Leith Sands Substation | Substation | 6 | Civil Engineering and Building Works | On Street - Other | Structures | 1A | BB | 82189.305 | 0
Leith Sands Substation | Substation | 6 | Completion of envelope | On Street - Other | Structures | 1A | BB | 82189.305 | 0
Leith Sands Substation | Substation | Snagging | Snagging | On Street - Other | Structures | 1A | BB | 1660.39 | 0
0
Victoria Dock Entrance Bridge (S16) | [8 empty] | 0
Victoria Dock Entrance Bridge (S16) | Bridge | [7 empty] | 0
Victoria Dock Entrance Bridge (S16) | Bridge | 131 | Reprofile and Waterproof Deck (Dummy) | On Street - Other | Structures | 1A | BB | 337015.305 | 0
Victoria Dock Entrance Bridge (S16) | Bridge | 12330 | Permanent Diversion of Services (by Others) | On Street - Other | Structures | 1A | BB | 337015.305 | 0
Victoria Dock Entrance Bridge (S16) | Bridge | Snagging | Snagging | On Street - Other | Structures | 1A | BB | 6808.39 | 0
Tower Place Bridge (S17) | [8 empty] | 0
Tower Place Bridge (S17) | Bridge | [7 empty] | 0
Tower Place Bridge (S17) | Bridge | A1770 | Piling | On Street - Other | Structures | 1A | BB | 174346.11 | 0
Tower Place Bridge (S17) | Bridge | A16050 | Temporary Diversion of Services (by others) | On Street - Other | Structures | 1A | BB | 174346.11 | 0
Tower Place Bridge (S17) | Bridge | A16060 | Temporary Platforms and Demolition | On Street - Other | Structures | 1A | BB | 174346.11 | 0
Tower Place Bridge (S17) | Bridge | Deck Finishes |  | On Street - Other | Structures | 1A | BB | 0 | 0
Tower Place Bridge (S17) | Bridge | A16090 | Permanent Diversion of Services (by others) | On Street - Other | Structures | 1A | BB | 24346.11 | 0
Tower Place Bridge (S17) | Bridge | A16100 | Finishes | On Street - Other | Structures | 1A | BB | 24346.11 | 0
Tower Place Bridge (S17) | Bridge | South Widening |  | On Street - Other | Structures | 1A | BB | 0 | 0
Tower Place Bridge (S17) | Bridge | A1760 | Install Beams | On Street - Other | Structures | 1A | BB | 324346.11 | 0
Tower Place Bridge (S17) | Bridge | A31 | Superstructure | On Street - Other | Structures | 1A | BB | 174346.11 | 0
Tower Place Bridge (S17) | Bridge | A16080 | Substructure | On Street - Other | Structures | 1A | BB | 174346.11 | 0
Tower Place Bridge (S17) | Bridge | North Widening |  | On Street - Other | Structures | 1A | BB | 0 | 0
Tower Place Bridge (S17) | Bridge | A11 | Install Beams | On Street - Other | Structures | 1A | BB | 324346.11 | 0
Tower Place Bridge (S17) | Bridge | A101 | Substructure | On Street - Other | Structures | 1A | BB | 174346.11 | 0
Tower Place Bridge (S17) | Bridge | A16070 | Superstructure | On Street - Other | Structures | 1A | BB | 174346.11 | 0
Tower Place Bridge (S17) | Bridge | Snagging | Snagging | On Street - Other | Structures | 1A | BB | 19371.79 | 0
Ocean Terminal Tram Stop | [8 empty] | 0
Ocean Terminal Tram Stop | Tramstop | [7 empty] | 0
Ocean Terminal Tram Stop | Tramstop | 14 | Civil Engineering and Building Works | On Street - Other | Structures | 1A | BB | 127953.54 | 0
Ocean Terminal Tram Stop | Tramstop | 14 | Civil Engineering and Building Works | On Street - Other | Structures | 1A | BB | 127953.54 | 0
Ocean Terminal Tram Stop | Tramstop | Snagging | Snagging | On Street - Other | Structures | 1A | BB | 2584.92 | 0
Ocean Terminal Tram Stop | Tramstop | A1720 | Deliver and Install Shelter | On Street - Other | Structures | 1A | S | 34772.76 | 0
Ocean Terminal Tram Stop | Tramstop | Snagging | Snagging | On Street - Other | Structures | 1A | S | 351.24 | 0
0
Ocean Drive Tram Stop | [8 empty] | 0
Ocean Drive Tram Stop | Tramstop | [7 empty] | 0
Port of Leith Tram Stop | Tramstop | 17 | Civil Engineering and Building Works | On Street - Other | Structures | 1A | BB | 127953.54 | 0
Port of Leith Tram Stop | Tramstop | 17 | Civil Engineering and Building Works | On Street - Other | Structures | 1A | BB | 127953.54 | 0
Port of Leith Tram Stop | Tramstop | Snagging | Snagging | On Street - Other | Structures | 1A | BB | 2584.92 | 0
Port of Leith Tram Stop | Tramstop | A1800 | Deliver and Install Shelter | On Street - Other | Structures | 1A | S | 34772.76 | 0
Port of Leith Tram Stop | Tramstop | Snagging | Snagging | On Street - Other | Structures | 1A | S | 351.24 | 0
0
Constitution Street Tram Stop | [8 empty] | 0
Constitution Street Tram Stop | Tramstop | [7 empty] | 0
Constitution Street Tram Stop | Tramstop | 20 | Civil Engineering And Building Works | On Street - Other | Structures | 1A | BB | 127953.54 | 0
Constitution Street Tram Stop | Tramstop | 20 | Civil Engineering And Building Works | On Street - Other | Structures | 1A | BB | 127953.54 | 0
Constitution Street Tram Stop | Tramstop | Snagging | Snagging | On Street - Other | Structures | 1A | BB | 2584.92 | 0
Constitution Street Tram Stop | Tramstop | A1850 | Deliver and Install Shelter | On Street - Other | Structures | 1A | S | 34772.76 | 0
Constitution Street Tram Stop | Tramstop | Snagging | Snagging | On Street - Other | Structures | 1A | S | 351.24 | 0
0
Foot of the Walk Tram Stop | [8 empty] | 0
Foot of the Walk Tram Stop | Tramstop | [7 empty] | 0
Foot of the Walk Tram Stop | Tramstop | 50 | Civil Engineering And Building Works | On Street - Other | Structures | 1B | BB | 115464.69 | 0
Foot of the Walk Tram Stop | Tramstop | 50 | Civil Engineering And Building Works | On Street - Other | Structures | 1B | BB | 115464.69 | 0
Foot of the Walk Tram Stop | Tramstop | Snagging | Snagging | On Street - Other | Structures | 1B | BB | 2332.62 | 0
Foot of the Walk Tram Stop | Tramstop | A2560 | Deliver and Install Shelter | On Street - Other | Structures | 1B | S | 34772.76 | 0
Foot of the Walk Tram Stop | Tramstop | Snagging | Snagging | On Street - Other | Structures | 1B | S | 351.24 | 0
Leith Walk Substation | [8 empty] | 0
Leith Walk Substation | Substation | [7 empty] | 0
Leith Walk Substation | Substation | 176 | Civil Engineering and Building Works | On Street - Other | Structures | 1B | BB | 74081.205 | 0
Leith Walk Substation | Substation | 176 | Completion of envelope | On Street - Other | Structures | 1B | BB | 74081.205 | 0
Leith Walk Substation | Substation | Snagging | Snagging | On Street - Other | Structures | 1B | BB | 1496.59 | 0
0
Balfour Street Tram Stop | [8 empty] | 0
Balfour Street Tram Stop | Tramstop | [7 empty] | 0
Balfour Street Tram Stop | Tramstop | 590 | Civil Engineering And Building Works | On Street - Other | Structures | 1B | BB | 115464.69 | 0
Balfour Street Tram Stop | Tramstop | 590 | Civil Engineering And Building Works | On Street - Other | Structures | 1B | BB | 115464.69 | 0
Balfour Street Tram Stop | Tramstop | Snagging | Snagging | On Street - Other | Structures | 1B | BB | 2332.62 | 0
Balfour Street Tram Stop | Tramstop | A2600 | Deliver and Install Shelter | On Street - Other | Structures | 1B | S | 34772.76 | 0
Balfour Street Tram Stop | Tramstop | Snagging | Snagging | On Street - Other | Structures | 1B | S | 351.24 | 0
0
0
McDonald Road Tramstop | [8 empty] | 0
McDonald Road Tramstop | Tramstop | [7 empty] | 0
McDonald Road Tramstop | Tramstop | 600 | Civil Engineering And Building Works | On Street - Other | Structures | 1C | BB | 75454.335 | 0
McDonald Road Tramstop | Tramstop | 600 | Civil Engineering And Building Works | On Street - Other | Structures | 1C | BB | 75454.335 | 0
McDonald Road Tramstop | Tramstop | Snagging | Snagging | On Street - Other | Structures | 1C | BB | 1524.33 | 0
McDonald Road Tramstop | Tramstop | A2660 | Deliver and Install Shelter | On Street - Other | Structures | 1C | S | 34772.76 | 0
McDonald Road Tramstop | Tramstop | Snagging | Snagging | On Street - Other | Structures | 1C | S | 351.24 | 0
0
Picardy Place Tram Stop | [8 empty] | 0
Picardy Place Tram Stop | Tramstop | [7 empty] | 0
Picardy Place Tram Stop | Tramstop | 610 | Civil Engineering And Building Works | On Street - Other | Structures | 1C | BB | 75454.335 | 0
Picardy Place Tram Stop | Tramstop | 610 | Civil Engineering And Building Works | On Street - Other | Structures | 1C | BB | 75454.335 | 0
Picardy Place Tram Stop | Tramstop | Snagging | Snagging | On Street - Other | Structures | 1C | BB | 1524.33 | 0
Picardy Place Tram Stop | Tramstop | A2720 | Deliver and Install Shelter | On Street - Other | Structures | 1C | S | 34772.76 | 0
Picardy Place Tram Stop | Tramstop | Snagging | Snagging | On Street - Other | Structures | 1C | S | 351.24 | 0
Cathedral SubStation | [8 empty] | 0
Cathedral SubStation | Substation | [7 empty] | 0
Cathedral SubStation | Substation | 356 | Civil Engineering and Building Works | On Street - Other | Structures | 1C | BB | 77085.855 | 0
Cathedral SubStation | Substation | 356 | Completion of envelope | On Street - Other | Structures | 1C | BB | 77085.855 | 0
Cathedral SubStation | Substation | Snagging | Snagging | On Street - Other | Structures | 1C | BB | 1557.29 | 0
0
Princes Street West Tram Stop | [8 empty] | 0
Princes Street West Tram Stop | Tramstop | [7 empty] | 0
Princes Street West Tram Stop | Tramstop | 630 | Civil Engineering And Building Works | On Street - Princes St | Structures | 1C | BB | 75454.335 | 75454.335
Princes Street West Tram Stop | Tramstop | 630 | Civil Engineering And Building Works | On Street - Princes St | Structures | 1C | BB | 75454.335 | 75454.335
Princes Street West Tram Stop | Tramstop | Snagging | Snagging | On Street - Princes St | Structures | 1C | BB | 1524.33 | 0
Princes Street West Tram Stop | Tramstop | A2780 | Deliver and Install Shelter | On Street - Princes St | Structures | 1C | S | 34772.76 | 0
Princes Street West Tram Stop | Tramstop | Snagging | Snagging | On Street - Princes St | Structures | 1C | S | 351.24 | 0
St Andrews Square Tram Stop | [8 empty] | 0
St Andrews Square Tram Stop | Tramstop | [7 empty] | 0
St Andrews Square Tram Stop | Tramstop | 620 | Civil Engineering And Building Works | On Street - Other | Structures | 1C | BB | 75454.335 | 0
St Andrews Square Tram Stop | Tramstop | 620 | Civil Engineering And Building Works | On Street - Other | Structures | 1C | BB | 75454.335 | 0
St Andrews Square Tram Stop | Tramstop | Snagging | Snagging | On Street - Other | Structures | 1C | BB | 1524.33 | 0
St Andrews Square Tram Stop | Tramstop | A2750 | Deliver and Install Shelter | On Street - Other | Structures | 1C | S | 34772.76 | 0
St Andrews Square Tram Stop | Tramstop | Snagging | Snagging | On Street - Other | Structures | 1C | S | 351.24 | 0
0
0
Shandwick Place Tram Stop | [8 empty] | 0
Shandwick Place Tram Stop | Tramstop | [7 empty] | 0
Shandwick Place Tram Stop | Tramstop | A2810 | Deliver and Install Shelter | On Street - Other | Structures | 1D | S | 34772.76 | 0
Shandwick Place Tram Stop | Tramstop | Snagging | Snagging | On Street - Other | Structures | 1D | S | 351.24 | 0
Shandwick Place Tram Stop | Tramstop | 640 | Completion of Envelope | On Street - Other | Structures | 1D | BB | 211473.405 | 0
Shandwick Place Tram Stop | Tramstop | 640 | Civil Engineering And Building Works | On Street - Other | Structures | 1D | BB | 211473.405 | 0
Shandwick Place Tram Stop | Tramstop | Snagging | Snagging | On Street - Other | Structures | 1D | BB | 4272.19 | 0
0
0
0
Haymarket Station Viaduct (S19) | [8 empty] | 0
Haymarket Station Viaduct (S19) | Bridge | [7 empty] | 0
Haymarket Station Viaduct (S19) | Bridge | 1138 | Demolish Caledonian Ale House | Off Street - Other | Structures | 2A | BB | 100487.277 | 100487.277
Haymarket Station Viaduct (S19) | Bridge | 1139 | Bankseat at Grid line 1 | Off Street - Other | Structures | 2A | BB | 100487.277 | 2009.7455
Haymarket Station Viaduct (S19) | Bridge | 192 | Pier 2 | Off Street - Other | Structures | 2A | BB | 100487.277 | 100487.277
Haymarket Station Viaduct (S19) | Bridge | 227 | Pier 3 | Off Street - Other | Structures | 2A | BB | 100487.277 | 100487.277
Haymarket Station Viaduct (S19) | Bridge | 498 | Pier 4 | Off Street - Other | Structures | 2A | BB | 100487.277 | 75365.4577
Haymarket Station Viaduct (S19) | Bridge | 508 | Pier 5 | Off Street - Other | Structures | 2A | BB | 100487.277 | 0
Haymarket Station Viaduct (S19) | Bridge | 560 | Bankseat at Gridline 6 | Off Street - Other | Structures | 2A | BB | 100487.277 | 0
Haymarket Station Viaduct (S19) | Bridge | 570 | Superstructure - First Pour | Off Street - Other | Structures | 2A | BB | 125487.277 | 0
Haymarket Station Viaduct (S19) | Bridge | 570 | Superstructure - Second Pour | Off Street - Other | Structures | 2A | BB | 125487.277 | 0
Haymarket Station Viaduct (S19) | Bridge | 580 | Finishes | Off Street - Other | Structures | 2A | BB | 50487.277 | 0
Haymarket Station Viaduct (S19) | Bridge | Snagging | Snagging | Off Street - Other | Structures | 2A | BB | 10150.23 | 0
Haymarket Station Viaduct (S19) | Bridge | 3rd Party | Third Party Sign-off | Off Street - Other | Structures | 2A | BB | 25000 | 0
Haymarket Terrace Substation | [8 empty] | 0
Haymarket Terrace Substation | Substation | [7 empty] | 0
Haymarket Terrace Substation | Substation | 336 | Completion of envelope | Off Street - Other | Structures | 2A | BB | 227515.86 | 0
Haymarket Terrace Substation | Substation | 336 | Civil Engineering and Building Works | Off Street - Other | Structures | 2A | BB | 227515.86 | 0
Haymarket Terrace Substation | Substation | Snagging | Snagging | Off Street - Other | Structures | 2A | BB | 4596.28 | 0
Haymarket Station Tram Stop | [8 empty] | 0
Haymarket Station Tram Stop | Tramstop | [7 empty] | 0
Haymarket Station Tram Stop | Tramstop | 135 | Civil Engineering and Building Works | Off Street - Other | Structures | 2A | BB | 120505.275 | 0
Haymarket Station Tram Stop | Tramstop | 135 | Civil Engineering and Building Works | Off Street - Other | Structures | 2A | BB | 120505.275 | 0
Haymarket Station Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | Structures | 2A | BB | 2434.45 | 0
Haymarket Station Tram Stop | Tramstop | A2480 | Deliver and Install Shelter | Off Street - Other | Structures | 2A | S | 34772.76 | 0
Haymarket Station Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | Structures | 2A | S | 351.24 | 0
Russel Road Underbridge (S20) | [8 empty] | 0
Russel Road Underbridge (S20) | Bridge | [7 empty] | 0
Russel Road Underbridge (S20) | Bridge | 103 | Excavation | Off Street - Other | Structures | 5A | BB | 117330.642 | 0
Russel Road Underbridge (S20) | Bridge | 103 | Piling | Off Street - Other | Structures | 5A | BB | 175995.963 | 0
Russel Road Underbridge (S20) | Bridge | 238 | Bases | Off Street - Other | Structures | 5A | BB | 117330.642 | 0
Russel Road Underbridge (S20) | Bridge | 429 | Abutments | Off Street - Other | Structures | 5A | BB | 58665.321 | 0
Russel Road Underbridge (S20) | Bridge | 429 | Wing Walls | Off Street - Other | Structures | 5A | BB | 175995.963 | 0
Russel Road Underbridge (S20) | Bridge | 439 | Deck | Off Street - Other | Structures | 5A | BB | 234661.284 | 0
Russel Road Underbridge (S20) | Bridge | 439 | Parapets | Off Street - Other | Structures | 5A | BB | 175995.963 | 0
Russel Road Underbridge (S20) | Bridge | 449 | Bridge Finishes | Off Street - Other | Structures | 5A | BB | 117330.642 | 0
Russel Road Underbridge (S20) | Bridge | Snagging | Snagging | Off Street - Other | Structures | 5A | BB | 11851.58 | 0
Russell Road Retaining Walls (W3 and W4) | [8 empty] | 0
Russell Road Retaining Walls (W3 and W4) | Retaining Wall | [7 empty] | 0
Russell Road Retaining Walls (W3 and W4) | Retaining Wall | 107 | Site Clearance | Off Street - Other | Structures | 5A | BB | 99651.0735 | 49825.5368
Russell Road Retaining Walls (W3 and W4) | Retaining Wall | 250 | Demolish Existing Buildings | Off Street - Other | Structures | 5A | BB | 199302.147 | 0
Russell Road Retaining Walls (W3 and W4) | Retaining Wall | 338 | Temporary Access Road | Off Street - Other | Structures | 5A | BB | 0 | 0
Russell Road Retaining Walls (W3 and W4) | Retaining Wall | 348 | Bored Piling | Off Street - Other | Structures | 5A | BB | 99651.0735 | 0
Russell Road Retaining Walls (W3 and W4) | Retaining Wall | 370 | Pile Caps | Off Street - Other | Structures | 5A | BB | 199302.147 | 0
Russell Road Retaining Walls (W3 and W4) | Retaining Wall | 659 | Retaining Wall | Off Street - Other | Structures | 5A | BB | 199302.147 | 0
Russell Road Retaining Walls (W3 and W4) | Retaining Wall | 669 | Waterproofing | Off Street - Other | Structures | 5A | BB | 199302.147 | 0
Russell Road Retaining Walls (W3 and W4) | Retaining Wall | 679 | Imported Fill - 50% | Off Street - Other | Structures | 5A | BB | 199302.147 | 0
Russell Road Retaining Walls (W3 and W4) | Retaining Wall | 679 | Imported Fill | Off Street - Other | Structures | 5A | BB | 298953.2205 | 0
Russell Road Retaining Walls (W3 and W4) | Retaining Wall | 689 | Parapet | Off Street - Other | Structures | 5A | BB | 298953.2205 | 0
Russell Road Retaining Walls (W3 and W4) | Retaining Wall | 699 | Road Reinstate | Off Street - Other | Structures | 5A | BB | 199302.147 | 0
Russell Road Retaining Walls (W3 and W4) | Retaining Wall | Snagging | Snagging | Off Street - Other | Structures | 5A | BB | 20131.53 | 0
Russell Road Retaining Walls (W3 and W4) | Retaining Wall | 3rd Party | Third Party Sign-off | Off Street - Other | Structures | 5A | BB | 25000 | 0
Murrayfield Tram Stop Retaining Wall (W18) | [8 empty] | 0
Murrayfield Tram Stop Retaining Wall (W18) | Retaining Wall | [7 empty] | 0
Murrayfield Tram Stop Retaining Wall (W18) | Retaining Wall | 108 | Site Clearance | Off Street - Other | Structures | 5A | BB | 52297.0965 | 52297.0965
Murrayfield Tram Stop Retaining Wall (W18) | Retaining Wall | 182 | Foundations | Off Street - Other | Structures | 5A | BB | 52297.0965 | 0
Murrayfield Tram Stop Retaining Wall (W18) | Retaining Wall | 217 | Reinforced Earth Wall - One Seventh Length | Off Street - Other | Structures | 5A | BB | 52297.0965 | 0
Murrayfield Tram Stop Retaining Wall (W18) | Retaining Wall | 217 | Reinforced Earth Wall - One Seventh Length | Off Street - Other | Structures | 5A | BB | 104594.193 | 0
Murrayfield Tram Stop Retaining Wall (W18) | Retaining Wall | 217 | Reinforced Earth Wall - One Seventh Length | Off Street - Other | Structures | 5A | BB | 104594.193 | 0
Murrayfield Tram Stop Retaining Wall (W18) | Retaining Wall | 217 | Reinforced Earth Wall - One Seventh Length | Off Street - Other | Structures | 5A | BB | 104594.193 | 0
Murrayfield Tram Stop Retaining Wall (W18) | Retaining Wall | 217 | Reinforced Earth Wall - One Seventh Length | Off Street - Other | Structures | 5A | BB | 104594.193 | 0
Murrayfield Tram Stop Retaining Wall (W18) | Retaining Wall | 217 | Reinforced Earth Wall - One Seventh Length | Off Street - Other | Structures | 5A | BB | 104594.193 | 0
Murrayfield Tram Stop Retaining Wall (W18) | Retaining Wall | 217 | Reinforced Earth Wall - One Seventh Length | Off Street - Other | Structures | 5A | BB | 104594.193 | 0
Murrayfield Tram Stop Retaining Wall (W18) | Retaining Wall | 418 | Coping | Off Street - Other | Structures | 5A | BB | 104594.193 | 0
Murrayfield Tram Stop Retaining Wall (W18) | Retaining Wall | 440 | Steps | Off Street - Other | Structures | 5A | BB | 104594.193 | 0
Murrayfield Tram Stop Retaining Wall (W18) | Retaining Wall | 428 | Handrail | Off Street - Other | Structures | 5A | BB | 52297.0965 | 0
Murrayfield Tram Stop Retaining Wall (W18) | Retaining Wall | Snagging | Snagging | Off Street - Other | Structures | 5A | BB | 10565.07 | 0
Murrayfield Tram Stop | [8 empty] | 0
Murrayfield Tram Stop | Tramstop | [7 empty] | 0
Murrayfield Tram Stop | Tramstop | 105 | Civil Engineering and Building Works | Off Street - Other | Structures | 5A | BB | 192857.445 | 0
Murrayfield Tram Stop | Tramstop | 105 | Civil Engineering and Building Works | Off Street - Other | Structures | 5A | BB | 192857.445 | 0
Murrayfield Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | Structures | 5A | BB | 3896.11 | 0
Murrayfield Tram Stop | Tramstop | A2030 | Deliver and Install Shelter | Off Street - Other | Structures | 5A | S | 34772.76 | 0
Murrayfield Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | Structures | 5A | S | 351.24 | 0
0
Roseburn Street Viaduct (S21A) | [8 empty] | 0
Roseburn Street Viaduct (S21A) | Bridge | [7 empty] | 0
Roseburn Street Viaduct (S21A) | Bridge | 10751 | Remove Scotrail Oil Tanks | Off Street - Other | Structures | 5A | BB | 0 | 0
Roseburn Street Viaduct (S21A) | Bridge | 109 | Bankseat at Grid line A | Off Street - Other | Structures | 5A | BB | 127966.5338 | 0
Roseburn Street Viaduct (S21A) | Bridge | 172 | Pier B | Off Street - Other | Structures | 5A | BB | 127966.5338 | 0
Roseburn Street Viaduct (S21A) | Bridge | 207 | Pier C | Off Street - Other | Structures | 5A | BB | 127966.5338 | 0
Roseburn Street Viaduct (S21A) | Bridge | 398 | Pier D | Off Street - Other | Structures | 5A | BB | 127966.5338 | 0
Roseburn Street Viaduct (S21A) | Bridge | 408 | Pier E | Off Street - Other | Structures | 5A | BB | 127966.5338 | 0
Roseburn Street Viaduct (S21A) | Bridge | 420 | Bankseat at Gridline F | Off Street - Other | Structures | 5A | BB | 127966.5338 | 0
Roseburn Street Viaduct (S21A) | Bridge | 430 | Structural steelwok | Off Street - Other | Structures | 5A | BB | 341244.09 | 0
Roseburn Street Viaduct (S21A) | Bridge | 729 | Deck Concrete | Off Street - Other | Structures | 5A | BB | 426555.1125 | 0
Roseburn Street Viaduct (S21A) | Bridge | 739 | Finishes | Off Street - Other | Structures | 5A | BB | 170622.045 | 0
Roseburn Street Viaduct (S21A) | Bridge | Snagging | Snagging | Off Street - Other | Structures | 5A | BB | 17234.55 | 0
Roseburn Street Viaduct (S21A) | Bridge | 3rd Party | Third Party Sign-off | Off Street - Other | Structures | 5A | BB | 25000 | 0
Murrayfield Retaining Walls (S21B) | [8 empty] | 0
Murrayfield Retaining Walls (S21B) | Retaining Wall | [7 empty] | 0
Murrayfield Retaining Walls (S21B) | Retaining Wall | 110 | Site Clearance | Off Street - Other | Structures | 5A | BB | 72847.5165 | 72847.5165
Murrayfield Retaining Walls (S21B) | Retaining Wall | 197 | Demolition | Off Street - Other | Structures | 5A | BB | 72847.5165 | 0
Murrayfield Retaining Walls (S21B) | Retaining Wall | 378 | Foundations | Off Street - Other | Structures | 5A | BB | 72847.5165 | 0
Murrayfield Retaining Walls (S21B) | Retaining Wall | 388 | Reinforced Earth Wall - One Third | Off Street - Other | Structures | 5A | BB | 291390.066 | 0
Murrayfield Retaining Walls (S21B) | Retaining Wall | 388 | Reinforced Earth Wall - One Third | Off Street - Other | Structures | 5A | BB | 291390.066 | 0
Murrayfield Retaining Walls (S21B) | Retaining Wall | 388 | Reinforced Earth Wall - One Third | Off Street - Other | Structures | 5A | BB | 364237.5825 | 0
Murrayfield Retaining Walls (S21B) | Retaining Wall | 400 | Coping | Off Street - Other | Structures | 5A | BB | 72847.5165 | 0
Murrayfield Retaining Walls (S21B) | Retaining Wall | 410 | Handrail | Off Street - Other | Structures | 5A | BB | 218542.5495 | 0
Murrayfield Retaining Walls (S21B) | Retaining Wall | 10760 | Murrayfield Stadium Accomodation Works | Off Street - Other | Structures | 5A | BB | 0 | 0
Murrayfield Retaining Walls (S21B) | Retaining Wall | Snagging | Snagging | Off Street - Other | Structures | 5A | BB | 14716.67 | 0
Murrayfield Retaining Walls (S21B) | Retaining Wall | 3rd Party | Third Party Sign-off | Off Street - Other | Structures | 5A | BB | 25000 | 0
Murrayfield Stadium Underpass (S21C) | [8 empty] | 0
Murrayfield Stadium Underpass (S21C) | Underpass | [7 empty] | 0
Murrayfield Stadium Underpass (S21C) | Underpass | 112 | Site Clearance | Off Street - Other | Structures | 5A | BB | 9388.9125 | 9388.9125
Murrayfield Stadium Underpass (S21C) | Underpass | 187 | Temporary Works - Demolition | Off Street - Other | Structures | 5A | BB | 18777.825 | 0
Murrayfield Stadium Underpass (S21C) | Underpass | 358 | Earthworks | Off Street - Other | Structures | 5A | BB | 18777.825 | 0
Murrayfield Stadium Underpass (S21C) | Underpass | 368 | Base | Off Street - Other | Structures | 5A | BB | 18777.825 | 0
Murrayfield Stadium Underpass (S21C) | Underpass | 380 | Walls | Off Street - Other | Structures | 5A | BB | 37555.65 | 0
Murrayfield Stadium Underpass (S21C) | Underpass | 390 | Roof | Off Street - Other | Structures | 5A | BB | 46944.5625 | 0
Murrayfield Stadium Underpass (S21C) | Underpass | 709 | Parapet Walls | Off Street - Other | Structures | 5A | BB | 18777.825 | 0
Murrayfield Stadium Underpass (S21C) | Underpass | 719 | Finishes | Off Street - Other | Structures | 5A | BB | 18777.825 | 0
Murrayfield Stadium Underpass (S21C) | Underpass | Snagging | Snagging | Off Street - Other | Structures | 5A | BB | 1896.75 | 0
Murrayfield Stadium Underpass (S21C) | Underpass | 3rd Party | Third Party Sign-off | Off Street - Other | Structures | 5A | BB | 25000 | 0
Murrayfield Stadium Underpass (S21C) | Underpass | Crit. Milestone | Completion of Murrayfield Stadium Underpass (S21C) (6) | Off Street - Other | Structures | 5A | BB | 0 | 0
Murrayfield Retaining Walls (S21D) | [8 empty] | 0
Murrayfield Retaining Walls (S21D) | Retaining Wall | [7 empty] | 0
Murrayfield Retaining Walls (S21D) | Retaining Wall | 10760 | Murrayfield Stadium Accomodation Works (dummy) | Off Street - Other | Structures | 5A | BB | 0 | 0
Murrayfield Retaining Walls (S21D) | Retaining Wall | 10760 | Completion of SRU Murrayfield Accommodation works | Off Street - Other | Structures | 5A | BB | 0 | 0
Murrayfield Retaining Walls (S21B) | Retaining Wall | Crit. Milestone | Completion of SRU Murrayfield Accommodation works (9) | Off Street - Other | Structures | 5A | BB | 0 | 0
Murrayfield Retaining Walls (S21D) | Retaining Wall | 111 | Site Clearance | Off Street - Other | Structures | 5A | BB | 35241.1785 | 15000
Murrayfield Retaining Walls (S21D) | Retaining Wall | 438 | Foundations | Off Street - Other | Structures | 5A | BB | 35241.1785 | 0
Murrayfield Retaining Walls (S21D) | Retaining Wall | 448 | Reinforced Earth Wall | Off Street - Other | Structures | 5A | BB | 140964.714 | 0
Murrayfield Retaining Walls (S21D) | Retaining Wall | 448 | Reinforced Earth Wall | Off Street - Other | Structures | 5A | BB | 140964.714 | 0
Murrayfield Retaining Walls (S21D) | Retaining Wall | 448 | Reinforced Earth Wall | Off Street - Other | Structures | 5A | BB | 140964.714 | 0
Murrayfield Retaining Walls (S21D) | Retaining Wall | 450 | Coping | Off Street - Other | Structures | 5A | BB | 0 | 0
Murrayfield Retaining Walls (S21D) | Retaining Wall | 460 | Handrail | Off Street - Other | Structures | 5A | BB | 211447.071 | 0
Murrayfield Retaining Walls (S21D) | Retaining Wall | Snagging | Snagging | Off Street - Other | Structures | 5A | BB | 7119.43 | 0
Murrayfield Retaining Walls (S21D) | Retaining Wall | 3rd Party | Third Party Sign-off | Off Street - Other | Structures | 5A | BB | 25000 | 0
Water of Leith Bridge (S21E) | [8 empty] | 0
Water of Leith Bridge (S21E) | Bridge | [7 empty] | 0
Water of Leith Bridge (S21E) | Bridge | 113 | Leaf Pier - Construct Cofferdam | Off Street - Other | Structures | 5A | BB | 59175.7155 | 0
Water of Leith Bridge (S21E) | Bridge | 113 | Leaf Pier - Install Piles/Excavation | Off Street - Other | Structures | 5A | BB | 236702.862 | 0
Water of Leith Bridge (S21E) | Bridge | 113 | Leaf Pier - Trim Piles | Off Street - Other | Structures | 5A | BB | 59175.7155 | 0
Water of Leith Bridge (S21E) | Bridge | 113 | Leaf Pier - Extract Cofferdam | Off Street - Other | Structures | 5A | BB | 59175.7155 | 0
Water of Leith Bridge (S21E) | Bridge | 639 | End Supports | Off Street - Other | Structures | 5A | BB | 118351.431 | 0
Water of Leith Bridge (S21E) | Bridge | 649 | Superstructure - Steel Beams | Off Street - Other | Structures | 5A | BB | 355054.293 | 0
Water of Leith Bridge (S21E) | Bridge | 649 | Superstructure - Concrete Deck | Off Street - Other | Structures | 5A | BB | 177527.1465 | 0
Water of Leith Bridge (S21E) | Bridge | 649 | Superstructure - Completion | Off Street - Other | Structures | 5A | BB | 118351.431 | 0
Water of Leith Bridge (S21E) | Bridge | Snagging | Snagging | Off Street - Other | Structures | 5A | BB | 11954.69 | 0
Water of Leith Bridge (S21E) | Bridge | 3rd Party | Third Party Sign-off | Off Street - Other | Structures | 5A | BB | 25000 | 0
Baird Drive Retaining Walls (W8) | [8 empty] | 0
Baird Drive Retaining Walls (W8) | Retaining Wall | [7 empty] | 0
Baird Drive Retaining Walls (W8) | Retaining Wall | 114 | Site Clearance | Off Street - Other | Structures | 5A | BB | 51318.8775 | 20000
Baird Drive Retaining Walls (W8) | Retaining Wall | 458 | Foundations | Off Street - Other | Structures | 5A | BB | 153956.6325 | 0
Baird Drive Retaining Walls (W8) | Retaining Wall | 468 | Reinforced Earth Wall - 1 Third | Off Street - Other | Structures | 5A | BB | 205275.51 | 0
Baird Drive Retaining Walls (W8) | Retaining Wall | 468 | Reinforced Earth Wall | Off Street - Other | Structures | 5A | BB | 513188.775 | 0
Baird Drive Retaining Walls (W8) | Retaining Wall | 470 | Coping | Off Street - Other | Structures | 5A | BB | 51318.8775 | 0
Baird Drive Retaining Walls (W8) | Retaining Wall | 480 | Handrail | Off Street - Other | Structures | 5A | BB | 51318.8775 | 0
Baird Drive Retaining Walls (W8) | Retaining Wall | Snagging | Snagging | Off Street - Other | Structures | 5A | BB | 10367.45 | 0
Baird Drive Retaining Walls (W8) | Retaining Wall | Crit. Milestone | Completion of Baird Drive Retained Embankment - (W8) (5) | Off Street - Other | Structures | 5A | BB | 0 | 0
Baird Drive Retaining Walls (W8) | Retaining Wall | 3rd Party | Third Party Sign-off | Off Street - Other | Structures | 5A | BB | 25000 | 0
Balgreen Road Bridge (S22) and Retaining Walls (W9) | [8 empty] | 0
Balgreen Road Bridge (S22) and Retaining Walls (W9) | Bridge & Retaining Wall | [7 empty] | 0
Balgreen Road Bridge (S22) and Retaining Walls (W9) | Bridge & Retaining Wall | 115 | Balgreen Road Bridge (S22) - Dummy Activity | Off Street - Other | Structures | 5A | BB | 420038.19 | 8400.7638
Balgreen Road Bridge (S22) and Retaining Walls (W9) | Bridge & Retaining Wall | 115 | Balgreen Road Bridge (S22) - Dummy Activity | Off Street - Other | Structures | 5A | BB | 420038.19 | 8400.7638
Balgreen Road Bridge (S22) and Retaining Walls (W9) | Bridge & Retaining Wall | 115 | Balgreen Road Bridge (S22) - Dummy Activity | Off Street - Other | Structures | 5A | BB | 420038.19 | 8400.7638
Balgreen Road Bridge (S22) and Retaining Walls (W9) | Bridge & Retaining Wall | 115 | Balgreen Road Bridge (S22) - Dummy Activity | Off Street - Other | Structures | 5A | BB | 420038.19 | 8400.7638
Balgreen Road Bridge (S22) and Retaining Walls (W9) | Bridge & Retaining Wall | 115 | Balgreen Road Reatining Wall (S22) - Dummy Activity | Off Street - Other | Structures | 5A | BB | 245400.21 | 4908.0042
Balgreen Road Bridge (S22) and Retaining Walls (W9) | Bridge & Retaining Wall | Snagging | Snagging | Off Street - Other | Structures | 5A | BB | 19450.03 | 0
Balgreen Road Bridge (S22) and Retaining Walls (W9) | Bridge & Retaining Wall | 3rd Party | Third Party Sign-off | Off Street - Other | Structures | 5A | BB | 25000 | 0
Balgreen Road Bridge (S22) and Retaining Walls (W9) | Bridge & Retaining Wall | 3rd Party | Third Party Sign-off | Off Street - Other | Structures | 5A | BB | 25000 | 0
Balgreen Road Bridge (S22) and Retaining Walls (W9) | Bridge & Retaining Wall | Crit. Milestone | Completion of Balgreen Rd Retaining wall (W9) (7) | Off Street - Other | Structures | 5A | BB | 0 | 0
Balgreen Road Bridge (S22) and Retaining Walls (W9) | Bridge & Retaining Wall | Crit. Milestone | Completion of Balgreen Road Bridge (S22) (8) | Off Street - Other | Structures | 5A | BB | 0 | 0
Balgreen Road Tram Stop | [8 empty] | 0
Balgreen Road Tram Stop | Tramstop | [7 empty] | 0
Balgreen Road Tram Stop | Tramstop | 117 | Civil Engineering and Builders Work | Off Street - Other | Structures | 5A | BB | 102719.43 | 0
Balgreen Road Tram Stop | Tramstop | 117 | Civil Engineering and Builders Work | Off Street - Other | Structures | 5A | BB | 102719.43 | 0
Balgreen Road Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | Structures | 5A | BB | 2075.14 | 0
Balgreen Road Tram Stop | Tramstop | A2300 | Deliver and Install Shelter | Off Street - Other | Structures | 5A | S | 34772.76 | 0
Balgreen Road Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | Structures | 5A | S | 351.24 | 0
Jenners Depository Substation | [8 empty] | 0
Jenners Depository Substation | Substation | [7 empty] | 0
Jenners Depository Substation | Substation | 296 | Completion of envelope | Off Street - Other | Structures | 5A | BB | 80965.665 | 0
Jenners Depository Substation | Substation | 296 | Civil Engineering and Building Works | Off Street - Other | Structures | 5A | BB | 80965.665 | 0
Jenners Depository Substation | Substation | Snagging | Snagging | Off Street - Other | Structures | 5A | BB | 1635.67 | 0
0
0
Carrick Knowe Bridge (S23) | [8 empty] | 0
Carrick Knowe Bridge (S23) | Bridge | [7 empty] | 0
Carrick Knowe Bridge (S23) | Bridge | Possessions | [6 empty] | 0
Carrick Knowe Bridge (S23) | Bridge | 11 | Establishment | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | 12 | Temporary Fencing | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | 13 | Haul Roads | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | 24 | Possessions 1 (12hrs) | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | C14 | Remove Crash Deck and Barriers | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | B14 | Erect Network Rail Safety Barrier | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | A15 | Possessions 2 (12hrs) | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | C13 | Possessions 4 (12hrs) | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | North Abutment - Excavate and Blind | [6 empty] | 0
Carrick Knowe Bridge (S23) | Bridge | 35 | North Abutment | Off Street - Other | Structures | 5B | BB | 32259.3386 | -2.9104e-11
Carrick Knowe Bridge (S23) | Bridge | 16 | Blinding | Off Street - Other | Structures | 5B | BB | 32259.3386 | 32259.3386
Carrick Knowe Bridge (S23) | Bridge | 96 | Temporary Support to Railway Lines | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | 106 | Excavate | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | North Abutment - Base Construction | [6 empty] | 0
Carrick Knowe Bridge (S23) | Bridge | 7 | Concrete | Off Street - Other | Structures | 5B | BB | 32259.3386 | 32259.3386
Carrick Knowe Bridge (S23) | Bridge | 37 | Steel fixing | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | 87 | Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | North Abutment - Abutment Wall | [6 empty] | 0
Carrick Knowe Bridge (S23) | Bridge | 28 | Concrete | Off Street - Other | Structures | 5B | BB | 32259.3386 | 32259.3386
Carrick Knowe Bridge (S23) | Bridge | 38 | Shutter rear face | Off Street - Other | Structures | 5B | BB |  | 0
Carrick Knowe Bridge (S23) | Bridge | 58 | Steelfixing | Off Street - Other | Structures | 5B | BB |  | 0
Carrick Knowe Bridge (S23) | Bridge | 128 | Shutter front face | Off Street - Other | Structures | 5B | BB |  | 0
Carrick Knowe Bridge (S23) | Bridge | North Abutment - Ballast Wall | [6 empty] | 0
Carrick Knowe Bridge (S23) | Bridge | A10 | Ballast Wall | Off Street - Other | Structures | 5B | BB | 32259.3386 | 0
Carrick Knowe Bridge (S23) | Bridge | North Abutment - Wing Walls | [6 empty] | 0
Carrick Knowe Bridge (S23) | Bridge | 69 | S23 Carricknowe bridge Backfill | Off Street - Other | Structures | 5B | BB | 32259.3386 | 0
Carrick Knowe Bridge (S23) | Bridge | A14060 | S23 Carricknowe bridge Wing Walls | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | A14070 | S23 Carricknowe bridge Parapet Beams | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | A14080 | S23 Carricknowe bridge Backfill | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | A14090 | S23 Carricknowe bridge Wing Walls | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | South Abutment - Excavate and Blind | [6 empty] | 0
Carrick Knowe Bridge (S23) | Bridge | 23 | South Abutment | Off Street - Other | Structures | 5B | BB | 32259.3386 | 0
Carrick Knowe Bridge (S23) | Bridge | 116 | Blinding | Off Street - Other | Structures | 5B | BB | 32259.3386 | 32259.3386
Carrick Knowe Bridge (S23) | Bridge | 206 | Temporary Support to Railway Lines | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | 236 | Excavate | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | South Abutment - Base Construction | [6 empty] | 0
Carrick Knowe Bridge (S23) | Bridge | 97 | Concrete | Off Street - Other | Structures | 5B | BB | 32259.3386 | 32259.3386
Carrick Knowe Bridge (S23) | Bridge | 177 | Steel fixing | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | 237 | Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | South Abutment - Abutment Wall | [6 empty] | 0
Carrick Knowe Bridge (S23) | Bridge | 688 | Concrete | Off Street - Other | Structures | 5B | BB | 32259.3386 | 32259.3386
Carrick Knowe Bridge (S23) | Bridge | 698 | Shutter rear face | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | 708 | Steelfixing | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | 718 | Shutter front face | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | A14040 | Strike Shutters and Cure | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | South Abutment - Ballast Wall | [6 empty] | 0
Carrick Knowe Bridge (S23) | Bridge | A14050 | Ballast Wall | Off Street - Other | Structures | 5B | BB | 32259.3386 | 0
Carrick Knowe Bridge (S23) | Bridge | South Abutment - Wing Walls | [6 empty] | 0
Carrick Knowe Bridge (S23) | Bridge | 89 | S23 Carricknowe bridge Backfill | Off Street - Other | Structures | 5B | BB | 32259.3386 | 0
Carrick Knowe Bridge (S23) | Bridge | A14100 | S23 Carricknowe bridge Wing Walls | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | A14110 | S23 Carricknowe bridge Parapet Beams | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | A1012 | S23 Carricknowe bridge Backfill | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | A1015 | S23 Carricknowe bridge Wing Walls | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | Superstructure - Reinforced Concrete Deck | [6 empty] | 0
Carrick Knowe Bridge (S23) | Bridge | 31 | Superstructure | Off Street - Other | Structures | 5B | BB | 32259.3386 | 0
Carrick Knowe Bridge (S23) | Bridge | 104 | Permanent Formwork | Off Street - Other | Structures | 5B | BB | 32259.3386 | 0
Carrick Knowe Bridge (S23) | Bridge | 285 | Deck Reinforcement | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | 246 | Deck Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | 27 | Concrete Diaphragms | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | 247 | Concrete Deck | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | 257 | Concrete Parapet Beam | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | Superstructure - Deck Finishes | [6 empty] | 0
Carrick Knowe Bridge (S23) | Bridge | 728 | S23 Carricknowe Bridge Waterproofing (inc. deck curing) | Off Street - Other | Structures | 5B | BB | 32259.3386 | 0
Carrick Knowe Bridge (S23) | Bridge | 59 | S23 Carricknowe Bridge Expansion Joints | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | 70 | S23 Carricknowe Bridge Parapet Rails | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | 80 | S23 Carricknowe Bridge Walkway Constructon | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | Superstructure - Pre cast Concrete Beams | [6 empty] | 0
Carrick Knowe Bridge (S23) | Bridge | 32 | Bearings | Off Street - Other | Structures | 5B | BB | 32259.3386 | 0
Carrick Knowe Bridge (S23) | Bridge | 63 | Possession 3 (16hrs) | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | 93 | Place Beams | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | 193 | Erect Crash Deck | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Bridge | Superstructure - Run On Run Off Slabs | [6 empty] | 0
Carrick Knowe Bridge (S23) | Bridge | 34 | Backfill and cast slab south | Off Street - Other | Structures | 5B | BB | 32259.3386 | 0
Carrick Knowe Bridge (S23) | Bridge | 275 | Backfill and cast slab north | Off Street - Other | Structures | 5B | BB | 0 | 0
Bridges | Trackwork | [7 empty] | 0
Carrick Knowe Bridge (S23) | Carrick Knowe Disruptive Possessions | 44 | Containment Slabs | Off Street - Other | Structures | 5B | BB | 0 | 0
Carrick Knowe Bridge (S23) | Carrick Knowe Disruptive Possessions | 45 | Fix Rails | Off Street - Other | Structures | 5B | S | 32259.3386 | 0
Saughton Road Bridge (S24) | [8 empty] | 0
Saughton Road Bridge (S24) | Bridge | [7 empty] | 0
Saughton Road Bridge (S24) | Bridge | 121 | Existing Structure | Off Street - Other | Structures | 5B | BB | 0 | 0
Saughton Road North Tram Stop | [8 empty] | 0
Saughton Road North Tram Stop | Tramstop | [7 empty] | 0
Saughton Road North Tram Stop | Tramstop | 123 | Civil Engineering and Building Works | Off Street - Other | Structures | 5B | BB | 102719.43 | 0
Saughton Road North Tram Stop | Tramstop | 123 | Civil Engineering and Building Works | Off Street - Other | Structures | 5B | BB | 102719.43 | 0
Saughton Road North Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | Structures | 5B | BB | 2075.14 | 0
Saughton Road North Tram Stop | Tramstop | A2080 | Deliver and Install Shelter | Off Street - Other | Structures | 5B | S | 34772.76 | 0
Saughton Road North Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | Structures | 5B | S | 351.24 | 0
0
Bankhead Drive Substation | [8 empty] | 0
Bankhead Drive Substation | Substation | [7 empty] | 0
Bankhead Drive Substation | Substation | 266 | Completion of envelope | Off Street - Other | Structures | 5B | BB | 80965.665 | 0
Bankhead Drive Substation | Substation | 266 | Civil Engineering and Building Works | Off Street - Other | Structures | 5B | BB | 80965.665 | 0
Bankhead Drive Substation | Substation | Snagging | Snagging | Off Street - Other | Structures | 5B | BB | 817.835 | 0
Bankhead Retaining Wall (W11) | [8 empty] | 0
Bankhead Retaining Wall (W11) | Retaining Wall | [7 empty] | 0
Bankhead Retaining Wall (W11) | Retaining Wall | 127 | Retaining Wall Construction | Off Street - Other | Structures | 5B | BB | 57694.23 | 0
Bankhead Retaining Wall (W11) | Retaining Wall | Snagging | Snagging | Off Street - Other | Structures | 5B | BB | 576.9423 | 0
Bankhead Retaining Wall (W11) | Retaining Wall | 3rd Party | Third Party Sign-off | Off Street - Other | Structures | 5B | BB | 25000 | 0
Broomhouse Road Bridge (S25) | [8 empty] | 0
Broomhouse Road Bridge (S25) | Bridge | [7 empty] | 0
Broomhouse Road Bridge (S25) | Bridge | 125 | Existing Structure | Off Street - Other | Structures | 5B | BB | 0 | 0
South Gyle Access Tram Stop | [8 empty] | 0
South Gyle Access Tram Stop | Tramstop | [7 empty] | 0
South Gyle Access Tram Stop | Tramstop | 129 | Civil Engineering and Building Works | Off Street - Other | Structures | 5B | BB | 102719.43 | 0
South Gyle Access Tram Stop | Tramstop | 129 | Civil Engineering and Building Works | Off Street - Other | Structures | 5B | BB | 102719.43 | 0
South Gyle Access Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | Structures | 5B | BB | 2075.14 | 0
South Gyle Access Tram Stop | Tramstop | A2230 | Deliver and Install Shelter | Off Street - Other | Structures | 5B | S | 34772.76 | 0
South Gyle Access Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | Structures | 5B | S | 351.24 | 0
South Gyle Access Bridge (S26) | [8 empty] | 0
South Gyle Access Bridge (S26) | Bridge | [7 empty] | 0
South Gyle Access Bridge (S26) | Bridge | 156 | Substructure - Extend Piles | Off Street - Other | Structures | 5B | BB | 149817.096 | 0
South Gyle Access Bridge (S26) | Bridge | 156 | Substructure - Construct Pile Cap | Off Street - Other | Structures | 5B | BB | 149817.096 | 0
South Gyle Access Bridge (S26) | Bridge | 276 | Superstructure - Concrete Deck | Off Street - Other | Structures | 5B | BB | 224725.644 | 0
South Gyle Access Bridge (S26) | Bridge | 276 | Superstructure - Run On Slabs | Off Street - Other | Structures | 5B | BB | 224725.644 | 0
South Gyle Access Bridge (S26) | Bridge | Snagging | Snagging | Off Street - Other | Structures | 5B | BB | 5296.564 | 0
South Gyle Access Bridge (S26) | Bridge | 3rd Party | Third Party Sign-off | Off Street - Other | Structures | 5B | BB | 25000 | 0
0
Edinburgh Park Station Tram Stop | [8 empty] | 0
Edinburgh Park Station Tram Stop | Tramstop | [7 empty] | 0
Edinburgh Park Station Tram Stop | Tramstop | 132 | Civil Engineering and Builderworks | Off Street - Other | Structures | 5B | BB | 102719.43 | 0
Edinburgh Park Station Tram Stop | Tramstop | 132 | Civil Engineering and Builderworks | Off Street - Other | Structures | 5B | BB | 102719.43 | 0
Edinburgh Park Station Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | Structures | 5B | BB | 2075.14 | 0
Edinburgh Park Station Tram Stop | Tramstop | A2140 | Deliver and Install Shelter | Off Street - Other | Structures | 5B | S | 34772.76 | 0
Edinburgh Park Station Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | Structures | 5B | S | 351.24 | 0
0
Edinburgh Park Tram Stop | [8 empty] | 0
Edinburgh Park Tram Stop | Tramstop | [7 empty] | 0
Edinburgh Park Tram Stop | Tramstop | 166 | Civil Engineering and Building Works | Off Street - Other | Structures | 5B | BB | 102719.43 | 0
Edinburgh Park Tram Stop | Tramstop | 166 | Civil Engineering and Building Works | Off Street - Other | Structures | 5B | BB | 102719.43 | 0
Edinburgh Park Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | Structures | 5B | BB | 2075.14 | 0
Edinburgh Park Tram Stop | Tramstop | A2110 | Deliver and Install Shelter | Off Street - Other | Structures | 5B | S | 34772.76 | 0
Edinburgh Park Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | Structures | 5B | S | 351.24 | 0
Edinburgh Park Station Bridge (S27) | [8 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | [7 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | Establishment | [6 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | 41 | Establishment | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 42 | Temporary Fencing | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 363 | Haul Roads | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 184 | Possession 1 (12hrs) | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | A14 | Remove Protection Barrier and Crash deck | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | A14120 | Possession 2 (12hrs) | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | A14130 | Network Rail Protection Barrier | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | A12 | Possession 5 (12hrs) | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | North Approach Ramp - Base Construction | [6 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | 758 | Steelfixing | Off Street - Other | Structures | 5B | BB | 119485.7628 | 119485.7628
Edinburgh Park Station Bridge (S27) | Bridge | 479 | Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 1101 | Concrete | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | North Approach Ramp - Wall Construction | [6 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | 768 | Steelfixing | Off Street - Other | Structures | 5B | BB | 133272.58 | 93290.806
Edinburgh Park Station Bridge (S27) | Bridge | 579 | Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 1111 | Concrete | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 292 | Ballast Wall | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 513 | Cladding | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | North Approach Ramp - Excavation | [6 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | 426 | Excavation | Off Street - Other | Structures | 5B | BB | 119485.7628 | 119485.7628
Edinburgh Park Station Bridge (S27) | Bridge | 267 | Blinding | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | North Approach Ramp - Reinforced Earth Wall | [6 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | 748 | Mass Concrete Footing | Off Street - Other | Structures | 5B | BB | 133272.58 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 469 | Place Fill | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 101 | Build Wall units | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 212 | Place Coping Units | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | South Approach Ramp - Reinforced Earth Wall | [6 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | 122 | South Abutment | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 738 | Mass Concrete Footing | Off Street - Other | Structures | 5B | BB | 133272.58 | 6663.629
Edinburgh Park Station Bridge (S27) | Bridge | 459 | Place Fill | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | A14160 | Build Wall units | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | A102 | Place Coping Units | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Abutment - Excavation | [6 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | 436 | Excavation | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 277 | Blinding | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Abutment - Base Construction | [6 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | 778 | Steelfixing | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 589 | Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | A111 | Concrete | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Abutment - Wall Construction | [6 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | 788 | Steelfixing | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 599 | Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 1121 | Concrete | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 322 | Ballast Wall | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 523 | Cladding | Off Street - Other | Structures | 5B | BB | 133272.58 | 93290.806
Edinburgh Park Station Bridge (S27) | Bridge | Pier 1 | [6 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | 19 | Pier 1 | Off Street - Other | Structures | 5B | BB | 229780.34 | 229780.34
Edinburgh Park Station Bridge (S27) | Bridge | Base Construction |  | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 81 | Concrete | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 191 | Steel fixing | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 201 | Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Columns |  | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 202 | Steel fixing | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 383 | Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 393 | Concrete | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Excavation and Blinding |  | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 360 | Excavation | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 800 | Blinding | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Pier 2 | [6 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | 194 | Pier 2 | Off Street - Other | Structures | 5B | BB | 119485.7628 | 119485.7628
Edinburgh Park Station Bridge (S27) | Bridge | Excavation and Blinding |  | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 120 | Excavation | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 290 | Blinding | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Base Construction |  | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 241 | Concrete | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 251 | Steel fixing | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 261 | Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Columns |  | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 232 | Steel fixing | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 403 | Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 413 | Concrete | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Pier 3 | [6 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | 359 | Pier 3 | Off Street - Other | Structures | 5B | BB | 119485.7628 | 119485.7628
Edinburgh Park Station Bridge (S27) | Bridge | Excavation and Blinding |  | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 810 | Blinding | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 820 | Excavation | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Base Construction |  | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 211 | Concrete | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 221 | Steel fixing | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 231 | Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Columns |  | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 222 | Steel fixing | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | A103 | Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | A113 | Concrete | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Pier 4 | [6 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | 174 | Pier 4 | Off Street - Other | Structures | 5B | BB | 119485.7628 | 119485.7628
Edinburgh Park Station Bridge (S27) | Bridge | Excavation and Blinding |  | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 850 | Excavation | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 860 | Blinding | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Base Construction |  | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 331 | Concrete | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 341 | Steel fixing | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 351 | Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Columns |  | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 242 | Steel fixing | Off Street - Other | Structures | 5B | BB |  | 0
Edinburgh Park Station Bridge (S27) | Bridge | A123 | Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | A133 | Concrete | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Pier 5 | [6 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | 349 | Pier 5 | Off Street - Other | Structures | 5B | BB | 119485.7628 | 119485.7628
Edinburgh Park Station Bridge (S27) | Bridge | Excavation and Blinding |  | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 830 | Excavation | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 840 | Blinding | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Base Construction |  | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 271 | Concrete | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 291 | Steel fixing | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 321 | Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Columns |  | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 262 | Steel fixing | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 443 | Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 453 | Concrete | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Pier 6 | [6 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | Pier 6 | Pier 6 | Off Street - Other | Structures | 5B | BB | 119485.7628 | 119485.7628
Edinburgh Park Station Bridge (S27) | Bridge | Excavation and Blinding |  | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 890 | Excavation | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 900 | Blinding | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Base Construction |  | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 361 | Concrete | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 371 | Steel fixing | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 381 | Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Columns |  | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 252 | Steel fixing | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 423 | Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 433 | Concrete | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Pier 7 | [6 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | Pier 7 | Pier 7 | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Excavation and Blinding |  | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 870 | Excavation | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 880 | Blinding | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Base Construction |  | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 391 | Concrete | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 401 | Steel fixing | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 591 | Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Columns |  | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 272 | Steel fixing | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 463 | Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 473 | Concrete | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Superstructure - Span South Ramp to Pier 1 | [6 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | 601 | Fix Bearings | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 611 | Temporary Beam Supports | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 621 | Place Beams | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 631 | Deck Reinforcement | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 641 | Permanent Formwork | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 651 | Deck Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 661 | Cast Diaphragm | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 671 | Cast Deck | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 681 | Cast Parapet Beams | Off Street - Other | Structures | 5B | BB | 133272.58 | 133272.58
Edinburgh Park Station Bridge (S27) | Bridge | Superstructure - Span Pier 1 to Pier 2 | [6 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | 431 | Fix Bearings | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 411 | Temporary Beam Supports | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 421 | Place Beams | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 461 | Deck Reinforcement | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 441 | Permanent Formwork | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 451 | Deck Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 471 | Cast Diaphragm | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 481 | Cast Deck | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 491 | Cast Parapet Beams | Off Street - Other | Structures | 5B | BB | 133272.58 | 133272.58
Edinburgh Park Station Bridge (S27) | Bridge | Superstructure - Span Pier 2 to Pier 3 | [6 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | 521 | Fix Bearings | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 501 | Temporary Beam Supports | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 511 | Place Beams | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 551 | Deck Reinforcement | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 531 | Permanent Formwork | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 541 | Deck Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 561 | Cast Diaphragm | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 571 | Cast Deck | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 581 | Cast Parapet Beams | Off Street - Other | Structures | 5B | BB | 133272.58 | 133272.58
Edinburgh Park Station Bridge (S27) | Bridge | Superstructure - Span Pier 3 to Pier 4 | [6 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | 691 | Fix Bearings | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 701 | Temporary Beam Supports | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 711 | Place Beams | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 721 | Deck Reinforcement | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 731 | Permanent Formwork | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 741 | Deck Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 751 | Cast Diaphragm | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 761 | Cast Deck | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 771 | Cast Parapet Beams | Off Street - Other | Structures | 5B | BB | 133272.58 | 133272.58
Edinburgh Park Station Bridge (S27) | Bridge | 592 | Possession 4 (16hrs) | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 910 | Possession 3 (16hrs) | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Superstructure - Span Pier 6 to Pier 7 | [6 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | 881 | Fix Bearings | Off Street - Other | Structures | 5B | BB |  | 0
Edinburgh Park Station Bridge (S27) | Bridge | 861 | Temporary Beam Supports | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 871 | Place Beams | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 911 | Deck Reinforcement | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 891 | Permanent Formwork | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 901 | Deck Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 921 | Cast Diaphragm | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 931 | Cast Deck | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 941 | Cast Parapet Beams | Off Street - Other | Structures | 5B | BB | 133272.58 | 133272.58
Edinburgh Park Station Bridge (S27) | Bridge | Structure - Span Pier 7 to North Ramp | [6 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | 971 | Fix Bearings | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 9'51 | Temporary Beam Supports | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 9'61 | Place Beams | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | A1001 | Deck Reinforcement | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 981 | Permanent Formwork | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 991 | Deck Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | A1011 | Cast Diaphragm | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | A1021 | Cast Deck | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | A1031 | Cast Parapet Beams | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | Superstructure - Span Pier 4 to Pier 5 | [6 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | 1011 | Fix Bearings | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 1021 | Temporary Beam Supports | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 1031 | Place Beams | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 1041 | Deck Reinforcement | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 1051 | Permanent Formwork | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 1061 | Deck Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 1071 | Cast Diaphragm | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 1081 | Cast Deck | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 1091 | Cast Parapet Beams | Off Street - Other | Structures | 5B | BB | 133272.58 | 133272.58
Edinburgh Park Station Bridge (S27) | Bridge | Superstructure - Span Pier 5 to Pier 6 | [6 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | 791 | Fix Bearings | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 781 | Temporary Beam Supports | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 801 | Place Beams | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 821 | Deck Reinforcement | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 811 | Permanent Formwork | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 831 | Deck Shuttering | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 841 | Cast Diaphragm | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 851 | Cast Deck | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 1001 | Cast Parapet Beams | Off Street - Other | Structures | 5B | BB | 133272.58 | 133272.58
Edinburgh Park Station Bridge (S27) | Bridge | Superstructure - Deck Finishes | [6 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | 282 | Waterproofing | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 483 | Expansion Joints | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 493 | Parapet Rails | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 503 | Walkway Construction | Off Street - Other | Structures | 5B | BB | 133272.58 | 0
Edinburgh Park Station Bridge (S27) | Trackwork | [7 empty] | 0
Edinburgh Park Station Bridge (S27) | Bridge | 258 | Trackwork | Off Street - Other | Structures | 5B | BB | 0 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 339 | Containment Slabs | Off Street - Other | Structures | 5B | BB | 133272.58 | 0
Edinburgh Park Station Bridge (S27) | Bridge | 90 | S27 Edinburgh Park Station bridge - Fix Rails | Off Street - Other | Structures | 5B | S | 133272.58 | 0
Edinburgh Park Station Bridge (S27) | E & M Installations | [7 empty] | 0
Edinburgh Park Station Bridge (S27) | E & M Installations | 3rd Party | Third Party Sign-off | Off Street - Other | Structures | 5B | BB | 25000 | 0
|  | Crit. Milestone | Completion of Edinburgh Park Station Bridge (2) |  |  |  |  | 0 | 0
0
0
Gyle Tram Stop | [8 empty] | 0
Tramstop | Tramstop | [7 empty] | 0
Gyle Tram Stop | Tramstop | 141 | Civil Engineering and Building Works | Off Street - Other | Structures | 5C | BB | 112438.755 | 0
Gyle Tram Stop | Tramstop | 141 | Civil Engineering and Building Works | Off Street - Other | Structures | 5C | BB | 112438.755 | 0
Gyle Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | Structures | 5C | BB | 2271.49 | 0
Gyle Tram Stop | Tramstop | A2170 | Deliver and Install Shelter | Off Street - Other | Structures | 5C | S | 34772.76 | 0
Gyle Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | Structures | 5C | S | 351.24 | 0
Gyle Tram Stop Retaining Wall (W16) | [8 empty] | 0
Gyle Tram Stop Retaining Wall (W16) | Retaining Wall | [7 empty] | 0
Gyle Tram Stop Retaining Wall (W16) | Retaining Wall | 139 | Wall Construction | Off Street - Other | Structures | 5C | BB | 172232.28 | 0
Gyle Tram Stop Retaining Wall (W16) | Retaining Wall | Snagging | Snagging | Off Street - Other | Structures | 5C | BB | 1722.3228 | 0
0
A8 Underpass (W28) | [8 empty] | 0
A8 Underpass (W28) | Underpass | [7 empty] | 0
A8 Underpass (W28) | Underpass | 143 | Phase 1 - Break Down Piles | Off Street - Other | Structures | 5C | BB | 242165.781 | 36324.8671
A8 Underpass (W28) | Underpass | 143 | Phase 1 | Off Street - Other | Structures | 5C | BB | 242165.781 | 36324.8671
A8 Underpass (W28) | Underpass | 519 | Phase 2 - Break Down Piles | Off Street - Other | Structures | 5C | BB | 242165.781 | 0
A8 Underpass (W28) | Underpass | 519 | Phase 2 | Off Street - Other | Structures | 5C | BB | 242165.781 | 0
A8 Underpass (W28) | Underpass | 529 | Phase 3 - Break Down Piles | Off Street - Other | Structures | 5C | BB | 242165.781 | 0
A8 Underpass (W28) | Underpass | 529 | Phase 3 | Off Street - Other | Structures | 5C | BB | 242165.781 | 0
A8 Underpass (W28) | Underpass | 539 | Phase 4 - Break Down Piles | Off Street - Other | Structures | 5C | BB | 242165.781 | 0
A8 Underpass (W28) | Underpass | 539 | Phase 4 | Off Street - Other | Structures | 5C | BB | 242165.781 | 0
A8 Underpass (W28) | Underpass | 549 | Subway Construction - Excavate | Off Street - Other | Structures | 5C | BB | 242165.781 | 0
A8 Underpass (W28) | Underpass | 549 | Subway Construction | Off Street - Other | Structures | 5C | BB | 242165.781 | 0
A8 Underpass (W28) | Underpass | Snagging | Snagging | Off Street - Other | Structures | 5C | BB | 24461.19 | 0
|  | Crit. Milestone | Completion of A8 Gogar Underpass (W28) (1) |  |  |  |  | 0 | 0
Depot Access Bridge (S32) | [8 empty] | 0
Depot Access Bridge (S32) | Bridge | [7 empty] | 0
Depot Access Bridge (S32) | Bridge | 144 | Dummy Activity | Off Street - Other | Structures | 5C | BB | 268611.255 | 0
Depot Access Bridge (S32) | Bridge | 144 | Dummy Activity | Off Street - Other | Structures | 5C | BB | 268611.255 | 0
Depot Access Bridge (S32) | Bridge | 144 | Dummy Activity | Off Street - Other | Structures | 5C | BB | 268611.255 | 0
Depot Access Bridge (S32) | Bridge | 144 | Dummy Activity | Off Street - Other | Structures | 5C | BB | 268611.255 | 0
Depot Access Bridge (S32) | Bridge | 144 | Dummy Activity | Off Street - Other | Structures | 5C | BB | 402916.8825 | 0
Depot Access Bridge (S32) | Bridge | 144 | Dummy Activity | Off Street - Other | Structures | 5C | BB | 134305.6275 | 0
Depot Access Bridge (S32) | Bridge | Snagging | Snagging | Off Street - Other | Structures | 5C | BB | 14651.523 | 0
A8 Retaining Walls (W16) | [8 empty] | 0
A8 Retaining Walls (W16) | Retaining Wall | [7 empty] | 0
A8 Retaining Walls (W16) | Retaining Wall | 145 | Soil Nailing | Off Street - Other | Structures | 5C | BB | 0 | 0
A8 Retaining Walls (W16) | Retaining Wall | Snagging | Snagging | Off Street - Other | Structures | 5C | BB | 0 | 0
0
Gogarburn Tram Stop | [8 empty] | 0
Gogarburn Tram Stop | Tramstop | [7 empty] | 0
Gogarburn Tram Stop | Tramstop | 149 | Civil Engineering and Building Works | Off Street - Other | Structures | 5C | BB | 112438.755 | 0
Gogarburn Tram Stop | Tramstop | 149 | Civil Engineering and Building Works | Off Street - Other | Structures | 5C | BB | 112438.755 | 0
Gogarburn Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | Structures | 5C | BB | 2271.49 | 0
Gogarburn Tram Stop | Tramstop | A2200 | Deliver and Install Shelter | Off Street - Other | Structures | 5C | S | 34772.76 | 0
Gogarburn Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | Structures | 5C | S | 351.24 | 0
0
0
0
Depot | [8 empty] | 0
Depot | Procurement | [7 empty] | 0
Depot Structure | Procurement | 1159 | Steel Work Fabrication | Off Street Depot | Structures | 6A | BB | 185376.3276 | 185376.3276
Depot Substation | Substation | [7 empty] | 0
Depot Substation | Substation | 316 | Civil Engineering and Building Works - Weathertight | Off Street Depot | Structures | 6A | BB | 147960.648 | 0
Depot Substation | Substation | 316 | Civil Engineering and Building Works - Plant & equipment | Off Street Depot | Structures | 6A | BB | 73980.324 | 0
Depot Substation | Substation | 316 | Civil Engineering and Building Works - Service Connections | Off Street Depot | Structures | 6A | BB | 24660.108 | 0
Depot Substation | Substation | Snagging | Snagging | Off Street Depot | Structures | 6A | BB | 2490.92 | 0
0
0
0
Gogarburn Underbridge (S29) | [8 empty] | 0
Gogarburn Underbridge (S29) | Bridge | [7 empty] | 0
Gogarburn Underbridge (S29) | Bridge | 159 | Temporary Access Roads-Bulk Excavation-Piling Platform | Off Street - Other | Structures | 7A | BB | 42871.95 | 42871.95
Gogarburn Underbridge (S29) | Bridge | 179 | East Abutment-Piles and Columns | Off Street - Other | Structures | 7A | BB | 128615.85 | 128615.85
Gogarburn Underbridge (S29) | Bridge | 189 | East Abutment-Reinforced Earth | Off Street - Other | Structures | 7A | BB | 85743.9 | 85743.9
Gogarburn Underbridge (S29) | Bridge | 199 | East Abutment-Parapets and Run on Slabs | Off Street - Other | Structures | 7A | BB | 85743.9 | 0
Gogarburn Underbridge (S29) | Bridge | 209 | West Abutment-Piles and Columns | Off Street - Other | Structures | 7A | BB | 128615.85 | 128615.85
Gogarburn Underbridge (S29) | Bridge | 219 | West Abutment-Reinforced Earth | Off Street - Other | Structures | 7A | BB | 85743.9 | 85743.9
Gogarburn Underbridge (S29) | Bridge | 229 | West Abutment-Parapets and Run on Slabs | Off Street - Other | Structures | 7A | BB | 85743.9 | 0
Gogarburn Underbridge (S29) | Bridge | 239 | Bridge Deck | Off Street - Other | Structures | 7A | BB | 171487.8 | 0
Gogarburn Underbridge (S29) | Bridge | 13041 | Treat area of contaminated land (Dummy duration) | Off Street - Other | Structures | 7A | BB | 42871.95 | 0
Gogarburn Underbridge (S29) | Bridge | Snagging | Snagging | Off Street - Other | Structures | 7A | BB | 8661 | 0
Gogarburn Culvert No1 (S30) | [8 empty] | 0
Gogarburn Culvert No1 (S30) | Culvert | [7 empty] | 0
Gogarburn Culvert No1 (S30) | Culvert | 160 | Temporary Access Roads-Divert Flows-Bulk Excavation | Off Street - Other | Structures | 7A | BB | 0 | 0
Gogarburn Culvert No1 (S30) | Culvert | 249 | Precast Culvert Units | Off Street - Other | Structures | 7A | BB | 0 | 0
Gogarburn Culvert No1 (S30) | Culvert | 259 | Reinforced Concrete Apron and Wingwalls | Off Street - Other | Structures | 7A | BB | 0 | 0
Gogarburn Culvert No1 (S30) | Culvert | 269 | Backfill and Finishes | Off Street - Other | Structures | 7A | BB | 37566.54 | 37566.54
Gogarburn Culvert No1 (S30) | Culvert | Snagging | Snagging | Off Street - Other | Structures | 7A | BB | 375.6654 | 0
Inglishton Park and Ride Tram Stop | [8 empty] | 0
Inglishton Park and Ride Tram Stop | Tramstop | [7 empty] | 0
Inglishton Park and Ride Tram Stop | Tramstop | 163 | Civil Engineering and Building Works | Off Street - Other | Structures | 7A | BB | 104885.055 | 0
Inglishton Park and Ride Tram Stop | Tramstop | 163 | Civil Engineering and Building Works | Off Street - Other | Structures | 7A | BB | 104885.055 | 0
Inglishton Park and Ride Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | Structures | 7A | BB | 2118.89 | 0
Inglishton Park and Ride Tram Stop | Tramstop | A1940 | Deliver and Install Shelter | Off Street - Other | Structures | 7A | S | 34772.76 | 0
Inglishton Park and Ride Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | Structures | 7A | S | 351.24 | 0
Ingliston Park and Ride Substation | [8 empty] | 0
Ingliston Park and Ride Substation | Substation | [7 empty] | 0
Ingliston Park and Ride Substation | Substation | 226 | Completion of envelope | Off Street - Other | Structures | 7A | BB | 82803.105 | 0
Ingliston Park and Ride Substation | Substation | 226 | Civil Engineering and Building Works | Off Street - Other | Structures | 7A | BB | 82803.105 | 0
Ingliston Park and Ride Substation | Substation | Snagging | Snagging | Off Street - Other | Structures | 7A | BB | 1672.79 | 0
Gogarburn Retaining Wall (W14) | [8 empty] | 0
Gogarburn Retaining Wall (W14) | Retaining Wall | [7 empty] | 0
Gogarburn Retaining Wall (W14) | Retaining Wall | 167 | Gogarburn Retaining Wall (W14) - Ph 1 | Off Street - Other | Structures | 7A | BB | 151751.952 | 0
Gogarburn Retaining Wall (W14) | Retaining Wall | 167 | Gogarburn Retaining Wall (W14) - Ph 2 | Off Street - Other | Structures | 7A | BB | 227627.928 | 0
Gogarburn Retaining Wall (W14) | Retaining Wall | Snagging | Snagging | Off Street - Other | Structures | 7A | BB | 3832.12 | 0
Gogarburn Culvert No2 (S31) | [8 empty] | 0
Gogarburn Culvert No2 (S31) | Culvert | [7 empty] | 0
Gogarburn Culvert No2 (S31) | Culvert | 165 | Divert Flows-Bulk Excavation | Off Street - Other | Structures | 7A | BB | 0 | 0
Gogarburn Culvert No2 (S31) | Culvert | 309 | Precast Culvert Units | Off Street - Other | Structures | 7A | BB | 0 | 0
Gogarburn Culvert No2 (S31) | Culvert | 319 | Reinforced Concrete Apron and Wingwalls | Off Street - Other | Structures | 7A | BB | 0 | 0
Gogarburn Culvert No2 (S31) | Culvert | 329 | Backfill and Finishes | Off Street - Other | Structures | 7A | BB | 37634.85 | 37634.85
Gogarburn Culvert No2 (S31) | Culvert | Snagging | Snagging | Off Street - Other | Structures | 7A | BB | 376.3485 | 376.3485
Gogarburn Culvert No3 (S34) | [8 empty] | 0
Gogarburn Culvert No3 (S34) | Culvert | [7 empty] | 0
Gogarburn Culvert No3 (S34) | Culvert | 196 | Divert Flows-Bulk Excavation | Off Street - Other | Structures | 7A | BB | 0 | 0
Gogarburn Culvert No3 (S34) | Culvert | 279 | Precast Culvert Units | Off Street - Other | Structures | 7A | BB | 0 | 0
Gogarburn Culvert No3 (S34) | Culvert | 289 | Reinforced Concrete Apron and Wingwalls | Off Street - Other | Structures | 7A | BB | 0 | 0
Gogarburn Culvert No3 (S34) | Culvert | 299 | Backfill and Finishes | Off Street - Other | Structures | 7A | BB | 82542.24 | 82542.24
Gogarburn Culvert No3 (S34) | Culvert | Snagging | Snagging | Off Street - Other | Structures | 7A | BB | 825.4224 | 0
Edinburgh Airport Tram Stop | [8 empty] | 0
Edinburgh Airport Tram Stop | Tramstop | [7 empty] | 0
Edinburgh Airport Tram Stop | Tramstop | 169 | Civil Engineering and Building Works | Off Street - Other | Structures | 7A | BB | 209770.11 | 0
Edinburgh Airport Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | Structures | 7A | BB | 2118.89 | 0
Edinburgh Airport Tram Stop | Tramstop | A1880 | Deliver and Install Shelter | Off Street - Other | Structures | 7A | S | 34772.76 | 0
Edinburgh Airport Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | Structures | 7A | S | 351.24 | 0
0
0
0
0
Depot | [8 empty] | 0
Depot Earthworks | Earthworks | [7 empty] | 0
Depot Earthworks | Earthworks | 1149 | Earth Works Depot - Depot Area | Off Street Depot | Depot | 6A | BB | 185376.3276 | 185376.3276
Depot Earthworks | Earthworks | 1149 | Earth Works Depot - Car Park | Off Street Depot | Depot | 6A | BB | 185376.3276 | 185376.3276
Depot Earthworks | Earthworks | 1149 | Earth Works Depot - Shunting area | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
Depot Structure | Depot Building | [7 empty] | 0
Depot Structure | Depot Building | A17170 | Foundations - Column Foundations | Off Street Depot | Depot | 6A | BB | 185376.3276 | 185376.3276
Depot Structure | Depot Building | A17170 | Foundations - Ground Beams | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
Depot Structure | Depot Building | A17170 | Foundations - OLE Foundations | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
Depot Structure | Depot Building | A17180 | Substructure and Superstructure - Primary GLs 20-10 | Off Street Depot | Depot | 6A | BB | 185376.3276 | 185376.3276
Depot Structure | Depot Building | A17180 | Substructure and Superstructure - Primary - GLs 10-1 | Off Street Depot | Depot | 6A | BB | 185376.3276 | 185376.3276
Depot Structure | Depot Building | A17180 | Substructure and Superstructure - Secondary - GLs 20-10 | Off Street Depot | Depot | 6A | BB | 185376.3276 | 185376.3276
Depot Structure | Depot Building | A17180 | Substructure and Superstructure - Secondary - GLs 10-1 | Off Street Depot | Depot | 6A | BB | 185376.3276 | 185376.3276
Depot Structure | Depot Building | A17190 | Pits - Wheel Lathe | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
Depot Structure | Depot Building | A17190 | Pits - Floor Jack | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
Depot Structure | Depot Building | A17190 | Pits - Inspection | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
Depot Structure | Depot Building | A17200 | Sub/Sup - First Fl Slab GLs 20-10 | Off Street Depot | Depot | 6A | BB | 185376.3276 | 185376.3276
Depot Structure | Depot Building | A17200 | Sub/Sup - First Fl Slab GLs 10-1 | Off Street Depot | Depot | 6A | BB | 185376.3276 | 185376.3276
Depot Structure | Depot Building | A17200 | Sub/Sup - Sub Blockwork GLs 20-10 | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
Depot Structure | Depot Building | A17200 | Sub/Sup - Sub Blockwork GLs 10-1 | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
Depot Structure | Depot Building | A17200 | Sub/Sup - Sevice Ducts GLs 20-10 | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
Depot Structure | Depot Building | A17200 | Sub/Sup - Service Ducts GLs 10-1 | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
Depot Structure | Depot Building | A17200 | Sub/Sup - Drainage GLs 20-10 | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
Depot Structure | Depot Building | A17200 | Sub/Sup - Drainage GLs 10-1 | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
Depot Structure | Depot Building | A17200 | Sub/Sup - Service Troughs GLs 20-10 | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
Depot Structure | Depot Building | A17200 | Sub/Sup - Service Troughs GLs 10-1 | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
Depot Structure | Depot Building | A17200 | Sub/Sup - Ground Fl Slab GLs 20-10 | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
Depot Structure | Depot Building | A17200 | Sub/Sup - Ground Fl Slab GLs 10-1 | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
Depot Structure | Depot Building | A17210 | Building Envelope - Roof Cladding | Off Street Depot | Depot | 6A | BB | 185376.3276 | 185376.3276
Depot Structure | Depot Building | A17210 | Building Envelope - Blockwork | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
Depot Structure | Depot Building | A17210 | Building Envelope - Wall Cladding | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
Depot Structure | Depot Building | A17210 | Building Envelope - Translucent Panels | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
Depot Structure | Depot Building | A17210 | Building Envelope - Louvres | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
Depot Structure | Depot Building | A17210 | Building Envelope - Sup Drainage | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
Depot Structure | Depot Building | A17210 | Building Envelope - Curtain Walling | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
Depot Structure | Depot Building | A17210 | Building Envelope - Ext Doors | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
Depot Structure | Building Services | [7 empty] | 0
Depot Structure | Building Services | 1249 | Building Services Installation | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
Depot Structure | Building Services | 1259 | Building Services Commissioning | Off Street Depot | Depot | 6A | BB | 0 | 0
Depot Structure | Fitting Out & Finishes | [7 empty] | 0
Depot Structure | Fitting Out & Finishes | 1269 | Fitting out and Finishes - Ground Floor | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
Depot Structure | Fitting Out & Finishes | 1269 | Fitting out and Finishes - First Floor | Off Street Depot | Depot | 6A | BB | 185376.3276 | 0
0
0
0
0
Lindsay Road Retaining Walls (W1) | [8 empty] | 0
Lindsay Road Retaining Walls (W1) | Roadworks | [7 empty] | 0
Lindsay Road Retaining Walls (W1) | Roadworks | A1100 | CH 0300 to 0700 - one half | On Street - Other | Highways | 1A | BB | 192024.9257 | 0
Lindsay Road Retaining Walls (W1) | Roadworks | A1100 | CH 0300 to 0700 | On Street - Other | Highways | 1A | BB | 128016.6171 | 0
Lindsay Road Retaining Walls (W1) | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1A | BB | 3232.7429 | 0
Lindsay Road Retaining Walls (W1) | Roadworks | A1110 | CH 0700 to 0850 | On Street - Other | Highways | 1A | BB | 120015.5786 | 0
Lindsay Road Retaining Walls (W1) | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1A | BB | 1212.2786 | 0
Lindsay Road Retaining Walls (W1) | Roadworks | A1090.1 | CH 0000 to 0160 | On Street - Other | Highways | 1A | BB | 120015.5786 | 0
Lindsay Road Retaining Walls (W1) | Roadworks | A1090 | CH 0160 to 0300 | On Street - Other | Highways | 1A | BB | 120015.5786 | 0
Lindsay Road Retaining Walls (W1) | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1A | BB | 2424.5571 | 0
0
Ocean Terminal Ch 850 - 1080 | [8 empty] | 0
Ocean Terminal Ch 850 - 1080 | Roadworks | [7 empty] | 0
Ocean Terminal Ch 850 - 1080 | Roadworks | A15510 | Excavate for new channel and kerb line / remove existing kerbs | On Street - Other | Highways | 1A | BB | 0 | 0
Ocean Terminal Ch 850 - 1080 | Roadworks | A15520 | Construct Kerb lines | On Street - Other | Highways | 1A | BB | 55207.1661 | 0
Ocean Terminal Ch 850 - 1080 | Roadworks | A15530 | Reset Gullies | On Street - Other | Highways | 1A | BB | 0 | 0
Ocean Terminal Ch 850 - 1080 | Roadworks | A15540 | Surface new channel | On Street - Other | Highways | 1A | BB | 0 | 0
Ocean Terminal Ch 850 - 1080 | Roadworks | A15550 | Pavement Works | On Street - Other | Highways | 1A | BB | 128816.721 | 0
Ocean Terminal Ch 850 - 1080 | Roadworks | A15560 | Street Lighting / Traffic Signals / Road Signs | On Street - Other | Highways | 1A | BB | 0 | 0
Ocean Terminal Ch 850 - 1080 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1A | BB | 1858.8271 | 0
Ocean Terminal to Rennies Isle Ch 1080 - 1410 | [8 empty] | 0
Ocean Terminal to Rennies Isle Ch 1080 - 1410 | Roadworks | [7 empty] | 0
Ocean Terminal to Rennies Isle Ch 1080 - 1410 | Roadworks | A15450 | Excavate for new channel and kerb line / remove existing kerbs | On Street - Other | Highways | 1A | BB | 0 | 0
Ocean Terminal to Rennies Isle Ch 1080 - 1410 | Roadworks | A15460 | Construct Kerb lines | On Street - Other | Highways | 1A | BB | 79210.2819 | 0
Ocean Terminal to Rennies Isle Ch 1080 - 1410 | Roadworks | A15470 | Reset Gullies | On Street - Other | Highways | 1A | BB | 0 | 0
Ocean Terminal to Rennies Isle Ch 1080 - 1410 | Roadworks | A15480 | Surface new channel | On Street - Other | Highways | 1A | BB | 0 | 0
Ocean Terminal to Rennies Isle Ch 1080 - 1410 | Roadworks | A15490 | Pavement Works | On Street - Other | Highways | 1A | BB | 184823.991 | 0
Ocean Terminal to Rennies Isle Ch 1080 - 1410 | Roadworks | A15500 | Street Lighting / Traffic Signals / Road Signs | On Street - Other | Highways | 1A | BB | 0 | 0
Ocean Terminal to Rennies Isle Ch 1080 - 1410 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1A | BB | 2667.0129 | 0
Rennies Isle to Casino Square Ch 1410 - 1880 | [8 empty] | 0
Rennies Isle to Casino Square Ch 1410 - 1880 | Roadworks | [7 empty] | 0
Rennies Isle to Casino Square Ch 1410 - 1880 | Roadworks | A15390 | Excavate for new channel and kerb line / remove existing kerbs | On Street - Other | Highways | 1A | BB | 0 | 0
Rennies Isle to Casino Square Ch 1410 - 1880 | Roadworks | A15400 | Construct Kerb lines | On Street - Other | Highways | 1A | BB | 131617.0845 | 0
Rennies Isle to Casino Square Ch 1410 - 1880 | Roadworks | A15410 | Reset Gullies | On Street - Other | Highways | 1A | BB | 0 | 0
Rennies Isle to Casino Square Ch 1410 - 1880 | Roadworks | A15420 | Surface new channel | On Street - Other | Highways | 1A | BB | 131617.0845 | 0
Rennies Isle to Casino Square Ch 1410 - 1880 | Roadworks | A15430 | Pavement Works | On Street - Other | Highways | 1A | BB | 112814.6439 | 0
Rennies Isle to Casino Square Ch 1410 - 1880 | Roadworks | A15440 | Street Lighting / Traffic Signals / Road Signs | On Street - Other | Highways | 1A | BB | 0 | 0
Rennies Isle to Casino Square Ch 1410 - 1880 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1A | BB | 3798.4729 | 0
0
Casino Square to Baltic Street Ch 1880 - 2110 | [8 empty] | 0
Roadworks | Roadworks |  |  |  | Highways |  | BB |  | 0
Casino Square to Baltic Street Ch 1880 - 2110 | Roadworks | A15090 | Excavate for new channel and kerb line / remove existing kerbs | On Street - Other | Highways | 1A | BB | 0 | 0
Casino Square to Baltic Street Ch 1880 - 2110 | Roadworks | A15100 | Construct Kerb lines | On Street - Other | Highways | 1A | BB | 55207.1661 | 0
Casino Square to Baltic Street Ch 1880 - 2110 | Roadworks | A15110 | Reset Gullies | On Street - Other | Highways | 1A | BB | 0 | 0
Casino Square to Baltic Street Ch 1880 - 2110 | Roadworks | A15120 | Surface new channel | On Street - Other | Highways | 1A | BB | 0 | 0
Casino Square to Baltic Street Ch 1880 - 2110 | Roadworks | A15130 | Pavement Works | On Street - Other | Highways | 1A | BB | 0 | 0
Casino Square to Baltic Street Ch 1880 - 2110 | Roadworks | A15140 | Street Lighting / Traffic Signals / Road Signs | On Street - Other | Highways | 1A | BB | 128816.721 | 0
Casino Square to Baltic Street Ch 1880 - 2110 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1A | BB | 1858.8271 | 0
0
Baltic to Queen Charlotte Ch 2110 - 2340 | [8 empty] | 0
Baltic to Queen Charlotte Ch 2110 - 2340 | Roadworks | [7 empty] | 0
Baltic to Queen Charlotte Ch 2110 - 2340 | Roadworks | A14950 | Excavate for new channel and kerb line / remove existing kerbs | On Street - Other | Highways | 1A | BB | 0 | 0
Baltic to Queen Charlotte Ch 2110 - 2340 | Roadworks | A14960 | Construct Kerb lines | On Street - Other | Highways | 1A | BB | 73609.5549 | 0
Baltic to Queen Charlotte Ch 2110 - 2340 | Roadworks | A14970 | Reset Gullies | On Street - Other | Highways | 1A | BB | 0 | 0
Baltic to Queen Charlotte Ch 2110 - 2340 | Roadworks | A14980 | Surface new channel | On Street - Other | Highways | 1A | BB | 0 | 0
Baltic to Queen Charlotte Ch 2110 - 2340 | Roadworks | A14990 | Pavement Works | On Street - Other | Highways | 1A | BB | 110414.3323 | 0
Baltic to Queen Charlotte Ch 2110 - 2340 | Roadworks | A15000 | Street Lighting / Traffic Signals / Road Signs | On Street - Other | Highways | 1A | BB | 0 | 0
Baltic to Queen Charlotte Ch 2110 - 2340 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1A | BB | 1858.8271 | 0
Queen Charlotte to Foot of the Walk Ch 2340 - 2730 | [8 empty] | 0
Queen Charlotte to Foot of the Walk Ch 2340 - 2730 | Roadworks | [7 empty] | 0
Queen Charlotte to Foot of the Walk Ch 2340 - 2730 | Roadworks | A14810 | Excavate for new channel and kerb line / remove existing kerbs | On Street - Other | Highways | 1A | BB | 31204.0504 | 0
Queen Charlotte to Foot of the Walk Ch 2340 - 2730 | Roadworks | A14820 | Construct Kerb lines | On Street - Other | Highways | 1A | BB | 31204.0504 | 0
Queen Charlotte to Foot of the Walk Ch 2340 - 2730 | Roadworks | A14830 | Reset Gullies - 50% | On Street - Other | Highways | 1A | BB | 62408.1009 | 0
Queen Charlotte to Foot of the Walk Ch 2340 - 2730 | Roadworks | A14830 | Reset Gullies - 50% | On Street - Other | Highways | 1A | BB | 62408.1009 | 0
Queen Charlotte to Foot of the Walk Ch 2340 - 2730 | Roadworks | A14840 | Surface new channel | On Street - Other | Highways | 1A | BB | 0 | 0
Queen Charlotte to Foot of the Walk Ch 2340 - 2730 | Roadworks | A14850 | Pavement Works | On Street - Other | Highways | 1A | BB | 124816.2017 | 0
Queen Charlotte to Foot of the Walk Ch 2340 - 2730 | Roadworks | A14860 | Street Lighting / Traffic Signals / Road Signs | On Street - Other | Highways | 1A | BB | 0 | 0
Queen Charlotte to Foot of the Walk Ch 2340 - 2730 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1A | BB | 3151.9243 | 0
0
0
Foot of the Walk Ch 0 - 100 | [8 empty] | 0
Foot of the Walk Ch 0 - 100 | Roadworks | [7 empty] | 0
Foot of the Walk Ch 0 - 100 | Roadworks | A12370 | Establish Traffic Management & Temp. Fencing | On Street - Other | Highways | 1B | BB | 25015.2766 | 0
Foot of the Walk Ch 0 - 100 | Roadworks | A12380 | Excavate for new channel and kerb line / remove existing kerbs | On Street - Other | Highways | 1B | BB | 0 | 0
Foot of the Walk Ch 0 - 100 | Roadworks | A12390 | Construct Kerb lines | On Street - Other | Highways | 1B | BB | 0 | 0
Foot of the Walk Ch 0 - 100 | Roadworks | A12400 | Reset Gullies | On Street - Other | Highways | 1B | BB | 0 | 0
Foot of the Walk Ch 0 - 100 | Roadworks | A12430 | Street Lighting / Traffic Signals / Road Signs | On Street - Other | Highways | 1B | BB | 0 | 0
Foot of the Walk Ch 0 - 100 | Roadworks | A12420 | Pavement Works | On Street - Other | Highways | 1B | BB | 0 | 0
Foot of the Walk Ch 0 - 100 | Roadworks | A12410 | Surface new channel | On Street - Other | Highways | 1B | BB | 0 | 0
Foot of the Walk Ch 0 - 100 | Roadworks | A12410 | One Half of All Works | On Street - Other | Highways | 1B | BB | 75045.8298 | 0
Foot of the Walk Ch 0 - 100 | Roadworks | A12440 | Remove fencing and Traffic Management | On Street - Other | Highways | 1B | BB | 25015.2766 | 0
Foot of the Walk Ch 0 - 100 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1B | BB | 1263.3978 | 0
Leith Walk Ch 350 - 100 | [8 empty] | 0
Leith Walk Ch 350 - 100 | Roadworks - Ph 1 | [7 empty] | 0
Leith Walk Ch 350 - 100 | Roadworks | A11970 | Establish Traffic Management & Temp. Fencing | On Street - Other | Highways | 1B | BB | 54720.9176 | 54720.9176
Leith Walk Ch 350 - 100 | Roadworks | A11980 | Excavate for new channel and kerb line / remove existing kerbs | On Street - Other | Highways | 1B | BB | 0 | 0
Leith Walk Ch 350 - 100 | Roadworks | A11990 | Construct Kerb lines | On Street - Other | Highways | 1B | BB | 46903.6436 | 42213.2793
Leith Walk Ch 350 - 100 | Roadworks | A12000 | Reset Gullies | On Street - Other | Highways | 1B | BB | 0 | 0
Leith Walk Ch 350 - 100 | Roadworks | A12030 | Street Lighting / Traffic Signals / Road Signs | On Street - Other | Highways | 1B | BB | 0 | 0
Leith Walk Ch 350 - 100 | Roadworks | A12020 | Pavement Works | On Street - Other | Highways | 1B | BB | 0 | 0
Leith Walk Ch 350 - 100 | Roadworks | A12010 | Surface new channel | On Street - Other | Highways | 1B | BB | 0 | 0
Leith Walk Ch 350 - 100 | Roadworks | A12040 | Remove fencing and Traffic Management | On Street - Other | Highways | 1B | BB | 54720.9176 | 10944.1835
Leith Walk Ch 350 - 100 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1B | BB | 1579.2473 | 0
Leith Walk Ch 350 - 100 | Roadworks - Ph 2 | [7 empty] | 0
Leith Walk Ch 350 - 100 | Roadworks | A11970 | Establish Traffic Management & Temp. Fencing | On Street - Other | Highways | 1B | BB | 54720.9176 | 0
Leith Walk Ch 350 - 100 | Roadworks | A11980 | Excavate for new channel and kerb line / remove existing kerbs | On Street - Other | Highways | 1B | BB | 0 | 0
Leith Walk Ch 350 - 100 | Roadworks | A11990 | Construct Kerb lines | On Street - Other | Highways | 1B | BB | 46903.6436 | 0
Leith Walk Ch 350 - 100 | Roadworks | A12000 | Reset Gullies | On Street - Other | Highways | 1B | BB | 0 | 0
Leith Walk Ch 350 - 100 | Roadworks | A12030 | Street Lighting / Traffic Signals / Road Signs | On Street - Other | Highways | 1B | BB | 0 | 0
Leith Walk Ch 350 - 100 | Roadworks | A12020 | Pavement Works | On Street - Other | Highways | 1B | BB | 0 | 0
Leith Walk Ch 350 - 100 | Roadworks | A12010 | Surface new channel | On Street - Other | Highways | 1B | BB | 0 | 0
Leith Walk Ch 350 - 100 | Roadworks | A12040 | Remove fencing and Traffic Management | On Street - Other | Highways | 1B | BB | 54720.9176 | 0
Leith Walk Ch 350 - 100 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1B | BB | 1579.2473 | 0
Leith Walk Ch 350 - 600 | [8 empty] | 0
Leith Walk Ch 350 - 600 | Roadworks | [7 empty] | 0
Leith Walk Ch 350 - 600 | Roadworks | A12050 | Establish Traffic Management & Temp. Fencing | On Street - Other | Highways | 1B | BB | 62538.1915 | 0
Leith Walk Ch 350 - 600 | Roadworks | A12060 | Excavate for new channel and kerb line / remove existing kerbs | On Street - Other | Highways | 1B | BB | 0 | 0
Leith Walk Ch 350 - 600 | Roadworks | A12070 | Construct Kerb lines | On Street - Other | Highways | 1B | BB | 0 | 0
Leith Walk Ch 350 - 600 | Roadworks | A12080 | Reset Gullies | On Street - Other | Highways | 1B | BB | 0 | 0
Leith Walk Ch 350 - 600 | Roadworks | A12110 | Street Lighting / Traffic Signals / Road Signs | On Street - Other | Highways | 1B | BB | 0 | 0
Leith Walk Ch 350 - 600 | Roadworks | A12100 | Pavement Works | On Street - Other | Highways | 1B | BB | 187614.5746 | 0
Leith Walk Ch 350 - 600 | Roadworks | A12090 | Surface new channel | On Street - Other | Highways | 1B | BB | 0 | 0
Leith Walk Ch 350 - 600 | Roadworks | A12120 | Remove fencing and Traffic Management | On Street - Other | Highways | 1B | BB | 62538.1915 | 0
Leith Walk Ch 350 - 600 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1B | BB | 3158.4945 | 0
0
Balfour Street Ch 600 - 850 | [8 empty] | 0
Balfour Street Ch 600 - 850 | Roadworks | [7 empty] | 0
Balfour Street Ch 600 - 850 | Roadworks | A12130 | Establish Traffic Management & Temp. Fencing | On Street - Other | Highways | 1B | BB | 78172.7394 | 0
Balfour Street Ch 600 - 850 | Roadworks | A12140 | Excavate for new channel and kerb line / remove existing kerbs | On Street - Other | Highways | 1B | BB | 0 | 0
Balfour Street Ch 600 - 850 | Roadworks | A12150 | Construct Kerb lines | On Street - Other | Highways | 1B | BB | 0 | 0
Balfour Street Ch 600 - 850 | Roadworks | A12160 | Reset Gullies | On Street - Other | Highways | 1B | BB | 0 | 0
Balfour Street Ch 600 - 850 | Roadworks | A12190 | Street Lighting / Traffic Signals / Road Signs | On Street - Other | Highways | 1B | BB | 0 | 0
Balfour Street Ch 600 - 850 | Roadworks | A12180 | Pavement Works | On Street - Other | Highways | 1B | BB | 156345.4788 | 0
Balfour Street Ch 600 - 850 | Roadworks | A12170 | Surface new channel | On Street - Other | Highways | 1B | BB | 0 | 0
Balfour Street Ch 600 - 850 | Roadworks | A12200 | Remove fencing and Traffic Management | On Street - Other | Highways | 1B | BB | 78172.7394 | 0
Balfour Street Ch 600 - 850 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1B | BB | 3158.4945 | 0
Pilrig / Iona Street Ch 850 - 950 | [8 empty] | 0
Pilrig / Iona Street Ch 850 - 950 | Roadworks | [7 empty] | 0
Pilrig / Iona Street Ch 850 - 950 | Roadworks | A12210 | Establish Traffic Management & Temp. Fencing | On Street - Other | Highways | 1B | BB | 62538.1915 | 0
Pilrig / Iona Street Ch 850 - 950 | Roadworks | A12220 | Excavate for new channel and kerb line / remove existing kerbs | On Street - Other | Highways | 1B | BB | 0 | 0
Pilrig / Iona Street Ch 850 - 950 | Roadworks | A12230 | Construct Kerb lines | On Street - Other | Highways | 1B | BB | 0 | 0
Pilrig / Iona Street Ch 850 - 950 | Roadworks | A12240 | Reset Gullies | On Street - Other | Highways | 1B | BB | 0 | 0
Pilrig / Iona Street Ch 850 - 950 | Roadworks | A12270 | Street Lighting / Traffic Signals / Road Signs | On Street - Other | Highways | 1B | BB | 0 | 0
Pilrig / Iona Street Ch 850 - 950 | Roadworks | A12260 | Pavement Works | On Street - Other | Highways | 1B | BB | 0 | 0
Pilrig / Iona Street Ch 850 - 950 | Roadworks | A12250 | Surface new channel | On Street - Other | Highways | 1B | BB | 0 | 0
Pilrig / Iona Street Ch 850 - 950 | Roadworks | A12280 | Remove fencing and Traffic Management | On Street - Other | Highways | 1B | BB | 62538.1915 | 0
Pilrig / Iona Street Ch 850 - 950 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1B | BB | 1263.3978 | 0
McDonald / Brunswick Road Ch 950 - 1250 | [8 empty] | 0
McDonald / Brunswick Road Ch 950 - 1250 | Roadworks | [7 empty] | 0
McDonald / Brunswick Road Ch 950 - 1250 | Roadworks | A12290 | Establish Traffic Management & Temp. Fencing | On Street - Other | Highways | 1B | BB | 93807.2873 | 0
McDonald / Brunswick Road Ch 950 - 1250 | Roadworks | A12300 | Excavate for new channel and kerb line / remove existing kerbs | On Street - Other | Highways | 1B | BB | 0 | 0
McDonald / Brunswick Road Ch 950 - 1250 | Roadworks | A12310 | Construct Kerb lines | On Street - Other | Highways | 1B | BB | 0 | 0
McDonald / Brunswick Road Ch 950 - 1250 | Roadworks | A12320 | Reset Gullies | On Street - Other | Highways | 1B | BB | 0 | 0
McDonald / Brunswick Road Ch 950 - 1250 | Roadworks | A12350 | Street Lighting / Traffic Signals / Road Signs | On Street - Other | Highways | 1B | BB | 0 | 0
McDonald / Brunswick Road Ch 950 - 1250 | Roadworks | A12340 | Pavement Works | On Street - Other | Highways | 1B | BB | 187614.5746 | 0
McDonald / Brunswick Road Ch 950 - 1250 | Roadworks | A12330 | Surface new channel | On Street - Other | Highways | 1B | BB | 0 | 0
McDonald / Brunswick Road Ch 950 - 1250 | Roadworks | A12360 | Remove fencing and Traffic Management | On Street - Other | Highways | 1B | BB | 93807.2873 | 0
McDonald / Brunswick Road Ch 950 - 1250 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1B | BB | 3790.1934 | 0
0
0
Leith Walk Ch 0 - 375 | [8 empty] | 0
Leith Walk Ch 0 - 375 | Roadworks | [7 empty] | 0
Leith Walk Ch 0 - 375 | Roadworks | A13540 | Dummy | On Street - Other | Highways | 1C | BB | 251611.6804 | 0
Leith Walk Ch 0 - 375 | Roadworks | A13540 | Dummy | On Street - Other | Highways | 1C | BB | 251611.6804 | 0
Leith Walk Ch 0 - 375 | Roadworks | A13540 | Dummy | On Street - Other | Highways | 1C | BB | 251611.6804 | 0
Leith Walk Ch 0 - 375 | Roadworks | A13540 | Dummy | On Street - Other | Highways | 1C | BB | 251611.6804 | 0
Leith Walk Ch 0 - 375 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1C | BB | 10166.1285 | 0
London Road Ch 375 - 450 | [8 empty] | 0
London Road Ch 375 - 450 | Roadworks | [7 empty] | 0
London Road Ch 375 - 450 | Roadworks | A13570 | Dummy | On Street - Other | Highways | 1C | BB | 50322.3361 | 0
London Road Ch 375 - 450 | Roadworks | A13570 | Dummy | On Street - Other | Highways | 1C | BB | 50322.3361 | 0
London Road Ch 375 - 450 | Roadworks | A13570 | Dummy | On Street - Other | Highways | 1C | BB | 50322.3361 | 0
London Road Ch 375 - 450 | Roadworks | A13570 | Dummy | On Street - Other | Highways | 1C | BB | 50322.3361 | 0
London Road Ch 375 - 450 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1C | BB | 2033.2257 | 0
0
Picardy Place Ch 450 - 700 | [8 empty] | 0
Picardy Place Ch 450 - 700 | Roadworks | [7 empty] | 0
Picardy Place Ch 450 - 700 | Roadworks | Phase 1 | [6 empty] | 0
Picardy Place Ch 450 - 700 | Roadworks | A13580 | Dummy | On Street - Other | Highways | 1C | BB | 0 | 0
Picardy Place Ch 450 - 700 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1C | BB | 0 | 0
Picardy Place Ch 450 - 700 | Roadworks | Phase 2 | [6 empty] | 0
Picardy Place Ch 450 - 700 | Roadworks | A13590 | Dummy | On Street - Other | Highways | 1C | BB | 0 | 0
Picardy Place Ch 450 - 700 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1C | BB | 0 | 0
Picardy Place Ch 450 - 700 | Roadworks | Phase 3 | [6 empty] | 0
Picardy Place Ch 450 - 700 | Roadworks | A13600 | Dummy | On Street - Other | Highways | 1C | BB | 0 | 0
Picardy Place Ch 450 - 700 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1C | BB | 0 | 0
Picardy Place Ch 450 - 700 | Roadworks | Phase 4 | [6 empty] | 0
Picardy Place Ch 450 - 700 | Roadworks | A13610 | Dummy | On Street - Other | Highways | 1C | BB | 0 | 0
Picardy Place Ch 450 - 700 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1C | BB | 0 | 0
Picardy Place Ch 450 - 700 | Roadworks | Phase 5 | [6 empty] | 0
Picardy Place Ch 450 - 700 | Roadworks | A13620 | Dummy | On Street - Other | Highways | 1C | BB | 0 | 0
Picardy Place Ch 450 - 700 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1C | BB | 0 | 0
Picardy Place Ch 450 - 700 | Roadworks | Phase 6 | [6 empty] | 0
Picardy Place Ch 450 - 700 | Roadworks | A13630 | Dummy | On Street - Other | Highways | 1C | BB | 0 | 0
Picardy Place Ch 450 - 700 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1C | BB | 0 | 0
York Place Ch 700 - 850 | [8 empty] | 0
York Place Ch 700 - 850 | Roadworks | [7 empty] | 0
York Place Ch 700 - 850 | Roadworks | Phase 1 | [6 empty] | 0
York Place Ch 700 - 850 | Roadworks | A13680 | Dummy - 40% | On Street - Other | Highways | 1C | BB | 80515.7377 | 0
York Place Ch 700 - 850 | Roadworks | A13680 | Dummy | On Street - Other | Highways | 1C | BB | 120773.6066 | 0
York Place Ch 700 - 850 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1C | BB | 2033.2257 | 0
York Place Ch 700 - 850 | Roadworks | Phase 2 | [6 empty] | 0
York Place Ch 700 - 850 | Roadworks | A13690 | Dummy | On Street - Other | Highways | 1C | BB | 201289.3443 | 0
York Place Ch 700 - 850 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1C | BB | 2033.2257 | 0
York Place Ch 850 - 1000 | [8 empty] | 0
York Place Ch 850 - 1000 | Roadworks | [7 empty] | 0
York Place Ch 850 - 1000 | Roadworks | Phase 1 | [6 empty] | 0
York Place Ch 850 - 1000 | Roadworks | A13700 | Dummy - 50% | On Street - Other | Highways | 1C | BB | 80515.7377 | 0
York Place Ch 850 - 1000 | Roadworks | A13700 | Dummy | On Street - Other | Highways | 1C | BB | 120773.6066 | 0
York Place Ch 850 - 1000 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1C | BB | 2033.2257 | 0
York Place Ch 850 - 1000 | Roadworks | Phase 2 | [6 empty] | 0
York Place Ch 850 - 1000 | Roadworks | A13710 | Dummy | On Street - Other | Highways | 1C | BB | 201289.3443 | 0
York Place Ch 850 - 1000 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1C | BB | 2033.2257 | 0
0
St Andrews Square to Waverley Bridge Ch 1000 - 1360 | [8 empty] | 0
St Andrews Square to Waverley Bridge Ch 1000 - 1360 | Roadworks | [7 empty] | 0
St Andrews Square to Waverley Bridge Ch 1000 - 1360 | Roadworks | A13520 | Dummy - 40% | On Street - Other | Highways | 1C | BB | 386475.5411 | 0
St Andrews Square to Waverley Bridge Ch 1000 - 1360 | Roadworks | A13520 | Dummy | On Street - Other | Highways | 1C | BB | 579713.3116 | 0
St Andrews Square to Waverley Bridge Ch 1000 - 1360 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1C | BB | 9759.4834 | 0
0
0
Lothian Road Junction Ch 440 - 280 | [8 empty] | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | [7 empty] | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | Phase 1 | [6 empty] | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A8250 | Establish Traffic Management & Temp. Fencing | On Street - Princes St | Highways | 1D | BB | 17295.9 | 17295.9
Lothian Road Junction Ch 440 - 280 | Roadworks | A8260 | Take down permanent traffic signs / signals | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A8270 | Excavate traffic islands | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A8280 | Subbase | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A8290 | Temporary surfacing | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A8300 | Temporary Traffic signals / signs / white lines | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A8310 | Remove fencing and Traffic Management | On Street - Princes St | Highways | 1D | BB | 17295.9 | 17295.9
Lothian Road Junction Ch 440 - 280 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1D | BB | 349.4121 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | Phase 2 | [6 empty] | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A8490 | Establish Traffic Management & Temp. Fencing | On Street - Princes St | Highways | 1D | BB | 17295.9 | 17295.9
Lothian Road Junction Ch 440 - 280 | Roadworks | A8500 | Excavate North kerbline | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A8510 | Relay North kerbs | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A8520 | Reset Gullies | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A8530 | Plane out wearing course | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A8540 | Resurface road | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A8550 | Pavement (1m strip) | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A8560 | White Lines | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A8570 | Street Lighting / Road signs | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A8670 | Remove fencing and Traffic Management | On Street - Princes St | Highways | 1D | BB | 17295.9 | 17295.9
Lothian Road Junction Ch 440 - 280 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1D | BB | 349.4121 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | Phase 3 | [6 empty] | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A8580 | Establish Traffic Management & Temp. Fencing | On Street - Princes St | Highways | 1D | BB | 17295.9 | 17295.9
Lothian Road Junction Ch 440 - 280 | Roadworks | A8590 | Excavate South kerbline | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A8600 | Relay South kerbs | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A8610 | Reset Gullies | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A8620 | Plane out wearing course | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A8630 | Resurface road | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A8640 | Pavement (1m strip) | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A8650 | White Lines | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A8660 | Street Lighting / Road signs | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A8665 | Remove fencing and Traffic Management | On Street - Princes St | Highways | 1D | BB | 17295.9 | 17295.9
Lothian Road Junction Ch 440 - 280 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1D | BB | 349.4121 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | Phase 4a | [6 empty] | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A9000 | Establish Traffic Management & Temp. Fencing | On Street - Princes St | Highways | 1D | BB | 17295.9 | 17295.9
Lothian Road Junction Ch 440 - 280 | Roadworks | A9010 | Excavat for new kerb lines & channel | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A9020 | Lay new kerbs | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A9030 | Reset Gullies | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A9040 | Surface new channels | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A9050 | Pavement | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A9060 | Rebuild Traffic Islands | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A9080 | Street Lighting / Road signs | On Street - Other | Highways | 1D | BB | 0 | 0
Lothian Road Junction Ch 440 - 280 | Roadworks | A9130 | Remove fencing and Traffic Management | On Street - Princes St | Highways | 1D | BB | 17295.9 | 17295.9
Lothian Road Junction Ch 440 - 280 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1D | BB | 349.4121 | 0
Princes Street Ch 280 - 0, 1980 - 1360 | [8 empty] | 0
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | [7 empty] | 0
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | North Channel | [6 empty] | 0
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13840 | Establish Traffic Management & Temp. Fencing | On Street - Princes St | Highways | 1D | BB | 19457.8875 | 19457.8875
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13850 | Excavate North kerbline | On Street - Princes St | Highways | 1D | BB | 38915.7749 | 38915.7749
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13860 | Relay North kerbs | On Street - Princes St | Highways | 1D | BB | 0 | 0
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13870 | Reset Gullies | On Street - Princes St | Highways | 1D | BB | 77831.5498 | 77831.5498
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13880 | Plane out wearing course | On Street - Princes St | Highways | 1D | BB | 77831.5498 | 77831.5498
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13890 | Resurface road | On Street - Princes St | Highways | 1D | BB | 77831.5498 | 77831.5498
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13900 | Pavement (1m strip) | On Street - Princes St | Highways | 1D | BB | 77831.5498 | 77831.5498
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13910 | White Lines | On Street - Princes St | Highways | 1D | BB | 0 | 0
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13920 | Street Lighting / Road signs | On Street - Princes St | Highways | 1D | BB | 0 | 0
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13930 | Remove fencing and Traffic Management | On Street - Princes St | Highways | 1D | BB | 19457.8875 | 19457.8875
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | Snagging | Snagging | On Street - Princes St | Highways | 1D | BB | 3930.8864 | 0
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | South Channel | [6 empty] | 0
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13940 | Establish Traffic Management & Temp. Fencing | On Street - Princes St | Highways | 1D | BB | 19457.8875 | 19457.8875
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13950 | Excavate South kerbline | On Street - Princes St | Highways | 1D | BB | 38915.7749 | 38915.7749
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13960 | Relay South kerbs | On Street - Princes St | Highways | 1D | BB | 38915.7749 | 38915.7749
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13970 | Reset Gullies | On Street - Princes St | Highways | 1D | BB | 38915.7749 | 38915.7749
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13980 | Plane out wearing course | On Street - Princes St | Highways | 1D | BB | 77831.5498 | 77831.5498
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13990 | Resurface road | On Street - Princes St | Highways | 1D | BB | 77831.5498 | 77831.5498
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A14000 | Pavement (1m strip) | On Street - Princes St | Highways | 1D | BB | 77831.5498 | 77831.5498
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A14010 | White Lines | On Street - Princes St | Highways | 1D | BB | 0 | 0
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A14020 | Street Lighting / Road signs | On Street - Princes St | Highways | 1D | BB | 0 | 0
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A14030 | Remove fencing and Traffic Management | On Street - Princes St | Highways | 1D | BB | 19457.8875 | 19457.8875
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | Snagging | Snagging | On Street - Princes St | Highways | 1D | BB | 3930.8864 | 0
0
Haymarket Ch 1250 - 1125 | [8 empty] | 0
Haymarket Ch 1250 - 1125 | Roadworks | [7 empty] | 0
Haymarket Ch 1250 - 1125 | Roadworks | Phase 1 | [6 empty] | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6390 | Establish Traffic Management & Temp. Fencing | On Street - Other | Highways | 1D | BB | 9008.2812 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6400 | Remove island surfacing and exc. to formation | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6410 | Construct Kerb lines | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6420 | Move Gullies | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6430 | Sub base | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6440 | Roadbase/base course/wearing course/temp ramps | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6450 | Pavement Works | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6460 | White Lines | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6470 | Street Lighting / Traffic Signals / Road Signs | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6475 | Remove fencing and Traffic Management | On Street - Other | Highways | 1D | BB | 9008.2812 | 0
Haymarket Ch 1250 - 1125 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1D | BB | 181.9855 | 0
Haymarket Ch 1250 - 1125 | Roadworks | Phase 2 | [6 empty] | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6480 | Establish Traffic Management & Temp. Fencing | On Street - Other | Highways | 1D | BB | 9008.2812 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6490 | Excavate for new channel and kerb line / remove existing kerbs | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6500 | Construct Kerb lines | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6510 | Reset Gullies | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6520 | Surface new channel | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6540 | Pavement Works | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6550 | White Lines | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6560 | Street Lighting / Traffic Signals / Road Signs | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6565 | Remove fencing and Traffic Management | On Street - Other | Highways | 1D | BB | 9008.2812 | 0
Haymarket Ch 1250 - 1125 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1D | BB | 181.9855 | 0
Haymarket Ch 1250 - 1125 | Roadworks | Phase 4a | [6 empty] | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6730 | Establish Traffic Management & Temp. Fencing | On Street - Other | Highways | 1D | BB | 9008.2812 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6740 | Remove island surfacing and exc. to formation | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6750 | Construct Kerb lines | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6760 | Move Gullies | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6770 | Sub base | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6780 | Roadbase/base course/wearing course/temp ramps | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6790 | Pavement Works | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6800 | White Lines | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6810 | Street Lighting / Traffic Signals / Road Signs | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6775 | Plane off wearing course | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6815 | Remove fencing and Traffic Management | On Street - Other | Highways | 1D | BB | 9008.2812 | 0
Haymarket Ch 1250 - 1125 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1D | BB | 181.9855 | 0
Haymarket Ch 1250 - 1125 | Roadworks | Phase 4b | [6 empty] | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6820 | Establish Traffic Management & Temp. Fencing | On Street - Other | Highways | 1D | BB | 9008.2812 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6830 | Remove island surfacing and exc. to formation | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6840 | Construct Kerb lines | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6850 | Move Gullies | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6860 | Sub base | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6880 | Roadbase/base course/wearing course/temp ramps | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6890 | Pavement Works | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6900 | White Lines | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6910 | Street Lighting / Traffic Signals / Road Signs | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6870 | Plane off wearing course | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A6915 | Remove fencing and Traffic Management | On Street - Other | Highways | 1D | BB | 9008.2812 | 0
Haymarket Ch 1250 - 1125 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1D | BB | 181.9855 | 0
Haymarket Ch 1250 - 1125 | Roadworks | Phase 6b | [6 empty] | 0
Haymarket Ch 1250 - 1125 | Roadworks | A7240 | Establish Traffic Management & Temp. Fencing | On Street - Other | Highways | 1D | BB | 9008.2812 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A7250 | Excavate for new channel and kerb line / remove existing kerbs | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A7260 | Construct Kerb lines | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A7270 | Reset Gullies | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A7280 | Surface new channel | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A7290 | Pavement Works | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A7310 | Street Lighting / Traffic Signals / Road Signs | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A7315 | Remove fencing and Traffic Management | On Street - Other | Highways | 1D | BB | 9008.2812 | 0
Haymarket Ch 1250 - 1125 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1D | BB | 181.9855 | 0
Haymarket Ch 1250 - 1125 | Roadworks | Phase 7 | [6 empty] | 0
Haymarket Ch 1250 - 1125 | Roadworks | A7320 | Establish Traffic Management & Temp. Fencing | On Street - Other | Highways | 1D | BB | 9008.2812 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A7330 | Replace north junction kerb line | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A7340 | Rebuild splitter island | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A7350 | White Lines / Traffic Signals / Road Signs | On Street - Other | Highways | 1D | BB | 0 | 0
Haymarket Ch 1250 - 1125 | Roadworks | A7355 | Remove fencing and Traffic Management | On Street - Other | Highways | 1D | BB | 9008.2812 | 0
Haymarket Ch 1250 - 1125 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1D | BB | 181.9855 | 0
Torphicen Ch 1125 - 940 | [8 empty] | 0
Torphicen Ch 1125 - 940 | Roadworks | [7 empty] | 0
Torphicen Ch 1125 - 940 | Roadworks | Phase 3 - North Pavement | [6 empty] | 0
Torphicen Ch 1125 - 940 | Roadworks | A7680 | Establish Traffic Management & Temp. Fencing | On Street - Other | Highways | 1D | BB | 26664.5124 | 0
Torphicen Ch 1125 - 940 | Roadworks | A7690 | Replace north kerb line | On Street - Other | Highways | 1D | BB | 0 | 0
Torphicen Ch 1125 - 940 | Roadworks | A7695 | Remove fencing and Traffic Management | On Street - Other | Highways | 1D | BB | 26664.5124 | 0
Torphicen Ch 1125 - 940 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1D | BB | 538.677 | 0
Torphicen Ch 1125 - 940 | Roadworks | Phase 3 - South Pavement | [6 empty] | 0
Torphicen Ch 1125 - 940 | Roadworks | A7700 | Establish Traffic Management & Temp. Fencing | On Street - Other | Highways | 1D | BB | 26664.5124 | 0
Torphicen Ch 1125 - 940 | Roadworks | A7710 | Excavate for new channel and kerb line / remove existing kerbs | On Street - Other | Highways | 1D | BB | 0 | 0
Torphicen Ch 1125 - 940 | Roadworks | A7720 | Construct Kerb lines | On Street - Other | Highways | 1D | BB | 0 | 0
Torphicen Ch 1125 - 940 | Roadworks | A7730 | Reset Gullies | On Street - Other | Highways | 1D | BB | 0 | 0
Torphicen Ch 1125 - 940 | Roadworks | A7740 | Surface new channel | On Street - Other | Highways | 1D | BB | 0 | 0
Torphicen Ch 1125 - 940 | Roadworks | A7750 | Pavement Works | On Street - Other | Highways | 1D | BB | 0 | 0
Torphicen Ch 1125 - 940 | Roadworks | A7760 | Street Lighting / Traffic Signals / Road Signs | On Street - Other | Highways | 1D | BB | 0 | 0
Torphicen Ch 1125 - 940 | Roadworks | A7765 | Remove fencing and Traffic Management | On Street - Other | Highways | 1D | BB | 26664.5124 | 0
Torphicen Ch 1125 - 940 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1D | BB | 538.677 | 0
Torphicen Ch 1125 - 940 | Roadworks | Phase 3 - Splitter Island | [6 empty] | 0
Torphicen Ch 1125 - 940 | Roadworks | A7770 | Establish Traffic Management & Temp. Fencing | On Street - Other | Highways | 1D | BB | 26664.5124 | 0
Torphicen Ch 1125 - 940 | Roadworks | A7780 | Excavate for new channel and kerb line / remove existing kerbs | On Street - Other | Highways | 1D | BB | 0 | 0
Torphicen Ch 1125 - 940 | Roadworks | A7790 | Construct Kerb lines | On Street - Other | Highways | 1D | BB | 0 | 0
Torphicen Ch 1125 - 940 | Roadworks | A7800 | Reset Gullies | On Street - Other | Highways | 1D | BB | 0 | 0
Torphicen Ch 1125 - 940 | Roadworks | A7810 | Surface new channel | On Street - Other | Highways | 1D | BB | 0 | 0
Torphicen Ch 1125 - 940 | Roadworks | A7820 | Pavement Works | On Street - Other | Highways | 1D | BB | 0 | 0
Torphicen Ch 1125 - 940 | Roadworks | A7830 | Street Lighting / Traffic Signals / Road Signs | On Street - Other | Highways | 1D | BB | 0 | 0
Torphicen Ch 1125 - 940 | Roadworks | A7835 | Remove fencing and Traffic Management | On Street - Other | Highways | 1D | BB | 26664.5124 | 0
Torphicen Ch 1125 - 940 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1D | BB | 538.677 | 0
West Maitland Ch 940 - 850 | [8 empty] | 0
West Maitland Ch 940 - 850 | Roadworks | [7 empty] | 0
West Maitland Ch 940 - 850 | Roadworks | Phase 1 - South Pavement | [6 empty] | 0
West Maitland Ch 940 - 850 | Roadworks | A7840 | Establish Traffic Management & Temp. Fencing | On Street - Other | Highways | 1D | BB | 19457.8875 | 0
West Maitland Ch 940 - 850 | Roadworks | A7850 | Excavate for new channel and kerb line / remove existing kerbs | On Street - Other | Highways | 1D | BB | 0 | 0
West Maitland Ch 940 - 850 | Roadworks | A7860 | Construct Kerb lines | On Street - Other | Highways | 1D | BB | 0 | 0
West Maitland Ch 940 - 850 | Roadworks | A7870 | Reset Gullies | On Street - Other | Highways | 1D | BB | 0 | 0
West Maitland Ch 940 - 850 | Roadworks | A7880 | Surface new channel | On Street - Other | Highways | 1D | BB | 0 | 0
West Maitland Ch 940 - 850 | Roadworks | A7885 | Remove fencing and Traffic Management | On Street - Other | Highways | 1D | BB | 19457.8875 | 0
West Maitland Ch 940 - 850 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1D | BB | 393.0886 | 0
West Maitland Ch 940 - 850 | Roadworks | Phase 1 - North Pavement | [6 empty] | 0
West Maitland Ch 940 - 850 | Roadworks | A7890 | Establish Traffic Management & Temp. Fencing | On Street - Other | Highways | 1D | BB | 19457.8875 | 0
West Maitland Ch 940 - 850 | Roadworks | A7900 | Excavate for new channel and kerb line / remove existing kerbs | On Street - Other | Highways | 1D | BB | 0 | 0
West Maitland Ch 940 - 850 | Roadworks | A7910 | Construct Kerb lines | On Street - Other | Highways | 1D | BB | 0 | 0
West Maitland Ch 940 - 850 | Roadworks | A7920 | Reset Gullies | On Street - Other | Highways | 1D | BB | 0 | 0
West Maitland Ch 940 - 850 | Roadworks | A7930 | Surface new channel | On Street - Other | Highways | 1D | BB | 0 | 0
West Maitland Ch 940 - 850 | Roadworks | A7935 | Remove fencing and Traffic Management | On Street - Other | Highways | 1D | BB | 19457.8875 | 0
West Maitland Ch 940 - 850 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1D | BB | 393.0886 | 0
Shandwick Ch 850 - 440 | [8 empty] | 0
Shandwick Ch 850 - 440 | Roadworks | [7 empty] | 0
Shandwick Ch 850 - 440 | Roadworks | Phase 1 | [6 empty] | 0
Shandwick Ch 850 - 440 | Roadworks | A8180 | Establish Traffic Management & Temp. Fencing | On Street - Other | Highways | 1D | BB | 106369.7848 | 0
Shandwick Ch 850 - 440 | Roadworks | A8190 | Excavate for new channel and kerb line / remove existing kerbs | On Street - Other | Highways | 1D | BB | 0 | 0
Shandwick Ch 850 - 440 | Roadworks | A8200 | Construct Kerb lines | On Street - Other | Highways | 1D | BB | 0 | 0
Shandwick Ch 850 - 440 | Roadworks | A8210 | Reset Gullies | On Street - Other | Highways | 1D | BB | 141826.3797 | 0
Shandwick Ch 850 - 440 | Roadworks | A8240 | Street Lighting / Traffic Signals / Road Signs | On Street - Other | Highways | 1D | BB | 0 | 0
Shandwick Ch 850 - 440 | Roadworks | A8230 | Pavement Works | On Street - Other | Highways | 1D | BB | 0 | 0
Shandwick Ch 850 - 440 | Roadworks | A8220 | Surface new channel | On Street - Other | Highways | 1D | BB | 0 | 0
Shandwick Ch 850 - 440 | Roadworks | A8245 | Remove fencing and Traffic Management | On Street - Other | Highways | 1D | BB | 106369.7848 | 0
Shandwick Ch 850 - 440 | Roadworks | Snagging | Snagging | On Street - Other | Highways | 1D | BB | 3581.4742 | 0
0
0
0
Haymarket to Roseburn Junction | [8 empty] | 0
Haymarket to Roseburn Junction | Trackwork | Highways | BoQ highway works | Off Street - Other | Highways | 2A | BB | 113851.98 | 0
Haymarket to Roseburn Junction | Trackwork | Snagging | Snagging | Off Street - Other | Highways | 2A | BB | 1150.02 | 0
0
0
0
Roseburn Junction to Murrayfield Trackwork (470m) | [8 empty] | 0
Roseburn Junction to Murrayfield Trackwork (470m) | Trackwork | [7 empty] | 0
Roseburn Junction to Murrayfield Trackwork (470m) | Trackwork | Highways | BoQ Highway works | Off Street - Other | Highways | 5A | BB | 99890.7049 | 0
Roseburn Junction to Murrayfield Trackwork (470m) | Trackwork | Snagging | Snagging | Off Street - Other | Highways | 5A | BB | 1008.997 | 0
0
Murrayfield to Balgreen Road Trackwork (1006m) | [8 empty] | 0
Roseburn Junction to Murrayfield Trackwork (470m) | Trackwork | [7 empty] | 0
Murrayfield to Balgreen Road Trackwork (1006m) | Trackwork | Highways | BoQ Highway works | Off Street - Other | Highways | 5A | BB | 213808.6151 | 0
Murrayfield to Balgreen Road Trackwork (1006m) | Trackwork | Snagging | Snagging | Off Street - Other | Highways | 5A | BB | 2159.683 | 0
0
0
Carrick Knowe Bridge (S23) | [8 empty] | 0
Carrick Knowe Bridge (S23) | Carrick Knowe Disruptive Possessions | Highways | Highways BoQ works | Off Street - Other | Highways | 5B | BB | 267944.7434 | 0
Carrick Knowe Bridge (S23) | Carrick Knowe Disruptive Possessions | Snagging | Snagging | Off Street - Other | Highways | 5B | BB | 2706.5126 | 0
0
Saughton Road North to South Gyle Access Trackwork (1260m) | [8 empty] | 0
Saughton Road North to South Gyle Access Trackwork (1260m) | Trackwork | Highways | Highways BoQ works | Off Street - Other | Highways | 5B | BB | 199769.4537 | 0
Saughton Road North to South Gyle Access Trackwork (1260m) | Trackwork | Snagging | Snagging | Off Street - Other | Highways | 5B | BB | 2017.8733 | 0
0
South Gyle Access to Edinburgh Park Station Trackwork (790m) | [8 empty] | 0
South Gyle Access to Edinburgh Park Station Trackwork (790m) | Trackwork | Highways | Highways BoQ works | Off Street - Other | Highways | 5B | BB | 125252.2765 | 0
South Gyle Access to Edinburgh Park Station Trackwork (790m) | Trackwork | Snagging | Snagging | Off Street - Other | Highways | 5B | BB | 1265.1745 | 0
0
Edinburgh Park Station to Edinburgh Park Trackwork (854m) | [8 empty] | 0
Edinburgh Park Station to Edinburgh Park Trackwork (854m) | Trackwork | Highways | Highways BoQ works | Off Street - Other | Highways | 5B | BB | 135399.2964 | 0
Edinburgh Park Station to Edinburgh Park Trackwork (854m) | Trackwork | Snagging | Snagging | Off Street - Other | Highways | 5B | BB | 1367.6697 | 0
0
0
Gyle Tram Stop | [8 empty] | 0
Gyle Tram Stop | Tramstop | Highways | Highways BoQ works | Off Street - Other | Highways | 5C | BB | 172784.4268 | 0
Gyle Tram Stop | Tramstop | Snagging | Snagging | Off Street - Other | Highways | 5C | BB | 1745.2972 | 0
0
A8 Underpass (W28) | [8 empty] | 0
A8 Underpass (W28) | Underpass | Highways | Highways BoQ works | Off Street - Other | Highways | 5C | BB | 127769.5366 | 0
A8 Underpass (W28) | Underpass | Snagging | Snagging | Off Street - Other | Highways | 5C | BB | 1290.6014 | 0
0
Depot Stop to Gogarburn Trackwork (562m) | [8 empty] | 0
Depot Stop to Gogarburn Trackwork (562m) | Trackwork | Highways | Highways BoQ works | Off Street - Other | Highways | 5C | BB | 127769.5366 | 0
Depot Stop to Gogarburn Trackwork (562m) | Trackwork | Snagging | Snagging | Off Street - Other | Highways | 5C | BB | 1290.6014 | 0
0
0
0
Depot Access Road | [8 empty] | 0
Depot Access Road | Roadworks | [7 empty] | 0
Depot Access Road | Roadworks | 1179 | North Side - Capping & Drainage | Off Street Depot | Highways | 6A | BB | 178535.4714 | 0
Depot Access Road | Roadworks | 1179 | North Side | Off Street Depot | Highways | 6A | BB | 178535.4714 | 0
Depot Access Road | Roadworks | 1189 | South Side | Off Street Depot | Highways | 6A | BB | 341546.1192 | 0
Depot Access Road | Roadworks | 1199 | Finishes - Lighting | Off Street Depot | Highways | 6A | BB | 38812.059 | 0
Depot Access Road | Roadworks | 1199 | Finishes - Landscaping | Off Street Depot | Highways | 6A | BB | 38812.059 | 0
Depot Access Road | Roadworks | 1199 | Finishes | Off Street Depot | Highways | 6A | BB | 77624.118 | 0
Depot Access Road | Roadworks | 1209 | Car Park & Hardstanding - Surface Water Drainage | Off Street Depot | Highways | 6A | BB | 124198.5888 | 0
Depot Access Road | Roadworks | 1209 | Car Park & Hardstanding - External Services | Off Street Depot | Highways | 6A | BB | 186297.8832 | 0
Depot Access Road | Roadworks | 1219 | Track & Stabling Area - OLE Foundations | Off Street Depot | Highways | 6A | BB | 77624.118 | 0
Depot Access Road | Roadworks | 1219 | Track & Stabling Area | Off Street Depot | Highways | 6A | BB | 116436.177 | 0
Depot Access Road | Roadworks | 1229 | Shunting Area - OLE Foundations | Off Street Depot | Highways | 6A | BB | 58218.0885 | 0
Depot Access Road | Roadworks | 1229 | Shunting Area | Off Street Depot | Highways | 6A | BB | 135842.2065 | 0
Depot Access Road | Roadworks | 1239 | Handover to trackworks resource | Off Street Depot | Highways | 6A | BB | 0 | 0
Depot Access Road | Roadworks | Snagging | Snagging | Off Street Depot | Highways | 6A | BB | 15681.64 | 0
0
0
0
Gogarburn to Inglishton Park & Ride Enabling Works | [8 empty] | 0
Gogarburn to Inglishton Park & Ride Enabling Works | Enabling Works | A2000 | Highways BoQ works | Off Street - Other | Highways | 7A | BB | 54026.7683 | 8104.0152
Gogarburn to Inglishton Park & Ride Enabling Works | Enabling Works | Snagging | Snagging | Off Street - Other | Highways | 7A | BB | 545.7249 | 0
0
Inglishton Park & Ride to Edinburgh Airport Trackwork (833m) | [8 empty] | 0
Inglishton Park & Ride to Edinburgh Airport Trackwork (833m) | Trackwork | Highways | Highways BoQ works | Off Street - Other | Highways | 7A | BB | 25716.7417 | 0
Inglishton Park & Ride to Edinburgh Airport Trackwork (833m) | Trackwork | Snagging | Snagging | Off Street - Other | Highways | 7A | BB | 259.7651 | 0
Count
Value
Cumul. Count
Cumul. Value
[7 empty] | Value | Prelims
Structures
Depot
Highways
Track
OLE
SCC
NR Immun
Cumul. Prelims
Cumul. Structures
Cumul. Depot
Cumul. Highways
Cumul. Track
Cumul. OLE
Cumul. SCC
Cumul. NR Immun
[7 empty] | Count | Prelims
Structures
Depot
Highways
Track
OLE
SCC
NR Immun
Cumul. Prelims
Cumul. Structures
Cumul. Depot
Cumul. Highways
Cumul. Track
Cumul. OLE
Cumul. SCC
Cumul. NR Immun
[7 empty] | Value | 0
1A
1B
1C
1D
2A
5A
5B
5C
6A
7A
NR Imm
Cumul. 0
Cumul. 1A
Cumul. 1B
Cumul. 1C
Cumul, 1D
Cumul. 2A
Cumul. 5A
Cumul. 5B
Cumul. 5C
Cumul. 6A
Cumul. 7A
Cumul. NR Immun
[7 empty] | Count | 0
1A
1B
1C
1D
2A
5A
5B
5C
6A
7A
NR Immun
Cumul. 0
Cumul. 1A
Cumul. 1B
Cumul. 1C
Cumul. 1D
Cumul. 2A
Cumul. 5A
Cumul. 5B
Cumul. 5C
Cumul. 6A
Cumul. 7A
Cumul. NR Immun

## Sheet2
Breakdown of COWD to P11 2009/10 per milestone schedule | [5 empty] | 87291002.7749
L4 | L5 | Activity ID | Section | Contractor | Classification | £'s
Mobilisation | Mobilisation | 00A | 0 | BB | Mobilisation Payments | 19100000
Mobilisation | Mobilisation | 00A | 0 | S | Mobilisation Payments | 19100000
Mobilisation | Mobilisation | 00B | 0 | BB | Mobilisation Payments | 3500000
Mobilisation | Mobilisation | 00C | 0 | S | Mobilisation Payments | 3500000
Preliminaries | Preliminaries | Mth 1 | 0 | BB | Prelims | 539898.6029
Preliminaries | Preliminaries | Mth 2 | 0 | BB | Prelims | 539898.6029
Preliminaries | Preliminaries | Mth 3 | 0 | BB | Prelims | 539898.6029
Preliminaries | Preliminaries | Mth 4 | 0 | BB | Prelims | 539898.6029
Preliminaries | Preliminaries | Mth 5 | 0 | BB | Prelims | 539898.6029
Preliminaries | Preliminaries | Mth 6 | 0 | BB | Prelims | 539898.6029
Preliminaries | Preliminaries | Mth 7 | 0 | BB | Prelims | 1027883.703
Preliminaries | Preliminaries | Mth 8 | 0 | BB | Prelims | 1027883.703
Preliminaries | Preliminaries | Mth 9 | 0 | BB | Prelims | 1027883.703
Preliminaries | Preliminaries | Mth 10 | 0 | BB | Prelims | 1027883.703
Preliminaries | Preliminaries | Mth 11 | 0 | BB | Prelims | 1027883.703
Preliminaries | Preliminaries | Mth 12 | 0 | BB | Prelims | 1027883.703
Preliminaries | Preliminaries | Mth 13 | 0 | BB | Prelims | 1027883.703
Preliminaries | Preliminaries | Mth 14 | 0 | BB | Prelims | 1027883.703
Preliminaries | Preliminaries | Mth 15 | 0 | BB | Prelims | 1027883.703
Preliminaries | Preliminaries | Mth 16 | 0 | BB | Prelims | 1027883.703
Preliminaries | Preliminaries | Mth 17 | 0 | BB | Prelims | 1027883.703
Preliminaries | Preliminaries | Mth 18 | 0 | BB | Prelims | 1027883.703
Preliminaries | Preliminaries | Mth 19 | 0 | BB | Prelims | 1027883.703
Preliminaries | Preliminaries | Mth 20 | 0 | BB | Prelims | 1027883.703
Preliminaries | Preliminaries | Mth 21 | 0 | BB | Prelims | 1027883.703
Preliminaries | Preliminaries | Mth 22 | 0 | BB | Prelims | 1027883.703
Preliminaries | Preliminaries | Mth 23 | 0 | BB | Prelims | 1027883.703
Preliminaries | Preliminaries | Mth 1 | 0 | S | Prelims | 232162.2065
Preliminaries | Preliminaries | Mth 2 | 0 | S | Prelims | 232162.2065
Preliminaries | Preliminaries | Mth 3 | 0 | S | Prelims | 232162.2065
Preliminaries | Preliminaries | Mth 4 | 0 | S | Prelims | 232162.2065
Preliminaries | Preliminaries | Mth 5 | 0 | S | Prelims | 232162.2065
Preliminaries | Preliminaries | Mth 6 | 0 | S | Prelims | 232162.2065
Preliminaries | Preliminaries | Mth 7 | 0 | S | Prelims | 442001.4606
Preliminaries | Preliminaries | Mth 8 | 0 | S | Prelims | 442001.4606
Preliminaries | Preliminaries | Mth 9 | 0 | S | Prelims | 442001.4606
Preliminaries | Preliminaries | Mth 10 | 0 | S | Prelims | 442001.4606
Preliminaries | Preliminaries | Mth 11 | 0 | S | Prelims | 442001.4606
Preliminaries | Preliminaries | Mth 12 | 0 | S | Prelims | 442001.4606
Preliminaries | Preliminaries | Mth 13 | 0 | S | Prelims | 442001.4606
Preliminaries | Preliminaries | Mth 14 | 0 | S | Prelims | 442001.4606
Preliminaries | Preliminaries | Mth 15 | 0 | S | Prelims | 442001.4606
Preliminaries | Preliminaries | Mth 16 | 0 | S | Prelims | 442001.4606
Preliminaries | Preliminaries | Mth 17 | 0 | S | Prelims | 442001.4606
Preliminaries | Preliminaries | Mth 18 | 0 | S | Prelims | 442001.4606
Preliminaries | Preliminaries | Mth 19 | 0 | S | Prelims | 442001.4606
Preliminaries | Preliminaries | Mth 20 | 0 | S | Prelims | 442001.4606
Preliminaries | Preliminaries | Mth 21 | 0 | S | Prelims | 442001.4606
Preliminaries | Preliminaries | Mth 22 | 0 | S | Prelims | 442001.4606
Preliminaries | Preliminaries | Mth 23 | 0 | S | Prelims | 442001.4606
Network Rail Immunisation | Network Rail Immunisation | Mth 4 | NR Imm | S | NR Immun | 184615
Network Rail Immunisation | Network Rail Immunisation | Mth 5 | NR Imm | S | NR Immun | 70000
Network Rail Immunisation | Network Rail Immunisation | Mth 6 | NR Imm | S | NR Immun | 44622.7179
Network Rail Immunisation | Network Rail Immunisation | Mth 7 | NR Imm | S | NR Immun | 20615.3846
SDS Interface | SDS Interface | Mth 1 | 0 | S | SDS Interface | 292307.6923
SDS Interface | SDS Interface | Mth 2 | 0 | S | SDS Interface | 292307.6923
SDS Interface | SDS Interface | Mth 3 | 0 | S | SDS Interface | 292307.6923
SDS Interface | SDS Interface | Mth 4 | 0 | S | SDS Interface | 292307.6923
SDS Interface | SDS Interface | Mth 5 | 0 | S | SDS Interface | 292307.6923
SDS Interface | SDS Interface | Mth 6 | 0 | S | SDS Interface | 292307.6923
SDS Interface | SDS Interface | Mth 7 | 0 | S | SDS Interface | 292307.6923
SDS Interface | SDS Interface | Mth 8 | 0 | S | SDS Interface | 292307.6923
SDS Interface | SDS Interface | Mth 9 | 0 | S | SDS Interface | 292307.6923
SDS Interface | SDS Interface | Mth 10 | 0 | S | SDS Interface | 292307.6923
SDS Interface | SDS Interface | Mth 11 | 0 | S | SDS Interface | 292307.6923
SDS Interface | SDS Interface | Mth 12 | 0 | S | SDS Interface | 292307.6923
SDS Interface | SDS Interface | Mth 13 | 0 | S | SDS Interface | 292307.6923
Lothian Road Junction Ch 440 - 280 | Trackwork | A8320 | 1D | BB | On Street - Other | 2413.8
Lothian Road Junction Ch 440 - 280 | Trackwork | A8350 | 1D | BB | On Street - Other | 12069
Princes Street Ch 280 - 0, 1980 - 1360 | Trackwork | A13770 | 1D | BB | On Street - Princes St | 163603.6
Princes Street Ch 280 - 0, 1980 - 1360 | Trackwork | A13790 | 1D | BB | On Street - Princes St | 40900.9
Princes Street Ch 280 - 0, 1980 - 1360 | Trackwork | A13810 | 1D | S | On Street - Princes St | 383070.6528
Princes Street Ch 280 - 0, 1980 - 1360 | Trackwork | A13810 | 1D | S | On Street - Princes St | 468197.4645
Princes Street Ch 280 - 0, 1980 - 1360 | Trackwork | A13830 | 1D | BB | On Street - Princes St | 81801.8
Princes Street Ch 280 - 0, 1980 - 1360 | Trackwork | A13820 | 1D | BB | On Street - Princes St | 138782.7
Guided Busway | Trackwork | 1543 | 5B | BB | Off Street - Other | 82954
Edinburgh Park to Gyle Trackwork (760m) | Trackwork | 140 | 5C | BB | Off Street - Other | 29271.42
Princes Street West Tram Stop | Tramstop | 630 | 1C | BB | On Street - Princes St | 75454.335
Princes Street West Tram Stop | Tramstop | 630 | 1C | BB | On Street - Princes St | 75454.335
Haymarket Station Viaduct (S19) | Bridge | 1138 | 2A | BB | Off Street - Other | 100487.277
Haymarket Station Viaduct (S19) | Bridge | 1139 | 2A | BB | Off Street - Other | 2009.7455
Haymarket Station Viaduct (S19) | Bridge | 192 | 2A | BB | Off Street - Other | 100487.277
Haymarket Station Viaduct (S19) | Bridge | 227 | 2A | BB | Off Street - Other | 100487.277
Haymarket Station Viaduct (S19) | Bridge | 498 | 2A | BB | Off Street - Other | 75365.4577
Russell Road Retaining Walls (W3 and W4) | Retaining Wall | 107 | 5A | BB | Off Street - Other | 49825.5368
Murrayfield Tram Stop Retaining Wall (W18) | Retaining Wall | 108 | 5A | BB | Off Street - Other | 52297.0965
Murrayfield Retaining Walls (S21B) | Retaining Wall | 110 | 5A | BB | Off Street - Other | 72847.5165
Murrayfield Stadium Underpass (S21C) | Underpass | 112 | 5A | BB | Off Street - Other | 9388.9125
Murrayfield Retaining Walls (S21D) | Retaining Wall | 111 | 5A | BB | Off Street - Other | 15000
Baird Drive Retaining Walls (W8) | Retaining Wall | 114 | 5A | BB | Off Street - Other | 20000
Balgreen Road Bridge (S22) and Retaining Walls (W9) | Bridge & Retaining Wall | 115 | 5A | BB | Off Street - Other | 8400.7638
Balgreen Road Bridge (S22) and Retaining Walls (W9) | Bridge & Retaining Wall | 115 | 5A | BB | Off Street - Other | 8400.7638
Balgreen Road Bridge (S22) and Retaining Walls (W9) | Bridge & Retaining Wall | 115 | 5A | BB | Off Street - Other | 8400.7638
Balgreen Road Bridge (S22) and Retaining Walls (W9) | Bridge & Retaining Wall | 115 | 5A | BB | Off Street - Other | 8400.7638
Balgreen Road Bridge (S22) and Retaining Walls (W9) | Bridge & Retaining Wall | 115 | 5A | BB | Off Street - Other | 4908.0042
Carrick Knowe Bridge (S23) | Bridge | 16 | 5B | BB | Off Street - Other | 32259.3386
Carrick Knowe Bridge (S23) | Bridge | 7 | 5B | BB | Off Street - Other | 32259.3386
Carrick Knowe Bridge (S23) | Bridge | 28 | 5B | BB | Off Street - Other | 32259.3386
Carrick Knowe Bridge (S23) | Bridge | 116 | 5B | BB | Off Street - Other | 32259.3386
Carrick Knowe Bridge (S23) | Bridge | 97 | 5B | BB | Off Street - Other | 32259.3386
Carrick Knowe Bridge (S23) | Bridge | 688 | 5B | BB | Off Street - Other | 32259.3386
Edinburgh Park Station Bridge (S27) | Bridge | 758 | 5B | BB | Off Street - Other | 119485.7628
Edinburgh Park Station Bridge (S27) | Bridge | 768 | 5B | BB | Off Street - Other | 93290.806
Edinburgh Park Station Bridge (S27) | Bridge | 426 | 5B | BB | Off Street - Other | 119485.7628
Edinburgh Park Station Bridge (S27) | Bridge | 738 | 5B | BB | Off Street - Other | 6663.629
Edinburgh Park Station Bridge (S27) | Bridge | 523 | 5B | BB | Off Street - Other | 93290.806
Edinburgh Park Station Bridge (S27) | Bridge | 19 | 5B | BB | Off Street - Other | 229780.34
Edinburgh Park Station Bridge (S27) | Bridge | 194 | 5B | BB | Off Street - Other | 119485.7628
Edinburgh Park Station Bridge (S27) | Bridge | 359 | 5B | BB | Off Street - Other | 119485.7628
Edinburgh Park Station Bridge (S27) | Bridge | 174 | 5B | BB | Off Street - Other | 119485.7628
Edinburgh Park Station Bridge (S27) | Bridge | 349 | 5B | BB | Off Street - Other | 119485.7628
Edinburgh Park Station Bridge (S27) | Bridge | Pier 6 | 5B | BB | Off Street - Other | 119485.7628
Edinburgh Park Station Bridge (S27) | Bridge | 681 | 5B | BB | Off Street - Other | 133272.58
Edinburgh Park Station Bridge (S27) | Bridge | 491 | 5B | BB | Off Street - Other | 133272.58
Edinburgh Park Station Bridge (S27) | Bridge | 581 | 5B | BB | Off Street - Other | 133272.58
Edinburgh Park Station Bridge (S27) | Bridge | 771 | 5B | BB | Off Street - Other | 133272.58
Edinburgh Park Station Bridge (S27) | Bridge | 941 | 5B | BB | Off Street - Other | 133272.58
Edinburgh Park Station Bridge (S27) | Bridge | 1091 | 5B | BB | Off Street - Other | 133272.58
Edinburgh Park Station Bridge (S27) | Bridge | 1001 | 5B | BB | Off Street - Other | 133272.58
A8 Underpass (W28) | Underpass | 143 | 5C | BB | Off Street - Other | 36324.8671
A8 Underpass (W28) | Underpass | 143 | 5C | BB | Off Street - Other | 36324.8671
Depot Structure | Procurement | 1159 | 6A | BB | Off Street - Depot | 185376.3276
Gogarburn Underbridge (S29) | Bridge | 159 | 7A | BB | Off Street - Other | 42871.95
Gogarburn Underbridge (S29) | Bridge | 179 | 7A | BB | Off Street - Other | 128615.85
Gogarburn Underbridge (S29) | Bridge | 189 | 7A | BB | Off Street - Other | 85743.9
Gogarburn Underbridge (S29) | Bridge | 209 | 7A | BB | Off Street - Other | 128615.85
Gogarburn Underbridge (S29) | Bridge | 219 | 7A | BB | Off Street - Other | 85743.9
Gogarburn Culvert No1 (S30) | Culvert | 269 | 7A | BB | Off Street - Other | 37566.54
Gogarburn Culvert No2 (S31) | Culvert | 329 | 7A | BB | Off Street - Other | 37634.85
Gogarburn Culvert No2 (S31) | Culvert | Snagging | 7A | BB | Off Street - Other | 376.3485
Gogarburn Culvert No3 (S34) | Culvert | 299 | 7A | BB | Off Street - Other | 82542.24
Depot Earthworks | Earthworks | 1149 | 6A | BB | Off Street - Depot | 185376.3276
Depot Earthworks | Earthworks | 1149 | 6A | BB | Off Street - Depot | 185376.3276
Depot Structure | Depot Building | A17170 | 6A | BB | Off Street - Depot | 185376.3276
Depot Structure | Depot Building | A17180 | 6A | BB | Off Street - Depot | 185376.3276
Depot Structure | Depot Building | A17180 | 6A | BB | Off Street - Depot | 185376.3276
Depot Structure | Depot Building | A17180 | 6A | BB | Off Street - Depot | 185376.3276
Depot Structure | Depot Building | A17180 | 6A | BB | Off Street - Depot | 185376.3276
Depot Structure | Depot Building | A17200 | 6A | BB | Off Street - Depot | 185376.3276
Depot Structure | Depot Building | A17200 | 6A | BB | Off Street - Depot | 185376.3276
Depot Structure | Depot Building | A17210 | 6A | BB | Off Street - Depot | 185376.3276
Leith Walk Ch 350 - 100 | Roadworks | A11970 | 1B | BB | On Street - Other | 54720.9176
Leith Walk Ch 350 - 100 | Roadworks | A11990 | 1B | BB | On Street - Other | 42213.2793
Leith Walk Ch 350 - 100 | Roadworks | A12040 | 1B | BB | On Street - Other | 10944.1835
Lothian Road Junction Ch 440 - 280 | Roadworks | A8250 | 1D | BB | On Street - Other | 17295.9
Lothian Road Junction Ch 440 - 280 | Roadworks | A8310 | 1D | BB | On Street - Other | 17295.9
Lothian Road Junction Ch 440 - 280 | Roadworks | A8490 | 1D | BB | On Street - Other | 17295.9
Lothian Road Junction Ch 440 - 280 | Roadworks | A8670 | 1D | BB | On Street - Other | 17295.9
Lothian Road Junction Ch 440 - 280 | Roadworks | A8580 | 1D | BB | On Street - Other | 17295.9
Lothian Road Junction Ch 440 - 280 | Roadworks | A8665 | 1D | BB | On Street - Other | 17295.9
Lothian Road Junction Ch 440 - 280 | Roadworks | A9000 | 1D | BB | On Street - Other | 17295.9
Lothian Road Junction Ch 440 - 280 | Roadworks | A9130 | 1D | BB | On Street - Other | 17295.9
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13840 | 1D | BB | On Street - Princes St | 19457.8875
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13850 | 1D | BB | On Street - Princes St | 38915.7749
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13870 | 1D | BB | On Street - Princes St | 77831.5498
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13880 | 1D | BB | On Street - Princes St | 77831.5498
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13890 | 1D | BB | On Street - Princes St | 77831.5498
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13900 | 1D | BB | On Street - Princes St | 77831.5498
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13930 | 1D | BB | On Street - Princes St | 19457.8875
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13940 | 1D | BB | On Street - Princes St | 19457.8875
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13950 | 1D | BB | On Street - Princes St | 38915.7749
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13960 | 1D | BB | On Street - Princes St | 38915.7749
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13970 | 1D | BB | On Street - Princes St | 38915.7749
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13980 | 1D | BB | On Street - Princes St | 77831.5498
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A13990 | 1D | BB | On Street - Princes St | 77831.5498
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A14000 | 1D | BB | On Street - Princes St | 77831.5498
Princes Street Ch 280 - 0, 1980 - 1360 | Roadworks | A14030 | 1D | BB | On Street - Princes St | 19457.8875
Gogarburn to Inglishton Park & Ride Enabling Works | Enabling Works | A2000 | 7A | BB | Off Street - Other | 8104.0152