## Sheet1
Risk Review - Budget Costings 8/4/09
Risk
Reference | Description | [5 empty] | Best | Likely | Worst
974 | Inaccurate Topo Survey Results
| Depot - Additional Bulk Excavation |  |  | Agreed | 1425174
| Section 7 - OGL's low - Additional Fill |  | 16000m3 x £55 | Estimate | 880000
| Re-location of spoil to section 7 (RBS Bunds) |  | 10000m3 x £25 |  | 250000
| Miscellaneous (Not Yet Identified) |  |  |  | 750000 | 3305174 | 2555 | 2930 | 3305
173 | Removal of contaminated / hazardous material
| Removal of knotweed |  |  | Estimate | 75000
| Hazardous Material |  | 5000m3 x £50p/m3 | Estimate | 250000 | 325000 | 150 | 325 | 400
NEW | Excavation of soft, unsuitable material, below
Earthworks Outline
| Allow - Outwith Earthworks Outline (Depot) |  | 10000m3 x £40 | Estimate | 400000
| Contaminated material at Carricknowe |  |  | Estimate | 95000
| Edinburgh Park - Sub-structure / founds |  |  | Estimate | 75000
| Unforseen ground conditions - Haymarket |  |  | Estimate | 25000
| Contaminated material at Carricknowe |  |  | Agreed | 83028
| Edinburgh Park South Abutment |  |  | Estimate | 10000
| Gogarbrun Bridge - Bases |  |  | Estimate | 25000
| Carricknowe Bridge - Bases |  |  | Estimate | 25000
| Section 5B - Capping |  |  | Estimate | 600000
| A8 Underpass - Longer Piles Required |  |  | Estimate | 250000
| Gogarburn Bridge - Soft ground identified |  |  | Estimate | 50000
| Section 7 - (Gogar - Ingliston) |  | 15000m3 x £55 | Estimate | 825000
| Section 5A (Allow) |  |  | Estimate | 500000
| Section 5C (Allow) |  |  | Estimate | 500000
| Princes Street (Actual Cost - Tender) |  |  | Estimate | 1000000
| St Andrews SQ - Granton (Actual Cost - Tender) |  |  | Estimate | 3000000
| Bases / Founds (Not Yet identified) |  |  | Estimate | 150000 | 7613028 | 4613 | 6000 | 7613
172 | Contamination / unstable ground (Tip)
| Surcharge | (This needs reviewed)
| Soil Nailing Embankment |  |  |  |  | 1192000 | 950 | 1192 | 1500 | ??
NEW | Costs associated with additional works requested
by CEC Planners
| Ocean Terminal - Enhanced Finish |  |  | Estimate | 600000
| Tramstop - Enhanced Finish | 20nr x £100k |  |  | 2000000 |  | 500 | 2600 | 3500
49 | Design Change, BDDI - IFC
Roads (Full Depth - Qualification)) - Incl Risk 35
| Roads (Full Depth - Over Marked drgs) |  |  | Estimate | 3700000 |  |  |  |  | Assumes BSC have only priced to plane all roads
| Guided Bus Way (Unsuitable Sub-Base) |  |  | Estimate | 950000
| Structures - £300k x 8nr |  |  | Estimate | 2400000 |  |  |  |  | £300k Estiamte received - Carricknowe / Gogarburn
| Railway Corridor (Previous Excercise) |  |  | Estimate | 6000000
| Markd up drgs - IFC (Roads) - St Andrews SQ |  |  | Estimate | 1400000
| Russell Road - Piling |  |  | Estimate | 1000000
| Soil Nailing - A8 Embankment |  |  | Estimate | 300000
| Section 7 - Drainage (None on BBDI) |  |  | Estimate | 300000
| Princes Street - Drainage (None on BBDI) |  |  | Estimate | 150000
| Bottom Batter Embankment Drainage |  |  | Estimate | 300000 |  |  |  |  | land Drain
| Earth Reinforcement - Gogar |  |  | Estimate | 75000
| Trackslab - Increased Depth (385 - 540) |  |  | Estimate | 750000
| Not Yet Identified |  |  | Estimate | 2500000 | 19825000 | 5000 | 12000 | 19825
343 | Overall Delay - Allow Period 40 weeks
Pro - rata cost - 7 wks, 4 days - £2,500,000
| 2500000 x 200 / 38 |  |  | Estimate | 13157
| Less recovery from Change (25000 x 7.4%) |  |  |  | -1850 | 11307 | 11307 | 11307 | 11307