## Summary P11
PHASE 1A - BUDGET AT FINANCIAL CLOSE
| PROJECT NAME: |  | Edinburgh Tram
ADVISOR NAME
| PERIOD: |  | 11 - 07/08
| tie REPRESENTATIVE: |  | 0
ADVISOR CONTACT:
|  |  | 04/05/06 | 2006-04-01 | 2006-05-01 | 2006-06-01 | 2006-07-01 | 2006-08-01 | 2006-09-01 | 2006-10-01 | 2006-11-01 | 2006-12-01 | 2007-01-01 | 2007-02-01 | 2007-03-01 | 06/07 | Cumulative | 1 - 07/08 | 2 - 07/08 | 3 - 07/08 | 4 - 07/08 | 5 - 07/08 | 6 - 07/08 | 7 - 07/08 | 8 - 07/08 | 9 - 07/08 | 10 - 07/08 | 11 - 07/08 | 12 - 07/08 | 13 - 07/08 | 07/08 | Cumulative | 1 - 08/09 | 2 - 08/09 | 3 - 08/09 | 4 - 08/09 | 5 - 08/09 | 6 - 08/09 | 7 - 08/09 | 8 - 08/09 | 9 - 08/09 | 10 - 08/09 | 11 - 08/09 | 12 - 08/09 | 13 - 08/09 | 08/09 | Cumulative | 1 - 09/10 | 2 - 09/10 | 3 - 09/10 | 4 - 09/10 | 5 - 09/10 | 6 - 09/10 | 7 - 09/10 | 8 - 09/10 | 9 - 09/10 | 10 - 09/10 | 11 - 09/10 | 12 - 09/10 | 13 - 09/10 | 09/10 | Cumulative | 1 - 10/11 | 2 - 10/11 | 3 - 10/11 | 4 - 10/11 | 5 - 10/11 | 6 - 10/11 | 7 - 10/11 | 8 - 10/11 | 9 - 10/11 | 10 - 10/11 | 11 - 10/11 | 12 - 10/11 | 13 - 10/11 | 10/11 | Cumulative | 1 - 11/12 | 2 - 11/12 | 3 - 11/12 | 4 - 11/12 | 5 - 11/12 | 6 - 11/12 | 7 - 11/12 | 8 - 11/12 | 9 - 11/12 | 10 - 11/12 | 11 - 11/12 | 12 - 11/12 | 13 - 11/12 | 11/12 | Cumulative | 1 - 12/13 | 2 - 12/13 | 3 - 12/13 | 4 - 12/13 | 5 - 12/13 | 6 - 12/13 | 7 - 12/13 | 8 - 12/13 | 9 - 12/13 | 10 - 12/13 | 11 - 12/13 | 12 - 12/13 | 13 - 12/13 | AFC | AFC |  | Restate to | FBC | Infraco | Tramco | Other |  |  | FIN CLOSE
|  |  | 0 | 2006-05-01 | 2006-06-01 | 2006-07-01 | 2006-08-01 | 2006-09-01 | 2006-10-01 | 2006-11-01 | 2006-12-01 | 2007-01-01 | 2007-02-01 | 2007-03-01 | 1 - 07/08 | 0 | 0 | 2 - 07/08 | 3 - 07/08 | 4 - 07/08 | 5 - 07/08 | 6 - 07/08 | 7 - 07/08 | 8 - 07/08 | 9 - 07/08 | 10 - 07/08 | 11 - 07/08 | 12 - 07/08 | 13 - 07/08 | 1 - 08/09 | 0 | 0 | 2 - 08/09 | 3 - 08/09 | 4 - 08/09 | 5 - 08/09 | 6 - 08/09 | 7 - 08/09 | 8 - 08/09 | 9 - 08/09 | 10 - 08/09 | 11 - 08/09 | 12 - 08/09 | 13 - 08/09 | 1 - 09/10 | 0 | 0 | 2 - 09/10 | 3 - 09/10 | 4 - 09/10 | 5 - 09/10 | 6 - 09/10 | 7 - 09/10 | 8 - 09/10 | 9 - 09/10 | 10 - 09/10 | 11 - 09/10 | 12 - 09/10 | 13 - 09/10 | 1 - 10/11 | 0 | 0 | 2 - 10/11 | 3 - 10/11 | 4 - 10/11 | 5 - 10/11 | 6 - 10/11 | 7 - 10/11 | 8 - 10/11 | 9 - 10/11 | 10 - 10/11 | 11 - 10/11 | 12 - 10/11 | 13 - 10/11 | 1 - 11/12 | 0 | 0 | 2 - 11/12 | 3 - 11/12 | 4 - 11/12 | 5 - 11/12 | 6 - 11/12 | 7 - 11/12 | 8 - 11/12 | 9 - 11/12 | 10 - 11/12 | 11 - 11/12 | 12 - 11/12 | 13 - 11/12 | 1 - 12/13 | 0 | 0 | 2 - 12/13 | 3 - 12/13 | 4 - 12/13 | 5 - 12/13 | 6 - 12/13 | 7 - 12/13 | 8 - 12/13 | 9 - 12/13 | 10 - 12/13 | 11 - 12/13 | 12 - 12/13 | 13 - 12/13 | 1 - 13/14 | 0
|  |  | 2006-03-31 | 2006-04-30 | 2006-05-31 | 2006-06-30 | 2006-07-31 | 2006-08-31 | 2006-09-30 | 2006-10-31 | 30/44/06 | 2006-12-31 | 2007-01-31 | 2007-02-28 | 2007-03-31 | 2007-03-31 | 0 | 2007-04-28 | 2007-05-26 | 2007-06-23 | 2007-07-21 | 2007-08-18 | 2007-09-15 | 2007-10-13 | 2007-11-10 | 2007-12-08 | 2008-01-05 | 2008-02-02 | 2008-03-01 | 2008-03-31 | 2008-03-31 | 0 | 2008-04-26 | 2008-05-24 | 2008-06-21 | 2008-07-19 | 2008-08-16 | 2008-09-13 | 2008-10-11 | 2008-11-08 | 2008-12-06 | 2009-01-03 | 2009-01-31 | 2009-02-28 | 2009-03-31 | 2009-03-31 | 0 | 2009-04-25 | 2009-05-23 | 2009-06-20 | 2009-07-18 | 2009-08-15 | 2009-09-12 | 2009-10-10 | 2009-11-07 | 2009-12-05 | 2010-01-02 | 2010-01-30 | 2010-02-27 | 2010-03-31 | 2010-01-31 | 0 | 2010-05-01 | 2010-05-29 | 2010-06-26 | 2010-07-24 | 2010-08-21 | 2010-09-18 | 2010-10-16 | 2010-11-13 | 2010-12-11 | 2011-01-08 | 2011-02-05 | 2011-03-05 | 2011-03-31 | 2011-03-31 | 0 | 2011-04-29 | 2011-05-27 | 2011-06-24 | 2011-07-22 | 2011-08-19 | 2011-09-16 | 2011-10-14 | 2011-11-11 | 2011-12-09 | 2012-01-06 | 2012-02-03 | 2012-03-02 | 2012-03-31 | 2012-03-31 | 0 | 2012-04-27 | 2012-05-25 | 2012-06-22 | 2012-07-20 | 2012-08-17 | 2012-09-14 | 2012-10-12 | 2012-11-09 | 2012-12-07 | 2013-01-04 | 2013-02-01 | 2013-03-01 | 2013-03-31 | P11 Report | Period 10 |  | FBC |  | Award | Award | Costs
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 90
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 123
| 11 - 07/08 | FORECAST THIS PERIOD
2806 | T01.01 | Project management Staff Costs | 1456288.59 | 162852.0783 | 162852.0783 | 215115 | 261366 | 256200.8145 | 269949.194 | 270000 | 270000 | 335403 | 195121 | 408571 | 543908 | 3351338.165 | 4807626.755 | 395023.7086 | 406954 | 425187 | 429810 | 437210 | 323708 | 641724 | 520821 | 598967 | 552993.795 | 593167 | 550587 | 550587 | 6426739.5036 | 11234366.2586 | 489711.1009 | 489711.1009 | 489711.1009 | 502168.8125 | 502168.8125 | 502168.8125 | 487482.8841 | 487482.8841 | 487482.8841 | 487482.8841 | 442024.2247 | 442024.2247 | 442024.2247 | 6251643.9505 | 17486010.2092 | 334565 | 334565 | 334565 | 334565 | 334565 | 334565 | 351293 | 351293 | 351293 | 351293 | 351293 | 351293 | 351293 | 4466441 | 21952451.2092 | 234717.1616 | 234717.1616 | 234717.1616 | 234717.1616 | 234717.1616 | 234717.1616 | 234717.1616 | 234717.1616 | 234717.1616 | 234717.1616 | 234717.1616 | 234717.1616 | 234717.1616 | 3051323.1011 | 25003774.3102 | 159557.5743 | 159557.5743 | 159557.5743 | 159557.5743 | 159557.5743 | 159557.5743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 957345.446 | 25961119.7562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25961119.7562 | 25347457 | 613662.7562 | 530801 | 26491920.7562 | [5 empty] | 26491920.7562
2807 | T01.02 | Recruitment Fees | 38611.75 | 0 | 0 | 0 | 0 | 0 | 8375 | 0 | 0 | 0 | 46351 | 22675 | 25925 | 103326 | 141937.75 | 56666.6666 | 0 | 0 | 10303 | 0 | 0 | 10303 | 0 | 15853 | 12363 | 15257 | 9469 | 8876 | 139090.6666 | 281028.4166 | 35700 | 21000 | 6500 | 3803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67003 | 348031.4166 | 37485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37485 | 385516.4166 | 39359.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39359.25 | 424875.6666 | 41326.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41326.95 | 466202.6166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 466202.6166 | 456203 | 9999.6166 |  | 466202.6166 | [5 empty] | 466202.6166
2808 | T01.03 | Travel & Subsistence / Conference | 25629.24 | 3000 | 3000 | 8883 | 6176 | 5000 | 6496 | -8114 | 10000 | 5000 | 0 | 817 | 5885 | 46143 | 71772.24 | 4803.87 | 4659.97 | 4776.19 | 4720.84 | 0 | 4776.97 | 4797.94 | 7587.73 | 9223.14 | 12571.71 | 2547 | 4193.52 | 5116.1 | 69774.98 | 141547.22 | 5011.0769 | 5011.0769 | 5011.0769 | 5011.0769 | 5011.0769 | 5011.0769 | 5011.0769 | 5011.0769 | 5011.0769 | 5011.0769 | 5011.0769 | 5011.0769 | 5011.0769 | 65144 | 206691.22 | 5215.6154 | 5215.6154 | 5215.6154 | 5215.6154 | 5215.6154 | 5215.6154 | 5215.6154 | 5215.6154 | 5215.6154 | 5215.6154 | 5215.6154 | 5215.6154 | 5215.6154 | 67803 | 274494.22 | 5429.4615 | 5429.4615 | 5429.4615 | 5429.4615 | 5429.4615 | 5429.4615 | 5429.4615 | 5429.4615 | 5429.4615 | 5429.4615 | 5429.4615 | 5429.4615 | 5429.4615 | 70583 | 345077.22 | 3015.5 | 2457.5 | 1786.5 | 1786.5 | 1641.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10687.5 | 355764.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355764.72 | 355765 | -0.28 |  | 355764.72 | [5 empty] | 355764.72
2809 | T01.04 | Allocations from central O/H | 910013.9336 | 75298.7943 | 73710.1831 | 116748 | 188591 | 150809 | 150809 | 163186 | 150809 | 150809 | 228623 | 150809 | 96000 | 1696201.9773 | 2606215.9109 | 156605.4615 | 162453 | 160460 | 156605.4615 | 201692 | 103605 | 65292 | 65292 | 173168 | 79346 | -192026 | 79346 | 79346 | 1291184.9231 | 3897400.834 | 78456.5385 | 78456.5385 | 78456.5385 | 78456.5385 | 78456.5385 | 78456.5385 | 78456.5385 | 78456.5385 | 78456.5385 | 78456.5385 | 78456.5385 | 78456.5385 | 78456.5385 | 1019935.001 | 4917335.835 | 27889.6154 | 27889.6154 | 27889.6154 | 27889.6154 | 27889.6154 | 27889.6154 | 27889.6154 | 27889.6154 | 27889.6154 | 27889.6154 | 27889.6154 | 27889.6154 | 27889.6154 | 362565.0005 | 5279900.8355 | 29284.0962 | 29284.0962 | 29284.0962 | 29284.0962 | 29284.0962 | 29284.0962 | 29284.0962 | 29284.0962 | 29284.0962 | 29284.0962 | 29284.0962 | 29284.0962 | 29284.0962 | 380693.2512 | 5660594.0867 | 36901.301 | 36901.3 | 36901.301 | 36901.301 | 36901.301 | 36901.301 | 36901.301 | 36901.301 | 36901.301 | 36901.301 | 36901.301 | 36901.301 | 36901.301 | 479716.9117 | 6140310.9984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6140310.9984 | 5815685 | 324625.9984 | -445937 | 5694373.9984 | [5 empty] | 5694373.9984
2810 | T01.05 | IT & Software Costs / fitout | 214591.66 | 307000 | 90000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 35191 | 73196 | 561387 | 775978.66 | 34393.6154 | 46091 | 363784.6154 | 289669.6154 | 0 | 23385 | 0 | 0 | -136036 | 68018 | 0 | 24000 | 64018 | 777323.8462 | 1553302.5062 | 31893 | 31893 | 31893 | 31893 | 31893 | 31893 | 31893 | 31893 | 31893 | 31893 | 31893 | 31893 | 31893 | 414609 | 1967911.5062 | 32877 | 32877 | 32877 | 32877 | 32877 | 32877 | 32877 | 32877 | 32877 | 32877 | 32877 | 32877 | 32877 | 427401 | 2395312.5062 | 34495 | 34495 | 34495 | 34495 | 34495 | 34495 | 34495 | 34495 | 34495 | 34495 | 34495 | 34495 | 34495 | 448435 | 2843747.5062 | 30612 | 30612 | 30612 | 30612 | 30612 | 30612 | 30612 | 30612 | 30612 | 30612 | 30612 | 30612 | 30612 | 397956 | 3241703.5062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3241703.5062 | 3241704 | -0.49385 |  | 3241703.5062 | [5 empty] | 3241703.5062
2811 | T01.06 | Citypoint - rent,rates,s/c | 29174 | 20000 | 20000 | 20000 | 20000 | 20000 | 20249 | 19751 | 20000 | 20000 | 20000 | 20000 | 40634 | 260634 | 289808 | 67447 | 45114 | 45114 | 45114 | 45114 | 45114 | 45114 | 45114 | 17903 | 44572 | 62908 | 44572 | 44572 | 597772 | 887580 | 22438.2232 | 22438.2232 | 22438.2232 | 22438.2232 | 22438.2232 | 22438.2232 | 22438.2232 | 22438.2232 | 22438.2232 | 22438.2232 | 22438.2232 | 22438.2232 | 22438.2232 | 291696.9012 | 1179276.9012 | 22869.8458 | 22869.8458 | 22869.8458 | 22869.8458 | 22869.8458 | 22869.8458 | 22869.8458 | 22869.8458 | 22869.8458 | 22869.8458 | 22869.8458 | 22869.8458 | 22869.8458 | 297307.9951 | 1476584.8963 | 23323.0497 | 23323.0497 | 23323.0497 | 23323.0497 | 23323.0497 | 23323.0497 | 23323.0497 | 23323.0497 | 23323.0497 | 23323.0497 | 23323.0497 | 23323.0497 | 23323.0497 | 303199.6459 | 1779784.5422 | 37057.6829 | 37057.6829 | 37057.6829 | 37057.6829 | 37057.6829 | 37057.6829 | 37057.6829 | 37057.6829 | 37057.6829 | 37057.6829 | 37057.6829 | 37057.6829 | 37057.6829 | 481749.8779 | 2261534.4201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2261534.4201 | 2243198 | 18336.4201 |  | 2261534.4201 | [5 empty] | 2261534.4201
2812 | T01.07 | Recovered from SDS | 0 | -13000 | -4000 | -4000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2813 | T01.08 | Short Term Contractors | 85542 | 50000 | 50000 | 11262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111262 | 196804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196804 | 196804 | 0 | -196804 | 0 | [5 empty] | 0
2814 | T01.09 | City Point Overheads | 0 | 4000 | 4000 | 1323 | 4000 | 4000 | 4125 | 4000 | 4000 | 4000 | -14107 | 2000 | -1746 | 19595 | 19595 | 3076.9231 | 0 | 0 | 3355.9231 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 954 | 955 | 8841.8462 | 28436.8462 | 19541 | 5587 | 5587 | 5587 | 5587 | 5587 | 2731 | 3230.7692 | 3230.7692 | 3230.7692 | 3230.7692 | 3230.7692 | 3230.7692 | 69591.6154 | 98028.4615 | 3392.3077 | 3392.3077 | 3392.3077 | 3392.3077 | 3392.3077 | 3392.3077 | 3392.3077 | 3392.3077 | 3392.3077 | 3392.3077 | 3392.3077 | 3392.3077 | 3392.3077 | 44100 | 142128.4615 | 3561.9231 | 3561.9231 | 3561.9231 | 3561.9231 | 3561.9231 | 3561.9231 | 3561.9231 | 3561.9231 | 3561.9231 | 3561.9231 | 3561.9231 | 3561.9231 | 3561.9231 | 46305 | 188433.4615 | 4721.7692 | 4721.7692 | 4721.7692 | 4721.7692 | 4721.7692 | 4721.7692 | 4721.7692 | 4721.7692 | 4721.7692 | 4721.7692 | 4721.7692 | 4721.7692 | 4721.7692 | 61383 | 249816.4615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249816.4615 | 236816 | 13000.4615 | -221379.6154 | 28436.8462 | [5 empty] | 28436.8462
2815 | T01.10 | Active Risk Manager | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23344 | 23344 | 21588 | -5190 | 6799 | 0 | 69885 | 69885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11229 | 0 | 0 | 0 | 10239 | 0 | 21468 | 91353 | 1733.9231 | 1733.9231 | 1733.9231 | 1733.9231 | 1733.9231 | 1733.9231 | 1733.9231 | 1733.9231 | 1733.9231 | 1733.9231 | 1733.9231 | 1733.9231 | 1733.9231 | 22541 | 113894 | 1820.6154 | 1820.6154 | 1820.6154 | 1820.6154 | 1820.6154 | 1820.6154 | 1820.6154 | 1820.6154 | 1820.6154 | 1820.6154 | 1820.6154 | 1820.6154 | 1820.6154 | 23668 | 137562 | 1911.6923 | 1911.6923 | 1911.6923 | 1911.6923 | 1911.6923 | 1911.6923 | 1911.6923 | 1911.6923 | 1911.6923 | 1911.6923 | 1911.6923 | 1911.6923 | 1911.6923 | 24852 | 162414 | 2534.1538 | 2534.1538 | 2534.1538 | 2534.1538 | 2534.1538 | 2534.1538 | 2534.1538 | 2534.1538 | 2534.1538 | 2534.1538 | 2534.1538 | 2534.1538 | 2534 | 32943.8462 | 195357.8462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195357.8462 | 195358 | -0.15385 |  | 195357.8462 | [5 empty] | 195357.8462
2816 | T01.11 | Archaeological supervisor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 20000 | 45000 | 45000 | 8000 | 8000 | 8000 | 8000 | 8000 | 3346.0769 | 3346.0769 | 3346.0769 | 3346.0769 | 3346.0769 | 3346.0769 | 3346.0769 | 3346.0769 | 66768.6154 | 111768.6154 | 3311.2308 | 3311.2308 | 3311.2308 | 3311.2308 | 3311.2308 | 3311.2308 | 3311.2308 | 3311.2308 | 3311.2308 | 3311.2308 | 3311.2308 | 3311.2308 | 3311.2308 | 43046 | 154814.6154 | 3271.6154 | 3271.6154 | 3271.6154 | 3271.6154 | 3271.6154 | 3271.6154 | 3271.6154 | 3271.6154 | 3271.6154 | 3271.6154 | 3271.6154 | 3076.6154 | 0 | 39064.3846 | 193879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193879 | 193881 | -2 |  | 193879 | [5 empty] | 193879
2817 | T01.12 | MUDFA Site Overheads | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 4500 | 4500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 8000 | 0 |  | 8000 | [5 empty] | 8000
2818 | T01.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2819 | T01.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2820 | T01.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2821 | T01.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2822 | T01.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2823 | T01.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2824 | T01.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2825 | T01.20 | Period Adjustments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -198240 | -234717.1616 | -432957.1616 | -432957.1616 | -159557.5743 | -159557.5743 | -159557.5743 | -159557.5743 | -159557.5743 | -159557.5743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -957345.446 | -1390302.6076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1390302.6076 |  | -1390302.6076 | 1678735 | 288432.3924 | [5 empty] | 288432.3924
2826 | T01 | Total tie PM costs | 2759851.1736 | 609150.8726 | 399562.2613 | 376331 | 508133 | 443009.8145 | 467003.194 | 479167 | 485153 | 543800 | 477798 | 646862 | 783802 | 6219772.1424 | 8979623.3159 | 718017.2452 | 665271.97 | 999321.8054 | 939578.84 | 685016 | 501088.97 | 767730.94 | 650543.73 | 679578.14 | 770364.505 | 482353 | 748860.52 | 773970.1 | 9381695.7656 | 18361319.0815 | 692984.8626 | 664330.8626 | 649830.8626 | 659591.5742 | 655788.5742 | 651134.6511 | 633592.7227 | 633592.492 | 633592.492 | 633592.492 | 588133.8325 | 588133.8325 | 588133.8325 | 8272433.0835 | 26633752.1651 | 469426.2304 | 431941.2304 | 431941.2304 | 431941.2304 | 431941.2304 | 431941.2304 | 448669.2304 | 448669.2304 | 448669.2304 | 448669.2304 | 448669.2304 | 448669.2304 | 448669.2304 | 5769816.9956 | 32403569.1607 | 375353.2499 | 335993.9999 | 335993.9999 | 335993.9999 | 335993.9999 | 335993.9999 | 335993.9999 | 335993.9999 | 335993.9999 | 335993.9999 | 335993.9999 | 137558.9999 | 98005.2229 | 3970857.4711 | 36374426.6318 | 156169.3569 | 114284.406 | 113613.407 | 113613.407 | 113468.407 | 111826.907 | 111826.907 | 111826.907 | 111826.907 | 111826.907 | 111826.907 | 111826.907 | 111826.7531 | 1505764.0857 | 37880190.7175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37880190.7175 | 38290871 | -410680.2825 | 1345415.3846 | 39225606.1022 | 0 | 0 | 0 | 0 | 0 | 39225606.1022
2827 | [107 empty] | 0
2828 | T02.01 | Core Team | 386879.57 | 30000 | 30000 | -2661 | 50000 | 50000 | 50000 | 30200 | 30200 | 30200 | 30200 | 30200 | 30200 | 388539 | 775418.57 | 35527 | 35527 | 35527 | 27200 | 25769 | 27000 | 30000 | 36756 | 39364 | 39364 | 39364 | 39364 | 52014 | 462776 | 1238194.57 | 42097.47 | 44082.21 | 44970.12 | 46761.88 | 54195 | 54195 | 57734 | 60147 | 60147 | 60147 | 73653 | 87455 | 87455 | 773039.68 | 2011234.25 | 93001 | 93001 | 93001 | 97651 | 97651 | 97651 | 88398 | 88398 | 88398 | 88398 | 88398 | 94094 | 94094 | 1202134 | 3213368.25 | 124627 | 194977 | 304879 | 365009 | 407755 | 469931 | 512677 | 574658 | 622747 | 840532 | 0 | 0 | 0 | 4417792 | 7631160.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7631160.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7631160.25 | 7631160 | 0.25 |  | 7631160.25 | [5 empty] | 7631160.25
2829 | T02.02 | Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2830 | T02.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2831 | T02.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2832 | T02.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2833 | T02.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2834 | T02.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2835 | T02.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2836 | T02.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2837 | T02.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2838 | T02.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2839 | T02.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2840 | T02.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2841 | T02.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2842 | T02.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2843 | T02 | Total DPOF | 386879.57 | 30000 | 30000 | -2661 | 50000 | 50000 | 50000 | 30200 | 30200 | 30200 | 30200 | 30200 | 30200 | 388539 | 775418.57 | 35527 | 35527 | 35527 | 27200 | 25769 | 27000 | 30000 | 36756 | 39364 | 39364 | 39364 | 39364 | 52014 | 462776 | 1238194.57 | 42097.47 | 44082.21 | 44970.12 | 46761.88 | 54195 | 54195 | 57734 | 60147 | 60147 | 60147 | 73653 | 87455 | 87455 | 773039.68 | 2011234.25 | 93001 | 93001 | 93001 | 97651 | 97651 | 97651 | 88398 | 88398 | 88398 | 88398 | 88398 | 94094 | 94094 | 1202134 | 3213368.25 | 124627 | 194977 | 304879 | 365009 | 407755 | 469931 | 512677 | 574658 | 622747 | 840532 | 0 | 0 | 0 | 4417792 | 7631160.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7631160.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7631160.25 | 7631160 | 0.25 | 0 | 7631160.25 | 0 | 0 | 0 | 0 | 0 | 7631160.25
0
2951 | T06.01 | Techincal Services | 1233000 | 280000 | 190000 | 240000 | 354000 | 191000 | 464000 | 467000 | 345000 | 401000 | 320000 | 330000 | 478261 | 4060261 | 5293261 | 214663 | 193947 | 216074 | 557000 | 164781 | 243637.7003 | 224243 | 219963 | 156685 | 193940.74 | 148000 | 169219 | 151115 | 2853268.4403 | 8146529.4403 | 60567 | 54687 | 54687 | 47085 | 36207 | 41205 | 24998 | 29996 | 24998 | 29996 | 24998 | 29996 | 49998 | 509418 | 8655947.4403 | 22531 | 17564 | 14084 | 9117 | 14084 | 9117 | 14084 | 9117 | 14084 | 9117 | 9117 | 9117 | 34117 | 185250 | 8841197.4403 | 11169 | 11169 | 11169 | 11169 | 11169 | 11169 | 11169 | 11169 | 11169 | 11169 | 11169 | 11169 | 11169 | 145197 | 8986394.4403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8986394.4403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8986394.4403 | 8986393 | 1.4403 |  | 8986394.4403 |  |  | 300000 |  |  | 9286394.4403
2952 | T06.02 | Land agreement/negotiations | 113000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113000 | 113000 | 0 |  | 113000 | [5 empty] | 113000
2953 | T06.03 | TSS Second to CEC-Approvals support | 0 | 0 | 0 | 3002 | 15539 | 16929 | 15984 | 18569 | 17216 | 4058 | 1084 | 0 | 0 | 92381 | 92381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92381 | 92381 | 0 |  | 92381 | [5 empty] | 92381
2954 | [107 empty] | 0 |  | 0 | [5 empty] | 0
2955 | T06.05 | EARL interface | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2956 | T06.06 | tie Corporate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2957 | T06.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2958 | T06.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2959 | T06.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2960 | T06.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2961 | T06.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2962 | T06.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2963 | T06.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2964 | T06.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2965 | T06.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2966 | T06 | Total TSS | 1346000 | 280000 | 190000 | 243002 | 369539 | 207929 | 479984 | 485569 | 362216 | 405058 | 321084 | 330000 | 478261 | 4152642 | 5498642 | 214663 | 193947 | 216074 | 557000 | 164781 | 243637.7003 | 224243 | 219963 | 156685 | 193940.74 | 148000 | 169219 | 151115 | 2853268.4403 | 8351910.4403 | 60567 | 54687 | 54687 | 47085 | 36207 | 41205 | 24998 | 29996 | 24998 | 29996 | 24998 | 29996 | 49998 | 509418 | 8861328.4403 | 22531 | 17564 | 14084 | 9117 | 14084 | 9117 | 14084 | 9117 | 14084 | 9117 | 9117 | 9117 | 34117 | 185250 | 9046578.4403 | 11169 | 11169 | 11169 | 11169 | 11169 | 11169 | 11169 | 11169 | 11169 | 11169 | 11169 | 11169 | 11169 | 145197 | 9191775.4403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9191775.4403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9191775.4403 | 9191774 | 1.4403 | 0 | 9191775.4403 | 0 | 0 | 300000 | 0 | 0 | 9491775.4403
2954 | T06.04 | CEC staff costs | 0 | 0 | 40000 | -3002 | 24461 | 33071 | 34016 | -98569 | 22784 | 5942 | 58916 | 85000 | -3000 | 199619 | 199619 | 120000 | 0 | 30554 | 66374 | 58240 | 46975 | 81553 | 36084 | 76186 | 9193 | -5656 | 41928.44 | 42451.63 | 603883.07 | 803502.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 803502.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 803502.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 803502.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 803502.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 803502.07 | 953340 | -149837.93 | 149838 | 953340.07 |  |  | 483870 |  |  | 1437210.07
3064 | T12.01.01 | Fees / production Items - WS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3065 | T12.01.02 | PR fees | 86876 | 18500 | 18500 | 18500 | 18500 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 194000 | 280876 | 41478.27 | 40235.83 | 16995 | 40764.7 | 15500 | 0 | 0 | -42353 | 7000 | 3000 | 3000 | 3000 | 3000 | 131620.8 | 412496.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412496.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412496.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412496.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412496.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412496.8 | 412497 | -0.2 |  | 412496.8 | [5 empty] | 412496.8
3066 | T12.01.03 | PA fees | 0 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 |  | 6000 | [5 empty] | 6000
3067 | T12.01.04 | Sundries | 0 | 1850 | 1850 | 1850 | 1850 | 0 | 1500 | 2625 | 1500 | 1500 | 2943 | 0 | 3000 | 20468 | 20468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20468 | 20468 | 0 |  | 20468 | [5 empty] | 20468
3068 | T12.01.05 | Production | 0 | 4300 | 1164 | 11847 | 3095 | 60509 | 38550 | 19219 | 118088 | 7050 | 0 | 13550 | 41727 | 319099 | 319099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319099 | 319099 | 0 |  | 319099 | [5 empty] | 319099
3069 | T12.01.06 | Outlook | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 |  | 2500 | [5 empty] | 2500
3070 | T12.01.07 | Branding / advertising | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3071 | T12.01.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3072 | T12.01.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3073 | T12.01.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3074 | T12.01 | Subtotal WS | 86876 | 29150 | 23514 | 34197 | 23445 | 75509 | 55050 | 36844 | 134588 | 23550 | 17943 | 28550 | 59727 | 542067 | 628943 | 41478.27 | 40235.83 | 16995 | 40764.7 | 15500 | 0 | 0 | -42353 | 7000 | 3000 | 3000 | 3000 | 3000 | 131620.8 | 760563.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760563.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760563.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760563.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760563.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760563.8 | 760564 | -0.2 | 0 | 760563.8 | 0 | 0 | 0 | 0 | 0 | 760563.8
3075 | T12.02.01 | Fees / production Items - MH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3076 | T12.02.02 | PR fees | 0 | 0 | 0 | 0 | 11000 | 12538 | 12538 | 12538 | 12538 | 12538 | 11923 | 12538 | 12538 | 110689 | 110689 | 12595.9 | 12596 | 12596 | 0 | 0 | 0 | 0 | 75065 | 13000 | 7000 | 7000 | 7000 | 7000 | 153852.9 | 264541.9 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 84500 | 349041.9 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 84500 | 433541.9 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 84500 | 518041.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518041.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518041.9 | 525542 | -7500.1 |  | 518041.9 | [5 empty] | 518041.9
3077 | T12.02.03 | PA fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3078 | T12.02.04 | Sundries | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3079 | T12.02.05 | Production | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 4000 | 2000 | 0 | 0 | 0 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 8000 | 0 |  | 8000 | [5 empty] | 8000
3080 | T12.02.06 | Outlook | 0 | 0 | 0 | 0 | 2500 | 0 | 2500 | 0 | 2500 | 0 | 0 | 0 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 |  | 7500 |  | 7500 | [5 empty] | 7500
3081 | T12.02.07 | Branding / advertising | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3082 | T12.02.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3083 | T12.02.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3084 | T12.02.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3085 | T12.02 | Subtotal MH | 0 | 0 | 0 | 0 | 13500 | 12538 | 17038 | 12538 | 19038 | 14538 | 11923 | 12538 | 12538 | 126189 | 126189 | 12595.9 | 12596 | 12596 | 0 | 0 | 0 | 0 | 75065 | 13000 | 7000 | 7000 | 7000 | 7000 | 153852.9 | 280041.9 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 84500 | 364541.9 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 84500 | 449041.9 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 84500 | 533541.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 533541.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 533541.9 | 533542 | -0.1 | 0 | 533541.9 | 0 | 0 | 0 | 0 | 0 | 533541.9
3086 | T12.03 | Tram branding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 12500 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 37500 | 0 |  | 37500 | [5 empty] | 37500
3087 | T12.04 | PR Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000 | 9000 | -32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3088 | T12.05 | Business development and marketing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 3000 | -9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3089 | T12.06 | Media monitoring | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 375 | 4915 | 375 | 375 | 375 | 375 | 375 | 7915 | 7915 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 4875 | 12790 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 4875 | 17665 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 4875 | 22540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22540 | 22540 | 0 |  | 22540 | [5 empty] | 22540
3090 | T12.07 | Media training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | -4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 6500 | 6500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 6500 | 13000 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 6500 | 19500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19500 | 19500 | 0 |  | 19500 | [5 empty] | 19500
3091 | T12.08 | Promotional materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 1000 | -2580 | 600 | 600 | 600 | 600 | 600 | 3420 | 3420 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 24375 | 27795 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 24375 | 52170 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 24375 | 76545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76545 | 76545 | 0 |  | 76545 | [5 empty] | 76545
3092 | T12.09 | Websites | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 500 | -1010 | 2000 | 500 | 500 | 500 | 500 | 4490 | 4490 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 26000 | 30490 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 26000 | 56490 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 26000 | 82490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82490 | 82490 | 0 |  | 82490 | [5 empty] | 82490
3093 | T12.10 | Events | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 3000 | -5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 13000 | 13000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 13000 | 26000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 13000 | 39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39000 | 39000 | 0 |  | 39000 | [5 empty] | 39000
3094 | T12.11 | Advertising | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 1000 | -800 | 1500 | 1000 | 1000 | 1500 | 1000 | 9200 | 9200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 19500 | 28700 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 19500 | 48200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 19500 | 67700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67700 | 67700 | 0 |  | 67700 | [5 empty] | 67700
3095 | T12.12 | Internal communications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 250 | 841 | 250 | 250 | 250 | 250 | 250 | 2841 | 2841 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 3250 | 6091 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 3250 | 9341 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 3250 | 12591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12591 | 12591 | 0 |  | 12591 | [5 empty] | 12591
3096 | T12.01-12 | Subtotal Communications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 54750 | 18125 | -44467.3333 | 8891.6667 | 6891.6667 | 2725 | 3225 | 2725 | 65366 | 65366 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 97500 | 162866 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 97500 | 260366 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 97500 | 357866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 357866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 357866 | 357866 | 0 | 0 | 357866 | 0 | 0 | 0 | 0 | 0 | 357866
3097 | T12.13 | S/H – Wider Community Consultations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15145 | 15645 | -25830 | 0 | 6000 | 6000 | 16960 | 16960 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 182000 | 198960 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 182000 | 380960 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 182000 | 562960 | 14000 | 4186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18186 | 581146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 581146 | 584895 | -3749 |  | 581146 | [5 empty] | 581146
3098 | T12.14 | S/H – Events | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4082 | 0 | 0 | 0 | 4082 | 4082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4082 | 4082 | 0 |  | 4082 | [5 empty] | 4082
3099 | T12.15 | S/H – Open for Business | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19745 | 0 | 0 | 0 | 19745 | 19745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19745 | 19745 | 0 |  | 19745 | [5 empty] | 19745
3100 | T12.16 | S/H – Sundry Expenses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15648 | 3749 | 0 | 0 | 19397 | 19397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19397 | 15648 | 3749 |  | 19397 | [5 empty] | 19397
3101 | T12.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3102 | T12.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3103 | T12.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3104 | T12.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3105 | T12.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3106 | T12.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3107 | T12.13-22 | Subtotal Stakeholder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15145 | 15645 | 13645 | 3749 | 6000 | 6000 | 60184 | 60184 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 182000 | 242184 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 182000 | 424184 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 182000 | 606184 | 14000 | 4186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18186 | 624370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624370 | 624370 | 0 | 0 | 624370 | 0 | 0 | 0 | 0 | 0 | 624370
3108 | T12.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3109 | T12.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3110 | T12.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3111 | T12.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3112 | T12.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3113 | T12.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3114 | T12.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3115 | T12.30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3116 | T12.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3117 | T12.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3118 | T12.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3119 | T12.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3120 | T12.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3121 | T12.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3122 | T12.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3123 | T12.23-37 | Subtotal Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3124 | T12 | Total COMMS / MARKETING | 86876 | 29150 | 23514 | 34197 | 36945 | 88047 | 72088 | 49382 | 153626 | 38088 | 29866 | 41088 | 72265 | 668256 | 755132 | 54074.17 | 52831.83 | 29591 | 40764.7 | 28000 | 54750 | 18125 | 3389.6667 | 44536.6667 | 30536.6667 | 16474 | 19225 | 18725 | 411023.7 | 1166155.7 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 364000 | 1530155.7 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 364000 | 1894155.7 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 364000 | 2258155.7 | 14000 | 4186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18186 | 2276341.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2276341.7 | 2276342 | -0.3 | 0 | 2276341.7 | 0 | 0 | 0 | 0 | 0 | 2276341.7
3126 | T13.01 | Non Executive Board | 19947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14405 | 14405 | 34352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34352 | 34352 | 0 |  | 34352 | [5 empty] | 34352
3127 | T13.02 | Search Fees | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 0 |  | 5000 | [5 empty] | 5000
3128 | T13.03 | Overheads | 0 | 65000 | 65000 | 7875 | 65000 | 65000 | 52137 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 620012 | 620012 | 25083 | 48000 | 51000 | 73000 | 53000 | 93000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 560083 | 1180095 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 403000 | 1583095 | 44000 | 39000 | 49000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 522000 | 2105095 | 45000 | 40000 | 50000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 25000 | 59562 | 59562 | 59562 | 578686 | 2683781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2683781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2683781 | 2683781 | 0 |  | 2683781 | [5 empty] | 2683781
3129 | T13.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3130 | T13.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3131 | T13.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3132 | T13.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3133 | T13.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3134 | T13.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3135 | T13.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3136 | T13 | Total TEL | 24947 | 65000 | 65000 | 7875 | 65000 | 65000 | 52137 | 50000 | 50000 | 50000 | 50000 | 50000 | 64405 | 634417 | 659364 | 25083 | 48000 | 51000 | 73000 | 53000 | 93000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 560083 | 1219447 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 403000 | 1622447 | 44000 | 39000 | 49000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 522000 | 2144447 | 45000 | 40000 | 50000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 25000 | 59562 | 59562 | 59562 | 578686 | 2723133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2723133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2723133 | 2723133 | 0 | 0 | 2723133 | 0 | 0 | 0 | 0 | 0 | 2723133
0
4173 | T99.01 | Miscellaneous | 20762.74 | 5000 | 5000 | 26737 | 69 | 35000 | 12885 | 10000 | 10000 | 10000 | 10000 | -19056 | 11385 | 117020 | 137782.74 | 6455 | 898 | 20978 | 3322 | 0 | 0 | 0 | 0 | -17844 | 0 | 0 | 4461 | 4461 | 22731 | 160513.74 | 7062 | 2601 | 2601 | 2601 | 2603 | 2601 | 2601 | 2601 | 2601 | 2601 | 2601 | 2601 | 2607 | 38282 | 198795.74 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 22100 | 220895.74 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 22100 | 242995.74 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 2220 | 22620 | 265615.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265615.74 | 265616 | -0.26 |  | 265615.74 | [5 empty] | 265615.74
4174 | T99.02 | Previous years | 3093000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3093000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3093000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3093000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3093000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3093000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3093000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3093000 | 3093000 | 0 |  | 3093000 | [5 empty] | 3093000
4175 | T99.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
4176 | T99.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
4177 | T99.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
4178 | T99.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
4179 | T99.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
4180 | T99.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
4181 | T99.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
4182 | T99.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
4183 | T99.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
4184 | T99.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
4185 | T99.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
4186 | T99.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
4187 | T99.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
4188 | T99.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
4189 | T99.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
4190 | T99.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
4191 | T99.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
4192 | T99.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
4193 | T99 | Total Miscellaneous | 3113762.74 | 5000 | 5000 | 26737 | 69 | 35000 | 12885 | 10000 | 10000 | 10000 | 10000 | -19056 | 11385 | 117020 | 3230782.74 | 6455 | 898 | 20978 | 3322 | 0 | 0 | 0 | 0 | -17844 | 0 | 0 | 4461 | 4461 | 22731 | 3253513.74 | 7062 | 2601 | 2601 | 2601 | 2603 | 2601 | 2601 | 2601 | 2601 | 2601 | 2601 | 2601 | 2607 | 38282 | 3291795.74 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 22100 | 3313895.74 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 22100 | 3335995.74 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 2220 | 22620 | 3358615.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3358615.74 | 3358616 | -0.26 | 0 | 3358615.74 | 0 | 0 | 0 | 0 | 0 | 3358615.74
| TT01 | Total Project management | 7718316.4836 | 1018300.8726 | 753076.2613 | 682479 | 1054147 | 922056.8145 | 1168113.194 | 1005749 | 1113979 | 1083088 | 977864 | 1164094 | 1437318 | 12380265.1424 | 20098581.6259 | 1173819.4152 | 996475.8 | 1383045.8054 | 1707239.54 | 1014806 | 966451.6703 | 1152651.94 | 977736.3967 | 1009505.8067 | 1074398.9117 | 711535 | 1054057.96 | 1073736.73 | 14295460.9759 | 34394042.6018 | 861711.3326 | 824701.0726 | 811088.9826 | 815039.4542 | 807793.5742 | 808135.6511 | 777925.7227 | 785336.492 | 780338.492 | 785336.492 | 748385.8325 | 767185.8325 | 787193.8325 | 10360172.7635 | 44754215.3653 | 658658.2304 | 611206.2304 | 617726.2304 | 607409.2304 | 612376.2304 | 607409.2304 | 619851.2304 | 614884.2304 | 619851.2304 | 614884.2304 | 614884.2304 | 620580.2304 | 645580.2304 | 8065300.9956 | 52819516.3609 | 585849.2499 | 611839.9999 | 731741.9999 | 781871.9999 | 824617.9999 | 886793.9999 | 929539.9999 | 991520.9999 | 1039609.9999 | 1242394.9999 | 436424.9999 | 237989.9999 | 198436.2229 | 9498632.4711 | 62318148.8321 | 171869.3569 | 120170.406 | 115313.407 | 115313.407 | 115168.407 | 113526.907 | 113526.907 | 113526.907 | 113526.907 | 113526.907 | 113526.907 | 113526.907 | 114046.7531 | 1546570.0857 | 63864718.9178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63864718.9178 | 64425236 | -560517.0822 | 1495253.3846 | 65359972.3025 | 0 | 0 | 783870 | 0 | 0 | 66143842.3025
2845 | T03.01 | DLA-SDS | 76499.47 | 0 | 1915 | 2646 | 27 | 0 | 371 | 0 | 1196 | 227 | 80 | 5000 | 0 | 11462 | 87961.47 | 0 | 96.76 | 0 | 0 | 5000 | 0 | 0 | 286 | 20209.56 | 7939.14 | -478.67 | 0 | 0 | 33052.79 | 121014.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121014.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121014.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121014.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121014.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121014.26 | 121493 | -478.74 |  | 121014.26 | [5 empty] | 121014.26
2846 | T03.02 | DLA-TSS | 29835.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2164 | 0 | 0 | 0 | 0 | 2164 | 31999.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.49 | 0 | 0 | 0 | 0 | -0.49 | 31999.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31999.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31999.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31999.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31999.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31999.37 | 31999 | 0.37 |  | 31999.37 | [5 empty] | 31999.37
2847 | T03.03 | DLA- Site Investigation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1116.25 | 0 | 0 | 0 | 0 | 1116.25 | 1116.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1116.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1116.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1116.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1116.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1116.25 | 1116 | 0.25 |  | 1116.25 | [5 empty] | 1116.25
2848 | T03.04 | DLA-MUDFA | 354360.76 | 7000 | 31085 | 59268 | 78604 | 5000 | 32179 | 5000 | 29928 | 7772 | 505 | 1000 | 8879 | 266220 | 620580.76 | 3000 | 5345.87 | 2732.52 | 11155.84 | 2376.72 | 0 | 0 | 0 | 16757.29 | -147.95 | -2531.53 | 5000 | 5000 | 48688.76 | 669269.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669269.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669269.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669269.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669269.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669269.52 | 676801 | -7531.48 |  | 669269.52 | [5 empty] | 669269.52
2849 | T03.05 | DLA-Network Rail / Scotrail | 48665.11 | 0 | 1792 | 1577 | 6683 | 2500 | 4515 | 500 | -184 | 8259 | -1979 | 2000 | -942 | 24721 | 73386.11 | 1500 | 2422.04 | 699.19 | 1750 | 556.48 | 2000 | 2000 | 3000 | 10896.44 | 3194.72 | 8810.58 | 5000 | 5000 | 46829.45 | 120215.56 | 386.53 | 404.76 | 412.91 | 409.61 | 406.45 | 412.74 | 416.45 | 414.88 | 421.73 | 411.35 | 414.58 | 459 | 459 | 5429.99 | 125645.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125645.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125645.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125645.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125645.55 | 121835 | 3810.55 |  | 125645.55 | [5 empty] | 125645.55
2850 | T03.06 | DLA-JRC | 27275.32 | 0 | 0 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 27383.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.5 | 0 | 0 | 0 | 0 | -0.5 | 27382.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27382.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27382.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27382.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27382.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27382.82 | 27383 | -0.18 |  | 27382.82 | [5 empty] | 27382.82
2851 | T03.07 | DLA-Infraco | 141282.71 | 65000 | 37383 | 4783 | 22985 | 55000 | 55905 | 55000 | 49192 | 24944 | 21040 | 60000 | 44401 | 495633 | 636915.71 | 37700 | 1182.08 | 10319.82 | 11750 | 9658.49 | 20000 | 10000 | 10000 | 140142.47 | 30589.11 | 25331.96 | 250000 | 272212 | 828885.93 | 1465801.64 | 1923 | 1923 | 1923 | 1923 | 1923 | 1923 | 1923 | 1923 | 1923 | 1923 | 1923 | 1923 | 1924 | 25000 | 1490801.64 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 760 | 10000 | 1500801.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500801.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500801.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500801.64 | 993258 | 507543.64 | -864307 | 636494.64 |  |  | 700000 |  |  | 1336494.64
2852 | T03.08 | DLA-Vehicles & Driver supply contract | 142160.42 | 40000 | 21089 | 13010 | 18588 | 5000 | 16481 | 30000 | 14394 | 33543 | -13036 | 30000 | -16977 | 192092 | 334252.42 | 35855 | 18935.58 | 23882.18 | 6295 | 12765.92 | 0 | 0 | 3300 | 24433.13 | -9321.58 | 9400 | 600 | 600 | 126745.23 | 460997.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460997.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460997.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460997.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460997.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460997.65 | 452198 | 8799.65 |  | 460997.65 | [5 empty] | 460997.65
2853 | T03.09 | DLA-BAA | 1009.5 | 0 | 95 | 151 | 54 | 2500 | 132 | 500 | -2480 | 500 | 0 | 1000 | -1000 | 1452 | 2461.5 | 7500 | -6500 | -64.75 | 200 | -38.75 | 0 | 0 | 0 | 14040.33 | 3708.64 | -1686.1 | 0 | 0 | 17159.37 | 19620.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19620.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19620.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19620.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19620.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19620.87 | 21307 | -1686.13 |  | 19620.87 | [5 empty] | 19620.87
2854 | T03.10 | DLA-Land & Property (3rd parties) | 5328.44 | 500 | 0 | 1841 | 3441 | 2000 | 647 | 500 | 4719 | 1269 | 681 | 2000 | -444 | 17154 | 22482.44 | 5000 | -4161.37 | -306.5 | 0 | 1000 | 1000 | 1000 | 2000 | 7931.67 | -4996.83 | -2000 | 0 | 0 | 6466.97 | 28949.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28949.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28949.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28949.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28949.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28949.41 | 32449 | -3499.59 |  | 28949.41 | [5 empty] | 28949.41
2855 | T03.11 | DLA-Ticketing Agreements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2856 | T03.12 | DLA-DPOF | 0 | 0 | 623 | 4521 | 2214 | 10000 | 8021 | 10000 | -13721 | -7196 | 4414 | 2500 | 14677 | 36053 | 36053 | 10000 | 6646.75 | 9111.54 | 516.5 | 4836.78 | 2000 | 0 | 0 | 10169.18 | 5998.18 | 291.55 | 5000 | 5000 | 59570.48 | 95623.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95623.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95623.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95623.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95623.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95623.48 | 100332 | -4708.52 |  | 95623.48 | [5 empty] | 95623.48
2857 | T03.13 | DLA-Tram Netwk/Roads Interface | 9163.01 | 500 | 586 | 3331 | 252 | 2000 | 3062 | 1000 | -2199 | -2438 | 0 | 500 | -500 | 6094 | 15257.01 | 0 | 0 | 0 | 250 | -37.15 | 0 | 0 | 0 | -499.41 | 0 | 0 | 0 | 0 | -286.56 | 14970.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14970.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14970.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14970.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14970.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14970.45 | 14970 | 0.45 |  | 14970.45 | [5 empty] | 14970.45
2858 | T03.14 | DLA-EARL interface | 2413.16 | 2200 | 2760 | 134 | 0 | 1000 | 3400 | 1000 | 4017 | 2637 | 1484 | 1000 | 2725 | 22357 | 24770.16 | 3000 | -3000 | 2000 | 1600 | -31.89 | 0 | 0 | 0 | 10879.12 | 0 | 0 | 0 | 0 | 14447.23 | 39217.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39217.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39217.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39217.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39217.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39217.39 | 39217 | 0.39 |  | 39217.39 | [5 empty] | 39217.39
2859 | T03.15 | DLA-Commissioning Svcs Agmt | 0 | 500 | 845 | 776 | 364 | 4500 | 1942 | 1500 | -4801 | 0 | 0 | 1000 | -1000 | 5626 | 5626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1266.48 | 0 | 0 | 0 | 0 | 1266.48 | 6892.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6892.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6892.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6892.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6892.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6892.48 | 6892 | 0.48 |  | 6892.48 | [5 empty] | 6892.48
2860 | T03.16 | OCIP | 0 | 0 | 0 | 0 | 701 | 2000 | 0 | 2000 | -201 | 4483 | 7095 | 4000 | -7685 | 12393 | 12393 | 0 | 1074.16 | 1725.63 | 350 | 1130 | 500 | 0 | 0 | -3837.32 | 7854.59 | 250 | 0 | 0 | 9047.06 | 21440.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21440.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21440.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21440.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21440.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21440.06 | 24190 | -2749.94 |  | 21440.06 | [5 empty] | 21440.06
2861 | T03.17 | Infraco Enabling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7901.63 | 0 | 0 | 0 | 0 | 7901.63 | 7901.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7901.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7901.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7901.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7901.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7901.63 | 7902 | -0.37 |  | 7901.63 | [5 empty] | 7901.63
2862 | T03.18 | HR Issues | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1218 | 1218 | 1218 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | -1301.56 | -217.75 | 0 | 0 | 0 | -519.31 | 698.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 698.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 698.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 698.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 698.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 698.69 | 699 | -0.31 |  | 698.69 | [5 empty] | 698.69
2863 | T03.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2864 | T03.19.01 | Ingliston Park & Ride | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 997 | 997 | 997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -997.5 | 0 | 500 | 0 | 0 | -497.5 | 499.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499.5 | -1 | 500.5 |  | 499.5 | [5 empty] | 499.5
2865 | T03.19.02 | Mass Earthworks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1136 | 1136 | 1136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.06 | 0 | 0 | 0 | 0 | 0.06 | 1136.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1136.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1136.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1136.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1136.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1136.06 | 1136 | 0.06 |  | 1136.06 | [5 empty] | 1136.06
2866 | T03.19.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2867 | T03.19.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2868 | T03.19.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2869 | T03.19.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2870 | T03.19.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2871 | T03.19.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2872 | T03.19.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2873 | T03.19.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2874 | T03.01-19 | Subtotal DLA | 837993.76 | 115700 | 98173 | 92146 | 133913 | 91500 | 126655 | 107000 | 82024 | 74000 | 20284 | 110000 | 45485 | 1096880 | 1934873.76 | 103555 | 22041.87 | 50099.63 | 33867.34 | 38216.6 | 25500 | 13000 | 18586 | 259106.83 | 44600.27 | 37887.79 | 265600 | 287812 | 1199873.33 | 3134747.09 | 2309.53 | 2327.76 | 2335.91 | 2332.61 | 2329.45 | 2335.74 | 2339.45 | 2337.88 | 2344.73 | 2334.35 | 2337.58 | 2382 | 2383 | 30429.99 | 3165177.08 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 760 | 10000 | 3175177.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3175177.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3175177.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3175177.08 | 2675176 | 500001.08 | -864307 | 2310870.08 | 0 | 0 | 700000 | 0 | 0 | 3010870.08
2875 | T03.20 | D&W-General Advice | 458319 | 10020 | 38691 | 19737 | 13146 | 15000 | 18300 | 8635 | 23080 | -7988 | 4000 | -615 | 21334 | 163340 | 621659 | 2800 | 2428 | 2000 | 3000 | 2500 | 1500 | 2700 | 1500 | 3375 | 500 | 4000 | 3375 | 3375 | 33053 | 654712 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 4077 | 41000.0769 | 695712.0769 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 40000 | 735712.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 735712.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 735712.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 735712.0769 | 735087 | 625.0769 |  | 735712.0769 | [5 empty] | 735712.0769
2876 | T03.21 | D&W-TRO's | 0 | 9765 | 22653 | 885 | 5657 | 7000 | 9124 | 14888 | 29535 | -14377 | 14000 | 7568 | 29156 | 135854 | 135854 | 3070 | 33430 | 41564.429 | 36161.1712 | 7000 | 32000 | 16500 | 25000 | 32200 | 8000 | -125188 | 32200 | 32200 | 174137.6003 | 309991.6003 | 21277.1089 | 18477.1089 | 31747.1089 | 31747.1089 | 31747.1089 | 31747.1089 | 31747.1089 | 31747.1089 | 31747.1089 | 31747.1089 | 31747.1089 | 31747.1089 | 31747.1089 | 388972.4159 | 698964.0162 | 18131.5834 | 18131.5834 | 18139.5834 | 4861.5834 | 4861.5834 | 4861.5834 | 4861.5834 | 4861.5834 | 4861.5834 | 4861.5834 | 4861.5834 | 4861.5833 | 4861.5833 | 103018.5839 | 801982.6001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801982.6001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801982.6001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801982.6001 | 801983 | -0.39989 |  | 801982.6001 | [5 empty] | 801982.6001
2877 | T03.22 | D&W-Property | 0 | 10270 | 18534 | 18970 | 18787 | 29000 | 20723 | 71785 | 66283 | 28864 | 49000 | 32052 | 40184 | 404452 | 404452 | 15800 | 15620 | 10000 | 15000 | 15000 | 20000 | 37000 | 30000 | 45000 | 16500 | 28000 | 45000 | 45000 | 337920 | 742372 | 10720.5385 | 10720.5385 | 10720.5385 | 10720.5385 | 10720.5385 | 10720.5385 | 10720.5385 | 10720.5385 | 10720.5385 | 10720.5385 | 10720.5385 | 10720.5385 | 10720.5385 | 139367 | 881739 | 4400 | 4400 | 4400 | 4400 | 4400 | 4400 | 4400 | 4400 | 4400 | 4400 | 4400 | 4400 | 4400 | 57200 | 938939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 938939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 938939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 938939 | 997789 | -58850 |  | 938939 | [5 empty] | 938939
2878 | T03.23 | D&W-Planning Monitoring | 0 | 7266 | 5838 | 906 | 5226 | 9000 | 13896 | 8488 | 16060 | -3134 | 11000 | 7282 | 11454 | 93282 | 93282 | 9600 | 2860 | 12000 | 6000 | 3000 | 2000 | 6100 | 10000 | 4475 | 5000 | 4475 | 4475 | 4475 | 74460 | 167742 | 5760 | 5760 | 5760 | 5760 | 5760 | 5760 | 5760 | 5760 | 5760 | 5760 | 5760 | 5760 | 5760 | 74880 | 242622 | 3840 | 3840 | 3840 | 3840 | 3840 | 3840 | 3840 | 3840 | 3840 | 3840 | 3840 | 3840 | 3840 | 49920 | 292542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292542 | 292542 | 0 |  | 292542 | [5 empty] | 292542
2879 | T03.24 | D&W-TDWG | 0 | 11496 | 6814 | 4578 | 9430 | 11000 | 1038 | 3098 | 4772 | 6680 | 6000 | 5368 | 2196 | 72470 | 72470 | 0 | 8890 | 3500 | 1000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15390 | 87860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87860 | 87860 | 0 |  | 87860 | [5 empty] | 87860
2880 | T03.25 | D&W -Public Realm | 0 | 0 | 10296 | -10296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2881 | T03.26 | D&W-Litigation | 0 | 0 | 0 | 220 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2882 | T03.27 | D&W-Secondments | 0 | 41465 | 41956 | 23531 | 30798 | 14400 | 0 | 0 | 0 | 0 | 0 | 0 | -27 | 152123 | 152123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152123 | 152123 | 0 |  | 152123 | [5 empty] | 152123
2883 | T03.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2884 | T03.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2885 | T03.30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2886 | T03.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2887 | T03.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2888 | T03.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2889 | T03.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2890 | T03.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2891 | T03.20-35 | Subtotal D&W | 458319 | 90282 | 144782 | 58531 | 83084 | 85400 | 63081 | 106894 | 139730 | 10045 | 84000 | 51655 | 104037 | 1021521 | 1479840 | 31270 | 63228 | 69064.429 | 61161.1712 | 29500 | 55500 | 62300 | 66500 | 85050 | 30000 | -88713 | 85050 | 85050 | 634960.6003 | 2114800.6003 | 40834.5705 | 38034.5705 | 51304.5705 | 51304.5705 | 51304.5705 | 51304.5705 | 51304.5705 | 51304.5705 | 51304.5705 | 51304.5705 | 51304.5705 | 51304.5705 | 52304.6474 | 644219.4929 | 2759020.0931 | 29448.5065 | 29448.5065 | 29456.5065 | 16178.5065 | 16178.5065 | 16178.5065 | 16178.5065 | 16178.5065 | 16178.5065 | 16178.5065 | 16178.5065 | 16178.5064 | 16178.5064 | 250138.5839 | 3009158.677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3009158.677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3009158.677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3009158.677 | 3067384 | -58225.323 | 0 | 3009158.677 | 0 | 0 | 0 | 0 | 0 | 3009158.677
2892 | T03.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
2893 | T03.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
2894 | T03.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
2895 | T03.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
2896 | T03.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
2897 | T03.40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
2898 | T03.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
2899 | T03.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
2900 | T03.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
2901 | T03.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
2902 | T03.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
2903 | T03.35-45 | Subtotal Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
2904 | T03 | Total LEGALS | 1296312.76 | 205982 | 242955 | 150677 | 216997 | 176900 | 189736 | 213894 | 221754 | 84045 | 104284 | 161655 | 149522 | 2118401 | 3414713.76 | 134825 | 85269.87 | 119164.059 | 95028.5112 | 67716.6 | 81000 | 75300 | 85086 | 344156.83 | 74600.27 | -50825.21 | 350650 | 372862 | 1834833.9303 | 5249547.6903 | 43144.1005 | 40362.3305 | 53640.4805 | 53637.1805 | 53634.0205 | 53640.3105 | 53644.0205 | 53642.4505 | 53649.3005 | 53638.9205 | 53642.1505 | 53686.5705 | 54687.6474 | 674649.4829 | 5924197.1731 | 30218.5065 | 30218.5065 | 30226.5065 | 16948.5065 | 16948.5065 | 16948.5065 | 16948.5065 | 16948.5065 | 16948.5065 | 16948.5065 | 16948.5065 | 16948.5064 | 16938.5064 | 260138.5839 | 6184335.757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6184335.757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6184335.757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6184335.757 | 5742560 | 441775.757 | -864307 | 5320028.757 | 0 | 0 | 700000 | 0 | 0 | 6020028.757
2968 | T07.01 | Consultancies | 20521.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10583 | 10583 | 31104.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10583 | 0 | 0 | -10583 | 20521.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20521.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20521.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20521.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20521.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20521.46 | 31104 | -10582.54 |  | 20521.46 | [5 empty] | 20521.46
2969 | T07.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2970 | T07.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2971 | T07.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2972 | T07.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2973 | T07.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2974 | T07.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2975 | T07.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2976 | T07.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2977 | T07.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2978 | T07 | Total UTILITIES | 20521.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10583 | 10583 | 31104.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10583 | 0 | 0 | -10583 | 20521.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20521.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20521.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20521.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20521.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20521.46 | 31104 | -10582.54 | 0 | 20521.46 | 0 | 0 | 0 | 0 | 0 | 20521.46
2980 | T08.01 | Tech. Advisors-Parl.Support | 268642.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268642.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268642.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268642.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268642.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268642.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268642.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268642.76 | 268643 | -0.24 |  | 268642.76 | [5 empty] | 268642.76
2981 | T08.02 | Tech. Advisors-Parl.Support-PM | 29382.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29382.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29382.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29382.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29382.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29382.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29382.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29382.99 | 29383 | -0.01 |  | 29382.99 | [5 empty] | 29382.99
2982 | T08.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2983 | T08.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2984 | T08.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2985 | T08.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2986 | T08.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2987 | T08.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2988 | T08.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2989 | T08.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2990 | T08 | Total DESIGN SUPPORT | 298025.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298025.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298025.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298025.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298025.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298025.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298025.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298025.75 | 298026 | -0.25 | 0 | 298025.75 | 0 | 0 | 0 | 0 | 0 | 298025.75
3138 | T14.01 | Operator Consultancy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3139 | T14.02 | Financial Consultancy | 53727 | 30000 | 20000 | 7196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | 70196 | 123923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13500 | 24520 | 0 | 0 | 38020 | 161943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161943 | 157423 | 4520 |  | 161943 | [5 empty] | 161943
3140 | T14.03 | WP1 modelling (FM) | 39646.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22462 | -22462 | 17184.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17184.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17184.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17184.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17184.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17184.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17184.03 | 17184 | 0.03 |  | 17184.03 | [5 empty] | 17184.03
3141 | T14.04 | WP2 modelling (MVA) | 10496.61 | 0 | 0 | 651.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 651.78 | 11148.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148.39 | 11148 | 0.39 |  | 11148.39 | [5 empty] | 11148.39
3142 | T14.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3143 | T14.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3144 | T14.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3145 | T14.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3146 | T14.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3147 | T14.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3148 | T14 | Total SERVICE INTEGRATION | 103869.64 | 30000 | 20000 | 7847.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9462 | 48385.78 | 152255.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13500 | 24520 | 0 | 0 | 38020 | 190275.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190275.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190275.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190275.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190275.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190275.42 | 185755 | 4520.42 | 0 | 190275.42 | 0 | 0 | 0 | 0 | 0 | 190275.42
3150 | T15.01 | INFRACO (PUK) | 73279.05 | 6000 | 6000 | 14229 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 10229 | 84458 | 157737.05 | 8020 | 5101 | 6222 | 8248.46 | 7268.61 | 5732.18 | 7691.34 | 26881 | 8410 | 10000 | 3609 | 10000 | 0 | 107183.59 | 264920.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264920.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264920.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264920.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264920.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264920.64 | 251312 | 13608.64 |  | 264920.64 | [5 empty] | 264920.64
3151 | T15.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3152 | T15.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3153 | T15.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3154 | T15.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3155 | T15.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3156 | T15.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3157 | T15.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3158 | T15.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3159 | T15.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3160 | T15 | Total PUK | 73279.05 | 6000 | 6000 | 14229 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 10229 | 84458 | 157737.05 | 8020 | 5101 | 6222 | 8248.46 | 7268.61 | 5732.18 | 7691.34 | 26881 | 8410 | 10000 | 3609 | 10000 | 0 | 107183.59 | 264920.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264920.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264920.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264920.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264920.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264920.64 | 251312 | 13608.64 | 0 | 264920.64 | 0 | 0 | 0 | 0 | 0 | 264920.64
3162 | T16.01 | Financial advisor 05/06 | 244340 | 0 | 20000 | 18246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2700 | 40946 | 285286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285286 | 285286 | 0 |  | 285286 | [5 empty] | 285286
3163 | T16.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3164 | T16.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3165 | T16.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3166 | T16.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3167 | T16.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3168 | T16.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3169 | T16.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3170 | T16.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3171 | T16.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3172 | T16 | Total FINANCIAL ADVISOR | 244340 | 0 | 20000 | 18246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2700 | 40946 | 285286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285286 | 285286 | 0 | 0 | 285286 | 0 | 0 | 0 | 0 | 0 | 285286
| TT02 | Total other resources | 2036348.66 | 241982 | 288955 | 190999.78 | 222997 | 182900 | 195736 | 219894 | 227754 | 90045 | 110284 | 167655 | 163572 | 2302773.78 | 4339122.44 | 142845 | 90370.87 | 125386.059 | 103276.9712 | 74985.21 | 86732.18 | 82991.34 | 111967 | 352566.83 | 98100.27 | -33279.21 | 360650 | 372862 | 1969454.5203 | 6308576.9603 | 43144.1005 | 40362.3305 | 53640.4805 | 53637.1805 | 53634.0205 | 53640.3105 | 53644.0205 | 53642.4505 | 53649.3005 | 53638.9205 | 53642.1505 | 53686.5705 | 54687.6474 | 674649.4829 | 6983226.4431 | 30218.5065 | 30218.5065 | 30226.5065 | 16948.5065 | 16948.5065 | 16948.5065 | 16948.5065 | 16948.5065 | 16948.5065 | 16948.5065 | 16948.5065 | 16948.5064 | 16938.5064 | 260138.5839 | 7243365.027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7243365.027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7243365.027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7243365.027 | 6794043 | 449322.027 | -864307 | 6379058.027 | 0 | 0 | 700000 | 0 | 0 | 7079058.027
2906 | T04.01 | Design Services under SDS | 3110000 | 305000 | 1214000 | 1784000 | 779659 | 713873 | 930275 | 861209 | 913968 | 825000 | 850000 | 1559832 | -2180864.75 | 8555951.25 | 11665951.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11665951.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11665951.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11665951.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11665951.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11665951.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11665951.25 | 11665951.25 | 0 |  | 11665951.25 | [5 empty] | 11665951.25
2907 | T04.01.01 | Overall Value Main Works ( Unallocated ) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 393551 | 393551 | 380997 | 258554 | 135000 | -362500 | -679385 | 194459 | 89250 | 89250 | 173000 | 173000 | 581847 | 1820574 | 1820574 | -326192.3764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20345 | 23000 | 24000 | -258847.3764 | 1561726.6236 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 24000 | 300000 | 1861726.6236 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 24000 | 300000 | 2161726.6236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2161726.6236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2161726.6236 | 4086727 | -1925000.3764 |  | 2161726.6236 | [5 empty] | 2161726.6236
2908 | T04.01.02 | Section 1 Newhaven Road to Haymarket | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1252075.1604 | 1252075.1604 | 1252075.1604 | 277184.6522 | 395860.2963 | 380584.3158 | 333729.7147 | -1048668.7944 | 117668.8251 | 465253.9596 | 123170.1509 | -63684.2757 | 318991.8727 | 46488.1541 | 12131.0656 | 18005.0553 | 1376714.9923 | 2628790.1526 | 280898.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280898.01 | 2909688.1626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2909688.1626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2909688.1626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2909688.1626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2909688.1626 | 2909688.1626 | 0 |  | 2909688.1626 | [5 empty] | 2909688.1626
2909 | T04.01.03 | Section 2 Haymarket Corridor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175977.52 | 175977.52 | 175977.52 | 26293.3439 | 34464.2022 | 3286.9085 | 1401.7698 | -3310.1244 | -27935.3059 | 30912 | 0 | -2831.6369 | -1543.6953 | 4875.1005 | 1455.8257 | 747.0684 | 67815.4565 | 243792.9765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243792.9765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243792.9765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243792.9765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243792.9765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243792.9765 | 243792.9765 | 0 |  | 243792.9765 | [5 empty] | 243792.9765
2910 | T04.01.03 | Section 3 Haymarket to Granton Sq | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 907113.5614 | 907113.5614 | 907113.5614 | 772065.4714 | 244489.5581 | 137448.0914 | 81396.1404 | -7952.927 | -4682.3256 | -10607.3502 | -39138.9974 | -119949.67 | 159959.4647 | 42921.8501 | 9203 | 0 | 1265152.3058 | 2172265.8672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172265.8672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172265.8672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172265.8672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172265.8672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172265.8672 | 2172265.8672 | 0 |  | 2172265.8672 | [5 empty] | 2172265.8672
2911 | T04.01.04 | Section 3 1B deduction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1000000 | -1000000 | -1000000 | -354446 | -253486 | -191799 | -42171 | -16853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -858755 | -1858755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1858755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1858755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1858755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1858755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1858755 | -1858755 | 0 |  | -1858755 | [5 empty] | -1858755
2912 | T04.01.05 | Section 4 Granton Sq to Newhaven Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0
2913 | T04.01.06 | Section 5 Roseburn Junction to Gogar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 628551.6837 | 628551.6837 | 628551.6837 | 299507.205 | 193351.8763 | 202156.5343 | 75318.3259 | -206598.7164 | 299.4414 | 80699.9635 | 13804.4925 | -79999.3095 | 140489.358 | 56856.0333 | 42312.3793 | 6857.9098 | 825055.4933 | 1453607.1771 | 1237.173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1237.173 | 1454844.3501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1454844.3501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1454844.3501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1454844.3501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1454844.3501 | 1454844.3501 | 0 |  | 1454844.3501 | [5 empty] | 1454844.3501
2914 | T04.01.07 | Section 6 Gogar Depot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94842.259 | 94842.259 | 94842.259 | 40323.1094 | 53412.6166 | 26288.8118 | 44847.2046 | 4267.2644 | 8969.3495 | 17745 | 0 | -9530.7 | 19276.8335 | 20233.0793 | 7219 | 887.6154 | 233939.1845 | 328781.4435 | 1684.1933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1684.1933 | 330465.6368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330465.6368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330465.6368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330465.6368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330465.6368 | 330465.6368 | 0 |  | 330465.6368 | [5 empty] | 330465.6368
2915 | T04.01.08 | Section 7 Gogar to Edinburgh Airport | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224954.2006 | 224954.2006 | 224954.2006 | 137615.2978 | 46400.6534 | 54665.7698 | 8845.1246 | -48894.0475 | 28031.1228 | -8577.488 | -17065.1438 | -63273.8236 | -22147.7624 | 24365.1661 | 45978.7106 | 32309.3642 | 218252.944 | 443207.1446 | 42373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42373 | 485580.1446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485580.1446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485580.1446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485580.1446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485580.1446 | 485580.1446 | 0 |  | 485580.1446 | [5 empty] | 485580.1446
2916 | T04.01.09 | Section 8 Ingliston West / Newbridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0
2917 | T04.01.10 | MUDFA / Utilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348021.3636 | 348021.3636 | 348021.3636 | 68110.4591 | 36716.3996 | 25116.5767 | 37321.1992 | 24207.5764 | 13131.6601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204603.8711 | 552625.2348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552625.2348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552625.2348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552625.2348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552625.2348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552625.2348 | 552625.2348 | 0 |  | 552625.2348 | [5 empty] | 552625.2348
2918 | T04.01.11 | Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1925000 | 1925000 | 1925000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1925000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1925000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1925000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1925000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1925000 |  | 1925000 |  | 1925000 |  |  | 500000 |  |  | 2425000
2919 | T04.01.12 | Variations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2920 | T04.01.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2921 | T04.01.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2922 | T04.01.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2923 | T04.01.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2924 | T04.01.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2925 | T04.01.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2926 | T04.01.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2927 | T04.01.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2928 | T04.02 | Site Investigation under SDS | 190000 | 145000 | 210000 | 90000 | 105000 | 200000 | 210000 | 200000 | 40000 | 25000 | 0 | 0 | 0 | 1225000 | 1415000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1415000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1415000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1415000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 75000 | 225000 | 1640000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1640000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1640000 | 1640000 | 0 |  | 1640000 | [5 empty] | 1640000
2929 | T04.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2930 | T04.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2931 | T04.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2932 | T04.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2933 | T04.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2934 | T04.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2935 | T04.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2936 | T04.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2937 | T04 | Total SDS | 3300000 | 450000 | 1424000 | 1874000 | 884659 | 913873 | 1140275 | 1061209 | 953968 | 850000 | 850000 | 1559832 | 450670.9987 | 12412486.9987 | 15712486.9987 | 1660204.5388 | 1144760.6024 | 1018745.0083 | 799242.479 | -1168802.7687 | -227017.2327 | -103958.915 | 275229.5022 | -250019.4157 | 704276.0711 | 368739.3836 | 291299.9812 | 2565654.0132 | 7078353.2476 | 22790840.2463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20345 | 23000 | 24000 | 67345 | 22858185.2463 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 24000 | 300000 | 23158185.2463 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 98000 | 98000 | 99000 | 525000 | 23683185.2463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23683185.2463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23683185.2463 | 23683185.6227 | -0.37637 | 0 | 23683185.2463 | 0 | 0 | 500000 | 0 | 0 | 24183185.2463
0
| TT03 | Total design | 3300000 | 450000 | 1424000 | 1874000 | 884659 | 913873 | 1140275 | 1061209 | 953968 | 850000 | 850000 | 1559832 | 450670.9987 | 12412486.9987 | 15712486.9987 | 1660204.5388 | 1144760.6024 | 1018745.0083 | 799242.479 | -1168802.7687 | -227017.2327 | -103958.915 | 275229.5022 | -250019.4157 | 704276.0711 | 368739.3836 | 291299.9812 | 2565654.0132 | 7078353.2476 | 22790840.2463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20345 | 23000 | 24000 | 67345 | 22858185.2463 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 24000 | 300000 | 23158185.2463 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 98000 | 98000 | 99000 | 525000 | 23683185.2463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23683185.2463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23683185.2463 | 23683185.6227 | -0.37637 | 0 | 23683185.2463 | 0 | 0 | 500000 | 0 | 0 | 24183185.2463
2939 | T05.01 | Integrated Transport Model | 365000 | 55000 | 42000 | 14614 | 86000 | 55000 | 140000 | 180000 | 8000 | 134156 | 97000 | 105000 | 29000 | 945770 | 1310770 | 55000 | 15000 | 47000 | 44000 | 58000 | 28000 | 27000 | 29439.315 | 35000 | 35000 | -3373 | 46538.8425 | 46538.8425 | 463144 | 1773914 | 29500 | 29500 | 9407 | 9407 | 9407 | 9407 | 9407 | 9407 | 9407 | 9407 | 9407 | 9407 | 9413 | 162483 | 1936397 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2316 | 30000 | 1966397 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2316 | 30000 | 1996397 | 4285 | 4285 | 4285 | 4285 | 4285 | 4285 | 4290 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 150000 | 2146397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2146397 | 2082770 | 63627 |  | 2146397 | [5 empty] | 2146397
2940 | T05.02 | Surveys (MM) | 147195.78 | 3000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4607 | 18393 | 165588.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165588.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165588.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165588.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165588.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165588.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165588.78 | 165589 | -0.22 |  | 165588.78 | [5 empty] | 165588.78
2941 | T05.03 | Consultancy (Halcrow) | 9916.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9916.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9916.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9916.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9916.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9916.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9916.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9916.21 | 9916 | 0.21 |  | 9916.21 | [5 empty] | 9916.21
2942 | T05.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2943 | T05.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2944 | T05.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2945 | T05.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2946 | T05.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2947 | T05.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2948 | T05.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2949 | T05 | Total JRC | 522111.99 | 58000 | 52000 | 24614 | 86000 | 55000 | 140000 | 180000 | 8000 | 134156 | 97000 | 105000 | 24393 | 964163 | 1486274.99 | 55000 | 15000 | 47000 | 44000 | 58000 | 28000 | 27000 | 29439.315 | 35000 | 35000 | -3373 | 46538.8425 | 46538.8425 | 463144 | 1949418.99 | 29500 | 29500 | 9407 | 9407 | 9407 | 9407 | 9407 | 9407 | 9407 | 9407 | 9407 | 9407 | 9413 | 162483 | 2111901.99 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2316 | 30000 | 2141901.99 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2316 | 30000 | 2171901.99 | 4285 | 4285 | 4285 | 4285 | 4285 | 4285 | 4290 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 150000 | 2321901.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2321901.99 | 2258275 | 63626.99 | 0 | 2321901.99 | 0 | 0 | 0 | 0 | 0 | 2321901.99
0
3042 | T11.01 | Legal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3043 | T11.02 | TRO's - Technnical | 1312.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.95 | 1313 | -0.05 |  | 1312.95 | [5 empty] | 1312.95
3044 | T11.03 | Other TRO codes??? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3045 | T11.04 | Other TRO codes??? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3046 | T11.05 | Other TRO codes??? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3047 | T11.06 | Other TRO codes??? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3048 | T11.07 | Other TRO codes??? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3049 | T11.08 | Other TRO codes??? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3050 | T11.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3051 | T11.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3052 | T11.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3053 | T11.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3054 | T11.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3055 | T11.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3056 | T11.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3057 | T11.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3058 | T11.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3059 | T11.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3060 | T11.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3061 | T11.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3062 | T11 | Total TROs | 1312.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.95 | 1313 | -0.05 | 0 | 1312.95 | 0 | 0 | 0 | 0 | 0 | 1312.95
0
| TT04 | Total traffic management and modelling | 523424.94 | 58000 | 52000 | 24614 | 86000 | 55000 | 140000 | 180000 | 8000 | 134156 | 97000 | 105000 | 24393 | 964163 | 1487587.94 | 55000 | 15000 | 47000 | 44000 | 58000 | 28000 | 27000 | 29439.315 | 35000 | 35000 | -3373 | 46538.8425 | 46538.8425 | 463144 | 1950731.94 | 29500 | 29500 | 9407 | 9407 | 9407 | 9407 | 9407 | 9407 | 9407 | 9407 | 9407 | 9407 | 9413 | 162483 | 2113214.94 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2316 | 30000 | 2143214.94 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2307 | 2316 | 30000 | 2173214.94 | 4285 | 4285 | 4285 | 4285 | 4285 | 4285 | 4290 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 150000 | 2323214.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2323214.94 | 2259588 | 63626.94 | 0 | 2323214.94 | 0 | 0 | 0 | 0 | 0 | 2323214.94
2992 | T09.01 | Network Rail Legal Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2993 | T09.01.01 | Network Rail (PM) | 0 | 0 | 0 | 22519 | 30000 | 15000 | 0 | 20000 | 20000 | 5756 | 15000 | 10000 | 10000 | 148275 | 148275 | 33626.13 | 0 | 38878.4 | 10968.18 | 0 | 14921 | 0 | 0 | 6342 | 0 | 0 | 18284 | 18284 | 141303.71 | 289578.71 | 11597 | 7988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19585 | 309163.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 309163.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 309163.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 309163.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 309163.71 | 309164 | -0.29 |  | 309163.71 | [5 empty] | 309163.71
2994 | T09.01.02 | Network Rail (Legal) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | -10000 | 0 | 0 | 7500 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | 0 |  | 7500 | [5 empty] | 7500
2995 | T09.02 | BAA legal costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2996 | T09.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2997 | T09.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2998 | T09.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
2999 | T09.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3000 | T09.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3001 | T09.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3002 | T09.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3003 | T09.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3004 | T09 | Total 3RD PARTY NEGOTIATIONS | 0 | 0 | 0 | 22519 | 30000 | 15000 | 0 | 30000 | 20000 | -4244 | 15000 | 10000 | 17500 | 155775 | 155775 | 33626.13 | 0 | 38878.4 | 10968.18 | 0 | 14921 | 0 | 0 | 6342 | 0 | 0 | 18284 | 18284 | 141303.71 | 297078.71 | 11597 | 7988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19585 | 316663.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316663.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316663.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316663.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316663.71 | 316664 | -0.29 | 0 | 316663.71 | 0 | 0 | 0 | 0 | 0 | 316663.71
| TT05 | Total 3rd party interfaces | 0 | 0 | 0 | 22519 | 30000 | 15000 | 0 | 30000 | 20000 | -4244 | 15000 | 10000 | 17500 | 155775 | 155775 | 33626.13 | 0 | 38878.4 | 10968.18 | 0 | 14921 | 0 | 0 | 6342 | 0 | 0 | 18284 | 18284 | 141303.71 | 297078.71 | 11597 | 7988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19585 | 316663.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316663.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316663.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316663.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316663.71 | 316664 | -0.29 | 0 | 316663.71 | 0 | 0 | 0 | 0 | 0 | 316663.71
3006 | T10.01 | D&W (10.01 &11.01) | 25843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25843 | 25843 | 0 |  | 25843 | [5 empty] | 25843
3007 | T10.02 | Advisors (Colliers / DV) | 35624 | 2085 | 5000 | -1260 | 265 | 6000 | 6000 | -6500 | 5000 | -3125 | 2000 | 3330 | 4100 | 22895 | 58519 | 9149 | 4101 | 8750 | 4500 | 6650 | 10150 | 9490 | 6470 | 6650 | 8850 | -846 | 4000 | 4056 | 81970 | 140489 | 6205.93 | 4404.23 | 4492.94 | 4459.74 | 4426.71 | 4495.22 | 3479.46 | 1804.51 | 1834.3 | 1789.42 | 1805.55 | 1999 | 1999 | 43196.01 | 183685.01 | 1603.33 | 1748.15 | 1779.18 | 1769.53 | 1754.97 | 1780.04 | 1799.03 | 787.81 | 821.58 | 774.26 | 790.19 | 975.15 | 1052.79 | 17436.01 | 201121.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 201121.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 201121.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 201121.02 | 201121 | 0.02 |  | 201121.02 | [5 empty] | 201121.02
3008 | T10.03 | Technical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3009 | T10.04 | Advance Purchases 05/06 (Fees) | 60181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60181 | 60181 | 0 |  | 60181 | [5 empty] | 60181
3010 | T10.05.01 | Advance Purchases (GVD) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9076400 | -743923 | -1535149 | 0 | 0 | 0 | 1633944 | 0 | 1679546 | 1785000 | 0 | 0 | 0 | 11895818 | 11895818 | 1760000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1760000 | 13655818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13655818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13655818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13655818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13655818 | 13655818 | 0 |  | 13655818 | [5 empty] | 13655818
3011 | T10.05.02 | Advance Purchases (gifted / free issue) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319935 | -27279 | 1785000 | 4512025 | -140163 | -473180 | 0 | 0 | 0 | -1785000 | 0 | 0 | 508989 | 4700327 | 4700327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4700327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4700327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4700327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4700327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4700327 | 4700327 | 0 |  | 4700327 | [5 empty] | 4700327
3012 | T10.05.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3013 | T10.05.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3014 | T10.05.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3015 | T10.05.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3016 | T10.05.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3017 | T10.05.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3018 | T10.05.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3019 | T10.05.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3020 | T10.01-.05 | Subtotal Land | 121648 | 2085 | 5000 | -1260 | 265 | 6000 | 6000 | -6500 | 5000 | -3125 | 2000 | 3330 | 4100 | 22895 | 144543 | 9405484 | -767101 | 258601 | 4516525 | -133513 | -463030 | 1643434 | 6470 | 1686196 | 8850 | -846 | 4000 | 513045 | 16678115 | 16822658 | 1766205.93 | 4404.23 | 4492.94 | 4459.74 | 4426.71 | 4495.22 | 3479.46 | 1804.51 | 1834.3 | 1789.42 | 1805.55 | 1999 | 1999 | 1803196.01 | 18625854.01 | 1603.33 | 1748.15 | 1779.18 | 1769.53 | 1754.97 | 1780.04 | 1799.03 | 787.81 | 821.58 | 774.26 | 790.19 | 975.15 | 1052.79 | 17436.01 | 18643290.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18643290.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18643290.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18643290.02 | 18643290 | 0.02 | 0 | 18643290.02 | 0 | 0 | 0 | 0 | 0 | 18643290.02
3021 | T10.06.01 | Business Compo Primary payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 88000 | 88000 | -74000 | -25000 | 20000 | 50000 | 50000 | 213000 | 213000 | 107769 | 107769 | 107769 | 107769 | 107769 | 107769 | 107769 | 107769 | 107769 | 107769 | 107769 | 107769 | 93772 | 1387000 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 1600000 | 0 |  | 1600000 | [5 empty] | 1600000
3022 | T10.06.02 | Business Compo Enhanced payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 350000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 350000 | 0 |  | 350000 | [5 empty] | 350000
3023 | T10.06.03 | Business Compo Admin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 2000 | 2000 | 1230 | 1846 | 1846 | 1846 | 1846 | 16614 | 16614 | 1846 | 1846 | 1846 | 1846 | 1846 | 1846 | 1846 | 1846 | 1846 | 1846 | 1846 | 1846 | 1846 | 23998 | 40612 | 1846 | 1846 | 1846 | 1846 | 2004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9388 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 0 |  | 50000 | [5 empty] | 50000
3024 | T10.06.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3025 | T10.06.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3026 | T10.06.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3027 | T10.06.07 | Sundry costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3028 | T10.06.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3029 | T10.06.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3030 | T10.06.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3031 | T10.06 | Subtotal Business Compensation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 18000 | 90000 | 90000 | -72770 | -23154 | 21846 | 51846 | 51846 | 229614 | 229614 | 109615 | 109615 | 109615 | 109615 | 109615 | 109615 | 109615 | 109615 | 109615 | 109615 | 109615 | 459615 | 95618 | 1760998 | 1990612 | 1846 | 1846 | 1846 | 1846 | 2004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9388 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 2000000
3032 | T10.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3033 | T10.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3034 | T10.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3035 | T10.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3036 | T10.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3037 | T10.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3038 | T10.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3039 | T10.07-13 | Subtotal Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3040 | T10 | Total LAND & PROPERTY | 121648 | 2085 | 5000 | -1260 | 265 | 6000 | 6000 | -6500 | 5000 | -3125 | 2000 | 3330 | 4100 | 22895 | 144543 | 9405484 | -767101 | 258601 | 4518525 | -133513 | -445030 | 1733434 | 96470 | 1613426 | -14304 | 21000 | 55846 | 564891 | 16907729 | 17052272 | 1875820.93 | 114019.23 | 114107.94 | 114074.74 | 114041.71 | 114110.22 | 113094.46 | 111419.51 | 111449.3 | 111404.42 | 111420.55 | 461614 | 97617 | 3564194.01 | 20616466.01 | 3449.33 | 3594.15 | 3625.18 | 3615.53 | 3758.97 | 1780.04 | 1799.03 | 787.81 | 821.58 | 774.26 | 790.19 | 975.15 | 1052.79 | 26824.01 | 20643290.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20643290.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20643290.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20643290.02 | 20643290 | 0.02 | 0 | 20643290.02 | 0 | 0 | 0 | 0 | 0 | 20643290.02
3041 | [107 empty] | 0
| TT06 | Total land and other compensation claims | 121648 | 2085 | 5000 | -1260 | 265 | 6000 | 6000 | -6500 | 5000 | -3125 | 2000 | 3330 | 4100 | 22895 | 144543 | 9405484 | -767101 | 258601 | 4518525 | -133513 | -445030 | 1733434 | 96470 | 1613426 | -14304 | 21000 | 55846 | 564891 | 16907729 | 17052272 | 1875820.93 | 114019.23 | 114107.94 | 114074.74 | 114041.71 | 114110.22 | 113094.46 | 111419.51 | 111449.3 | 111404.42 | 111420.55 | 461614 | 97617 | 3564194.01 | 20616466.01 | 3449.33 | 3594.15 | 3625.18 | 3615.53 | 3758.97 | 1780.04 | 1799.03 | 787.81 | 821.58 | 774.26 | 790.19 | 975.15 | 1052.79 | 26824.01 | 20643290.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20643290.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20643290.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20643290.02 | 20643290 | 0.02 | 0 | 20643290.02 | 0 | 0 | 0 | 0 | 0 | 20643290.02
3174 | T17.01 | Insurance consultancy | 36123 | 1700 | 1700 | 5757 | 3000 | 8540 | 4000 | 4500 | 8281 | 6000 | 6000 | 6000 | 8813 | 64291 | 100414 | 2500 | 3857.53 | 5000 | 6930 | 6090 | 3000 | 53676.43 | -33175 | 6635.0711 | 6635.0711 | 6635.0711 | 6635.0711 | 6635.07 | 81054.3144 | 181468.3144 | 4986.3014 | 4986.3014 | 4986.3014 | 4986.3014 | 4986.3014 | 4986.3014 | 4986.3014 | 4986.3014 | 4986.3014 | 4986.3014 | 4986.3014 | 4986.3014 | 5164.3836 | 65000 | 246468.3144 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4767.1233 | 60000 | 306468.3144 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4767.1233 | 60000 | 366468.3144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 366468.3144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 366468.3144 | 366468 | 0.31436 |  | 366468.3144 | [5 empty] | 366468.3144
3175 | T17.02 | OCIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | -29000 | -10000 | -317724 | 11015.6992 | 21865.2535 | 76127.2 | 77104 | 102104 | 331492.1528 | 331492.1528 | 80711.4285 | 80711.4285 | 90711.4285 | 80711.4285 | 80269.4285 | 80235.4285 | 80235.4285 | 80235.4285 | 80235.4285 | 80235.4285 | 76859.6994 | 76859.6994 | 251859.699 | 1219871.3829 | 1551363.5356 | 76859.6994 | 76859.6994 | 76859.6994 | 76859.6994 | 76859.6994 | 76859.6994 | 76859.6994 | 91444.5753 | 106279.7401 | 106279.7401 | 106279.7401 | 106279.7401 | 231279.7401 | 1285861.172 | 2837224.7076 | 106279.7401 | 106279.7401 | 106279.7401 | 106279.7401 | 106156.8682 | 106046.9781 | 106046.9781 | 97805.2198 | 82970.055 | 82970.055 | 71659.8276 | 0 | 125000 | 1203774.9424 | 4040999.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 4140999.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4140999.65 | 4141000 | -0.34996 |  | 4140999.65 | [5 empty] | 4140999.65
3176 | T17.03 | OCIP deduction only INFRACO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3177 | T17.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3178 | T17.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3179 | T17.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3180 | T17.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3181 | T17.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3182 | T17.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3183 | T17.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3184 | T17 | Total INSURANCE | 36123 | 1700 | 1700 | 5757 | 3000 | 8540 | 4000 | 4500 | 8281 | 6000 | 6000 | 6000 | 8813 | 64291 | 100414 | 2500 | 3857.53 | 5000 | 6930 | 406090 | -26000 | 43676.43 | -350899 | 17650.7703 | 28500.3246 | 82762.2711 | 83739.0711 | 108739.07 | 412546.4671 | 512960.4671 | 85697.7299 | 85697.7299 | 95697.7299 | 85697.7299 | 85255.7299 | 85221.7299 | 85221.7299 | 85221.7299 | 85221.7299 | 85221.7299 | 81846.0008 | 81846.0008 | 257024.0826 | 1284871.3829 | 1797831.85 | 81462.4391 | 81462.4391 | 81462.4391 | 81462.4391 | 81462.4391 | 81462.4391 | 81462.4391 | 96047.315 | 110882.4799 | 110882.4799 | 110882.4799 | 110882.4799 | 236046.8634 | 1345861.172 | 3143693.022 | 110882.4799 | 110882.4799 | 110882.4799 | 110882.4799 | 110759.6079 | 110649.7178 | 110649.7178 | 102407.9596 | 87572.7947 | 87572.7947 | 76262.5673 | 4602.7397 | 129767.1233 | 1263774.9424 | 4407467.9644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 4507467.9644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4507467.9644 | 4507468 | -0.035601 | 0 | 4507467.9644 | 0 | 0 | 0 | 0 | 0 | 4507467.9644
| TT07 | Total Insurance | 36123 | 1700 | 1700 | 5757 | 3000 | 8540 | 4000 | 4500 | 8281 | 6000 | 6000 | 6000 | 8813 | 64291 | 100414 | 2500 | 3857.53 | 5000 | 6930 | 406090 | -26000 | 43676.43 | -350899 | 17650.7703 | 28500.3246 | 82762.2711 | 83739.0711 | 108739.07 | 412546.4671 | 512960.4671 | 85697.7299 | 85697.7299 | 95697.7299 | 85697.7299 | 85255.7299 | 85221.7299 | 85221.7299 | 85221.7299 | 85221.7299 | 85221.7299 | 81846.0008 | 81846.0008 | 257024.0826 | 1284871.3829 | 1797831.85 | 81462.4391 | 81462.4391 | 81462.4391 | 81462.4391 | 81462.4391 | 81462.4391 | 81462.4391 | 96047.315 | 110882.4799 | 110882.4799 | 110882.4799 | 110882.4799 | 236046.8634 | 1345861.172 | 3143693.022 | 110882.4799 | 110882.4799 | 110882.4799 | 110882.4799 | 110759.6079 | 110649.7178 | 110649.7178 | 102407.9596 | 87572.7947 | 87572.7947 | 76262.5673 | 4602.7397 | 129767.1233 | 1263774.9424 | 4407467.9644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 4507467.9644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4507467.9644 | 4507468 | -0.035601 | 0 | 4507467.9644 | 0 | 0 | 0 | 0 | 0 | 4507467.9644
0
3186 | T18.01.01 | Pre-construction Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3187 | T18.01.02 | Contract prelims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3188 | T18.01.03.01 | Section 1a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3189 | T18.01.03.02 | Section 1b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3190 | T18.01.03.03 | Section 1c | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3191 | T18.01.03.04 | Section 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3192 | T18.01.03.05 | Section 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3193 | T18.01.03.06 | Section 3a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3194 | T18.01.03.07 | Section 3b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3195 | T18.01.03.08 | Section 3c | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3196 | T18.01.03.09 | Section 4a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3197 | T18.01.03.10 | Section 4b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3198 | T18.01.03.11 | Section 5a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3199 | T18.01.03.12 | Section 5b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3200 | T18.01.03.13 | Section 5c | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3201 | T18.01.03.14 | Section 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3202 | T18.01.03.15 | Section 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3203 | T18.01.03.16 | Unallocated to section | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 210000 | 450000 | 83333 | 88333.3333 | 93333.3333 | 1024999.6667 | 1024999.6667 | 200000 | 200000 | 200000 | 1285166 | 2156081.05 | 2352615.8532 | 2259566.34 | -4089696.84 | 1905000 | 933508 | 1949250 | 1819236 | 1811957 | 12982683.4032 | 14007683.0699 | 3214747 | 3984117 | 4353727 | 2636046 | 1781541 | 2126180 | 1479004 | 1509915 | 1128264 | 712126 | 635445 | 468708 | 1710332 | 25740152 | 39747835.0699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39747835.0699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39747835.0699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39747835.0699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39747835.0699 | 39775122 | -27286.9301 | 27287 | 39775122.0699 | -3000000 |  |  |  |  | 36775122.0699
3204 | T18.01.03.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3205 | T18.01.03.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3206 | T18.01.03.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3207 | T18.01.03.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3208 | T18.01.03.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3209 | T18.01.03.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3210 | T18.01.03.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3211 | T18.01.03.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3212 | T18.01.03.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3213 | T18.01.03.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3214 | T18.01.03.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3215 | T18.01.03.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3216 | T18.01.03.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3217 | T18.01.03.30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3218 | T18.01.03 | Subtotal measured work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 210000 | 450000 | 83333 | 88333.3333 | 93333.3333 | 1024999.6667 | 1024999.6667 | 200000 | 200000 | 200000 | 1285166 | 2156081.05 | 2352615.8532 | 2259566.34 | -4089696.84 | 1905000 | 933508 | 1949250 | 1819236 | 1811957 | 12982683.4032 | 14007683.0699 | 3214747 | 3984117 | 4353727 | 2636046 | 1781541 | 2126180 | 1479004 | 1509915 | 1128264 | 712126 | 635445 | 468708 | 1710332 | 25740152 | 39747835.0699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39747835.0699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39747835.0699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39747835.0699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39747835.0699 | 39775122 | -27286.9301 | 27287 | 39775122.0699 | -3000000 | 0 | 0 | 0 | 0 | 36775122.0699
3219 | T18.01.04 | Variations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3220 | T18.01.05 | Reserve | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3221 | T18.01.06 | Claim(s) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3222 | T18.01.07 | Transfer to infraco | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 0 |  | 125000 | [5 empty] | 125000
3223 | T18.01.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3224 | T18.01.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3225 | T18.01.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3226 | T18.01.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3227 | T18.01.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3228 | T18.01.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3229 | T18.01.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3230 | T18.01.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3231 | T18.01.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3232 | T18.01.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3233 | T18.01.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3234 | T18.01.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3235 | T18.01.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3236 | T18.01 | Subtotal MUDFA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 210000 | 450000 | 83333 | 88333.3333 | 93333.3333 | 1024999.6667 | 1024999.6667 | 200000 | 200000 | 200000 | 1285166 | 2156081.05 | 2352615.8532 | 2259566.34 | -4089696.84 | 1905000 | 933508 | 1949250 | 1819236 | 1936957 | 13107683.4032 | 14132683.0699 | 3214747 | 3984117 | 4353727 | 2636046 | 1781541 | 2126180 | 1479004 | 1509915 | 1128264 | 712126 | 635445 | 468708 | 1710332 | 25740152 | 39872835.0699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39872835.0699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39872835.0699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39872835.0699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39872835.0699 | 39900122 | -27286.9301 | 27287 | 39900122.0699 | -3000000 | 0 | 0 | 0 | 0 | 36900122.0699
3237 | T18.02.01 | Pre-construction Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3238 | T18.02.02 | Contract prelims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3239 | T18.02.03.01 | Section 1a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3240 | T18.02.03.02 | Section 1b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3241 | T18.02.03.03 | Section 1c | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3242 | T18.02.03.04 | Section 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3243 | T18.02.03.05 | Section 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3244 | T18.02.03.06 | Section 3a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3245 | T18.02.03.07 | Section 3b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3246 | T18.02.03.08 | Section 3c | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3247 | T18.02.03.09 | Section 4a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3248 | T18.02.03.10 | Section 4b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3249 | T18.02.03.11 | Section 5a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3250 | T18.02.03.12 | Section 5b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3251 | T18.02.03.13 | Section 5c | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3252 | T18.02.03.14 | Section 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3253 | T18.02.03.15 | Section 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3254 | T18.02.03.16 | Unallocated to section | 21485 | 0 | 0 | 10350 | 100000 | 25000 | 0 | 30000 | 690665 | 51146 | 42750 | 55523 | 97750 | 1103184 | 1124669 | 0 | 0 | 73747 | 149000 | 749686.77 | 925481 | 870925 | -1677490 | 384805 | 93633 | 415566 | 342832 | 791520 | 3119705.77 | 4244374.77 | 801000 | 796500 | 695500 | 590419 | 890564 | 907136 | 539719 | 383080 | 358964 | 404125 | 425000 | 482465 | 108367 | 7382839 | 11627213.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11627213.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11627213.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11627213.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11627213.77 | 11627214 | -0.23 |  | 11627213.77 | [5 empty] | 11627213.77
3255 | T18.02.03.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3256 | T18.02.03.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3257 | T18.02.03.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3258 | T18.02.03.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3259 | T18.02.03.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3260 | T18.02.03.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3261 | T18.02.03.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3262 | T18.02.03.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3263 | T18.02.03.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3264 | T18.02.03.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3265 | T18.02.03.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3266 | T18.02.03.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3267 | T18.02.03.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3268 | T18.02.03.30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3269 | T18.02.03 | Subtotal measured work | 21485 | 0 | 0 | 10350 | 100000 | 25000 | 0 | 30000 | 690665 | 51146 | 42750 | 55523 | 97750 | 1103184 | 1124669 | 0 | 0 | 73747 | 149000 | 749686.77 | 925481 | 870925 | -1677490 | 384805 | 93633 | 415566 | 342832 | 791520 | 3119705.77 | 4244374.77 | 801000 | 796500 | 695500 | 590419 | 890564 | 907136 | 539719 | 383080 | 358964 | 404125 | 425000 | 482465 | 108367 | 7382839 | 11627213.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11627213.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11627213.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11627213.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11627213.77 | 11627214 | -0.23 | 0 | 11627213.77 | 0 | 0 | 0 | 0 | 0 | 11627213.77
3270 | T18.01.04 | Variations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3271 | T18.01.05 | Reserve | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3272 | T18.01.06 | Claim(s) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3273 | T18.01.07 | Transfer to infraco | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3274 | T18.01.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3275 | T18.01.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3276 | T18.01.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3277 | T18.01.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3278 | T18.01.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3279 | T18.01.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3280 | T18.01.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3281 | T18.01.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3282 | T18.01.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3283 | T18.01.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3284 | T18.01.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3285 | T18.01.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3286 | T18.01.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3287 | T18.02 | Subtotal utilities | 21485 | 0 | 0 | 10350 | 100000 | 25000 | 0 | 30000 | 690665 | 51146 | 42750 | 55523 | 97750 | 1103184 | 1124669 | 0 | 0 | 73747 | 149000 | 749686.77 | 925481 | 870925 | -1677490 | 384805 | 93633 | 415566 | 342832 | 791520 | 3119705.77 | 4244374.77 | 801000 | 796500 | 695500 | 590419 | 890564 | 907136 | 539719 | 383080 | 358964 | 404125 | 425000 | 482465 | 108367 | 7382839 | 11627213.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11627213.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11627213.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11627213.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11627213.77 | 11627214 | -0.23 | 0 | 11627213.77 | 0 | 0 | 0 | 0 | 0 | 11627213.77
3288 | T18.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3289 | T18.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3290 | T18.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3291 | T18.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3292 | T18.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3293 | T18.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3294 | T18.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3295 | T18.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3296 | T18.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3297 | T18.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3298 | T18.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3299 | T18.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3300 | T18.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3301 | T18.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3302 | T18.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3303 | T18.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3304 | T18.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3305 | T18.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3306 | T18.03-20 | Subtotal other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3307 | T18 | Total MUDFA / Utilities | 21485 | 0 | 0 | 10350 | 100000 | 25000 | 0 | 130000 | 900665 | 501146 | 126083 | 143856.3333 | 191083.3333 | 2128183.6667 | 2149668.6667 | 200000 | 200000 | 273747 | 1434166 | 2905767.82 | 3278096.8532 | 3130491.34 | -5767186.84 | 2289805 | 1027141 | 2364816 | 2162068 | 2728477 | 16227389.1732 | 18377057.8399 | 4015747 | 4780617 | 5049227 | 3226465 | 2672105 | 3033316 | 2018723 | 1892995 | 1487228 | 1116251 | 1060445 | 951173 | 1818699 | 33122991 | 51500048.8399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51500048.8399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51500048.8399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51500048.8399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51500048.8399 | 51527336 | -27287.1601 | 27287 | 51527335.8399 | -3000000 | 0 | 0 | 0 | 0 | 48527335.8399
| TT08 | Total MUDFA / Utilities | 21485 | 0 | 0 | 10350 | 100000 | 25000 | 0 | 130000 | 900665 | 501146 | 126083 | 143856.3333 | 191083.3333 | 2128183.6667 | 2149668.6667 | 200000 | 200000 | 273747 | 1434166 | 2905767.82 | 3278096.8532 | 3130491.34 | -5767186.84 | 2289805 | 1027141 | 2364816 | 2162068 | 2728477 | 16227389.1732 | 18377057.8399 | 4015747 | 4780617 | 5049227 | 3226465 | 2672105 | 3033316 | 2018723 | 1892995 | 1487228 | 1116251 | 1060445 | 951173 | 1818699 | 33122991 | 51500048.8399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51500048.8399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51500048.8399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51500048.8399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51500048.8399 | 51527336 | -27287.1601 | 27287 | 51527335.8399 | -3000000 | 0 | 0 | 0 | 0 | 48527335.8399
3309 | T19.01.01 | Prelims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3310 | T19.01.02 | Infraco early mobilisation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1910898 | 794551 | 794551 | 3500000 | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000 | 3500000 | 0 |  | 3500000 | [5 empty] | 3500000
3311 | T19.01.03 | Contractual milestones | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3312 | T19.01.04 | Transfer to MUDFA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27287 | 27287 | 27287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27287 |  | 27287 | -27287 | 0 | [5 empty] | 0
3313 | T19.01.05.01 | Section 1a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3314 | T19.01.05.02 | Section 1b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3315 | T19.01.05.03 | Section 1c | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3316 | T19.01.05.04 | Section 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3317 | T19.01.05.05 | Section 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3318 | T19.01.05.06 | Section 3a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3319 | T19.01.05.07 | Section 3b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3320 | T19.01.05.08 | Section 3c | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3321 | T19.01.05.09 | Section 4a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3322 | T19.01.05.10 | Section 4b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3323 | T19.01.05.11 | Section 5a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3324 | T19.01.05.12 | Section 5b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3325 | T19.01.05.13 | Section 5c | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3326 | T19.01.05.14 | Section 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3327 | T19.01.05.15 | Section 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3328 | T19.01.05.16 | Unallocated to section | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32740000 | 32740000 | 32740000 | 8534080.8491 | 1408544.5939 | 2512216.5212 | 3030907.6687 | 3151626.2479 | 4326643.2127 | 4945658.7279 | 6385318.5344 | 6752485.8364 | 4179556.4933 | 6400052.2376 | 6900208.0902 | 10598112.5537 | 69125411.567 | 101865411.567 | 5135446.3882 | 5879901.7185 | 7338231.5976 | 7440669.7277 | 5209648.2174 | 6788731.8692 | 8233394.7883 | 9560649.5103 | 4805499.3533 | 2679955.6767 | 8073116.3024 | 2559611.811 | 6780331.3414 | 80485188.302 | 182350599.869 | 3098693.7626 | 6870321.0216 | 2448515.2478 | 3681679.5545 | 2495566.9394 | 2869515.0854 | 1151603.7985 | 1219229.8144 | 1135069.125 | 6484421.8425 | 1219229.8144 | 1135069.125 | 0 | 33808915.131 | 216159515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216159515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216159515 | 216159515 | 0 |  | 216159515 | 5400361 |  |  |  |  | 221559876
3329 | T19.01.05.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -214764 | -214764 | -214764 | -214764 | -214764 | -214764 | -214764 | -214764 | -214764 | -214764 | -214764 | -214764 | -214764 | -2791932 | -2791932 | -214764 | -214764 | -214764 | -214764 | -214764 | -214764 | -214764 | -214764 | -214764 | -214764 | -214764 | -214764 | -214764 | -2791932 | -5583864 | -214764 | -214764 | -214764 | -214764 | -214764 | -214764 | -214764 | -214764 | -214764 | -214764 | -214764 | -214764 | -214764 | -2791932 | -8375796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8375796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8375796 | -8375796 | 0 |  | -8375796 | 8375796 |  |  |  |  | 0
3330 | T19.01.05.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3331 | T19.01.05.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3332 | T19.01.05.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3333 | T19.01.05 | Subtotal Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1910898 | 794551 | 33561838 | 36267287 | 36267287 | 8319316.8491 | 1193780.5939 | 2297452.5212 | 2816143.6687 | 2936862.2479 | 4111879.2127 | 4730894.7279 | 6170554.5344 | 6537721.8364 | 3964792.4933 | 6185288.2376 | 6685444.0902 | 10383348.5537 | 66333479.567 | 102600766.567 | 4920682.3882 | 5665137.7185 | 7123467.5976 | 7225905.7277 | 4994884.2174 | 6573967.8692 | 8018630.7883 | 9345885.5103 | 4590735.3533 | 2465191.6767 | 7858352.3024 | 2344847.811 | 6565567.3414 | 77693256.302 | 180294022.869 | 2883929.7626 | 6655557.0216 | 2233751.2478 | 3466915.5545 | 2280802.9394 | 2654751.0854 | 936839.7985 | 1004465.8144 | 920305.125 | 6269657.8425 | 1004465.8144 | 920305.125 | -214764 | 31016983.131 | 211311006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211311006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211311006 | 211283719 | 27287 | -27287 | 211283719 | 13776157 | 0 | 0 | 0 | 0 | 225059876
3334 | T19.01.06 | Testing and commissioning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3335 | T19.01.07 | Maintenance advance mobilisation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3336 | T19.01.08 | Variations / changes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3337 | T19.01.09 | Non infrastructure works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27307.1067 | 27307.1067 | 110730.3177 | 110730.3177 | 144864.2011 | 144864.2011 | 75772.9066 | 75772.9066 | 75772.9066 | 75772.9066 | 75772.9066 | 122513.5709 | 122513.5709 | 1189694.9258 | 1189694.9258 | 95206.4642 | 95206.4642 | 95206.4642 | 95206.4642 | 95206.4642 | 95206.4642 | 95206.4642 | 95206.4642 | 95206.4642 | 95206.4642 | 48465.7999 | 48465.7999 | 48465.7999 | 1097462.0417 | 2287156.9675 | 48465.7999 | 48465.7999 | 48465.7999 | 48465.7999 | 14331.9165 | 14331.9165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222527.0325 | 2509684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2509684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2509684 | 2509684 | 0 |  | 2509684 | [5 empty] | 2509684
3338 | T19.01.10 | Contingency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76923.0769 | 76923.0769 | 76923.0769 | 76923.0769 | 76923.0769 | 76923.0769 | 76923.0769 | 76923.0769 | 76923.0769 | 76923.0769 | 76923.0769 | 76923.0769 | 76923.0769 | 1000000 | 1000000 | 115384.6154 | 115384.6154 | 115384.6154 | 115384.6154 | 115384.6154 | 115384.6154 | 115384.6154 | 115384.6154 | 115384.6154 | 115384.6154 | 115384.6154 | 115384.6154 | 115384.6154 | 1500000 | 2500000 | 115384.6154 | 115384.6154 | 115384.6154 | 115384.6154 | 115384.6154 | 115384.6154 | 115384.6154 | 115384.6154 | 115384.6154 | 115384.6154 | 115384.6154 | 115384.6154 | 115384.6154 | 1500000 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 |  | 4000000 | [5 empty] | 4000000
3339 | T19.01.11 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3340 | T19.01.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3341 | T19.01.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3342 | T19.01.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3343 | T19.01.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3344 | T19.01.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3345 | T19.01.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3346 | T19.01.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3347 | T19.01.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3348 | T19.01.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3349 | T19.01.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3350 | T19.01.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3351 | T19.01.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3352 | T19.01.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3353 | T19.01.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3354 | T19.01.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3355 | T19.01.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3356 | T19.01.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3357 | T19.01.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3358 | T19.01.30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3359 | T19.01.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3360 | T19.01.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3361 | T19.01.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3362 | T19.01.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3363 | T19.01.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3364 | T19.01.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3365 | T19.01.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3366 | T19.01.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3367 | T19.01.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3368 | T19.01.40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3369 | T19.01 | Subtotal Infraco main works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1910898 | 794551 | 33561838 | 36267287 | 36267287 | 8423547.0327 | 1298010.7776 | 2485105.9159 | 3003797.0634 | 3158649.5259 | 4333666.4907 | 4883590.7114 | 6323250.5179 | 6690417.8199 | 4117488.4769 | 6337984.2211 | 6884880.738 | 10582785.2015 | 68523174.4928 | 104790461.4928 | 5131273.4678 | 5875728.7981 | 7334058.6772 | 7436496.8073 | 5205475.2969 | 6784558.9488 | 8229221.8679 | 9556476.5899 | 4801326.4329 | 2675782.7562 | 8022202.7177 | 2508698.2263 | 6729417.7566 | 80290718.3437 | 185081179.8364 | 3047780.1778 | 6819407.4368 | 2397601.6631 | 3630765.9698 | 2410519.4713 | 2784467.6173 | 1052224.4139 | 1119850.4298 | 1035689.7404 | 6385042.4579 | 1119850.4298 | 1035689.7404 | -99379.3846 | 32739510.1636 | 217820690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217820690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217820690 | 217793403 | 27287 | -27287 | 217793403 | 13776157 | 0 | 0 | 0 | 0 | 231569560
3370 | T19.02.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18000000 | -18000000 | -18000000 | 16758.6512 | 169.2793 | 0 | 0 | 127230.6582 | 129041.7708 | 318582.0327 | 14078.1257 | 253916.5708 | 221200.6623 | 596510.1112 | 464112.2696 | 1285963.5653 | 3427563.6972 | -14572436.3028 | 435075.9431 | 589322.7375 | 1212261.4003 | 828790.0862 | 644304.3512 | 1058876.1632 | 2045893.4369 | 2128411.0177 | 496490.768 | 474995.1574 | 980394.1907 | 102502.0324 | 628591.959 | 11625909.2436 | -2946527.0592 | 439991.5301 | 874211.2334 | 335720.0773 | 378695.0413 | 416986.0583 | 491916.6196 | 4927.0415 | 2019.2995 | 20.397 | 0 | 2019.2995 | 20.397 | 0 | 2946526.9944 | -0.064807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.064807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.064807 |  | -0.064807 |  | -0.064807 | [5 empty] | -0.064807
3371 | T19.02.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 2500000 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 0 | 0 | -500000 | 0 | 0 | 0 | -1000000 | -1000000 | 0 | 0 | 0 | 0 | 0 | -2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3372 | T19.02.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3373 | T19.02.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3374 | T19.02.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3375 | T19.02.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3376 | T19.02.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3377 | T19.02.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3378 | T19.02.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3379 | T19.02.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3380 | T19.02 | Subtotal Funding adjustment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15500000 | -15500000 | -15500000 | 16758.6512 | 169.2793 | 0 | 0 | 127230.6582 | 129041.7708 | 318582.0327 | 14078.1257 | 253916.5708 | 221200.6623 | 596510.1112 | 464112.2696 | 1285963.5653 | 3427563.6972 | -12072436.3028 | 435075.9431 | 589322.7375 | 712261.4003 | 828790.0862 | 644304.3512 | 1058876.1632 | 1045893.4369 | 1128411.0177 | 496490.768 | 474995.1574 | 980394.1907 | 102502.0324 | 628591.959 | 9125909.2436 | -2946527.0592 | 439991.5301 | 874211.2334 | 335720.0773 | 378695.0413 | 416986.0583 | 491916.6196 | 4927.0415 | 2019.2995 | 20.397 | 0 | 2019.2995 | 20.397 | 0 | 2946526.9944 | -0.064807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.064807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.064807 | 0 | -0.064807 | 0 | -0.064807 | 0 | 0 | 0 | 0 | 0 | -0.064807
3381 | T19.03.01 | SRU Murrayfield pitches | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3382 | T19.03.02 | Relocate historic monuments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 | 42000 | 0 |  | 42000 | [5 empty] | 42000
3383 | T19.03.03 | Environ. impacts - badgers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 5000 | 0 | -15000 | 0 | 2000 | 0 | 0 | 0 | 4500 | 6400 | 9100 | 32000 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 32000 | 0 |  | 32000 | [5 empty] | 32000
3384 | T19.03.04 | Invasive species | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37000 | 0 | 14642 | 0 | 25820 | 0 | 0 | 0 | 0 | 0 | 15000 | 92462 | 92462 | 15000 | 0 | 15000 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 152462 | 25000 | 0 | 25000 | 25000 | 0 | 25000 | 25000 | 22538 | 0 | 0 | 0 | 0 | 0 | 147538 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 0 |  | 300000 | [5 empty] | 300000
3385 | T19.03.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3386 | T19.03.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3387 | T19.03.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3388 | T19.03.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3389 | T19.03.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3390 | T19.03.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3391 | T19.03.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3392 | T19.03.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3393 | T19.03.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3394 | T19.03.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3395 | T19.03.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3396 | T19.03 | Subtotal advance works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 42000 | 0 | -358 | 0 | 27820 | 0 | 0 | 0 | 4500 | 6400 | 24100 | 124462 | 124462 | 15000 | 0 | 15000 | 15000 | 0 | 15000 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 102000 | 226462 | 25000 | 0 | 25000 | 25000 | 0 | 25000 | 25000 | 22538 | 0 | 0 | 0 | 0 | 0 | 147538 | 374000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374000 | 374000 | 0 | 0 | 374000 | 0 | 0 | 0 | 0 | 0 | 374000
3397 | T19.04.01 | Unallocated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134574 | 134574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134574 | 134574 | 0 |  | 134574 | [5 empty] | 134574
3398 | T19.04.02 | Set up / mobilisation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179741 | 179741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179741 | 179741 | 0 |  | 179741 | [5 empty] | 179741
3399 | T19.04.03 | Phase 1 (150,000m3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405559 | 707000 | 1010441 | 569660 | 222025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2914685 | 2914685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2914685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2914685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2914685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2914685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2914685 | 2914685 | 0 |  | 2914685 | [5 empty] | 2914685
3400 | T19.04.04 | Phase 2 (100,000m3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 894600 | 409889 | 224552 | 0 | 583353 | 47593 | 0 | 0 | 2209987 | 2209987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2209987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2209987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2209987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2209987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2209987 | 2162394 | 47593 | -630946 | 1579041 | 630496 |  |  |  |  | 2209537
3401 | T19.04.05 | Phase 3 (94,093m3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3402 | T19.04.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3403 | T19.04.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3404 | T19.04.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3405 | T19.04.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3406 | T19.04.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3407 | T19.04.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3408 | T19.04.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3409 | T19.04.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3410 | T19.04.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3411 | T19.04.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3412 | T19.04 | Subtotal depot advance works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134574 | 585300 | 707000 | 1010441 | 619660 | 1116625 | 409889 | 224552 | 0 | 583353 | 47593 | 0 | 0 | 5438987 | 5438987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5438987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5438987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5438987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5438987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5438987 | 5391394 | 47593 | -630946 | 4808041 | 630496 | 0 | 0 | 0 | 0 | 5438537
3413 | T19.05.01.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3414 | T19.05.01.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3415 | T19.05.01.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3416 | T19.05.01.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3417 | T19.05.01.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3418 | T19.05.01.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3419 | T19.05.01.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3420 | T19.05.01.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3421 | T19.05.01.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3422 | T19.05.01.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3423 | T19.05.01.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3424 | T19.05.01.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3425 | T19.05.01.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3426 | T19.05.01.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3427 | T19.05.01.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3428 | T19.05.01.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3429 | T19.05.01.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3430 | T19.05.01.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3431 | T19.05.01.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3432 | T19.05.01.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3433 | T19.05.01 | Subtotal third party funded work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3434 | T19.05.02.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3435 | T19.05.02.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3436 | T19.05.02.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3437 | T19.05.02.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3438 | T19.05.02.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3439 | T19.05.02.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3440 | T19.05.02.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3441 | T19.05.02.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3442 | T19.05.02.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3443 | T19.05.02.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3444 | T19.05.02.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3445 | T19.05.02.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3446 | T19.05.02.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3447 | T19.05.02.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3448 | T19.05.02.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3449 | T19.05.02.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3450 | T19.05.02.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3451 | T19.05.02.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3452 | T19.05.02.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3453 | T19.05.02.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3454 | T19.05.02 | Subtotal third party funding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3455 | T19.05.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3456 | T19.05.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3457 | T19.05.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3458 | T19.05.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3459 | T19.05.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3460 | T19.05.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3461 | T19.05.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3462 | T19.05.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3463 | T19.05.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3464 | T19.05.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3465 | T19.05.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3466 | T19.05.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3467 | T19.05.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3468 | T19.05.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3469 | T19.05.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3470 | T19.05.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3471 | T19.05.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3472 | T19.05.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3473 | T19.05 | Subtotal third party works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3474 | T19.06.01.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3475 | T19.06.01.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3476 | T19.06.01.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3477 | T19.06.01.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3478 | T19.06.01.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3479 | T19.06.01.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3480 | T19.06.01.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3481 | T19.06.01.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3482 | T19.06.01.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3483 | T19.06.01.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3484 | T19.06.01.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3485 | T19.06.01.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3486 | T19.06.01.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3487 | T19.06.01.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3488 | T19.06.01.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3489 | T19.06.01.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3490 | T19.06.01.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3491 | T19.06.01.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3492 | T19.06.01.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3493 | T19.06.01.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3494 | T19.06.01 | Subtotal VE - Infraco | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
3495 | T19.06.02.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3496 | T19.06.02.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3497 | T19.06.02.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3498 | T19.06.02.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3499 | T19.06.02.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3500 | T19.06.02.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3501 | T19.06.02.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3502 | T19.06.02.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3503 | T19.06.02.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3504 | T19.06.02.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3505 | T19.06.02.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3506 | T19.06.02.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3507 | T19.06.02.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3508 | T19.06.02.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3509 | T19.06.02.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3510 | T19.06.02.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3511 | T19.06.02.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3512 | T19.06.02.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3513 | T19.06.02.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3514 | T19.06.02.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3515 | T19.06.02 | Subtotal VE - Non-Infraco | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
3516 | T19.06.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3517 | T19.06.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3518 | T19.06.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3519 | T19.06.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3520 | T19.06.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3521 | T19.06.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3522 | T19.06.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3523 | T19.06.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3524 | T19.06.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3525 | T19.06.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3526 | T19.06.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3527 | T19.06.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3528 | T19.06.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3529 | T19.06.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3530 | T19.06.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3531 | T19.06.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3532 | T19.06.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3533 | T19.06.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3534 | T19.06 | Subtotal VE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
3535 | T19.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3536 | T19.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3537 | T19.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3538 | T19.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3539 | T19.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3540 | T19.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3541 | T19.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3542 | T19.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3543 | T19.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3544 | T19.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3545 | T19.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3546 | T19.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3547 | T19.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3548 | T19.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3549 | T19.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3550 | T19.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3551 | T19.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3552 | T19.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3553 | T19.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3554 | T19.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3555 | T19.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3556 | T19.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3557 | T19.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3558 | T19.30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3559 | T19.07-30 | Subtotal other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3560 | T19 | Total Infraco | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134574 | 605300 | 749000 | 1010441 | 619302 | 1116625 | 437709 | 224552 | 0 | 583353 | 1962991 | 800951 | 18085938 | 26330736 | 26330736 | 8455305.6839 | 1298180.0569 | 2500105.9159 | 3018797.0634 | 3285880.1841 | 4477708.2614 | 5244172.7441 | 6337328.6436 | 6944334.3907 | 4338689.1392 | 6934494.3323 | 7348993.0076 | 11868748.7668 | 72052738.1899 | 98383474.1899 | 5591349.4109 | 6465051.5356 | 8071320.0775 | 8290286.8935 | 5849779.6481 | 7868435.112 | 9300115.3048 | 10707425.6076 | 5297817.2009 | 3150777.9137 | 9002596.9084 | 2611200.2587 | 7358009.7157 | 89564165.5873 | 187947639.7772 | 3487771.708 | 7693618.6702 | 2733321.7404 | 4009461.011 | 2827505.5296 | 3276384.2369 | 1057151.4554 | 1121869.7293 | 1035710.1374 | 6385042.4579 | 1121869.7293 | 1035710.1374 | -99379.3846 | 35686037.158 | 223633676.9352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223633676.9352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223633676.9352 | 223558797 | 74879.9352 | -658233 | 222975443.9352 | 14406653 | 0 | 0 | 0 | 0 | 237382096.9352
| TT09 | Total Infrastructure & Maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134574 | 605300 | 749000 | 1010441 | 619302 | 1116625 | 437709 | 224552 | 0 | 583353 | 1962991 | 800951 | 18085938 | 26330736 | 26330736 | 8455305.6839 | 1298180.0569 | 2500105.9159 | 3018797.0634 | 3285880.1841 | 4477708.2614 | 5244172.7441 | 6337328.6436 | 6944334.3907 | 4338689.1392 | 6934494.3323 | 7348993.0076 | 11868748.7668 | 72052738.1899 | 98383474.1899 | 5591349.4109 | 6465051.5356 | 8071320.0775 | 8290286.8935 | 5849779.6481 | 7868435.112 | 9300115.3048 | 10707425.6076 | 5297817.2009 | 3150777.9137 | 9002596.9084 | 2611200.2587 | 7358009.7157 | 89564165.5873 | 187947639.7772 | 3487771.708 | 7693618.6702 | 2733321.7404 | 4009461.011 | 2827505.5296 | 3276384.2369 | 1057151.4554 | 1121869.7293 | 1035710.1374 | 6385042.4579 | 1121869.7293 | 1035710.1374 | -99379.3846 | 35686037.158 | 223633676.9352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223633676.9352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223633676.9352 | 223558797 | 74879.9352 | -658233 | 222975443.9352 | 14406653 | 0 | 0 | 0 | 0 | 237382096.9352
0
3562 | T20.01.01 | Prelims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0
3563 | T20.01.02 | Tramco early mobilisation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 70000 | 150000 | 250000 | 250000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 450000 | 0 |  | 450000 | [5 empty] | 450000
3564 | T20.01.03.01 | Approval of preliminary design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1177964.813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1177964.813 | 1177964.813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1177964.813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1177964.813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1177964.813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1177964.813 | 1177964.813 | 0 |  | 1177964.813 | [5 empty] | 1177964.813
3565 | T20.01.03.02 | Delivery of mock up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0
3566 | T20.01.03.03 | Approval of final design / mock up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1766947.2195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1766947.2195 | 1766947.2195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1766947.2195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1766947.2195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1766947.2195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1766947.2195 | 1766947.2195 | 0 |  | 1766947.2195 | [5 empty] | 1766947.2195
3567 | T20.01.03.04 | Approvals and consents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0
3568 | T20.01.03.05 | Commencenent of tram works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10366090.3544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10366090.3544 | 10366090.3544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10366090.3544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10366090.3544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10366090.3544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10366090.3544 | 10366090.3544 | 0 |  | 10366090.3544 | [5 empty] | 10366090.3544
3569 | T20.01.03.06 | Completion 1st set bodyshells | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533894.439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533894.439 | 3533894.439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533894.439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533894.439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533894.439 | 3533894.439 | 0 |  | 3533894.439 | [5 empty] | 3533894.439
3570 | T20.01.03.07 | Completion 1st set bogies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533894.439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533894.439 | 3533894.439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533894.439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533894.439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533894.439 | 3533894.439 | 0 |  | 3533894.439 | [5 empty] | 3533894.439
3571 | T20.01.03.08 | Completion 1st tram assembly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533894.439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533894.439 | 3533894.439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533894.439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533894.439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533894.439 | 3533894.439 | 0 |  | 3533894.439 | [5 empty] | 3533894.439
3572 | T20.01.03.09 | Completion factory based type testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4122876.8455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4122876.8455 | 4122876.8455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4122876.8455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4122876.8455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4122876.8455 | 4122876.8455 | 0 |  | 4122876.8455 | [5 empty] | 4122876.8455
3573 | T20.01.03.10 | Delivery of preliminary tram maintenance manuals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533894.439 | 0 | 0 | 0 | 3533894.439 | 3533894.439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533894.439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533894.439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533894.439 | 3533894.439 | 0 |  | 3533894.439 | [5 empty] | 3533894.439
3574 | T20.01.03.11 | Delivery of spares | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1177964.813 | 0 | 0 | 0 | 1177964.813 | 1177964.813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1177964.813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1177964.813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1177964.813 | 1177964.813 | 0 |  | 1177964.813 | [5 empty] | 1177964.813
3575 | T20.01.03.12 | Delivery of final documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1177964.813 | 0 | 0 | 0 | 0 | 0 | 1177964.813 | 1177964.813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1177964.813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1177964.813 | 1177964.813 | 0 |  | 1177964.813 | [5 empty] | 1177964.813
3576 | T20.01.03.13 | Delivery of special tools | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588982.4065 | 0 | 0 | 0 | 0 | 0 | 588982.4065 | 588982.4065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588982.4065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588982.4065 | 588982.4065 | 0 |  | 588982.4065 | [5 empty] | 588982.4065
3577 | T20.01.03.14 | Completion of driver training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588982.4065 | 0 | 0 | 0 | 0 | 0 | 0 | 588982.4065 | 588982.4065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588982.4065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588982.4065 | 588982.4065 | 0 |  | 588982.4065 | [5 empty] | 588982.4065
3578 | T20.01.03.15 | Completion of maintainer training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588982.4065 | 0 | 0 | 0 | 0 | 0 | 0 | 588982.4065 | 588982.4065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588982.4065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588982.4065 | 588982.4065 | 0 |  | 588982.4065 | [5 empty] | 588982.4065
3579 | T20.01.03.16 | Completion of integrated system testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588982.4065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588982.4065 | 588982.4065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588982.4065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588982.4065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588982.4065 | 588982.4065 | 0 |  | 588982.4065 | [5 empty] | 588982.4065
3580 | T20.01.03.17 | Commencement of shadow running | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588982.4065 | 0 | 0 | 0 | 0 | 0 | 0 | 588982.4065 | 588982.4065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588982.4065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588982.4065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588982.4065 | 588982.4065 | 0 |  | 588982.4065 | [5 empty] | 588982.4065
3581 | T20.01.03.18 | Opening for passenger service | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588982.4065 | 0 | 0 | 0 | 588982.4065 | 588982.4065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588982.4065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588982.4065 | 588982.4065 | 0 |  | 588982.4065 | [5 empty] | 588982.4065
3582 | T20.01.03.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10803805 | 10803805 | 10803805 | 0 | 0 | 525843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525843 | 11329648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11329648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11329648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11329648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11329648 | 11329648 | 0 |  | 11329648 | [5 empty] | 11329648
3583 | T20.01.03.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -2509338 | -2509338 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -2509338 | -5018676 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -2509338 | -7528014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7528014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7528014 | -7528014 | 0 |  | -7528014 |  | 5259501 |  |  |  | -2268513
3584 | T20.01.03.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0
3585 | T20.01.03.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0
3586 | T20.01.03.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0
3587 | T20.01.03.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0
3588 | T20.01.03.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0
3589 | T20.01.03.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0
3590 | T20.01.03.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0
3591 | T20.01.03.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0
3592 | T20.01.03.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0
3593 | T20.01.03.30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0
3594 | T20.01.03 | Subtotal contractual milestones | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10803805 | 10803805 | 10803805 | 984938.813 | -193026 | 2099764.2195 | -193026 | 10173064.3544 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | 11327507.3869 | 22131312.3869 | -193026 | -193026 | 3340868.439 | 6874762.878 | 4518833.252 | -193026 | 395956.4065 | -193026 | -193026 | 4518833.252 | -193026 | -193026 | -193026 | 18105046.2275 | 40236358.6144 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | 984938.813 | 1573921.2195 | -193026 | 395956.4065 | -193026 | -193026 | -193026 | 1024556.439 | 41260915.0534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41260915.0534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41260915.0534 | 41710915.0534 | -450000 | 0 | 41710915.0534 | 0 | 5259501 | 0 | 0 | 0 | 46970416.0534
3595 | T20.01.04 | Delivery of trams | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1766947.2195 | 0 | 471186 | 235592 | 353389 | 2827114.2195 | 2827114.2195 | 235593 | 353389 | 353389 | 353389 | 353389 | 353389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2002538 | 4829652.2195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4829652.2195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4829652.2195 | 4829652 | 0.2195 |  | 4829652.2195 | [5 empty] | 4829652.2195
3596 | T20.01.05 | Testing and commissioning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2238133 | 0 | 235592 | 2473725 | 2473725 | 588982 | 0 | 353389 | 353389 | 353389 | 353389 | 353389 | 7 | 0 | 0 | 0 | 0 | 0 | 2355934 | 4829659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4829659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4829659 | 4829659 | 0 |  | 4829659 | [5 empty] | 4829659
3597 | T20.01.06 | Advance maintenance mobilisation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3598 | T20.01.07 | Variations / changes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3599 | T20.01.08 | Contingency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3600 | T20.01.09 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3601 | T20.01.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3602 | T20.01.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3603 | T20.01.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3604 | T20.01.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3605 | T20.01.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3606 | T20.01.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3607 | T20.01.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3608 | T20.01.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3609 | T20.01.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3610 | T20.01.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3611 | T20.01.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3612 | T20.01.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3613 | T20.01.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3614 | T20.01.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3615 | T20.01.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3616 | T20.01.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3617 | T20.01.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3618 | T20.01.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3619 | T20.01.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3620 | T20.01.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3621 | T20.01.30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3622 | T20.01.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3623 | T20.01.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3624 | T20.01.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3625 | T20.01.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3626 | T20.01.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3627 | T20.01.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3628 | T20.01.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3629 | T20.01.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3630 | T20.01.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3631 | T20.01.40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3632 | T20.01 | Subtotal Tramco main works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 70000 | 10953805 | 11053805 | 11053805 | 1184938.813 | -193026 | 2099764.2195 | -193026 | 10173064.3544 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | 11527507.3869 | 22581312.3869 | -193026 | -193026 | 3340868.439 | 6874762.878 | 4518833.252 | -193026 | 395956.4065 | -193026 | 1573921.2195 | 4518833.252 | 2516293 | 42566 | 395955 | 23405885.447 | 45987197.8339 | 631549 | 160363 | 513752 | 513752 | 513752 | 513752 | 1338327.813 | 1573928.2195 | -193026 | 395956.4065 | -193026 | -193026 | -193026 | 5383028.439 | 51370226.2729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51370226.2729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51370226.2729 | 51370226.0534 | 0.2195 | 0 | 51370226.2729 | 0 | 5259501 | 0 | 0 | 0 | 56629727.2729
3633 | T10.02.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8700000 | -8700000 | -8700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8700000 | 0 | 0 | 2175000 | 0 | 0 | 2175000 | 0 | 0 | 2175000 | 0 | 0 | 2175000 | 0 | 8700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3634 | T10.02.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3635 | T10.02.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3636 | T10.02.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3637 | T10.02.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3638 | T10.02.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3639 | T10.02.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3640 | T10.02.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3641 | T10.02.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3642 | T10.02.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3643 | T20.02 | Subtotal Funding adjustment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8700000 | -8700000 | -8700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8700000 | 0 | 0 | 2175000 | 0 | 0 | 2175000 | 0 | 0 | 2175000 | 0 | 0 | 2175000 | 0 | 8700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3644 | T20.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3645 | T20.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3646 | T20.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3647 | T20.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3648 | T20.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3649 | T20.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3650 | T20.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3651 | T20.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3652 | T20.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3653 | T20.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3654 | T20.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3655 | T20.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3656 | T20.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3657 | T20.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3658 | T20.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3659 | T20.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3660 | T20.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3661 | T20.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3662 | T20.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3663 | T20.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3664 | T20.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3665 | T20.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3666 | T20.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3667 | T20.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3668 | T20.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3669 | T20.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3670 | T20.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3671 | T20.30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0
3672 | T20.03-30 | Subtotal other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0
3673 | T20 | Total Tramco | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 70000 | 2253805 | 2353805 | 2353805 | 1184938.813 | -193026 | 2099764.2195 | -193026 | 10173064.3544 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | 11527507.3869 | 13881312.3869 | -193026 | -193026 | 5515868.439 | 6874762.878 | 4518833.252 | 1981974 | 395956.4065 | -193026 | 3748921.2195 | 4518833.252 | 2516293 | 2217566 | 395955 | 32105885.447 | 45987197.8339 | 631549 | 160363 | 513752 | 513752 | 513752 | 513752 | 1338327.813 | 1573928.2195 | -193026 | 395956.4065 | -193026 | -193026 | -193026 | 5383028.439 | 51370226.2729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51370226.2729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51370226.2729 | 51370226.0534 | 0.2195 | 0 | 51370226.2729 | 0 | 5259501 | 0 | 0 | 0 | 56629727.2729
| TT10 | Total Tram Supply & Maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 70000 | 2253805 | 2353805 | 2353805 | 1184938.813 | -193026 | 2099764.2195 | -193026 | 10173064.3544 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | -193026 | 11527507.3869 | 13881312.3869 | -193026 | -193026 | 5515868.439 | 6874762.878 | 4518833.252 | 1981974 | 395956.4065 | -193026 | 3748921.2195 | 4518833.252 | 2516293 | 2217566 | 395955 | 32105885.447 | 45987197.8339 | 631549 | 160363 | 513752 | 513752 | 513752 | 513752 | 1338327.813 | 1573928.2195 | -193026 | 395956.4065 | -193026 | -193026 | -193026 | 5383028.439 | 51370226.2729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51370226.2729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51370226.2729 | 51370226.0534 | 0.2195 | 0 | 51370226.2729 | 0 | 5259501 | 0 | 0 | 0 | 56629727.2729
4151 | T44.01 | Risk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 500000 | 1813600 | 1813600 | 2813600 | 1810300 | 1762700 | 1671600 | 1401200 | 1142900 | 1061600 | 423200 | 405800 | 379700 | 8074255 | 24574055 | 25074055 | 373500 | 388800 | 388800 | 401400 | 401400 | 401400 | 379200 | 378400 | 378400 | 308600 | 308600 | 308600 | 12433645 | 16850745 | 41924800 | 308600 | 308600 | 308600 | 308600 | 275600 | 275600 | 275600 | 296500 | 296500 | 4395000 | 0 | 0 | 0 | 7049200 | 48974000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48974000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48974000 | 48974000 |  |  | 48974000 | -11406653 | -5259501 | -1983870 |  |  | 30323976
4152 | T44.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0
4153 | T44.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0
4154 | T44.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0
4155 | T44.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0
4156 | T44.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0
4157 | T44.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0
4158 | T44.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0
4159 | T44.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0
4160 | T44.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0
4161 | T44.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0
4162 | T44.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0
4163 | T44.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0
4164 | T44.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0
4165 | T44.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0
4166 | T44.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0
4167 | T44.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0
4168 | T44.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0
4169 | T44.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0
4170 | T44.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0
4171 | T44 | Total Risk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 500000 | 1813600 | 1813600 | 2813600 | 1810300 | 1762700 | 1671600 | 1401200 | 1142900 | 1061600 | 423200 | 405800 | 379700 | 8074255 | 24574055 | 25074055 | 373500 | 388800 | 388800 | 401400 | 401400 | 401400 | 379200 | 378400 | 378400 | 308600 | 308600 | 308600 | 12433645 | 16850745 | 41924800 | 308600 | 308600 | 308600 | 308600 | 275600 | 275600 | 275600 | 296500 | 296500 | 4395000 | 0 | 0 | 0 | 7049200 | 48974000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48974000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48974000 | 48974000 | 0 | 0 | 48974000 | -11406653 | -5259501 | -1983870 | 0 | 0 | 30323976
4195 | T999 | Total | 13757346.0836 | 1772067.8726 | 2524731.2613 | 2809458.78 | 2381068 | 2128369.8145 | 2654124.194 | 2624852 | 3237647 | 2657066 | 2184231 | 3159767.3333 | 2297450.332 | 30430833.5878 | 44188179.6713 | 12808053.084 | 2288663.8024 | 3899403.2727 | 9634789.1702 | 3776635.2613 | 4792779.4708 | 6503995.135 | -4402691.6261 | 5074276.9912 | 3536465.5774 | 5505191.4447 | 4943434.8548 | 28318925.6557 | 86679922.0941 | 130868101.7654 | 18377062.5898 | 8801639.4198 | 13546639.2683 | 8940392.1678 | 18963881.573 | 10060113.1729 | 9510362.6772 | 10225224.8259 | 10340202.213 | 6730122.7015 | 9232759.8661 | 9883579.4114 | 22798612.3293 | 157410592.2161 | 288278693.9815 | 6570918.9169 | 7412613.8616 | 14734335.8725 | 16301192.4776 | 11509866.0462 | 10984716.328 | 10820639.9173 | 11646774.4695 | 10198949.2172 | 8747007.6424 | 12596302.3151 | 5912059.6254 | 21113544.1059 | 148548920.7958 | 436827614.7773 | 5149959.4377 | 8910611.1499 | 4423605.2201 | 5749874.4908 | 4577542.1374 | 5088486.9545 | 3736575.986 | 4111533.9082 | 2291673.932 | 12531273.659 | 1541838.2964 | 1185583.877 | 137113.9615 | 59435673.0105 | 496263287.7878 | 176154.3569 | 124455.406 | 119598.407 | 119598.407 | 119453.407 | 117811.907 | 117816.907 | 133526.907 | 133526.907 | 133526.907 | 133526.907 | 133526.907 | 234046.7531 | 1796570.0857 | 498059857.8735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 498059857.8735 | 498059833.6761 | 24.1974 | 0.38465 | 498059858.2582 | 0 | 0 | 0 | 0 | 0 | 498059858.2582
4197 | 0 | Cumulative | 13757346.0836 | 15529413.9561 | 18054145.2174 | 20863603.9974 | 23244671.9974 | 25373041.812 | 28027166.0059 | 30652018.0059 | 33889665.0059 | 36546731.0059 | 38730962.0059 | 41890729.3393 | 44188179.6713 | 44188179.6713 | 44188179.6713 | 56996232.7553 | 59284896.5578 | 63184299.8305 | 72819089.0007 | 76595724.262 | 81388503.7328 | 87892498.8678 | 83489807.2416 | 88564084.2328 | 92100549.8103 | 97605741.2549 | 102549176.1097 | 130868101.7654 | 130868101.7654 | 130868101.7654 | 149245164.3552 | 158046803.7751 | 171593443.0434 | 180533835.2113 | 199497716.7843 | 209557829.9571 | 219068192.6343 | 229293417.4602 | 239633619.6732 | 246363742.3747 | 255596502.2408 | 265480081.6522 | 288278693.9815 | 288278693.9815 | 288278693.9815 | 294849612.8984 | 302262226.7601 | 316996562.6326 | 333297755.1102 | 344807621.1563 | 355792337.4844 | 366612977.4017 | 378259751.8712 | 388458701.0884 | 397205708.7308 | 409802011.046 | 415714070.6714 | 436827614.7773 | 436827614.7773 | 436827614.7773 | 441977574.215 | 450888185.3649 | 455311790.585 | 461061665.0758 | 465639207.2132 | 470727694.1677 | 474464270.1537 | 478575804.0619 | 480867477.9939 | 493398751.6529 | 494940589.9493 | 496126173.8263 | 496263287.7878 | 496263287.7878 | 496263287.7878 | 496439442.1447 | 496563897.5507 | 496683495.9577 | 496803094.3647 | 496922547.7716 | 497040359.6786 | 497158176.5856 | 497291703.4925 | 497425230.3995 | 497558757.3065 | 497692284.2134 | 497825811.1204 | 498059857.8735 | 498059857.8735 | 498059857.8735 | 498059857.8735 | 498059857.8735 | 498059857.8735 | 498059857.8735 | 498059857.8735 | 498059857.8735 | 498059857.8735 | 498059857.8735 | 498059857.8735 | 498059857.8735 | 498059857.8735 | 498059857.8735 | 498059857.8735 | 498059857.8735
Risk Allowance Analysis:
|  | Infraco / Tramco Procurement | [107 empty] | 17526000 | -11406653 | -5259501 | -859846 |  |  | 0
|  | Infraco Delivery | [107 empty] | 3169000 | [5 empty] | 3169000
|  | Design & Consents | [107 empty] | 4313000 |  |  | -1124024 |  |  | 3188976
|  | Tramco Delivery | [107 empty] | 861000 | [5 empty] | 861000
|  | MUDFA | [107 empty] | 11447000 |  |  | -3000000 |  |  | 8447000
|  | General Programme Delay | [107 empty] | 3131000 |  |  | 3000000 |  |  | 6131000
|  | Land compensation | [107 empty] | 4296000 | [5 empty] | 4296000
|  | TROs | [107 empty] | 3208000 | [5 empty] | 3208000
|  | Network Rail | [107 empty] | 624000 | [5 empty] | 624000
|  | Other | [107 empty] | 399000 | [5 empty] | 399000
|  | Unspecified Risks (Contingency) | [113 empty] | 0
[110 empty] | 48974000 | -11406653 | -5259501 | -1983870 | 0 | 0 | 30323976
Note on DH11: Since FBC we've been covering increases on costs of Depot excavation, legal fees etc by ofset against PM cost - now restated to FBC.

## Infraco Financial Summary
INFRACO BUDGET RECONCILIATION
Final Deal
|  |  | At Preferred Bidder | Current Position |  |  | Variance | Weisbaden | Deltas | Total | Comment
INFRACO | [5 empty] | %
| Firm Prices |  | 159120890 | #REF! |  | #REF! | #REF! | 213910342 | 3800000 | 217710342
| Provisional Prices |  | 49579452 | #REF! |  | #REF! | #REF! | 0 |  | 0
| VE taken into price- with conditions | [6 empty] | -13818006 |  | -13818006
| Premium for firm price for previously provisional items | [6 empty] | 8000000 |  | 8000000
|  |  | 208700342 |  | #REF! |  | #REF! | 208092336 |  | 211892336
| Infraco Normalisation (provisional cums) |  | 17803222.0632 | #REF! |  | #REF! | #REF! | 10170090.2178 |  | 10170090.2178
Negotiated Infraco Contract Price |  |  | 226503564.0632 |  | #REF! | #REF! | #REF! | 218262426.2178 |  | 222062426.2178
Other Items / adjustments to Contract Price: |  |  |  | 3397089 |  | #REF! | 3397089
| EAL - Burnside Road | [6 empty] | 1000000 |  | 1000000
| Maintenance Mobilisation & Spare Parts | [6 empty] | 2397000 |  | 2397000 | MM £1.4m and and Spare Parts £1m
| Provisional sum included above for remaining SDS design | [7 empty] | -2000000 | -2000000 | Already included in AFC on SDS budget
| Employers Requirements additions since V3.1 | [7 empty] | 1600000 | 1600000
Value Engineering |  |  | -19708389
Contingency against conditions on VE not being realised |  |  | 4442000 | 1044911 |  |  | -3397089 | 4000000 |  | 4000000
Budget Allowance for Infraco (BBS) contract |  |  | 211237175.0632 |  | #REF! |  |  | 225659426.2178 |  | 229059426.2178
Items included in Infraco budget but not procured through BBS
| Non-Infraco works |  | 16502332.0024 | 16502332.0024 |  |  | 0 | 6769684 | 300000 | 7069684 | £300k IPR2 contingency
| Advance works by others | [5 empty] | 0 |  |  | 0
|  | Depot excavation | 4808041 | 4754041 |  |  | 0 | 4808041 | 630946 | 5438987 | £630k for final measurement at depot
|  | Minor contracts | 374000 | 332000 |  |  | 0 | 374000 |  | 374000
|  |  | 21684373.0024 | 21588373.0024 |  |  |  | 11951725 |  | 12882671
Value Engineering |  |  | -9946100 |  |  |  |  | -4560000 |  | -4560000
|  |  |  | -79250 |  |  | -79250
Net Non-Infraco Items |  |  | 11738273.0024 |  | #REF! |  |  | 7391725 |  | 8322671
Total £ included in Infraco Budget Line |  |  | 222975448.0656 |  | #REF! |  | #REF! | 233051151.2178 |  | 237382097.2178
Increase on Infraco line in the FBC Budget | [7 empty] | 10075703.1522 | 4330946 | 14406649.1522
Less: Utilities (MUDFA) scope included in Infraco | [7 empty] | -3000000 |  | -3000000 | Picardy Place
Transfer from Risk Allowance Required | [7 empty] | 7075703.1522 |  | 11406649.1522

## Tram Financial Summary
Tram Supply Figure Calculation |  | Date:- 19/12/07
|  |  | Recommended Final Deal w/ currency hedge | FBC Build Up | Delta |  | EUROs
BAFO figure (€77,604,671) |  |  | 53780037 | 53780037 |  |  | 77604670.9957
Omit figure for final design work negotiated in discussions with CAF |  |  | 721491 | 1033341 | 311850 |  | 1041112.5541
Revised figure |  |  | 53058546 | 52746696 | 311850 |  | 76563558.4416
Add mandatory variants (these are all savings)
Mandatory Variant MV 5 flange lubrication (for 6 trams) |  |  | 0 | -37317 | 37317 |  | 0
Mandatory Variant MV 6 Passenger Counting system (for 6 trams) |  |  | -456225 | -456225 |  |  | -658333.3333
Sub total |  |  | 52602321 | 52253154 | 349167 |  | 75905225.1082
Maintenance Mobilisation |  |  | 2130686 | 0 | 2130686 |  | 3074582.9726
Sub Total |  |  | 54733007 | 52253154 | 2479853 |  | 78979808.0808
Add options in variant bid that should be in base bid (these are all savings)
CAF Variant CAF V2 complianc ewith EN standards instead of BS regarding smoke and fire |  |  | -425547 | -425547 |  |  | -614064.9351
CAF Variant Spare parts saving |  |  | -203202 | -381150 | 177948 |  | -293220.7792
CAF Variant saving to Mock up |  |  | 0 | -76230 | 76230
Sub Total |  |  | 54104258 | 51370227 | 2734031 |  | 78072522.3665
Discount for 20% first milestone |  | 1% | -541042.58 | 0 | -541042.58 |  | -780725.2237
|  |  | 53563215.42 | 51370227 | 2192988.42 |  | 77291797.1429
Depot Equipment - Firm |  |  | 194285 |  | 194285 | C | 280353.5354
Depot Equipment - Provisional |  |  | 1941112 | 0 | 1941112 | C | 2801027.417
Sub Total |  |  | 55698612.42 | 51370227 | 4328385.42 |  | 80373178.0952
Currency fluctuation | BAFO £/Euro | 0.693
| Hedged £/Euro | 0.7362 | 3472121.2937 | 0 | 3472121.2937
| % change | 6.234%
Net currency fluctuation:
Adjustment for CAF share of currency risk | Half of 1% | 0.5% | -278493.0621 | 0 | -278493.0621 |  | 3193628.2316
Total |  |  | 58892240.6516 | 51370227 | 7522013.6516
Other items
Model |  |  | 6000 |  | 6000
Total Price |  |  | 58898240.6516 | 51370227 | 7528013.6516
Transfer from Infraco budget for Depot Equipment |  |  | 2268512.6571 |  | -2268512.6571 | C
Comparable figure with Tramco Budget |  |  | 56629727.9945
Tramco Budget |  |  | 51370227
Increase in Budget over FBC Base costs = required tfr from risk allowance |  |  | 5259500.9945 |  | 5259500.9945
Comprising
| Maintenance mobilisation |  | 2130686
| Other changes/options by us |  | 603345
| Discount for 20% upfront |  | -541042.58
| Currency fluctuation |  | 3193628.2316
| Tram Supply |  | 54360220.0101
| Maintenance Mobilisation |  | 2263507.9844
| Depot Equipment |  | 2268512.6571
| Other Items |  | 6000
58898240.6516

## Risk Allowance QRA
EDINBURGH TRAM PROJECT | [119 empty] | 2026-07-29
Risk Allocation Report
Current Period End | [57 empty] | Total Allocation | £k |  |  |  | 0
[54 empty] | Risk Mean Sum |  |  |  | Phase 1A | Phase 1B
Sim Run P90 1A+1B | 51647.1016 | £k | [51 empty] | 38634.2515 | £k |  |  | 47036.8889 | 4610.2127 | £k
WBS Item | Allocated Risks |  |  |  | Impact Assessment |  |  |  | Exposure Period | [43 empty] | No of Periods | Sim Run Risk Mean | P90 Risk Allocation | Proportion allocated to 1A | Parameter used to Split 1A/1B | P90 Risk Allocation 1A | P90 Risk Allocation 1B | P90 Value Per Period | total P90 | 80:20 Sum | 80:20 %age | [43 empty] | Utilised for Risk Treatment | Utilised for Risk Exposure
| Risk ID | Cause | Risk Event | Effect | Prob | Current Impact Assessment £k |  |  | Start | End | [41 empty] | Construction End | [9 empty] | Cumulative | Cumulative | [6 empty] | 2008/09 | [12 empty] | 2009/10 | [12 empty] | 2010/11 | [8 empty] | Construction Programme End | [5 empty] | QUANTITATIVE RISK CALCULATIONS
[5 empty] | % | Min | Most Likely | Max | [45 empty] | £k | £k |  |  |  |  | £k |  | £k (P90) | % (P90) | 2007-11-10 | 2007-12-08 | 2008-01-05 | 2008-02-02 | 2008-03-01 | 2008-03-31 | 2008-04-26 | 2008-05-24 | 2008-06-21 | 2008-07-19 | 2008-08-16 | 2008-09-13 | 2008-10-11 | 2008-11-08 | 2008-12-06 | 2009-01-03 | 2009-01-31 | 2009-02-28 | 2009-03-31 | 2009-04-25 | 2009-05-23 | 2009-06-20 | 2009-07-18 | 2009-08-15 | 2009-09-12 | 2009-10-10 | 2009-11-07 | 2009-12-05 | 2010-01-02 | 2010-01-30 | 2010-02-27 | 2010-03-31 | 2010-05-01 | 2010-05-29 | 2010-06-26 | 2010-07-24 | 2010-08-21 | 2010-09-18 | 2010-10-16 | 2010-11-13 | 2010-12-11 | 2011-01-08 |  | £k | £k |  |  | Risk Distribution | Sim Run Risk Mean | Probability | Reverse Probability | Most Likely | No Impact | Cost @Risk | No Impact | Overall Contingency | time axis 2007-11-10 to 2011-01-08
7.4 Tramco | 905 | Not controlled by Project | Tramco Insolvency | Trams are not delivered;legal costs;delay | 1 | 25000 | 25000 | 25000 | 2007-03-01 | 2008-01-31 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 250 | 334.2054 | 80 |  | 267.3643 | 66.8411 | 111.4018 | 334.2054 | 334.2054 | 0.6471% | 111.4018 | 111.4018 | 111.4018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334.2054 | 0 |  | Tramco Delivery |  | TRIANG | #NAME? | 0.01 | 0.99 | 25000 | 0 | #NAME? | 0 | #NAME?
7.4 Tramco | 351 | Depot not completed on time | Trams are manufacturered but Depot unavailable to take delivery | Trams need to be stored resulting in storage costs | 50 | 100 | 300 | 600 | 2007-03-01 | 2009-09-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 166.5315 | 222.623 | 100 |  | 222.623 | 0 | 8.9049 | 222.623 | 556.8284 | 1.078% | 8.9049 | 8.9049 | 8.9049 | 8.9049 | 8.9049 | 8.9049 | 8.9049 | 8.9049 | 8.9049 | 8.9049 | 8.9049 | 8.9049 | 8.9049 | 8.9049 | 8.9049 | 8.9049 | 8.9049 | 8.9049 | 8.9049 | 8.9049 | 8.9049 | 8.9049 | 8.9049 | 8.9049 | 8.9049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222.623 | 0 |  | Tramco Delivery |  | TRIANG | #NAME? | 0.5 | 0.5 | 300 | 0 | #NAME? | 0 | #NAME?
7.4 Tramco | 142 | Base estimate allows only for minimum on-board supervisory and comms equipment. | Specification for on-board and supervisory equipment has not been established for Trams on Phase 1A. | A high specification is required for on-board supervisory and comms equipment. | 50 | 0 | 75 | 675 | 2007-07-19 | 2009-10-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 125.7465 | 168.1006 | 100 |  | 168.1006 | 0 | 6.724 | 168.1006 | 724.929 | 1.404% | 6.724 | 6.724 | 6.724 | 6.724 | 6.724 | 6.724 | 6.724 | 6.724 | 6.724 | 6.724 | 6.724 | 6.724 | 6.724 | 6.724 | 6.724 | 6.724 | 6.724 | 6.724 | 6.724 | 6.724 | 6.724 | 6.724 | 6.724 | 6.724 | 6.724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168.1006 | 0 |  | Tramco Delivery |  | TRIANG | #NAME? | 0.5 | 0.5 | 75 | 0 | #NAME? | 0 | #NAME?
7.4 Tramco | 906 | Currency fluctation Euro/Sterling | Tramco pricing risk between now and awarding contract | price may go up/down | 5 | 0 | 1500 | 3000 | 2007-03-01 | 2008-01-31 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 78.2531 | 104.6104 | 100 |  | 104.6104 | 0 | 34.8701 | 104.6104 | 829.5394 | 1.606% | 34.8701 | 34.8701 | 34.8701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.6104 | 0 |  | Tramco Procurement |  | TRIANG | #NAME? | 0.05 | 0.95 | 1500 | 0 | #NAME? | 0 | #NAME?
7.4 Tramco | 71 | Inadequate definition of availability, reliability and maintainability requirements | Unclear scope of desired performance levels. | Increased capex investment is necessary. | 30 | 0 | 250 | 500 | 2007-03-01 | 2008-07-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 75.2919 | 100.6519 | 100 |  | 100.6519 | 0 | 10.0652 | 100.6519 | 930.1913 | 1.801% | 10.0652 | 10.0652 | 10.0652 | 10.0652 | 10.0652 | 10.0652 | 10.0652 | 10.0652 | 10.0652 | 10.0652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100.6519 | 0 |  | Tramco Delivery |  | TRIANG | #NAME? | 0.3 | 0.7 | 250 | 0 | #NAME? | 0 | #NAME?
7.4 Tramco | 155 | Increase in specification over and above assumptions in base estimate regarding equipment and quality specification for tram vehicles | Business case runtime and CEC requirements (change in equipment and quality specification) | Increased cost of tramsets | 20 | 160 | 270 | 600 | 2007-07-19 | 2009-10-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 69.2837 | 92.6199 | 100 |  | 92.6199 | 0 | 3.7048 | 92.6199 | 1022.8112 | 1.98% | 3.7048 | 3.7048 | 3.7048 | 3.7048 | 3.7048 | 3.7048 | 3.7048 | 3.7048 | 3.7048 | 3.7048 | 3.7048 | 3.7048 | 3.7048 | 3.7048 | 3.7048 | 3.7048 | 3.7048 | 3.7048 | 3.7048 | 3.7048 | 3.7048 | 3.7048 | 3.7048 | 3.7048 | 3.7048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92.6199 | 0 |  | Tramco Procurement |  | TRIANG | #NAME? | 0.2 | 0.8 | 270 | 0 | #NAME? | 0 | #NAME?
7.4 Tramco | 98 | Problems with tram supplier (industrial relations, financial problems etc) | Delay in supply of vehicles - 1B | Time delay to operations, costs relating procurement of replacement manufacturer | 25 | 0 | 240 | 400 | 2007-07-19 | 2009-10-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 53.6148 | 71.6734 | 0 |  | 0 | 71.6734 | 2.8669 | 71.6734 | 1094.4846 | 2.119% | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71.6734 | 0 |  | Tramco Delivery |  | TRIANG | #NAME? | 0.25 | 0.75 | 240 | 0 | #NAME? | 0 | #NAME?
7.4 Tramco | 899 | Stakeholder indecision/unclarified role | Inability to determine and sign off aeshetic requirements for Tram | Programme delay in finalising design; potential cost impacts | 20 | 0 | 250 | 500 | 2007-07-19 | 2008-07-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 50.1663 | 67.0634 | 100 |  | 67.0634 | 0 | 6.7063 | 67.0634 | 1161.5481 | 2.249% | 6.7063 | 6.7063 | 6.7063 | 6.7063 | 6.7063 | 6.7063 | 6.7063 | 6.7063 | 6.7063 | 6.7063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67.0634 | 0 |  | Tramco Procurement |  | TRIANG | #NAME? | 0.2 | 0.8 | 250 | 0 | #NAME? | 0 | #NAME?
7.4 Tramco | 900 | SDS & Infraco procurement not familiar with chosen tram reqts | Depot design is not compatible with tram | Programme delay whilst Infraco modify Depot; Performance risk on Tramco TMA | 15 | 10 | 250 | 500 | 2007-07-19 | 2009-10-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 38.3901 | 51.3207 | 100 |  | 51.3207 | 0 | 2.0528 | 51.3207 | 1212.8688 | 2.348% | 2.0528 | 2.0528 | 2.0528 | 2.0528 | 2.0528 | 2.0528 | 2.0528 | 2.0528 | 2.0528 | 2.0528 | 2.0528 | 2.0528 | 2.0528 | 2.0528 | 2.0528 | 2.0528 | 2.0528 | 2.0528 | 2.0528 | 2.0528 | 2.0528 | 2.0528 | 2.0528 | 2.0528 | 2.0528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51.3207 | 0 |  | Tramco Delivery |  | TRIANG | #NAME? | 0.15 | 0.85 | 250 | 0 | #NAME? | 0 | #NAME?
7.4 Tramco | 97 | Problems with tram supplier (industrial relations, financial problems etc) | Delay in supply of vehicles - 1A | Time delay to operations, costs relating procurement of replacement manufacturer | 15 | 0 | 260 | 450 | 2007-07-19 | 2009-10-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 35.8055 | 47.8656 | 100 |  | 47.8656 | 0 | 1.9146 | 47.8656 | 1260.7344 | 2.441% | 1.9146 | 1.9146 | 1.9146 | 1.9146 | 1.9146 | 1.9146 | 1.9146 | 1.9146 | 1.9146 | 1.9146 | 1.9146 | 1.9146 | 1.9146 | 1.9146 | 1.9146 | 1.9146 | 1.9146 | 1.9146 | 1.9146 | 1.9146 | 1.9146 | 1.9146 | 1.9146 | 1.9146 | 1.9146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.8656 | 0 |  | Tramco Delivery |  | TRIANG | #NAME? | 0.15 | 0.85 | 260 | 0 | #NAME? | 0 | #NAME?
7.4 Tramco | 143 | Base estimate allows only for minimum on-board supervisory and comms equipment. | Specification for on-board and supervisory equipment has not been established for Trams on Phase 1B. | A high specification is required for on-board supervisory and comms equipment. | 50 | 0 | 25 | 100 | 2007-07-19 | 2009-10-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 20.8975 | 27.9363 | 0 |  | 0 | 27.9363 | 1.1175 | 27.9363 | 1288.6707 | 2.495% | 1.1175 | 1.1175 | 1.1175 | 1.1175 | 1.1175 | 1.1175 | 1.1175 | 1.1175 | 1.1175 | 1.1175 | 1.1175 | 1.1175 | 1.1175 | 1.1175 | 1.1175 | 1.1175 | 1.1175 | 1.1175 | 1.1175 | 1.1175 | 1.1175 | 1.1175 | 1.1175 | 1.1175 | 1.1175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.9363 | 0 |  | Tramco Delivery |  | TRIANG | #NAME? | 0.5 | 0.5 | 25 | 0 | #NAME? | 0 | #NAME?
7.4 Tramco | 319 | Trams are not compatiable and interoperable with each other and other parts of the system | Trams found to be incompatible during commisisoning | Delay to commissioning, costs to deal with issue | 10 | 0 |  | 50 | 2009-10-01 | 2010-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 16 | 2.4505 | 3.2758 | 100 |  | 3.2758 | 0 | 0.20474 | 3.2758 | 1291.9465 | 2.501% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.20474 | 0.20474 | 0.20474 | 0.20474 | 0.20474 | 0.20474 | 0.20474 | 0.20474 | 0.20474 | 0.20474 | 0.20474 | 0.20474 | 0.20474 | 0.20474 | 0.20474 | 0.20474 | 0 | 3.2758 | 0 |  | Tramco Delivery |  | UNIFORM | #NAME? | 0.1 | 0.9 | 0 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 48 | Two stage tender pricing does not achieve price certainty for works at first stage. | Price certainty is not achieved | Price creep post tender (during pre-construction period). Tender evaluation period exceeds 2 months currently planned. Bidder may attempt to price low at first stage. | 50 | 5000 | 10000 | 15000 | 2007-01-12 | 2012-01-03 | [42 empty] | 42 | 4997.2601 | 6680.4452 | 80 |  | 5344.3561 | 1336.089 | 159.0582 | 6680.4452 | 7972.3916 | 15.44% | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 159.0582 | 6680.4452 | 0 |  | Infraco Procurement |  | TRIANG | #NAME? | 0.5 | 0.5 | 10000 | 0 | #NAME? | 0 | #NAME? | bar: 2007-11-10 to 2011-01-08
7.3 Infraco | 870 | SDS Designs are late and do not provide detail Infraco requires | Infraco does not have detail to achieve contract close without provisional designs | Delay to due diligence and start on site and need to appoint aditional design consultants | 94.5 |  | 3000 |  | 2007-01-31 | 2008-01-31 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2835 | 3789.8892 | 100 |  | 3789.8892 | 0 | 1263.2964 | 3789.8892 | 11762.2809 | 22.77% | 1263.2964 | 1263.2964 | 1263.2964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3789.8892 | 0 |  | Infraco Procurement |  | DISCRETE | #NAME? | 0.945 | 0.055 | 3000 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 952 | Scope of works relating to Wide Area Modelling (WAM) have not been agreed with SDS because they consider this to be out with the scope of their contract. | Uncertainty about extent of construction works required on road network relating to Wide Area Modelling issues. | Potential claim from SDS to deal with additional design work; Potential construction costs to deal with WAM issues (difficult to quantify without design) over and above those already included. | 95 | 0 |  | 3000 | 2006-07-03 | 2008-09-24 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1426.1748 | 1906.5412 | 100 |  | 1906.5412 | 0 | 158.8784 | 1906.5412 | 13668.8221 | 26.47% | 158.8784 | 158.8784 | 158.8784 | 158.8784 | 158.8784 | 158.8784 | 158.8784 | 158.8784 | 158.8784 | 158.8784 | 158.8784 | 158.8784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1906.5412 | 0 |  | Infraco Procurement |  | UNIFORM | #NAME? | 0.95 | 0.05 | 0 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 47 | Poor design and review processes; cumbersome approvals process; reiterative design/approvals process. | Completion of MUDFA works is delayed (due to late design/approvals) - late utility diversions in advance of Infraco works. | Increase in price and time delay in the Infraco contract; Infraco could end up delay to commencement or with utility diversion and would have to price for or have to carry out unplanned re-sequencing; Claims from MUDFA as a result of being unable to proce | 50 | 400 | 2400 | 4800 | 2007-10-01 | 2008-01-31 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1268.412 | 1695.6405 | 80 |  | 1356.5124 | 339.1281 | 565.2135 | 1695.6405 | 15364.4626 | 29.75% | 565.2135 | 565.2135 | 565.2135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1695.6405 | 0 |  | Infraco Procurement |  | TRIANG | #NAME? | 0.5 | 0.5 | 2400 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 70 | SDS does not provide its defined deliverables (technical specs) in accordance with the SDS contract. Infraco Proposals not fully considered. | Poor definition of design and Employers Requirements in Infraco tender documents | Creates impact on the Infraco ability to develop its tender - pricing and supply chain. Increase in time for BAFO and increase in costs. Increase in bidder queries. | 50 | 900 | 1800 | 2700 | 2006-10-02 | 2008-01-31 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 900.4144 | 1203.6934 | 100 |  | 1203.6934 | 0 | 401.2311 | 1203.6934 | 16568.156 | 32.08% | 401.2311 | 401.2311 | 401.2311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1203.6934 | 0 |  | Infraco Procurement |  | TRIANG | #NAME? | 0.5 | 0.5 | 1800 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 931 | Utilities assets uncovered during construction that were not previously accounted for; unidentified abandoned utilities assets; known redudant utilities; unknown live utilities; unknown redundant utilities. | Unknown or abandoned assets impacts scope of Infraco work | Re-design and delay as investigation takes place and solution implemented; Increase in Capex cost as a result of additional works. | 90 | 500 |  | 1000 | 2007-10-01 | 2010-07-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 675.2796 | 902.7283 | 80 |  | 722.1827 | 180.5457 | 25.0758 | 902.7283 | 17470.8843 | 33.83% | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 25.0758 | 0 | 0 | 0 | 0 | 0 | 0 | 902.7283 | 0 |  | Infraco Delivery |  | UNIFORM | #NAME? | 0.9 | 0.1 | 0 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 279 |  | Third party consents including Network Rail, CEC Planning, CEC Roads Department, Historic Scotland, Building Fixing Owner consent is denied or delayed | Delay to programme; Risk transfer response by bidders is to return risk to tie; Increased out-turn cost if transferred and also as a result of any delay due to inflation. | 50 |  | 1250 |  | 2006-07-03 | 2009-12-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 625 | 835.5135 | 90 |  | 751.9621 | 83.5513 | 29.8398 | 835.5135 | 18306.3978 | 35.45% | 29.8398 | 29.8398 | 29.8398 | 29.8398 | 29.8398 | 29.8398 | 29.8398 | 29.8398 | 29.8398 | 29.8398 | 29.8398 | 29.8398 | 29.8398 | 29.8398 | 29.8398 | 29.8398 | 29.8398 | 29.8398 | 29.8398 | 29.8398 | 29.8398 | 29.8398 | 29.8398 | 29.8398 | 29.8398 | 29.8398 | 29.8398 | 29.8398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 835.5135 | 0 |  | Design & Consents |  | DISCRETE | #NAME? | 0.5 | 0.5 | 1250 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 22 | Base estimate does not account for presence of hazardous materials on land | Hazardous materials encountered during construction | Additional treatment costs and protective measures | 50 | 100 | 400 | 2000 | 2008-01-01 | 2010-12-31 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 39 | 420.2385 | 561.784 | 80 |  | 449.4272 | 112.3568 | 14.4047 | 561.784 | 18868.1818 | 36.53% | 0 | 0 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 14.4047 | 0 | 561.784 | 0 |  | Infraco Delivery |  | TRIANG | #NAME? | 0.5 | 0.5 | 400 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 1011 |  | Occurrence of any delay caused by Utilities Works, MUDFA Works, breach of Third Party Agreements, Unplanned City Events, New Utilities and/or any other event referred to as a Compensation Event | Delay and additional cost | 40 |  | 1000 |  | 2007-09-27 | 2011-12-31 | [42 empty] | 42 | 400 | 534.7286 | 95 |  | 507.9922 | 26.7364 | 12.7316 | 534.7286 | 19402.9104 | 37.57% | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 12.7316 | 534.7286 | 0 |  | Infraco Delivery |  | DISCRETE | #NAME? | 0.4 | 0.6 | 1000 | 0 | #NAME? | 0 | #NAME? | bar: 2007-11-10 to 2011-01-08
7.3 Infraco | 178 | Procurement Strategy novates SDS to InfraCo after Detailed Design; Limited input on buidability from Infraco. | Infraco due diligence process reveals that design rework will be required after novation of SDS. | Bids will be higher than envisaged in base estimate as Infraco will price for re-work. | 75 |  | 500 |  | 2006-10-02 | 2008-01-31 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 375 | 501.3081 | 80 |  | 401.0465 | 100.2616 | 167.1027 | 501.3081 | 19904.2185 | 38.54% | 167.1027 | 167.1027 | 167.1027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 501.3081 | 0 |  | Infraco Procurement |  | DISCRETE | #NAME? | 0.75 | 0.25 | 500 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 132 | Realignment of existing road geometry required | Increase in off-route junction improvements, certain junctions requiring realignment of kerbs etc | Increase in design costs. | 80 | 0 | 250 | 500 | 2006-07-03 | 2009-01-26 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 199.8311 | 267.1386 | 80 |  | 213.7108 | 53.4277 | 16.6962 | 267.1386 | 20171.3571 | 39.06% | 16.6962 | 16.6962 | 16.6962 | 16.6962 | 16.6962 | 16.6962 | 16.6962 | 16.6962 | 16.6962 | 16.6962 | 16.6962 | 16.6962 | 16.6962 | 16.6962 | 16.6962 | 16.6962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267.1386 | 0 |  | Infraco Procurement |  | TRIANG | #NAME? | 0.8 | 0.2 | 250 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 172 | Area of possible contamination and unstable ground (unlicensed tip) has been highlighted during desk study immediately to east of Gogar Burn - investigation for CERT project indicates that this consists of building rubble and domestic waste. | Tramway runs through area of possible contamination and special foundation is required to cope with unstable ground | Increase in costs to provide special foundation solution | 95 | 100 | 200 | 300 | 2007-01-01 | 2008-07-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 190.0006 | 253.9969 | 100 |  | 253.9969 | 0 | 25.3997 | 253.9969 | 20425.354 | 39.55% | 25.3997 | 25.3997 | 25.3997 | 25.3997 | 25.3997 | 25.3997 | 25.3997 | 25.3997 | 25.3997 | 25.3997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253.9969 | 0 |  | Infraco Procurement |  | TRIANG | #NAME? | 0.95 | 0.05 | 200 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 105 | Encountering archaeological finds/burials/munitions during construction | Exhumation of archaeological finds/burials | Delay in construction programme | 85 | 0 | 150 | 500 | 2007-09-28 | 2010-07-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 183.5706 | 245.4011 | 90 |  | 220.861 | 24.5401 | 6.8167 | 245.4011 | 20670.7551 | 40.02% | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 6.8167 | 0 | 0 | 0 | 0 | 0 | 0 | 245.4011 | 0 |  | Infraco Delivery |  | TRIANG | #NAME? | 0.85 | 0.15 | 150 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 318 | Failure to make arrangements with Utilities for the phasing of necessary connections; Utility Company operational constraints | Utility connections cannot proceed as planned | Potential delay to start of Infraco works in certain sections | 50 | 100 |  | 500 | 2007-04-04 | 2009-01-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 150.3888 | 201.043 | 80 |  | 160.8344 | 40.2086 | 11.8261 | 201.043 | 20871.798 | 40.41% | 11.8261 | 11.8261 | 11.8261 | 11.8261 | 11.8261 | 11.8261 | 11.8261 | 11.8261 | 11.8261 | 11.8261 | 11.8261 | 11.8261 | 11.8261 | 11.8261 | 11.8261 | 11.8261 | 11.8261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 201.043 | 0 |  | Infraco Delivery |  | UNIFORM | #NAME? | 0.5 | 0.5 | 0 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 302 | Steel shortage due to global demand and ongoing Corus transfer of rail production facility | Delay or price increase due to steel shortage | Long lead times, additional cost due to inflation, programme delay. | 20 | 500 | 750 | 1000 | 2007-04-26 | 2008-01-31 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 149.9875 | 200.5065 | 80 |  | 160.4052 | 40.1013 | 66.8355 | 200.5065 | 21072.3045 | 40.8% | 66.8355 | 66.8355 | 66.8355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.5065 | 0 |  | Infraco Procurement |  | TRIANG | #NAME? | 0.2 | 0.8 | 750 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 66 | Infraco and Tram systems not compatible and/or contracts not aligned. | Inadequate system integration | Time delay and interface problems between specialist contractors / sub systems. | 10 | 0 | 1000 | 3000 | 2007-11-01 | 2008-01-31 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 132.9477 | 177.7273 | 80 |  | 142.1819 | 35.5455 | 59.2424 | 177.7273 | 21250.0318 | 41.14% | 59.2424 | 59.2424 | 59.2424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177.7273 | 0 |  | Infraco Delivery |  | TRIANG | #NAME? | 0.1 | 0.9 | 1000 | 1 | #NAME? | 1 | #NAME?
7.3 Infraco | 303 | Proximity in time and space to other works within Edinburgh | Third party works in Edinburgh impact on Tram infrastructure construction | CEC may limit the number of workfronts allowed; programme re-sequencing; slower overall construction rate; effective increase in preliminaries; overall programme delay | 40 | 100 | 300 | 500 | 2007-09-30 | 2010-07-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 119.7652 | 160.1047 | 80 |  | 128.0838 | 32.0209 | 4.4474 | 160.1047 | 21410.1365 | 41.45% | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 4.4474 | 0 | 0 | 0 | 0 | 0 | 0 | 160.1047 | 0 |  | Infraco Delivery |  | TRIANG | #NAME? | 0.4 | 0.6 | 300 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 173 | Uncertainty over extent of contaminated land on route | Tramway runs through area of previously unidentified contamination and material requires to be removed and replaced (dig and dump). | Increase in costs to remove material to special and other tip. | 2.5 | 1368 |  | 8208 | 2006-09-29 | 2010-07-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 119.6174 | 159.9072 | 80 |  | 127.9257 | 31.9814 | 4.4419 | 159.9072 | 21570.0437 | 41.76% | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 4.4419 | 0 | 0 | 0 | 0 | 0 | 0 | 159.9072 | 0 |  | Infraco Delivery |  | UNIFORM | #NAME? | 0.025 | 0.975 | 0 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 134 | Network Rail possessions over and above that estimate are required | Compensation paid to Train Operating Companies | Increased compensation paid to Train Operating Companies | 5 | 500 | 2000 | 4000 | 2007-10-01 | 2009-01-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 108.0024 | 144.38 | 100 |  | 144.38 | 0 | 8.4929 | 144.38 | 21714.4237 | 42.04% | 8.4929 | 8.4929 | 8.4929 | 8.4929 | 8.4929 | 8.4929 | 8.4929 | 8.4929 | 8.4929 | 8.4929 | 8.4929 | 8.4929 | 8.4929 | 8.4929 | 8.4929 | 8.4929 | 8.4929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144.38 | 0 |  | Network Rail |  | TRIANG | #NAME? | 0.05 | 0.95 | 2000 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 115 | Network Rail cancels planned possessions | Planned work at interface with Network Rail is delayed | Time delay and resulting cost increase | 10 | 350 | 750 | 2000 | 2007-10-01 | 2009-01-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 103.7259 | 138.6631 | 100 |  | 138.6631 | 0 | 8.1567 | 138.6631 | 21853.0868 | 42.31% | 8.1567 | 8.1567 | 8.1567 | 8.1567 | 8.1567 | 8.1567 | 8.1567 | 8.1567 | 8.1567 | 8.1567 | 8.1567 | 8.1567 | 8.1567 | 8.1567 | 8.1567 | 8.1567 | 8.1567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138.6631 | 0 |  | Network Rail |  | TRIANG | #NAME? | 0.1 | 0.9 | 750 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 1010 |  | Occurrence of termination or omission of Infraco Works if permission to resume not granted by tie within 6 months | Project suspension or cancellation | 1 |  | 10000 |  | 2007-09-27 | 2011-01-31 | [42 empty] | 42 | 101.98 | 136.3291 | 80 |  | 109.0633 | 27.2658 | 3.2459 | 136.3291 | 21989.4159 | 42.58% | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 3.2459 | 136.3291 | 0 |  | Infraco Procurement |  | DISCRETE | #NAME? | 0.01 | 0.99 | 10000 | 0 | #NAME? | 0 | #NAME? | bar: 2007-11-10 to 2011-01-08
7.3 Infraco | 865 | Buildings contain asbestos that was not uncovered during surveys | Asbestos found during demolition works and excavations for construction | Cost and delay during investigation and removal | 90 | 60 |  | 150 | 2008-01-01 | 2009-03-31 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 94.5494 | 126.3956 | 80 |  | 101.1165 | 25.2791 | 7.435 | 126.3956 | 22115.8115 | 42.82% | 0 | 0 | 7.435 | 7.435 | 7.435 | 7.435 | 7.435 | 7.435 | 7.435 | 7.435 | 7.435 | 7.435 | 7.435 | 7.435 | 7.435 | 7.435 | 7.435 | 7.435 | 7.435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126.3956 | 0 |  | Infraco Delivery |  | UNIFORM | #NAME? | 0.9 | 0.1 | 0 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 11 | Contractors methodology not adequately assessed | Land required for access to workfront not acquired | Additional management and acquisition costs relating to acquiring land to gain access | 20 | 300 |  | 300 | 2007-05-08 | 2009-01-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 60 | 80.2093 | 80 |  | 64.1674 | 16.0419 | 5.0131 | 80.2093 | 22196.0208 | 42.98% | 5.0131 | 5.0131 | 5.0131 | 5.0131 | 5.0131 | 5.0131 | 5.0131 | 5.0131 | 5.0131 | 5.0131 | 5.0131 | 5.0131 | 5.0131 | 5.0131 | 5.0131 | 5.0131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.2093 | 0 |  | Land compensation |  | UNIFORM | #NAME? | 0.2 | 0.8 | 0 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 67 | Interface with CEC as roads authority | Roads maintenance is not carried out | CEC is in breach of its statutory duties | 20 | 100 | 250 | 500 | 2008-01-01 | 2008-01-31 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 55.8916 | 74.7172 | 80 |  | 59.7737 | 14.9434 | 74.7172 | 74.7172 | 22270.7379 | 43.12% | 0 | 0 | 74.7172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.7172 | 0 |  | Infraco Delivery |  | TRIANG | #NAME? | 0.2 | 0.8 | 250 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 1007 |  | Introduction of alternative Submittal Programme where tie cannot comply with the original programme (not arising from Infraco default) | Delay | 10 |  | 500 |  | 2007-09-27 | 2011-12-31 | [42 empty] | 42 | 50 | 66.8411 | 100 |  | 66.8411 | 0 | 1.5915 | 66.8411 | 22337.579 | 43.25% | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 66.8411 | 0 |  | Infraco Delivery |  | DISCRETE | #NAME? | 0.1 | 0.9 | 500 | 0 | #NAME? | 0 | #NAME? | bar: 2007-11-10 to 2011-01-08
7.3 Infraco | 1003 |  | Failure to liaise with any party, as reasonably required, to produce information required so that the Infraco Works can be progressed properly, according to Programme and in accordance with the Infraco Contract | Delay to project and additional costs | 10 |  | 500 |  | 2007-09-27 | 2011-12-31 | [42 empty] | 42 | 50 | 66.8411 | 80 |  | 53.4729 | 13.3682 | 1.5915 | 66.8411 | 22404.4201 | 43.38% | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 66.8411 | 0 |  | Infraco Delivery |  | DISCRETE | #NAME? | 0.1 | 0.9 | 500 | 0 | #NAME? | 0 | #NAME? | bar: 2007-11-10 to 2011-01-08
7.3 Infraco | 1009 |  | Suspension on instructions of ties Representative in circumstances outwith the following: Suspension provided for in the Agreement, Suspension necessary by reason of default of the Infraco, Suspension necessary for the safety of the Infraco Works. | Delay to project | 5 |  | 1000 |  | 2007-09-27 | 2011-12-31 | [42 empty] | 42 | 50 | 66.8411 | 80 |  | 53.4729 | 13.3682 | 1.5915 | 66.8411 | 22471.2612 | 43.51% | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 1.5915 | 66.8411 | 0 |  | Infraco Delivery |  | DISCRETE | #NAME? | 0.05 | 0.95 | 1000 | 0 | #NAME? | 0 | #NAME? | bar: 2007-11-10 to 2011-01-08
7.3 Infraco | 103 | Delay in design information release from specialist tram manufacturer | Delay in detailing of stops, trackway, OLE etc for Phase 1A | Time delay and consequent costs | 15 | 0 | 225 | 750 | 2007-03-01 | 2008-11-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 48.0593 | 64.2468 | 90 |  | 57.8221 | 6.4247 | 4.5891 | 64.2468 | 22535.5079 | 43.63% | 4.5891 | 4.5891 | 4.5891 | 4.5891 | 4.5891 | 4.5891 | 4.5891 | 4.5891 | 4.5891 | 4.5891 | 4.5891 | 4.5891 | 4.5891 | 4.5891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64.2468 | 0 |  | Infraco Delivery |  | TRIANG | #NAME? | 0.15 | 0.85 | 225 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 100 | 3rd party agreements impact on works not accounted for in estimate/ become apparent during construction | Increase in fencing, walls, screen requirements | Additional construction costs | 30 | 60 | 120 | 240 | 2006-07-03 | 2008-01-31 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 41.8918 | 56.0018 | 80 |  | 44.8015 | 11.2004 | 18.6673 | 56.0018 | 22591.5098 | 43.74% | 18.6673 | 18.6673 | 18.6673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.0018 | 0 |  | Infraco Delivery |  | TRIANG | #NAME? | 0.3 | 0.7 | 120 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 54 | Contractor default e.g. insolvency. | Construction bond not available in the event of Infraco default | Increase in cost and progeamme due to appointment of replacement contractor | 1 | 0 | 3300 | 6300 | 2007-01-12 | 2011-12-31 | [42 empty] | 42 | 31.0578 | 41.5188 | 80 |  | 33.215 | 8.3038 | 0.98854 | 41.5188 | 22633.0286 | 43.82% | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 0.98854 | 41.5188 | 0 |  | Infraco Delivery |  | TRIANG | #NAME? | 0.01 | 0.99 | 3300 | 0 | #NAME? | 0 | #NAME? | bar: 2007-11-10 to 2011-01-08
7.3 Infraco | 1006 |  | Failure to comply with the Submittal Programme timescales | Delay and additional costs | 50 |  | 50 |  | 2007-09-27 | 2011-12-31 | [42 empty] | 42 | 27 | 36.0942 | 80 |  | 28.8753 | 7.2188 | 0.85939 | 36.0942 | 22669.1227 | 43.89% | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 0.85939 | 36.0942 | 0 |  | Infraco Delivery |  | DISCRETE | #NAME? | 0.5 | 0.5 | 50 | 0 | #NAME? | 0 | #NAME? | bar: 2007-11-10 to 2011-01-08
7.3 Infraco | 1013 |  | Indirect Losses sustained in by Third Parties claiming against tie or Infraco or because of third party agreements or land consents | Additional cost | 1 |  | 2000 |  | 2007-09-27 | 2011-01-31 | [42 empty] | 42 | 20 | 26.7364 | 90 |  | 24.0628 | 2.6736 | 0.63658 | 26.7364 | 22695.8592 | 43.94% | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 0.63658 | 26.7364 | 0 |  | Infraco Delivery |  | DISCRETE | #NAME? | 0.01 | 0.99 | 2000 | 0 | #NAME? | 0 | #NAME? | bar: 2007-11-10 to 2011-01-08
7.3 Infraco | 205 | Network Rail issue new Group and Company Standards during construction. Design and construction is aligned to current Network Rail Group and Company Standards. | Network Rail emerging Group and Company Standards are different at time of construction | New standards require to be adopted resulting in re-design, delay and increased construction cost. | 20 | 0 |  | 150 | 2007-10-01 | 2010-08-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 37 | 15.2786 | 20.4247 | 80 |  | 16.3398 | 4.0849 | 0.55202 | 20.4247 | 22716.2839 | 43.98% | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0.55202 | 0 | 0 | 0 | 0 | 0 | 20.4247 | 0 |  | Infraco Delivery |  | UNIFORM | #NAME? | 0.2 | 0.8 | 0 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 68 | Interface with Transdev | Supply of commissioning services from Transdev to Infraco. | Delay and costs incurred by Infraco. | 1 | 0 | 1000 | 3000 | 2009-09-30 | 2011-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 17 | 12.1569 | 16.2516 | 80 |  | 13.0013 | 3.2503 | 0.95598 | 16.2516 | 22732.5355 | 44.02% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95598 | 0.95598 | 0.95598 | 0.95598 | 0.95598 | 0.95598 | 0.95598 | 0.95598 | 0.95598 | 0.95598 | 0.95598 | 0.95598 | 0.95598 | 0.95598 | 0.95598 | 0.95598 | 0.95598 | 16.2516 | 0 |  | Infraco Delivery |  | TRIANG | #NAME? | 0.01 | 0.99 | 1000 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 1012 |  | Occurrence of any referable delay/costs caused by suspension by ties Representative |  | 1 |  | 1000 |  | 2007-09-27 | 2011-12-31 | [42 empty] | 42 | 10 | 13.3682 | 80 |  | 10.6946 | 2.6736 | 0.31829 | 13.3682 | 22745.9037 | 44.04% | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 0.31829 | 13.3682 | 0 |  | Infraco Delivery |  | DISCRETE | #NAME? | 0.01 | 0.99 | 1000 | 0 | #NAME? | 0 | #NAME? | bar: 2007-11-10 to 2011-01-08
7.3 Infraco | 150 | Blackspots for radio/mobile communications | Geographic areas where radio/mobile communications cannot obtain signal | Additional remedial equipment required e.g. repeater masts, booster packs etc | 50 | 0 |  | 10 | 2009-09-30 | 2010-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 16 | 2.4778 | 3.3124 | 80 |  | 2.6499 | 0.66247 | 0.20702 | 3.3124 | 22749.2161 | 44.05% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.20702 | 0.20702 | 0.20702 | 0.20702 | 0.20702 | 0.20702 | 0.20702 | 0.20702 | 0.20702 | 0.20702 | 0.20702 | 0.20702 | 0.20702 | 0.20702 | 0.20702 | 0.20702 | 0 | 3.3124 | 0 |  | Infraco Delivery |  | UNIFORM | #NAME? | 0.5 | 0.5 | 0 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 304 | Infrastructure design development e.g. building fixing approvals not achieved as designed | Utilities (diverted by MUDFA or left in place) are found to be in the path of infrastructure works at time of construction | Additional utilities diversions are required to be undertaken by Infraco with additional cost and programme impacts | 20 | 0 |  | 25 | 2007-10-01 | 2010-12-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 41 | 2.4612 | 3.2902 | 95 |  | 3.1257 | 0.16451 | 0.080248 | 3.2902 | 22752.5063 | 44.05% | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0.080248 | 0 | 3.2902 | 0 |  | Infraco Delivery |  | UNIFORM | #NAME? | 0.2 | 0.8 | 0 | 0 | #NAME? | 0 | #NAME?
7.2 MUDFA/Utilities | 164 | Utilities assets uncovered during construction that were not previously accounted for; unidentified abandoned utilities assets; asbestos found in excavation for utilities diversion; unknown cellars and basements intrude into works area; other physical obs | Unknown or abandoned assets or unforeseen/contaminated ground conditions affect scope of MUDFA work. | Re-design and delay as investigation takes place and solution implemented; Increase in Capex cost as a result of additional works. | 95 | 2000 | 5000 | 8500 | 2007-04-02 | 2008-12-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 4908.3995 | 6561.6544 | 95 |  | 6233.5717 | 328.0827 | 437.4436 | 6561.6544 | 29314.1607 | 56.76% | 437.4436 | 437.4436 | 437.4436 | 437.4436 | 437.4436 | 437.4436 | 437.4436 | 437.4436 | 437.4436 | 437.4436 | 437.4436 | 437.4436 | 437.4436 | 437.4436 | 437.4436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6561.6544 | 0 |  | MUDFA |  | TRIANG | #NAME? | 0.95 | 0.05 | 5000 | 0 | #NAME? | 0 | #NAME?
7.2 MUDFA/Utilities | 139 | Utilities diversion outline specification only from plans | Uncertainty of Utilities location and consequently required diversion work/ unforeseen utility services within LoD | Increase in MUDFA costs or delays as a result of carrying out more diversions than estimated | 90 | 0 | 2000 | 4000 | 2007-04-02 | 2008-12-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1795.6964 | 2400.5257 | 95 |  | 2280.4994 | 120.0263 | 160.035 | 2400.5257 | 31714.6863 | 61.41% | 160.035 | 160.035 | 160.035 | 160.035 | 160.035 | 160.035 | 160.035 | 160.035 | 160.035 | 160.035 | 160.035 | 160.035 | 160.035 | 160.035 | 160.035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400.5257 | 0 |  | MUDFA |  | TRIANG | #NAME? | 0.9 | 0.1 | 2000 | 0 | #NAME? | 0 | #NAME?
7.2 MUDFA/Utilities | 342 | Tram alignment at A8 crossing at Gogar co-incides BT data nests/cable (main coms link between Glasgow and Edinburgh) | A8 crossing tunnel requires special design or BT data nest/cables require to be moved | Capex cost to cover BT data nest/cable move; additional design costs; delay while works to undertake move are carried out; additional tunnelling costs. | 80 | 1000 | 1250 | 1500 | 2007-04-04 | 2008-09-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 999.7154 | 1336.4412 | 100 |  | 1336.4412 | 0 | 111.3701 | 1336.4412 | 33051.1275 | 63.99% | 111.3701 | 111.3701 | 111.3701 | 111.3701 | 111.3701 | 111.3701 | 111.3701 | 111.3701 | 111.3701 | 111.3701 | 111.3701 | 111.3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1336.4412 | 0 |  | MUDFA |  | TRIANG | #NAME? | 0.8 | 0.2 | 1250 | 0 | #NAME? | 0 | #NAME?
7.2 MUDFA/Utilities | 914 | Required approval/acceptance turnaround time does not reflect SUC standard practice; SUCs do not have enough resource or process capability to achieve 20 day turnaround | Statutory Utility Companies unable to meet design approval/acceptance turnaround time to meet programme | Additional period required for design approval/acceptance turnaround | 95 |  | 880 |  | 2007-03-02 | 2008-12-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 836 | 1117.5829 | 95 |  | 1061.7037 | 55.8791 | 74.5055 | 1117.5829 | 34168.7104 | 66.16% | 74.5055 | 74.5055 | 74.5055 | 74.5055 | 74.5055 | 74.5055 | 74.5055 | 74.5055 | 74.5055 | 74.5055 | 74.5055 | 74.5055 | 74.5055 | 74.5055 | 74.5055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1117.5829 | 0 |  | MUDFA |  | DISCRETE | #NAME? | 0.95 | 0.05 | 880 | 0 | #NAME? | 0 | #NAME?
7.2 MUDFA/Utilities | 911 | Scottish Power own and maintain a cable tunnel in the vicinity of Leith Walk that may or may not interfere with Tram construction and operation; exact location and depth of tunnel is unknown; condition of tunnel is unknown. | Presence of Scottish Power tunnel in Leith Walk requires radical solution | Tunnel may have to be decommissioned and re-laid in a more suitable location; tram alignment may require to be adjusted; special foundation soluiton e.g. cantilever may be required; increased capex; potential for tunnel collapse during operation and conse | 80 | 400 | 500 | 600 | 2007-04-02 | 2008-10-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 399.9756 | 534.6961 | 100 |  | 534.6961 | 0 | 41.1305 | 534.6961 | 34703.4064 | 67.19% | 41.1305 | 41.1305 | 41.1305 | 41.1305 | 41.1305 | 41.1305 | 41.1305 | 41.1305 | 41.1305 | 41.1305 | 41.1305 | 41.1305 | 41.1305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 534.6961 | 0 |  | MUDFA |  | TRIANG | #NAME? | 0.8 | 0.2 | 500 | 0 | #NAME? | 0 | #NAME?
7.1.3 Depot | 974 | Innacurate Topo Survey results | Increase in levels of Spoil Excavation | Increased Cost & Programme extension | 25 | 100 | 300 | 500 | 2007-05-14 | 2008-08-24 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 74.6895 | 99.8465 | 100 |  | 99.8465 | 0 | 9.077 | 99.8465 | 34803.2529 | 67.39% | 9.077 | 9.077 | 9.077 | 9.077 | 9.077 | 9.077 | 9.077 | 9.077 | 9.077 | 9.077 | 9.077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99.8465 | 0 |  | Infraco Delivery |  | TRIANG | #NAME? | 0.25 | 0.75 | 300 | 0 | #NAME? | 0 | #NAME?
7.1.3 Depot | 981 | Existing Spoil Site Unable to accept future spoil | Increase in the Lothian Valuation Joint Board rateable value of the spoil site | New Landfill site will have to be found and agreements reached. Possibility of increased costs | 80 | 0 | 25 | 50 | 2007-07-19 | 2008-03-31 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 20.0031 | 26.7406 | 100 |  | 26.7406 | 0 | 4.4568 | 26.7406 | 34829.9935 | 67.44% | 4.4568 | 4.4568 | 4.4568 | 4.4568 | 4.4568 | 4.4568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.7406 | 0 |  | Infraco Delivery |  | TRIANG | #NAME? | 0.8 | 0.2 | 25 | 0 | #NAME? | 0 | #NAME?
7.1.3 Depot | 876 | Agreement with SEPA fo use Gravity Drain Proposal | Gravity Drain Proposal | Cost & time saving | 79.5 | 12.5 | 12.5 | 12.5 | 2008-03-19 | 2008-07-08 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9.9375 | 13.2847 | 100 |  | 13.2847 | 0 | 3.3212 | 13.2847 | 34843.2782 | 67.46% | 0 | 0 | 0 | 0 | 0 | 3.3212 | 3.3212 | 3.3212 | 3.3212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.2847 | 0 |  | Infraco Delivery |  | TRIANG | #NAME? | 0.795 | 0.205 | 12.5 | 0 | #NAME? | 0 | #NAME?
7.1.2 Badger Relocation | 894 | Ineffective/Inappropriate Proposals; new setts must be built before old ones can be closed and licenses will not be issued until nearer time of closure; animals must have settled in new home before closure of old one can take place | Roseburn Badger Proposals for closure of old setts not approved by SNH | Delay in accessing land to construct Tram works and hence in Programme | 17.5 | 0 | 12.5 | 25 | 2008-10-01 | 2008-11-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2.2142 | 2.9599 | 0 |  | 0 | 2.9599 | 1.48 | 2.9599 | 34846.2381 | 67.47% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.48 | 1.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9599 | 0 |  |  |  | TRIANG | #NAME? | 0.175 | 0.825 | 12.5 | 0 | #NAME? | 0 | #NAME?
7.1.2 Badger Relocation | 883 | Ineffective/Inappropriate Proposals; new setts must be built before old ones can be closed and licenses will not be issued until nearer time of closure; animals must have settled in new home before closure of old one can take place | Gogarburn Badger/Otter Proposals for closure of old setts not approved by SNH/SEERAD | Delay in accessing land to construct Tram works and hence in Programme | 10 | 0 | 12.5 | 25 | 2007-10-01 | 2007-11-30 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.2564 | 1.6796 | 100 |  | 1.6796 | 0 | 1.6796 | 1.6796 | 34847.9177 | 67.47% | 1.6796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6796 | 0 |  | Other |  | TRIANG | #NAME? | 0.1 | 0.9 | 12.5 | 0 | #NAME? | 0 | #NAME?
7.1.1 Invasive Species | 869 | Surveying team unable to obtain access to Network Rail, BAA and other privately owned land because they were not cleared to access this land (including PTS). | Extent of Invasive Species Area Exceeds Estimate from Survey | Underestimating the extent of works; leads to an increase in cost | 17.5 |  | 20 |  | 2007-04-17 | 2009-04-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 3.5 | 4.6789 | 100 |  | 4.6789 | 0 | 0.24626 | 4.6789 | 34852.5966 | 67.48% | 0.24626 | 0.24626 | 0.24626 | 0.24626 | 0.24626 | 0.24626 | 0.24626 | 0.24626 | 0.24626 | 0.24626 | 0.24626 | 0.24626 | 0.24626 | 0.24626 | 0.24626 | 0.24626 | 0.24626 | 0.24626 | 0.24626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6789 | 0 |  | Other |  | DISCRETE | #NAME? | 0.175 | 0.825 | 20 | 0 | #NAME? | 0 | #NAME?
7.1.1 Invasive Species | 879 | Contractor is unable to get access to worksite due to access route being outside LOD and owned by others | Access to land to eradicate invasive species is not available when required | Programme Delay; contractor refuses to take ownership of risk 869 or includes high contingency in tender to allow for. | 10 | 0 | 10 | 20 | 2007-03-12 | 2009-04-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1.004 | 1.3422 | 3 |  | 0.040266 | 1.3019 | 0.070643 | 1.3422 | 34853.9388 | 67.48% | 0.070643 | 0.070643 | 0.070643 | 0.070643 | 0.070643 | 0.070643 | 0.070643 | 0.070643 | 0.070643 | 0.070643 | 0.070643 | 0.070643 | 0.070643 | 0.070643 | 0.070643 | 0.070643 | 0.070643 | 0.070643 | 0.070643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3422 | 0 |  |  |  | TRIANG | #NAME? | 0.1 | 0.9 | 10 | 0 | #NAME? | 0 | #NAME?
5 PALIAMENTARY PROCESS/ APPROVALS | 980 | Government/Parliament not persuaded of case for amendmnet to Traffic Order Regulations. Requirement for a mandatory publi hearing for TROs remains adding approximately 1 year to time required to confirm Orders. | Proposed Scottish Executive amendment of the Traffic Order Regulations fails thereby triggering public hearing | Public hearing required with additional cost (£1m) plus delay to making of TRO(s). Public hearing leads to greater risk of variation to promoted street and regulatory features. Increased difficulty of managing gap period - some constructed Infraco stree | 50 |  | 3000 |  | 2007-05-01 | 2008-10-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 1500 | 2005.2324 | 100 |  | 2005.2324 | 0 | 154.2486 | 2005.2324 | 36859.1712 | 71.37% | 154.2486 | 154.2486 | 154.2486 | 154.2486 | 154.2486 | 154.2486 | 154.2486 | 154.2486 | 154.2486 | 154.2486 | 154.2486 | 154.2486 | 154.2486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2005.2324 | 0 |  | TROs |  | DISCRETE | #NAME? | 0.5 | 0.5 | 3000 | 0 | #NAME? | 0 | #NAME?
5 PALIAMENTARY PROCESS/ APPROVALS | 977 | Legal challenge. Extension of statutory consultation process. Large number of objections. TRO process is subject to a public hearing process. | Delay in achievement of TRO(s) due to a large number of public objections and/or a legal challenge to using a TTRO to construct Infraco. | Requirement to start construction using TTROs | 90 |  | 1000 |  | 2007-06-18 | 2009-12-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 900 | 1203.1394 | 100 |  | 1203.1394 | 0 | 42.9693 | 1203.1394 | 38062.3106 | 73.7% | 42.9693 | 42.9693 | 42.9693 | 42.9693 | 42.9693 | 42.9693 | 42.9693 | 42.9693 | 42.9693 | 42.9693 | 42.9693 | 42.9693 | 42.9693 | 42.9693 | 42.9693 | 42.9693 | 42.9693 | 42.9693 | 42.9693 | 42.9693 | 42.9693 | 42.9693 | 42.9693 | 42.9693 | 42.9693 | 42.9693 | 42.9693 | 42.9693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1203.1394 | 0 |  | TROs |  | DISCRETE | #NAME? | 0.9 | 0.1 | 1000 | 0 | #NAME? | 0 | #NAME?
5 PALIAMENTARY PROCESS/ APPROVALS | 271 | Inadequate quality of submission of approval. Partial submission of package. Programme compression. Lack of CEC resources. | Failure to process prior approvals applications within 8 weeks | Delay and disruption to Infraco programme | 80 | 750 | 750 | 1000 | 2006-01-03 | 2008-08-29 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 666.7712 | 891.3541 | 100 |  | 891.3541 | 0 | 81.0322 | 891.3541 | 38953.6648 | 75.42% | 81.0322 | 81.0322 | 81.0322 | 81.0322 | 81.0322 | 81.0322 | 81.0322 | 81.0322 | 81.0322 | 81.0322 | 81.0322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 891.3541 | 0 |  | Design & Consents |  | TRIANG | #NAME? | 0.8 | 0.2 | 750 | 0 | #NAME? | 0 | #NAME?
5 PALIAMENTARY PROCESS/ APPROVALS | 986 | Inadequate information supplied by tie. | CEC failure to sign legal agreement - legal oficer level | Delay to commencement of contract | 17.5 | 2000 | 2500 | 3000 | 2007-11-26 | 2008-01-31 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 438.2183 | 585.8197 | 100 |  | 585.8197 | 0 | 292.9098 | 585.8197 | 39539.4844 | 76.56% | 0 | 292.9098 | 292.9098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 585.8197 | 0 |  | Infraco Procurement |  | TRIANG | #NAME? | 0.175 | 0.825 | 2500 | 0 | #NAME? | 0 | #NAME?
5 PALIAMENTARY PROCESS/ APPROVALS | 989 | tie fail to provide CEC with all relevant and necessary information in a timeous manner. tie fail to follow agreed protocols. | CEC lack the opportunity for informed decision making | Delay to project. Increased financial liability. Impact on quality. | 50 | 500 | 750 | 1000 | 2007-08-13 | 2010-12-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 41 | 375.0354 | 501.3554 | 90 |  | 451.2199 | 50.1355 | 12.2282 | 501.3554 | 40040.8398 | 77.53% | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 12.2282 | 0 | 501.3554 | 0 |  | Design & Consents |  | TRIANG | #NAME? | 0.5 | 0.5 | 750 | 0 | #NAME? | 0 | #NAME?
5 PALIAMENTARY PROCESS/ APPROVALS | 990 | SDS are behind programme with design review certificates and tie have decided not to extend programme period to account for this. | CEC carry financial impact of uncertified designs provided to Infraco | Modifications required to the designs post-contract award resulting in additional costs | 50 | 500 | 750 | 1000 | 2007-08-13 | 2008-01-31 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 374.8964 | 501.1696 | 80 |  | 400.9357 | 100.2339 | 167.0565 | 501.1696 | 40542.0095 | 78.5% | 167.0565 | 167.0565 | 167.0565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 501.1696 | 0 |  | Design & Consents |  | TRIANG | #NAME? | 0.5 | 0.5 | 750 | 0 | #NAME? | 0 | #NAME?
4.3 Business Case | 294 | Traffic model identifies areas where design is not compatible with efficient transport network operations. | Final Design impacts negatively on Final Business Case | Could be negative implications on Tram final business case. Potential to negatively impact BCR | 20 | 100 | 300 | 500 | 2007-03-31 | 2008-07-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 59.9535 | 80.1472 | 80 |  | 64.1177 | 16.0294 | 8.0147 | 80.1472 | 40622.1566 | 78.65% | 8.0147 | 8.0147 | 8.0147 | 8.0147 | 8.0147 | 8.0147 | 8.0147 | 8.0147 | 8.0147 | 8.0147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.1472 | 0 |  | Other |  | TRIANG | #NAME? | 0.2 | 0.8 | 300 | 0 | #NAME? | 0 | #NAME?
3 DESIGN | 102 | Change in Design Kinematic Envelope requirements | Detail design leads to kinematic envelope impact on vertical and horizontal alignment | Realignment of track to accommodate an increased 3 dimensional safe zone around the preferred route | 50 | 0 | 500 | 3250 | 2006-01-01 | 2008-11-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 631.3843 | 844.0482 | 80 |  | 675.2385 | 168.8096 | 64.9268 | 844.0482 | 41466.2048 | 80.29% | 64.9268 | 64.9268 | 64.9268 | 64.9268 | 64.9268 | 64.9268 | 64.9268 | 64.9268 | 64.9268 | 64.9268 | 64.9268 | 64.9268 | 64.9268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 844.0482 | 0 |  | Design & Consents |  | TRIANG | #NAME? | 0.5 | 0.5 | 500 | 0 | #NAME? | 0 | #NAME?
3 DESIGN | 336 | Adeqaute scope and extent of noise and vibration prevention measures/requirements are not provided to SDS; Specifications relating o Tram noise provided by Tramco are optimistic. | Design assumptions lead to Tram noise and vibration measures being inadequate during operation | Tram design requires to be re-worked; Post contruction elements need to be adjusted or re-constructed or additional noise and vibration measures need to be incorporated. | 10 | 100 |  | 1000 | 2007-01-01 | 2011-01-31 | [42 empty] | 42 | 55.1013 | 73.6606 | 80 |  | 58.9285 | 14.7321 | 1.7538 | 73.6606 | 41539.8654 | 80.43% | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 1.7538 | 73.6606 | 0 |  | Design & Consents |  | UNIFORM | #NAME? | 0.1 | 0.9 | 0 | 0 | #NAME? | 0 | #NAME? | bar: 2007-11-10 to 2011-01-08
3 DESIGN | 104 | Delay in design information release from specialist tram manufacturer | Delay in detailing of stops, trackway, OLE etc for Phase 1B | Time delay and consequent costs | 15 | 0 | 25 | 83 | 2007-01-01 | 2008-09-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 5.4528 | 7.2894 | 0 |  | 0 | 7.2894 | 0.60745 | 7.2894 | 41547.1548 | 80.44% | 0.60745 | 0.60745 | 0.60745 | 0.60745 | 0.60745 | 0.60745 | 0.60745 | 0.60745 | 0.60745 | 0.60745 | 0.60745 | 0.60745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2894 | 0 |  |  |  | TRIANG | #NAME? | 0.15 | 0.85 | 25 | 0 | #NAME? | 0 | #NAME?
3 DESIGN | 162 | Land is not acquired yet | Gaining access to land prior to purchase for advanced works | Increased management costs and delays to design | 10 | 0 |  | 30 | 2007-04-02 | 2008-09-28 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.5001 | 2.0053 | 80 |  | 1.6043 | 0.40106 | 0.16711 | 2.0053 | 41549.1601 | 80.45% | 0.16711 | 0.16711 | 0.16711 | 0.16711 | 0.16711 | 0.16711 | 0.16711 | 0.16711 | 0.16711 | 0.16711 | 0.16711 | 0.16711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0053 | 0 |  | Other |  | UNIFORM | #NAME? | 0.1 | 0.9 | 0 | 0 | #NAME? | 0 | #NAME?
2.9 TEL | 893 | VE process concentrates on reducing Capex to the detriment of Opex | VE Process makes TEL Business Case undeliverable | TEL Business Case becomes les undeliverable | 20 |  | 300 |  | 2010-10-31 | 2015-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 60 | 80.2093 | 80 |  | 64.1674 | 16.0419 | 26.7364 | 80.2093 | 41629.3694 | 80.6% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.7364 | 26.7364 | 26.7364 | 80.2093 | 0 |  | Other |  | DISCRETE | #NAME? | 0.2 | 0.8 | 300 | 0 | #NAME? | 0 | #NAME?
2.9 TEL | 889 | Unsuccessful negotiation. TEL believes costs inflated too much. | Target operating costs for Phase D are not agreed. | TEL Business Case becomes undeliverable. Potential to undertake Dispute Resolution to gain agreement. | 1 |  | 300 |  | 2010-01-04 | 2019-01-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 3 | 4.0105 | 80 |  | 3.2084 | 0.80209 | 0.3085 | 4.0105 | 41633.3798 | 80.61% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3085 | 0.3085 | 0.3085 | 0.3085 | 0.3085 | 0.3085 | 0.3085 | 0.3085 | 0.3085 | 0.3085 | 0.3085 | 0.3085 | 0.3085 | 4.0105 | 0 |  | Other |  | DISCRETE | #NAME? | 0.01 | 0.99 | 300 | 0 | #NAME? | 0 | #NAME?
2.9 TEL | 188 | Distribution Network Operator costs of supply are unknown | Power supply costs increase during Operation | Opex is not certain | 0 | 5 | 10 | 15 | 2009-04-20 | 2019-08-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 23 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 41633.3798 | 80.61% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | TRIANG | #NAME? | 0 | 1 | 10 | 0 | #NAME? | 0 | #NAME?
2.9 TEL | 188 | Distribution Network Operator costs of supply are unknown | Power supply costs increase during Operation | Opex is not certain | 0 | 5 | 10 | 15 | 2009-04-20 | 2019-08-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 23 | 0 | 0 | 80 |  | 0 | 0 | 0 | 0 | 41633.3798 | 80.61% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | TRIANG | #NAME? | 0 | 1 | 10 | 0 | #NAME? | 0 | #NAME?
2.2 Transdev | 888 | Design, construction and/or testing does not meet Transdev requirements and gain approval from the ROGS Competent Person | Transdev refuse to operate system on safety ground or apply overly restrictive procedures that are not directly the responsibility of Infraco (ROGS Competent Person agrees with this) | Delay to comencement of service, additional cost both for delay and rectification of the issue | 5 | 3000 | 4500 | 6000 | 2009-06-30 | 2010-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 19 | 223.6682 | 299.0044 | 80 |  | 239.2036 | 59.8009 | 15.7371 | 299.0044 | 41932.3843 | 81.19% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.7371 | 15.7371 | 15.7371 | 15.7371 | 15.7371 | 15.7371 | 15.7371 | 15.7371 | 15.7371 | 15.7371 | 15.7371 | 15.7371 | 15.7371 | 15.7371 | 15.7371 | 15.7371 | 15.7371 | 15.7371 | 15.7371 | 0 | 299.0044 | 0 |  | Other |  | TRIANG | #NAME? | 0.05 | 0.95 | 4500 | 0 | #NAME? | 0 | #NAME?
2.2 Transdev | 890 | DPOFA amendment is not fully negotiated | Key performance indicators for DPOFA are not agreed | In absence of KPIs, would have to refer to Dispute Resolution to resolve issues. | 2.5 |  | 300 |  | 2007-01-23 | 2008-10-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 7.5 | 10.0262 | 80 |  | 8.0209 | 2.0052 | 0.77124 | 10.0262 | 41942.4104 | 81.21% | 0.77124 | 0.77124 | 0.77124 | 0.77124 | 0.77124 | 0.77124 | 0.77124 | 0.77124 | 0.77124 | 0.77124 | 0.77124 | 0.77124 | 0.77124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0262 | 0 |  | Other |  | DISCRETE | #NAME? | 0.025 | 0.975 | 300 | 0 | #NAME? | 0 | #NAME?
2.1 tie Resources | 58 | Poor performance (quality) by Infraco during construction; poor materials; latent defects | Infraco fails to deliver construction quality; latent defects occur during or after Infraco maintenance period | Rework, stakeholder criticism, negative PR, programme delay if quality issue occurs during construction, operations affected by rework, project management costs to deal with issues | 10 | 25 | 62.5 | 100 | 2010-12-31 | 2016-12-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 6.2501 | 8.3552 | 80 |  | 6.6842 | 1.671 | 8.3552 | 8.3552 | 41950.7657 | 81.23% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3552 | 8.3552 | 0 |  | Other |  | TRIANG | #NAME? | 0.1 | 0.9 | 62.5 | 0 | #NAME? | 0 | #NAME?
2 PROCUREMENT CONSULTANT | 44 | SDS contractor does not deliver the required prior approval consents before novation | Late prior aproval consents | Delay to programme with additional resource costs and delay to infraco. procurement. Impact upon risk balance. | 50 | 900 | 1800 | 2700 | 2006-06-30 | 2008-11-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 898.4173 | 1201.0237 | 90 |  | 1080.9213 | 120.1024 | 85.7874 | 1201.0237 | 43151.7893 | 83.55% | 85.7874 | 85.7874 | 85.7874 | 85.7874 | 85.7874 | 85.7874 | 85.7874 | 85.7874 | 85.7874 | 85.7874 | 85.7874 | 85.7874 | 85.7874 | 85.7874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1201.0237 | 0 |  | Design & Consents |  | TRIANG | #NAME? | 0.5 | 0.5 | 1800 | 0 | #NAME? | 0 | #NAME?
2 PROCUREMENT CONSULTANT | 337 | Unsuccessful tenderer challenges procurement process (Tramco or Infraco) | OJEU procurement process is challenged | Possible retender; Delays; Legals costs to deal with challenge | 5 | 0 |  | 100 | 2007-01-12 | 2008-01-30 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2.4335 | 3.2532 | 100 |  | 3.2532 | 0 | 1.0844 | 3.2532 | 43155.0425 | 83.56% | 1.0844 | 1.0844 | 1.0844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2532 | 0 |  | Other |  | UNIFORM | #NAME? | 0.05 | 0.95 | 0 | 0 | #NAME? | 0 | #NAME?
2 PROCUREMENT CONSULTANT | 76 | Introduction of TEL as client | Change of client during works | Delay and cost during re-negotiation of DPOF contract and additional approvals process | 5 | 12.5 |  | 12.5 | 2006-07-03 | 2008-01-30 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0.625 | 0.83551 | 80 |  | 0.66841 | 0.1671 | 0.2785 | 0.83551 | 43155.878 | 83.56% | 0.2785 | 0.2785 | 0.2785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.83551 | 0 |  | Other |  | UNIFORM | #NAME? | 0.05 | 0.95 | 0 | 0 | #NAME? | 0 | #NAME?
11.1 Construction | 994 | The design for the lighting has yet to be approved by CECs Street Lighting section | Additional time or cost could be incurred in relation to the street lighting works | Compiance with their requireemnts may incur abortive works resulting in additional cost and delay to programme | 17.5 |  | 12.5 |  | 2007-08-29 | 2007-12-31 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2.1875 | 2.9243 | 80 |  | 2.3394 | 0.58486 | 1.4621 | 2.9243 | 43158.8023 | 83.56% | 1.4621 | 1.4621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9243 | 0 |  | Design & Consents |  | DISCRETE | #NAME? | 0.175 | 0.825 | 12.5 | 0 | #NAME? | 0 | #NAME?
11.1 Construction | 993 | Due to a terrorism event relating to Edinburgh Airport or due to the mitigation of the risk of such an event occuring traffic restrictions introduced in the vicinity of the airport cause unacceptable delays for vehicles accessing and exiting from the site | Free access cannot be guaranteed to the P&R site | Delays to construction vehicles could have impact on completion date and cost of construction, delays for car park users or buses could detract from usefulness and viability of facility | 2.5 |  | 12.5 |  | 2007-10-01 | 2009-03-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0.3125 | 0.41776 | 100 |  | 0.41776 | 0 | 0.021987 | 0.41776 | 43159.2201 | 83.57% | 0.021987 | 0.021987 | 0.021987 | 0.021987 | 0.021987 | 0.021987 | 0.021987 | 0.021987 | 0.021987 | 0.021987 | 0.021987 | 0.021987 | 0.021987 | 0.021987 | 0.021987 | 0.021987 | 0.021987 | 0.021987 | 0.021987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.41776 | 0 |  |  |  | DISCRETE | #NAME? | 0.025 | 0.975 | 12.5 | 4 | #NAME? | 4 | #NAME?
11.1 Construction | 964 | Prevarication over scope of project | Delay to start of work thereby jeopardising funding | Funding cannot be realised from SEStran and CEC to complete project | 2.5 | 12.5 | 12.5 | 12.5 | 2008-04-01 | 2008-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0.3125 | 0.41776 | 0 |  | 0 | 0.41776 | 0.13925 | 0.41776 | 43159.6378 | 83.57% | 0 | 0 | 0 | 0 | 0 | 0 | 0.13925 | 0.13925 | 0.13925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41776 | 0 |  |  |  | TRIANG | #NAME? | 0.025 | 0.975 | 12.5 | 0 | #NAME? | 0 | #NAME?
1.7 Miscellaneous | 343 | General delay to programme with various causes e.g. failure to obtain approvals on time; parliamentary processes, delays due to lack of prioritisation of BAA agreement with new owners | Delay to completion of project | Inflation at 5% causes increased out-turn cost due to delay plus revenue loss | 20 | 5900 | 15200 | 22600 | 2010-12-31 | 2011-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2903.0438 | 3880.8516 | 80 |  | 3104.6813 | 776.1703 | 3880.8516 | 3880.8516 | 47040.4894 | 91.08% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3880.8516 | 3880.8516 | 0 |  | Programme Delay |  | TRIANG | #NAME? | 0.2 | 0.8 | 15200 | 0 | #NAME? | 0 | #NAME?
1.3.1 NR Immunisation Project | 935 | Immunisation project not prioritised by Network Rail; Network Rail resources diverted to other projects or emergencies; Multiple iterations of design development; Tram requirements change as a result of Tram design development; Network Rail standards chan | Network Rail do not deliver the immunisation works before the drop dead date of October 2009. | Tram cannot be commissioned to programme; Critical delay. | 80 | 100 | 300 | 500 | 2009-04-30 | 2010-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 21 | 239.884 | 320.6821 | 100 |  | 320.6821 | 0 | 15.2706 | 320.6821 | 47361.1715 | 91.7% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.2706 | 15.2706 | 15.2706 | 15.2706 | 15.2706 | 15.2706 | 15.2706 | 15.2706 | 15.2706 | 15.2706 | 15.2706 | 15.2706 | 15.2706 | 15.2706 | 15.2706 | 15.2706 | 15.2706 | 15.2706 | 15.2706 | 15.2706 | 15.2706 | 0 | 320.6821 | 0 |  | Network Rail |  | TRIANG | #NAME? | 0.8 | 0.2 | 300 | 0 | #NAME? | 0 | #NAME?
1.3.1 NR Immunisation Project | 932 | Information handed over in draft format as part of continual design development; Downstream Tram design change that impacts on requirements; Zone of interference not defined adequately. | SDS gives wrong or insufficient infromation to Network Rail | Network Rail design their works inappropriately for final Tram requirements; Network Rail are unable to complete their design in time to meet programme; Cost to change design; Delay during redesign; Final works are not suitable and consequently Tram canno | 5 | 100 | 300 | 500 | 2007-04-02 | 2009-10-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 15.3198 | 20.4798 | 100 |  | 20.4798 | 0 | 0.78768 | 20.4798 | 47381.6513 | 91.74% | 0.78768 | 0.78768 | 0.78768 | 0.78768 | 0.78768 | 0.78768 | 0.78768 | 0.78768 | 0.78768 | 0.78768 | 0.78768 | 0.78768 | 0.78768 | 0.78768 | 0.78768 | 0.78768 | 0.78768 | 0.78768 | 0.78768 | 0.78768 | 0.78768 | 0.78768 | 0.78768 | 0.78768 | 0.78768 | 0.78768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.4798 | 0 |  | Network Rail |  | TRIANG | #NAME? | 0.05 | 0.95 | 300 | 0 | #NAME? | 0 | #NAME?
1.1 Land & Property | 352 | Increase in land values | Higher land compensation claims than anticipated | Additional uplift on compensation claims | 70 | 0 |  | 5750 | 2007-03-05 | 2010-12-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 41 | 2015.5725 | 2694.4608 | 100 |  | 2694.4608 | 0 | 65.7186 | 2694.4608 | 50076.1121 | 96.96% | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 65.7186 | 0 | 2694.4608 | 0 |  | Land compensation |  | UNIFORM | #NAME? | 0.7 | 0.3 | 0 | 2 | #NAME? | 2 | #NAME?
1.1 Land & Property | 354 | Land and property values experience a net reduction in value as a result of the introduction of the Tram | Part 1 Claims for land and property - (Noise and Vibration) | Possible successful claims resulting in increased costs to project with impact after construction | 50 | 0 |  | 3300 | 2011-12-30 | 2015-12-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 826.6722 | 1105.1132 | 100 |  | 1105.1132 | 0 | 1105.1132 | 1105.1132 | 51181.2253 | 99.1% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1105.1132 | 1105.1132 | 0 |  | Land compensation |  | UNIFORM | #NAME? | 0.5 | 0.5 | 0 | 0 | #NAME? | 0 | #NAME?
1.1 Land & Property | 10 | Costs of obtaining access rights are unknown | Cost associated with obtaining wayleaves | Increased legal costs relating to obtaining wayleaves | 40 | 50 | 200 | 500 | 2007-04-02 | 2008-10-25 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 100.1436 | 133.8741 | 100 |  | 133.8741 | 0 | 10.298 | 133.8741 | 51315.0993 | 99.36% | 10.298 | 10.298 | 10.298 | 10.298 | 10.298 | 10.298 | 10.298 | 10.298 | 10.298 | 10.298 | 10.298 | 10.298 | 10.298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133.8741 | 0 |  | Land compensation |  | TRIANG | #NAME? | 0.4 | 0.6 | 200 | 0 | #NAME? | 0 | #NAME?
1.1 Land & Property | 9 | Reclassification of land | Land reclassification changes value | Reclassification of land increases value/ cost of land. | 10 | 1000 |  | 1000 | 2007-03-20 | 2012-03-20 | [42 empty] | 42 | 100 | 133.6822 | 100 |  | 133.6822 | 0 | 3.1829 | 133.6822 | 51448.7815 | 99.62% | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 3.1829 | 133.6822 | 0 |  | Land compensation |  | UNIFORM | #NAME? | 0.1 | 0.9 | 0 | 0 | #NAME? | 0 | #NAME? | bar: 2007-11-10 to 2011-01-08
1.1 Land & Property | 357 | Landowner disagrees with District Valuer s Assessment of land value and submits a Certificate of Appropriate Alternative Development - Plot 322 | Submission of CAAD Claim for Plot 322 | Increase in land value for plot | 10 |  | 375 |  | 2006-04-03 | 2015-12-31 | [42 empty] | 42 | 37.5 | 50.1308 | 100 |  | 50.1308 | 0 | 1.1936 | 50.1308 | 51498.9123 | 99.71% | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 50.1308 | 0 |  | Land compensation |  | DISCRETE | #NAME? | 0.1 | 0.9 | 375 | 0 | #NAME? | 0 | #NAME? | bar: 2007-11-10 to 2011-01-08
1.1 Land & Property | 358 | Landowner disagrees with District Valuer s Assessment of land value and submits a Certificate of Appropriate Alternative Development - Plot 327 | Submission of CAAD Claim for plot 327 | Increase in land value for plot | 10 |  | 375 |  | 2006-04-03 | 2015-12-31 | [42 empty] | 42 | 37.5 | 50.1308 | 100 |  | 50.1308 | 0 | 1.1936 | 50.1308 | 51549.0431 | 99.81% | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 1.1936 | 50.1308 | 0 |  | Land compensation |  | DISCRETE | #NAME? | 0.1 | 0.9 | 375 | 0 | #NAME? | 0 | #NAME? | bar: 2007-11-10 to 2011-01-08
1.1 Land & Property | 26 | Protracted negotiation, additional claims, late acquisitions or late claims in relation to land and property | Use of legal advisors required beyond current budget | Legal/ advisor budget may be exceeded | 25 | 100 |  | 100 | 2007-03-20 | 2012-03-21 | [42 empty] | 42 | 25 | 33.4205 | 100 |  | 33.4205 | 0 | 0.79573 | 33.4205 | 51582.4637 | 99.87% | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 0.79573 | 33.4205 | 0 |  | Land compensation |  | UNIFORM | #NAME? | 0.25 | 0.75 | 0 | 0 | #NAME? | 0 | #NAME? | bar: 2007-11-10 to 2011-01-08
1.1 Land & Property | 6 | CEC fails to manage existing assets or changes | tie required to assume asset management role during and following construction | Increased legal and management costs to deal with change. Delay to construction programme. | 20 | 50 | 100 | 200 | 2007-04-11 | 2010-12-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 41 | 23.2966 | 31.1433 | 100 |  | 31.1433 | 0 | 0.75959 | 31.1433 | 51613.607 | 99.94% | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0.75959 | 0 | 31.1433 | 0 |  | Land compensation
1 GENERAL/OVERALL | 169 | Concurrent major projects in Edinburgh | Other major projects in Edinburgh interface with Tram | Delay in sequence in certain areas, Additional interface project management costs. | 50 | 0 |  | 100 | 2007-03-01 | 2010-12-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 41 | 25.0554 | 33.4946 | 80 |  | 26.7957 | 6.6989 | 0.81694 | 33.4946 | 51647.1016 | 100% | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0.81694 | 0 | 33.4946 | 0 |  | Programme Delay |  | UNIFORM | #NAME? | 0.5 | 0.5 | 0 | 0 | #NAME? | 0 | #NAME?
50922.1726
[53 empty] | p50= | 38634.2515 | [56 empty] | TOTALS | #NAME? | [6 empty] | #NAME?
[61 empty] | 51647.1016 | [44 empty] | 51647.1016
[55 empty] | 51647.1016 |  |  | 47036.8889 |  |  | 2333.38 |  |  | 4772.0087 | 5063.2389 | 5158.3337 | 1934.4264 | 1934.4264 | 1937.7476 | 1933.43 | 1933.43 | 1933.43 | 1929.9696 | 1879.7837 | 1789.6745 | 1520.1314 | 1248.7563 | 1156.8999 | 484.9157 | 463.2064 | 434.7308 | 434.7308 | 426.9568 | 442.2274 | 442.2274 | 457.9645 | 457.9645 | 457.9645 | 432.0467 | 431.259 | 431.259 | 358.4499 | 358.7584 | 358.7584 | 358.7584 | 358.7584 | 358.7584 | 358.7584 | 358.7584 | 317.9767 | 317.4247 | 317.4247 | 344.1611 | 344.1611 | 5213.0535 | 103294.2031
[55 empty] | Balance to FBC allowance |  |  | 1937.1111 |  |  | 53980.4816 | [47 empty] | Infraco Procurement
48974
[58 empty] | 17262.1458 | [50 empty] | Infraco Procurement
[58 empty] | 3168.6255 | [50 empty] | Infraco Delivery
[58 empty] | 4312.8996 | [50 empty] | Design & Consents
[58 empty] | 264.2938 | [50 empty] | Tramco Procurement
[58 empty] | 861.2019 | [50 empty] | Tramco Delivery
[58 empty] | 11446.912 | [50 empty] | MUDFA | x
[58 empty] | 3131.4769 | [50 empty] | Programme Delay
[58 empty] | 4296.1231 | [50 empty] | Land compensation | x
[58 empty] | 3208.3718 | [50 empty] | TROs | x
[58 empty] | 624.2049 | [50 empty] | Network Rail
[58 empty] | 397.2865 | [50 empty] | Other
48973.542

## Infraco - Provisionals
|  | Description | Synopsis | Estimating Notes | SCOOP 1 |  |  | SCOOP 2 |  |  | SCOOP 3 |  |  | ROLEY 1 |  |  | ROLEY 2 |  |  | BBS 3 |  |  | Elemental tag |  |  | Escalation Spread |  | Escalation factor | Comments from Meeting on 22 Aug 2007 |  | Section A | Section B | Section C | Section D | System Wide 1A | System Wide 1B
[5 empty] | 1A | 1B | Total | 1A | 1B | Total | 1A | 1B | Total | 1A | 1B | Total | 1A | 1B | Total | 1A | 1B | Total |  | Section | Base Date | Start | End
inf | 7 | Provide depot plant | Original bids did not include depot plant, latest submissions contain. | N/A |  |  | 0 |  |  | 0 |  |  | 0 | 2458117 |  | 2458117 |  |  | 0 |  |  | 0 | Depot |  | N/A | N/A | N/A |  |  | a
inf | 15 | Depot Drainage System | Value removed as per query response RF005 | N/A |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1283341 |  | 1283341 |  |  | 0 | Depot |  | N/A | N/A | N/A |  |  | a
inf | 24 | Depot - Ground Water Control | Bidder has suggested a reduced value of £80k. - Included |  |  |  | 0 | 250000 |  | 250000 |  |  | 0 | 288000 |  | 288000 | 288000 |  | 288000 |  |  | 0 | Depot | Depot | 2Q06 | 2008-05-01 | 2009-05-01 | 1.1196 | ● tie to review allowance | a
inf | 33 | Depot - add back 100,000m3 exc and disp | For Normalisation purposes, claim back as part of V.E. | Based on a rate |  |  | 0 | 597000 |  | 597000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Depot |  | N/A | N/A | N/A |  |  | a
inf | 34 | Provision of pumped surface water outfall system at A8 underpass |  |  | 500000 |  | 500000 | 500000 |  | 500000 | 100000 |  | 100000 |  |  | 0 |  |  | 0 | 100000 |  | 100000 | Depot | 5C | 2Q06 | 2008-05-01 | 2009-05-01 |  | ● Bidder accepts normalisation value. | a | 100000
inf | 49 | Raise level of Depot | Part of V.E, £1m banked, remainder as V.E saving |  | -1000000 |  | -1000000 |  |  | 0 | -1000000 |  | -1000000 | -1000000 |  | -1000000 |  |  | 0 |  |  | 0 | Depot |  | escalated | N/A | N/A |  | ● Bidder accepts normalisation value. | a
inf | 65 | Depot material disposal | SCOOP are proposing to incorporate material excavated at the Depot into adjacent landscape areas, ROLEY have priced 90,000m3 disposal off-site | [7 empty] | 900000 |  | 900000 | [8 empty] | 0 | Depot |  | escalated | N/A | N/A |  |  | a
inf | 66 | Inflation | Bid for systems element (c£109m) is at base date Q1 2007. Inflated using T. S indices to reflect program completion of Q1 2011. - Included in bid | Calculation based on Transport scotland indices and ROLEY 2 price split, insufficient detail in ROLEY 3 to undertake inflation calculation. |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 11933019 | 1633626 | 13566645 |  |  | 0 | Inflation |  | escalated | N/A | N/A |  | ● Bidder to provide fixed price for systems by 24th Aug 2007. | b
inf | 18 | Add anticipated additional Substation | Closing the loop Granton Square to Newhaven. Bidder stated that this is not necessary due to power distribution. - Included in bid | From contractor submissions | 1593034 |  | 1593034 | 887669 |  | 887669 |  |  | 0 | 1593034 |  | 1593034 | 887669 |  | 887669 |  |  | 0 | OLE |  | escalated | N/A | N/A |  | ● Bidder confirmed additional substation will not be required, remove from Normalisation | c
inf | 35 | 11kv Connections | SCOOP have included in Provisional Sums, ROLEY has included in main bid | From SCOOP submission |  |  | 0 | 500000 |  | 500000 | 500000 |  | 500000 |  |  | 0 |  |  | 0 |  |  | 0 | OLE |  | N/A | N/A | N/A |  |  | c
inf | 46 | Allow for Pantographs | Pantograph now part of Tram supply | Price based on £1200 escalated to out-turn | 1345648 | 363763 | 1709411 |  |  | 0 |  |  | 0 | 1345648 | 363763 | 1709411 |  |  | 0 |  |  | 0 | OLE |  | N/A | N/A | N/A |  |  | c
inf | 53 | Scottish Power connections included as part of NW reinforcement | see "Power - 11kv connections" | N/A | -500000 |  | -500000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | OLE |  | N/A | N/A | N/A |  |  | c
inf | 60 | Bid errors | Relates to the Substation price element within the SCOOP 2 bid | Value comes from SCOOP May 2007 submission |  |  | 0 |  | 698862 | 698862 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | OLE |  | escalated | N/A | N/A |  |  | c
inf | 62 | Spares not included in Price | Bidder has included in the Maintenance budget | Spares cost moved from maintenance to CAPEX for comparison | [8 empty] | 0 | [6 empty] | 174762 | 100000 | 274762 | OLE |  | escalated | N/A | N/A |  | ● Bidder agreed to transfer initial spares from OPEX to CAPEX. | c |  |  |  |  | 174762 | 100000
inf | 70 | Scottish Power Connections to Depot and IPR | Refer to letter from Scottish Power | [16 empty] | 750000 |  | 750000 | OLE | [6 empty] | c | 750000
inf | 1 | Omit allowance for SDS design |  | From ROLEY submission | 0 |  | 0 |  |  | 0 |  |  | 0 | -2000000 |  | -2000000 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 29 | Efficiency saving undertaking 1A & 1B concurrently | SCOOPs 2nd bid included a £25m premium for delaying start of Phase 1B, ROLEY offered a £5M saving for concurrent working | From bid submissions |  |  | 0 |  |  |  | 0 |  | 0 |  |  | 0 | [5 empty] | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 36 | Allowance for market price change on key commodities | Represents the cost of price volatile materials (Copper, aluminium and steel) | £379k included in Tramlines "Schedule of Provisional Activities not included in Core Price" for May submission, increased for Aug submission |  |  | 0 | 379000 |  | 379000 | 824188 |  | 824188 |  |  | 0 |  |  | 0 |  |  | 0 | Prelims |  | escalated | N/A | N/A |  |  | d
inf | 38 | Market Price fluctuation | Included in base estimate above (£14.6m) plus £1m in core price for fluctuations on metals | N/A |  |  | 0 |  |  | 0 |  |  | 0 | 6600000 |  | 6600000 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 41 | Omit allowance for invasive species removal (funded by others) - No item identified - what level of allowance should be deleted??? | see description | N/A |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 42 | Allowance for Due Diligence on detailed designs | Historic normalisations for bids 1 and 2, not required for latest bids | N/A | 1000000 |  | 1000000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 45 | SDS Design costs post novation | Historic normalisations for bids 1 and 2, not required for latest bids | N/A |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 51 | Allowance for delayed start to Project |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 6252443 | 1302936 | 7555379 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 54 | Tram Vehicle Discount - to Tramco | N/A | N/A |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 55 | Adjustment for Accommodation Works | Included in bids | N/A | 1000000 |  | 1000000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 56 | Allowance for Third Party Works | Stanley casino etc. £1M provisional sum included for accommodation works will cover | N/A | 115468 |  | 115468 |  |  | 0 |  |  | 0 | 115468 |  | 115468 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 67 | Stakeholder management | ROLEY have not included in their latest bid for managing stakeholders ie, public consultation, SCOOP have included | [9 empty] | 0 | [8 empty] | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 71 | Relocation of Ancient Monuments | Backup available | [16 empty] | 53700 |  | 53700 | Prelims | [6 empty] | d |  | 53700
inf | 25 | Tram on-board S&C equipment | Included within latest submissions | N/A |  |  | 0 |  |  | 0 |  |  | 0 | 1399594 | 207347 | 1606941 |  |  | 0 |  |  | 0 | Supervisory&Comms |  | N/A | N/A | N/A |  |  | e
inf | 63 | CCTV cameras | Bidder states in their clarifications that "The pricing of 139 No CCTV cameras for crossings has been removed pending a response to our TQ on the subject". Also, part of V.E. | Cost taken from SCOOP Aug 07 submission | [8 empty] | 0 | [7 empty] | 312861 | 312861 | Supervisory&Comms - Removed under VE |  | escalated | N/A | N/A |  | ● tie stated that this was for normalisation purposes and is subject to V.E. | e |  |  |  |  | 0 | 312861
inf | 8 | E/O carrier drains | Bidder appears not to have included in their latest bid. - Included | Number taken from SCOOP submission and applied to ROLEY Normalisation |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 2769914 | 1644578 | 4414492 |  | 1644578 | 1644578 | Track & Form | All | escalated | N/A | N/A |  | ● Bidder has calculated cost of additional drainage in 1A to £2.25m and accepts normalisation value until further information is available. | f |  |  | 822289 | 822289
inf | 16 | Allowance for minor utility diversions | Minor utilities relate to utilities at OLE foundations etc. not being undertaken by MUDFA. |  | 750000 | 250000 | 1000000 | 750000 | 250000 | 1000000 | 750000 | 250000 | 1000000 | 750000 | 250000 | 1000000 | 750000 | 250000 | 1000000 | 750000 | 250000 | 1000000 | Track & Form | All |  | 2008-07-01 | 2010-05-01 |  | ● Bidder accepts normalisation value. | f |  |  |  |  | 750000 | 250000
inf | 17 | Allow for finished surface between tracks | Bidder suggested a sum of £250k. - Included |  |  |  | 0 |  |  | 0 |  |  | 0 | 757947 |  | 757947 | 907158 |  | 907158 | 0 |  | 0 | Track & Form | All | escalated | 2008-07-01 | 2010-05-01 |  | ● Bidder confirmed item is within core price, remove from Normalisation. | f
inf | 23 | Archaeological Officer - impact on productivity MUDFA/INFRACO | It is anticipated this "interference" will reduce work lengths in key areas. Bidder has suggested a more likely cost of £50k based on their experience of officers with a watching brief | R.O.M |  |  | 0 | 350000 |  | 350000 | 405754.5495 |  | 405754.5495 |  |  | 0 | 350000 |  | 350000 | 405754.5495 |  | 405754.5495 | Track & Form | All | 2Q06 | 2008-07-01 | 2010-05-01 | 1.1593 | ● Bidder suggested any delay would be dealt with under compensation agreement. | f |  |  |  |  | 405754.5495
inf | 40 | Adjust track drainage allowances - if ITN pricing document used for base quantities then new carrier drains will have been priced where required (Roseburn) - No adjust reqd |  |  | 541223 | 274984 | 816207 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Track & Form |  | N/A | N/A | N/A |  |  | f
inf | 43 | Allow for reduced excavation - thinner track slab | Historic normalisations for bids 1 and 2, not required for latest bids | N/A |  |  | 0 |  |  | 0 |  |  | 0 | -571874 | -44429 | -616303 |  |  | 0 |  |  | 0 | Track & Form |  | N/A | N/A | N/A |  |  | f
inf | 44 | Reduced base plate spacing on curves | Historic normalisations for bids 1 and 2, not required for latest bids | N/A | 100000 |  | 100000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Track & Form |  | N/A | N/A | N/A |  |  | f
inf | 57 | Adjust track drainage allowances - Scoop allow connection every 50m Roley every 25m - adjust Scoop | Covered above in Normalisation 8. | N/A |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Track & Form |  | N/A | N/A | N/A |  |  | f
inf | 59 | Old Tramway workings | It is foreseen that old tramway workings will be encountered during excavation works | Is this covered under "Unforeseen Ground conditions" risk? |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Track & Form |  | N/A | N/A | N/A |  |  | f
inf | 64 | Ballast | Bidder included for non NR compliant ballast, addition of £300k as indicated by Bidder for the use of NR compliant ballast. Include in V.E list ref. RF006 | £300k given verbally by ROLEY as the extra cost of using compliant ballast | [8 empty] | 0 | [6 empty] | 300000 |  | 300000 | Track & Form |  | escalated | N/A | N/A |  | ● Bidder accepted value. | f | 300000
inf | 68 | Stray Current monitoring | Bidder has included for current monitoring only which does not comply with the E.R. - Included (See separate proposals) | [9 empty] | 0 | [8 empty] | 0 | Track & Form |  | escalated | N/A | N/A |  | ● Bidders stray current proposals non compliant and drainage issues* | f
inf | 50 | Gogarburn Tram Stop By RBS | The Tramstop is to be funded by RBS | Rates used from bid submissions | -171008 |  | -171008 | -167557 |  | -167557 | -167557 |  | -167557 | -132412 |  | -132412 | -184900 |  | -184900 |  |  | 0 | Tramstops - additional funding not construction cost saving |  | escalated | N/A | N/A |  | ● tie commented this is not a reduction in scope. Funding mechanism to be agreed. | g | 0
inf | 2 | Potential VE savings | From SCOOP Jan 07 submission | From SCOOP Jan 07 submission | -10000000 |  | -10000000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | V.E Opportunities |  | N/A | N/A | N/A |  |  | h
inf | 52 | Potential VE savings | Numbers included below the Normalisation totals | N/A |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | V.E Opportunities |  | N/A | N/A | N/A |  |  | h
| Sub Total Infraco Normalisation exc. Highways & Structures | [18 empty] | 2534216.5495 | 2307439 | 4841655.5495 | [8 empty] | 1150000 | 53700 | 822289 | 822289 | 1330516.5495 | 662861 | 0
inf | 3 | Charrette Changes (20% in 2nd drop) | Changes to cover Picardy Place and Leith Walk re-alignment | Breakdown available, £3m included for service diversions, not part of current MUDFA scope. | 5379599 |  | 5379599 | 5379599 |  | 5379599 | 6340324.3822 |  | 6340324.3822 | 5379599 |  | 5379599 | 5379599 |  | 5379599 | 6340324.3822 |  | 6340324.3822 | Highways | 1C | 2Q06 | 2008-03-01 | 2010-06-01 | 1.1325 | ● BBS to remeasure and provide value based on latest information by 24th Aug 07. For the interim value reduced to £2m, escalation applied. | i |  | 6340324.3822
inf | 4 | Extent of road refinishing in critical on street areas | Allowance for "wall to wall" finishes, bidder's assumption is based on minimal work, further design information awaited. | Siemens have suggested a value of £1m would be sufficient | 5210041 |  | 5210041 |  |  | 0 |  |  | 0 | 5210041 |  | 5210041 | 5210041 |  | 5210041 |  |  | 0 | Highways - all additional costs included in firm price | 1D, 1B, 1C |  | 2008-03-01 | 2010-06-01 | 1.1325 | ● Bidder to provide commentary based on drawings and their assumptions for the demarcation of finishes, by 31st Aug 07. | i |  | 0
inf | 5 | Allowance for surface finishes on Leith walk and princess street areas | Enhanced finished required (i.e. cobbles etc.). Lack of assurance of scope coverage within "Highways" section of the bids |  |  |  | 0 | 2000000 |  | 2000000 | 2000000 |  | 2000000 |  |  | 0 |  |  | 0 |  |  | 0 | Highways | 1C |  | 2008-03-01 | 2010-06-01 |  |  | i
inf | 21 | Adjust for natural stone paving in Princess Street in lieu of asphalt | Bidders have priced a like-for-like replacement, where it is anticipated CEC would require an enhanced finish, betterment?. Covered in normalisation 4 and 5. | N/A |  |  | 0 |  |  | 0 |  |  | 0 | 589112 |  | 589112 | 589112 |  | 589112 |  |  | 0 | Highways |  | N/A | N/A | N/A |  |  | i
inf | 22 | E/O Shell Grip | Bidder has indicated £200k would be sufficient | Estimated using £9.16 / m2, backup available |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 276998 | 108821 | 385819 | 319343.2872 | 125663.0672 | 445006.3544 | Highways | All | 2Q06 | 2008-03-01 | 2011-02-01 | 1.1529 |  | i |  |  |  |  | 319343.2872 | 125663.0672
inf | 27 | Mains Power Connection to street lights and traffic signals | Bidder suggests connections to be undertaken by Scottish Power | Price agreed with bidders |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 100000 | 25000 | 125000 | 115287.2177 | 28821.8044 | 144109.0221 | Highways | All | 2Q06 | 2008-03-01 | 2011-02-01 | 1.1529 | ● Bidder accepts normalisation value. | i |  |  |  |  | 115287.2177 | 28821.8044
inf | 39 | Allowance for landscaping (included) | ROLEY original bid contained no allowance for landscaping, subsequently included | N/A |  |  | 0 |  |  | 0 |  |  | 0 | 88500 | 40500 | 129000 |  |  | 0 |  |  | 0 | Highways |  | N/A | N/A | N/A |  |  | i
inf | 48 | Reduction in sub-base rate | Rate within SCOOP May 07 submission looked to be a mistake due to its magnitude | Revised rate applied consistent with other areas of the scheme |  |  | 0 | -72000 |  | -72000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Highways |  | N/A | N/A | N/A |  |  | i
inf | 10 | A8 Underpass piling | Originally thought bid excluded piling, however further to recent information piling is included | N/A |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 3267590 |  | 3267590 | 0 |  | 0 | Structures |  | N/A | N/A | N/A |  |  | j
inf | 13 | Crewe Gardens Bridge - Contiguous piling | Bidder not included piling. - Included | Taken from SCOOP bid |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 1825000 | 1825000 |  |  | 0 | Structures | 3A | escalated | 2009-07-01 | 2011-01-01 |  | ● Bidder to re-check estimate and provide comment by 24th Aug 07. | j
| Sub Total Highways | [18 empty] | 6774954.8871 | 154484.8717 | 6929439.7587 | [8 empty] | 0 | 6340324.3822 | 0 | 0 | 434630.5048 | 154484.8717
inf | 19 | Adjust for Network Rail Possessions support | Costs for PICOPS / COSS when undertaking works adjacent / over the railway. Bidder has suggested £50k based on 50 possessions at £1k per possession |  | 755307 |  | 755307 | 755307 |  | 755307 | 755307 |  | 755307 | 755307 |  | 755307 | 755307 |  | 755307 | 755307 |  | 755307 | Structures | 7A, 5C, 5B, 5A |  | 2008-03-01 | 2009-11-01 |  | ● Bidder suggests reduction to £50k for track safety only personnel, not allowance has been made within bid for design interface. | j | 755307
inf | 20 | Balgreen Road - new structure reqd | It is anticipated that a new structure will be required. Bidder suggested that £600k would be sufficient based on £2,500/m2 + £100k for removal of old deck |  | 500000 |  | 500000 | 750000 |  | 750000 | 750000 |  | 750000 | 500000 |  | 500000 | 750000 |  | 750000 |  |  | 0 | Structures - all additional costs taken into account in firming up price | 5A | escalated | 2008-03-01 | 2009-09-01 |  | ● Bidder has received most recent information and is in agreement with normalisation value. | j | 0
inf | 26 | S23 Carrick Knowe Widening | Allowance to increase deck to accommodate cycleway. Bidder has suggested a cost of £125k based on a widening rate of £2.5k for 50m2 | As per ROLEY rates |  |  | 0 |  |  | 0 | 139955.9189 |  | 139955.9189 |  |  | 0 | 250000 |  | 250000 |  |  | 0 | Structures - all additional costs taken into account in firming up price | 5B | 2Q06 | 2008-04-01 | 2009-11-01 | 1.1196 | ● Bidder accepts normalisation value. | j | 0
inf | 28 | Leith Walk substation demolition | Potential requirement to demolish existing structure. |  |  |  | 0 | 50000 |  | 50000 | 55661.7812 |  | 55661.7812 |  |  | 0 | 50000 |  | 50000 | 55661.7812 |  | 55661.7812 | Structures | 1B | 2Q06 | 2008-06-01 | 2008-12-01 | 1.1132 | ● Bidder queried level of contamination around buried tanks, tie to investigate. | j |  | 55661.7812
inf | 30 | Roseburn Corridor Drainage Pumps | Anticipation for pumping to outfalls, cost captured under Normalisation 61 | N/A |  |  | 0 |  | 50000 | 50000 |  |  | 0 |  |  | 0 |  | 50000 | 50000 |  |  | 0 | Structures |  | N/A | N/A | N/A |  |  | j
inf | 31 | Additional Crew Relief Facilities at Haymarket | Late addition to scheme, facility to be located under span of proposed Haymarket Viaduct (5-span) | From SCOOP submission for Granton Square facilities |  |  | 0 | 49950 |  | 49950 | 49950 |  | 49950 |  |  | 0 | 49950 |  | 49950 | 49950 |  | 49950 | Structures |  | escalated | N/A | N/A |  | ● Bidder accepts normalisation value. | j | 49950
inf | 32 | Structure S18 allowance for anticipated works | Minimal works required at this location. | SCOOP included £277,500 in bid and ROLEY did not price. Minimal works likely so align values to equal £27.5k |  |  | 0 | -250000 |  | -250000 | -250000 |  | -250000 |  |  | 0 | 27500 |  | 27500 |  |  | 0 | Structures - all additional costs taken into account in firming up price | 1B | escalated | 2009-02-01 | 2009-08-01 |  | ● Bidder accepts normalisation value. | j |  | 0
inf | 37 | Murrayfield Tram Stop Lift and Steps | Installation of staircase and lift at Murrayfield Tramstop. ROLEY have captured within main bid, SCOOP have not. | £40k - Provision and installation of staircase to North West corner of Murrayfield Tramstop retaining wall £60k - Provision, installation and commissioning to lift to North West corner of Murrayfield Tramstop retaining wall. |  |  | 0 | 100000 |  | 100000 | 100000 |  | 100000 |  |  | 0 |  |  | 0 |  |  | 0 | Structures | 5A | escalated | 2008-05-01 | 2009-09-01 |  |  | j
inf | 47 | Delete Crew Relief Facilities at Granton Sqr | No longer required, operators will be directed to use public facilities | From bid submissions |  |  | 0 |  | -49950 | -49950 |  | -49950 | -49950 |  |  | 0 |  |  | 0 |  |  | 0 | Structures |  | escalated | N/A | N/A |  |  | j
inf | 58 | Landfill Tax Post 2008 +33% | Marker | is this applicable, can spoil be reused around the network? |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Structures |  | N/A | N/A | N/A |  |  | j
inf | 61 | Roseburn corridor retaining wall align assumptions | Design not developed in this area, bidder has made his own assumptions | Values aligned due to vastly differing assumptions, Mean value used and Normalised accordingly | [7 empty] | -2008445 | -2008445 | [7 empty] | 3228456 | 3228456 | Structures |  | escalated | N/A | N/A |  | ● Bidder accepts normalisation value, level of design information available leaves this area uncertain. | j |  |  | 3228456
| Sub Total Structures | [18 empty] | 860918.7812 | 3228456 | 4089374.7812 | [8 empty] | 805257 | 55661.7812 | 3228456 | 0 | 0 | 0
| Total | [18 empty] | 10170090.2178 | 5690379.8717 | 15860470.0894
|  |  | Current Normalisation Total (24 August 2007) |  | 7119312 | 888747 | 8008059 | 12808968 | 948912 | 13757880 | 12253584.6318 | -1808395 | 10445189.6318 | 30378524 | 2120117 | 32498641 | 35690298 | 5537025 | 41227323 | 30510270.6533 | 17071139.615 | 47581410.2683
|  |  | Normalisation at 23 August 2007 | [16 empty] | 53822000 | 8619000 | 62441000
|  |  | Variance | [16 empty] | -23311729.3467 | 8452139.615 | -14859589.7317
Note on X1: terramic: Filters through to main summary sheets
Note on AC1: terramic: Using Average multiplier across duration
Note on AD5: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Groundwater control: o AMIS to control water until Infraco takes over. o BBS to take temp pumping into their bid. o Normalisation to be removed
Note on AD7: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Agreed.
Note on AD8: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Agreed – Allowance common to both bidders.
Note on AD10: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Inflation for systems. BBS to reconsider. Tie are willing to consider arrangements for pre purchase/commitment to price volatile metals or indexation arrangements for such materials. Tie are not willing for the systems price generally to be fluctuating price.
Note on AD11: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 BBS view is that the additional sub-station is not required and that system will comply with Employer’s Requirements with 1a operating on a standalone basis. Agreed to remove.
Note on AD16: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Spares. Agreed.
Note on AD32: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Agreed.
Note on AD33: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Carrier Drains: o BBS’s view is that this allowance for Phase 1a should be 2.25m. o Leave 1b as is for the moment.
Note on AD34: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Minor Utility Diversion – Common allowance for both bidders
Note on AD35: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Allowance for refinishing roads between tracks. BBS confirmed that they have allowed for surface finishes between the tracks within their bids. Normalisation to be removed.
Note on AD36: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Archeological Officer – Allowance agreed
Note on AD42: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Ballast. Allowance agreed.
Note on AD43: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Stray current monitoring – BBS to consider taking this risk into their bid. BBS to review allowances for trackform drainage within their bid following the Trackform review meeting with tie.
Note on AD44: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Agreed – Funding adjustment common to both bidders.
Note on AD50: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 BBS to review Picardy Place allowance and advise their view on 24/8/07.
Note on AD51: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 BBS have based their pricing on the indicative roads and pavings drawings and have allowed for the finishes indicated on the basis of like for like reinstatement. However, full paving reinstatements are only included where this is shown on the drawings. Unless otherwise shown on the drawings issued BBS have included for reinstatement to match existing e.g. York stone finishes are not allowed in Princes St except where existing finishes are York stone. For the whole of the on street alignment BBS have allowed for resurfacing the roads with a new surface coat, but have not allowed for extensive full reinstatement of roads and sub base. Need to have a clear definition of requirement. For clarity BBS will provide details of the scope of work that they have allowed for each section of the alignment. This will be provided for 24/08/07
Note on AD54: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 E/O shell grip. Allowance agreed
Note on AD55: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Agreed.
Note on AD59: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Crewe Gardens Bridge – BBS to consider appropriate allowance
Note on AD63: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Additional Network Rail Possession Support. o Costs for possessions included in bid. o BBS assume SDS will gain NWR approval of design including getting Form C approval. o tie to review and remove normalisation.
Note on AD64: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Balgreen Road. New Structure – Allowance of £750k agreed
Note on AD65: terramic: From GG minutes of meeting with BBS on 23 Aug 2007
Note on AD66: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Leith Walk Substation – Allowance agreed.
Note on AD68: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Agreed – BBS to check not duplicated
Note on AD69: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Agreed.
Note on AD73: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Roseburn Corridor retaining walls. Agreed.

## Non Infraco items
|  | Description | Synopsis | Estimating Notes | SCOOP 1 |  |  | SCOOP 2 |  |  | SCOOP 3 |  |  | ROLEY 1 |  |  | ROLEY 2 |  |  | BBS 3 |  |  | Elemental tag |  |  | Escalation Spread |  | Escalation factor | Comments from Meeting on 22 Aug 2007 |  | Section A | Section B | Section C | Section D | System Wide 1A | System Wide 1B
[5 empty] | 1A | 1B | Total | 1A | 1B | Total | 1A | 1B | Total | 1A | 1B | Total | 1A | 1B | Total | 1A | 1B | Total |  | Section | Base Date | Start | End
inf | 7 | Provide depot plant | Original bids did not include depot plant, latest submissions contain. | N/A |  |  | 0 |  |  | 0 |  |  | 0 | 2458117 |  | 2458117 |  |  | 0 |  |  | 0 | Depot |  | N/A | N/A | N/A |  |  | a
inf | 15 | Depot Drainage System | Value removed as per query response RF005 | N/A |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1283341 |  | 1283341 |  |  | 0 | Depot |  | N/A | N/A | N/A |  |  | a
inf | 24 | Depot - Ground Water Control | Bidder has suggested a reduced value of £80k. - Included |  |  |  | 0 | 250000 |  | 250000 |  |  | 0 | 288000 |  | 288000 | 288000 |  | 288000 |  |  | 0 | Depot | Depot | 2Q06 | 2008-05-01 | 2009-05-01 | 1.1196 | ● tie to review allowance | a
inf | 33 | Depot - add back 100,000m3 exc and disp | For Normalisation purposes, claim back as part of V.E. | Based on a rate |  |  | 0 | 597000 |  | 597000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Depot |  | N/A | N/A | N/A |  |  | a
inf | 49 | Raise level of Depot | Part of V.E, £1m banked, remainder as V.E saving |  | -1000000 |  | -1000000 |  |  | 0 | -1000000 |  | -1000000 | -1000000 |  | -1000000 |  |  | 0 |  |  | 0 | Depot |  | escalated | N/A | N/A |  | ● Bidder accepts normalisation value. | a
inf | 65 | Depot material disposal | SCOOP are proposing to incorporate material excavated at the Depot into adjacent landscape areas, ROLEY have priced 90,000m3 disposal off-site | [7 empty] | 900000 |  | 900000 | [8 empty] | 0 | Depot |  | escalated | N/A | N/A |  |  | a
inf | 66 | Inflation | Bid for systems element (c£109m) is at base date Q1 2007. Inflated using T. S indices to reflect program completion of Q1 2011. - Included in bid | Calculation based on Transport scotland indices and ROLEY 2 price split, insufficient detail in ROLEY 3 to undertake inflation calculation. |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 11933019 | 1633626 | 13566645 |  |  | 0 | Inflation |  | escalated | N/A | N/A |  | ● Bidder to provide fixed price for systems by 24th Aug 2007. | b
inf | 18 | Add anticipated additional Substation | Closing the loop Granton Square to Newhaven. Bidder stated that this is not necessary due to power distribution. - Included in bid | From contractor submissions | 1593034 |  | 1593034 | 887669 |  | 887669 |  |  | 0 | 1593034 |  | 1593034 | 887669 |  | 887669 |  |  | 0 | OLE |  | escalated | N/A | N/A |  | ● Bidder confirmed additional substation will not be required, remove from Normalisation | c
inf | 35 | 11kv Connections | SCOOP have included in Provisional Sums, ROLEY has included in main bid | From SCOOP submission |  |  | 0 | 500000 |  | 500000 | 500000 |  | 500000 |  |  | 0 |  |  | 0 |  |  | 0 | OLE |  | N/A | N/A | N/A |  |  | c
inf | 46 | Allow for Pantographs | Pantograph now part of Tram supply | Price based on £1200 escalated to out-turn | 1345648 | 363763 | 1709411 |  |  | 0 |  |  | 0 | 1345648 | 363763 | 1709411 |  |  | 0 |  |  | 0 | OLE |  | N/A | N/A | N/A |  |  | c
inf | 53 | Scottish Power connections included as part of NW reinforcement | see "Power - 11kv connections" | N/A | -500000 |  | -500000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | OLE |  | N/A | N/A | N/A |  |  | c
inf | 60 | Bid errors | Relates to the Substation price element within the SCOOP 2 bid | Value comes from SCOOP May 2007 submission |  |  | 0 |  | 698862 | 698862 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | OLE |  | escalated | N/A | N/A |  |  | c
inf | 1 | Omit allowance for SDS design |  | From ROLEY submission | 0 |  | 0 |  |  | 0 |  |  | 0 | -2000000 |  | -2000000 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 29 | Efficiency saving undertaking 1A & 1B concurrently | SCOOPs 2nd bid included a £25m premium for delaying start of Phase 1B, ROLEY offered a £5M saving for concurrent working | From bid submissions |  |  | 0 |  |  |  | 0 |  | 0 |  |  | 0 | [5 empty] | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 36 | Allowance for market price change on key commodities | Represents the cost of price volatile materials (Copper, aluminium and steel) | £379k included in Tramlines "Schedule of Provisional Activities not included in Core Price" for May submission, increased for Aug submission |  |  | 0 | 379000 |  | 379000 | 824188 |  | 824188 |  |  | 0 |  |  | 0 |  |  | 0 | Prelims |  | escalated | N/A | N/A |  |  | d
inf | 38 | Market Price fluctuation | Included in base estimate above (£14.6m) plus £1m in core price for fluctuations on metals | N/A |  |  | 0 |  |  | 0 |  |  | 0 | 6600000 |  | 6600000 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 41 | Omit allowance for invasive species removal (funded by others) - No item identified - what level of allowance should be deleted??? | see description | N/A |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 42 | Allowance for Due Diligence on detailed designs | Historic normalisations for bids 1 and 2, not required for latest bids | N/A | 1000000 |  | 1000000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 45 | SDS Design costs post novation | Historic normalisations for bids 1 and 2, not required for latest bids | N/A |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 51 | Allowance for delayed start to Project |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 6252443 | 1302936 | 7555379 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 54 | Tram Vehicle Discount - to Tramco | N/A | N/A |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 55 | Adjustment for Accommodation Works | Included in bids | N/A | 1000000 |  | 1000000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 56 | Allowance for Third Party Works | Stanley casino etc. £1M provisional sum included for accommodation works will cover | N/A | 115468 |  | 115468 |  |  | 0 |  |  | 0 | 115468 |  | 115468 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 67 | Stakeholder management | ROLEY have not included in their latest bid for managing stakeholders ie, public consultation, SCOOP have included | [9 empty] | 0 | [8 empty] | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 25 | Tram on-board S&C equipment | Included within latest submissions | N/A |  |  | 0 |  |  | 0 |  |  | 0 | 1399594 | 207347 | 1606941 |  |  | 0 |  |  | 0 | Supervisory&Comms |  | N/A | N/A | N/A |  |  | e
inf | 17 | Allow for finished surface between tracks | Bidder suggested a sum of £250k. - Included |  |  |  | 0 |  |  | 0 |  |  | 0 | 757947 |  | 757947 | 907158 |  | 907158 | 0 |  | 0 | Track & Form | All | escalated | 2008-07-01 | 2010-05-01 |  | ● Bidder confirmed item is within core price, remove from Normalisation. | f
inf | 40 | Adjust track drainage allowances - if ITN pricing document used for base quantities then new carrier drains will have been priced where required (Roseburn) - No adjust reqd |  |  | 541223 | 274984 | 816207 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Track & Form |  | N/A | N/A | N/A |  |  | f
inf | 43 | Allow for reduced excavation - thinner track slab | Historic normalisations for bids 1 and 2, not required for latest bids | N/A |  |  | 0 |  |  | 0 |  |  | 0 | -571874 | -44429 | -616303 |  |  | 0 |  |  | 0 | Track & Form |  | N/A | N/A | N/A |  |  | f
inf | 44 | Reduced base plate spacing on curves | Historic normalisations for bids 1 and 2, not required for latest bids | N/A | 100000 |  | 100000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Track & Form |  | N/A | N/A | N/A |  |  | f
inf | 57 | Adjust track drainage allowances - Scoop allow connection every 50m Roley every 25m - adjust Scoop | Covered above in Normalisation 8. | N/A |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Track & Form |  | N/A | N/A | N/A |  |  | f
inf | 59 | Old Tramway workings | It is foreseen that old tramway workings will be encountered during excavation works | Is this covered under "Unforeseen Ground conditions" risk? |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Track & Form |  | N/A | N/A | N/A |  |  | f
inf | 68 | Stray Current monitoring | Bidder has included for current monitoring only which does not comply with the E.R. - Included (See separate proposals) | [9 empty] | 0 | [8 empty] | 0 | Track & Form |  | escalated | N/A | N/A |  | ● Bidders stray current proposals non compliant and drainage issues* | f
inf | 2 | Potential VE savings | From SCOOP Jan 07 submission | From SCOOP Jan 07 submission | -10000000 |  | -10000000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | V.E Opportunities |  | N/A | N/A | N/A |  |  | h
inf | 52 | Potential VE savings | Numbers included below the Normalisation totals | N/A |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | V.E Opportunities |  | N/A | N/A | N/A |  |  | h
inf | 5 | Allowance for surface finishes on Leith walk and princess street areas | Enhanced finished required (i.e. cobbles etc.). Lack of assurance of scope coverage within "Highways" section of the bids |  |  |  | 0 | 2000000 |  | 2000000 | 2000000 |  | 2000000 |  |  | 0 |  |  | 0 |  |  | 0 | Highways | 1C |  | 2008-03-01 | 2010-06-01 |  |  | i
inf | 21 | Adjust for natural stone paving in Princess Street in lieu of asphalt | Bidders have priced a like-for-like replacement, where it is anticipated CEC would require an enhanced finish, betterment?. Covered in normalisation 4 and 5. | N/A |  |  | 0 |  |  | 0 |  |  | 0 | 589112 |  | 589112 | 589112 |  | 589112 |  |  | 0 | Highways |  | N/A | N/A | N/A |  |  | i
inf | 39 | Allowance for landscaping (included) | ROLEY original bid contained no allowance for landscaping, subsequently included | N/A |  |  | 0 |  |  | 0 |  |  | 0 | 88500 | 40500 | 129000 |  |  | 0 |  |  | 0 | Highways |  | N/A | N/A | N/A |  |  | i
inf | 48 | Reduction in sub-base rate | Rate within SCOOP May 07 submission looked to be a mistake due to its magnitude | Revised rate applied consistent with other areas of the scheme |  |  | 0 | -72000 |  | -72000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Highways |  | N/A | N/A | N/A |  |  | i
inf | 10 | A8 Underpass piling | Originally thought bid excluded piling, however further to recent information piling is included | N/A |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 3267590 |  | 3267590 | 0 |  | 0 | Structures |  | N/A | N/A | N/A |  |  | j
inf | 13 | Crewe Gardens Bridge - Contiguous piling | Bidder not included piling. - Included | Taken from SCOOP bid |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 1825000 | 1825000 |  |  | 0 | Structures | 3A | escalated | 2009-07-01 | 2011-01-01 |  | ● Bidder to re-check estimate and provide comment by 24th Aug 07. | j
inf | 30 | Roseburn Corridor Drainage Pumps | Anticipation for pumping to outfalls, cost captured under Normalisation 61 | N/A |  |  | 0 |  | 50000 | 50000 |  |  | 0 |  |  | 0 |  | 50000 | 50000 |  |  | 0 | Structures |  | N/A | N/A | N/A |  |  | j
inf | 37 | Murrayfield Tram Stop Lift and Steps | Installation of staircase and lift at Murrayfield Tramstop. ROLEY have captured within main bid, SCOOP have not. | £40k - Provision and installation of staircase to North West corner of Murrayfield Tramstop retaining wall £60k - Provision, installation and commissioning to lift to North West corner of Murrayfield Tramstop retaining wall. |  |  | 0 | 100000 |  | 100000 | 100000 |  | 100000 |  |  | 0 |  |  | 0 |  |  | 0 | Structures | 5A | escalated | 2008-05-01 | 2009-09-01 |  |  | j
inf | 47 | Delete Crew Relief Facilities at Granton Sqr | No longer required, operators will be directed to use public facilities | From bid submissions |  |  | 0 |  | -49950 | -49950 |  | -49950 | -49950 |  |  | 0 |  |  | 0 |  |  | 0 | Structures |  | escalated | N/A | N/A |  |  | j
inf | 58 | Landfill Tax Post 2008 +33% | Marker | is this applicable, can spoil be reused around the network? |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Structures |  | N/A | N/A | N/A |  |  | j
Non-infraco | 6 | Allowance for Traffic Signal and UTC works | This allowance is for off route modification (outwith L.O.D) to junction lights, sequencing, programming etc. | Allowance of £2.5M in light of discussions with bidders, ROLEY estimated £1M would be sufficient and SCOOP £4M | 2570487 |  | 2570487 | 5000000 |  | 5000000 | 2500000 |  | 2500000 |  |  | 0 | 5000000 |  | 5000000 | 2500000 |  | 2500000 | Budget Allowance | All |  | 2010-04-01 | 2011-04-01 |  | ● Bidder accepts common normalisation value but expressed desire to work together to establish more accurate costing. | [5 empty] | 2500000
Non-infraco | 9.1 | Murrayfield Modifications | Includes relocation of pitches | Bidders commented this value looks high. | 3355010 |  | 3355010 | 3355010 |  | 3355010 | 940010 |  | 940010 | 3355010 |  | 3355010 | 3355010 |  | 3355010 | 940010 |  | 940010 | Budget Allowance | 5A | escalated | 2008-05-01 | 2009-09-01 |  | ● Bidder accepts allowance pending further detail. |  | 940010
Non-infraco | 9.2 | Murrayfield Pitches flood prevention design and Capex impact | Allowance for flood prevention design and capex impact | as above | [6 empty] | 2415000 |  | 2415000 | [8 empty] | 0 | Budget Allowance - Removed under VE |  | escalated | 2008-05-01 | 2009-09-01 |  | ● Bidder accepts allowance pending further detail. |  | 0
Non-infraco | 11 | Network Rail Immunisation | Network Rail requirement to immunise against current leakage into their track circuits, also includes for AC leakage from OLE. - Network Rail costs to be paid by tie | Price extracted from Faber Mausell report, thought to include implementation, possession costs and TOC and/or FOC compensation | 7269188 |  | 7269188 | 6500000 |  | 6500000 | 7723445.0024 |  | 7723445.0024 | 7269188 |  | 7269188 | 6500000 |  | 6500000 | 1000000 |  | 1000000 | Network Rail Immunisation - £3m added to Infraco | 7A, 5C, 5B, 5A | 2Q06 | 2008-09-01 | 2010-07-01 | 1.1882 | ● Bidder confirmed inclusion of EMR (electro magnetic radiation) interference strategy which protects external 3rd party equipment. Not withstanding, value acceptable (provided it's common to both bidders) but thinks it unnecessary. | [5 empty] | 1000000
Non-infraco | 12 | Power - Network Reinforcement | This item was originally covered in the Risk Register, moved to firm and from R.R | Siemens have expressed concern over value of works and have suggested £1m. Value based on the Mean risk value |  |  | 0 | 1579674 | 604411 | 2184085 | 1579674 | 604000 | 2183674 |  |  | 0 | 1579674 | 604411 | 2184085 | 1579674 | 604000 | 2183674 | Network Reinforcement | All | escalated | 2008-09-01 | 2010-07-01 |  | ● Bidder offered to become involved with Scottish Power interface providing all information is made available form tie. | [5 empty] | 1579674 | 604000
Non-infraco | 14 | Add Electrical Power for Commissioning | Power to commission | Estimate is based on number provided by D.Powell (£1m + escalation) in line with Nottingham Tram consumption. Bidders commented this number appeared excessive | 1344203 |  | 1344203 | 1344203 |  | 1344203 | 1344203 |  | 1344203 | 1344203 |  | 1344203 | 1344203 |  | 1344203 |  |  | 0 | Power for Commissioning - now in Infraco bid |  | escalated | N/A | N/A |  | ● Bidder accepts normalisation value. | [5 empty] | 0
|  | Ticket Machines | Procured directly | [16 empty] | 750000
|  | IPR2 contingency | As agreed by TPB | [16 empty] | 300000
| Non-infraco Total | [18 empty] | 7069684 | 604000 | 6623684 | [6 empty] | 0 |  | 940010 | 0 | 0 | 0 | 5079674 | 604000
|  |  | Current Normalisation Total (24 August 2007) |  | 8734261 | 638747 | 9373008 | 22420556 | 1303323 | 23723879 | 19826520.0024 | 554050 | 20380570.0024 | 29884390 | 1870117 | 31754507 | 36934776 | 4113037 | 41047813 | 14139368 | 1208000 | 13247368
|  |  | Normalisation at 23 August 2007 | [16 empty] | 53822000 | 8619000 | 62441000
|  |  | Variance | [16 empty] | -39682632 | -7411000 | -49193632
Note on X1: terramic: Filters through to main summary sheets
Note on AC1: terramic: Using Average multiplier across duration
Note on AD5: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Groundwater control: o AMIS to control water until Infraco takes over. o BBS to take temp pumping into their bid. o Normalisation to be removed
Note on AD7: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Agreed – Allowance common to both bidders.
Note on AD9: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Inflation for systems. BBS to reconsider. Tie are willing to consider arrangements for pre purchase/commitment to price volatile metals or indexation arrangements for such materials. Tie are not willing for the systems price generally to be fluctuating price.
Note on AD10: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 BBS view is that the additional sub-station is not required and that system will comply with Employer’s Requirements with 1a operating on a standalone basis. Agreed to remove.
Note on AD28: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Allowance for refinishing roads between tracks. BBS confirmed that they have allowed for surface finishes between the tracks within their bids. Normalisation to be removed.
Note on AD34: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Stray current monitoring – BBS to consider taking this risk into their bid. BBS to review allowances for trackform drainage within their bid following the Trackform review meeting with tie.
Note on AD42: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Crewe Gardens Bridge – BBS to consider appropriate allowance
Note on AD48: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 UTC: tie have reduced normalisation based on BBS advice. Amount Agreed. This allowance represents BBS’s estimate of the requirements for work to traffic signals beyond the track alignment LOD. Note:- o BBS have included a provisional sum for all traffic signal works required along the alignment. o This allowance in BBS bid includes re-sequencing and re-configuring traffic signals along the alignment.
Note on AD49: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Agreed. GG advised that this adjustment is common to both bidders.
Note on AD50: terramic: From GG minutes of meeting with BBS on 23 Aug 2007
Note on AD51: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 NWR Immunisation. Agreed. Note:- o Siemens offered to assist tie in making the technical arguments to NWR that immunisation is not required. o GG advised that the allowance is common to both bidders. o tie to provide details of discussion to date with NWR.
Note on AD52: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Network reinforcement – Budget allowance common to both bidders.
Note on AD53: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Electrical Power for commissioning – Common allowance for both bidders.

## Non Infraco VE
EDINBURGH TRAM PROJECT - PHASE 1A | [15 empty] | Revision 32_12.12.7
VALUE ENGINEERING OPPORTUNITIES REGISTER
Item | Opportunity | Filter | Proposal Origin |  | Opportunity Champion | Cost of Project Element | Work Stream affected | Current Status | tie Adjustments |  |  |  | Work In Progress Items |  |  | Collated Summary |  |  | Anticipated Degree of Success | [6 empty] | Comments (s/s) |  |  | Scoop 3 (Rec 7.8.7) |  | Roley 3 (Rec 7.8.7) |  | Scoop 3 (Rec 7.8.7) |  | Roley 3 (Rec 7.8.7)
[9 empty] | Min | Max | Incl in Scoop/Rolly3 |  | Easy (80%) | Medium (50%) | Difficult (20%) | Scoop | BBS | Category | Scoop |  | BBS |  | Cautious View | Contract Change Notice Ref | General Comments (from 29.8.7) (SB 11.10.7 comments) Latest comments in red. |  | Effect On FBC Provision (within £498m). Decrease in brackets | Scoop 3 Comments | Min | Max | Min | Max | Min | Max | Min | Max | Technical Comment (Roley) AS 17 Sept 07 (LM/AS new comments 11/10/07) | TEL comment on Scoop if considered relevant | Transdev Comment by RNHJ 17 Sept 2007
[13 empty] | 0.8 | 0.5 | 0.2 |  |  |  | %age | £ | %age | £ |  |  | Requires action
SUMMARY (Columns 1 & 2) |  |  | SCOOP | BBS -Target |  | Degree of Confidence | BBS - Confidence Level | [9 empty] | Oct Commercial Report |  |  | SCOOP |  | BBS
Infraco
| Banked & Confirmed - Cat 1 (in base bids) |  | 0 | 0 | 1 | #DIV/0! | 0 |  |  |  |  | 1 | [6 empty] | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 1
| Banked - Cat 2 (confirmed by stakeholders/TEL) |  | 0 | 0 | 2 | #DIV/0! | 0 |  |  |  |  | 2 |  |  |  |  | 3077480 |  | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 2
| Post Preferred Bidder - Cat 3 |  | 500000 | 500000 | 3 | 0% | 0 |  |  |  |  | 3 |  |  |  |  | 6938567 |  | 20% | 100000 | 0% | 0 | 0 | 3
| Post Preferred Bidder - Cat 4 (Oct - Dec 2007) |  | 0 | 0 | 4 | #DIV/0! | 0 |  |  |  |  | 4 |  |  |  |  | 9650000 |  | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 4
| Sub Total |  | 500000 | 500000 |  | 0% | 0 | [9 empty] | 19666047 |  | 20% | 100000 | 0% | 0 | 0
Non Infraco
| Banked - Cat 5 |  | 4228600 | 3278600 | 5 | 41.57% | 1363000 | [9 empty] | 2755600 |  | 53.34% | 2255600 | 41.57% | 1363000 | 0 | 5
| Furtherwork - Cat 6 |  | 3595000 | 9085000 | 6 | 35.19% | 3197000 | [9 empty] | 7530500 |  | 67.2% | 2416000 | 35.19% | 3197000 | 0 | 6
| Sub Total |  | 7823600 | 12363600 |  | 36.88% | 4560000 | [9 empty] | 10286100 |  | 59.71% | 4671600 | 36.88% | 4560000 | 0
Overall Total |  |  | 8323600 | 12863600 |  | 35.45% | 4560000 | [9 empty] | 29952147 |  | 57.33% | 4771600 | 35.45% | 4560000 | 0
| OVERALL TOTALS | [7 empty] | 0 | 10700000 |  |  | 2920000 | 500000 | 182351.435 | 8323600 | 12863600 |  |  | 4771600 |  | 4560000 | 0 |  |  |  | 610000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| HIGHWAYS | [6 empty] | OPEN
36a | Material recovery and reprocessing - MUDFA 2 options - reconstituted planings & Type 1R | Highways |  |  | GB |  | Mudfa | OPEN |  |  |  |  | 120000 | 0 | 0 | 150000 | 150000 | 6 | 80% | 120000 | 80% | 120000 |  |  | SB - use Sign Off sheet estimate £150k | Who owns the granite blocks within the road construction? What is CEC position and has INFRACO bids taken disposal of high value items such as this within their respective bids?
36b | Material recovery and reprocessing - INFRACO 2 options - reconstituted planings & Type 1R | [5 empty] | INFRACO | OPEN | [11 empty] | 0 | 0% | 0 |  |  | 20.11.7 BBS to firm up figures
37 | Reduction in extent of road reinstatement. Premis that base course/road base material used in lieu of wearing course until properly reinstated under INFRACO MUDFA temporary reinstatements | Highways | Project |  |  | 5210041 | MUDFA | OPEN |  |  |  |  | 0 | 0 | 182351.435 | 145000 | 145000 | 6 | 80% | 116000 | 80% | 116000 |  |  | MUDFA Team assessment of opportunity £145,000 | AR -Very difficult to support!! Maybe after MUDFA but then fully reinstate by INFRACO
| HIGHWAYS TOTAL | [6 empty] | OPEN | 0 | 0 |  |  | 120000 | 0 | 182351.435 | 295000 | 295000 |  | 80% | 236000 | 80% | 236000 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| LAND & PROPERTY | [6 empty] | OPEN
136 | Land & Property - specific plots of land that may no longer be required | Land & property | Project |  |  |  | Land & Property | OPEN |  |  |  |  | 0 | 0 | 0 | 340000 | 0 | 5 | 100% | 340000 | 0% | 0 |  |  | 20.11.7 £340k saving already included in current project estimate under L&P. | A Sim to advise - Plots 96 and 101 - in the industrial area off Roseburn Street - may not be required Formal instruction has now been issued to SDS
| LAND & PROPERTY TOTAL | [6 empty] | OPEN | 0 | 0 |  |  | 0 | 0 | 0 | 340000 | 0 |  | 100% | 340000 | #DIV/0! | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| NETWORK RAIL | [6 empty] | OPEN
42 | NR Immunisation - ETN only to pay for Direct Current immunisation (£3.5m) | NR | Project - 7.2.4 |  | SB |  | Infraco | OPEN |  | 7700000 |  |  | 2800000 | 0 | 0 | 2800000 | 5000000 | 6 | 60% | 1680000 | 0% | 0 |  |  | Nico Decker Report confirms likley saving £3.5-4.0m. Next steps to identify cost impact for each bider before sign up. Target Date Mon 1st Oct. SB to lead with GG input. Refer to SB VE sheet for comments - NOW IN INFRACO BID AND NORMALISATIONS
| NETWORK RAIL TOTAL | [6 empty] | OPEN | 0 | 7700000 |  |  | 2800000 | 0 | 0 | 2800000 | 5000000 |  | 60% | 1680000 | 0% | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SYSTEM WIDE | [6 empty] | OPEN
161 | Savings to capex of E&M infrastructure and trams through a finance lease. | [5 empty] | Infraco | OPEN | [8 empty] | 3290000 | 6 |  |  | 90% | 2961000 |  |  | This would be achieved via a defeased tax structure, not a funded lease. Savings value quoted by two potential arrangers are between 3-5%, though commercial value would need to be negotiated with lessor. Also requires analysis of asset type. Either a Fre
| SYSTEM WIDE TOTAL | [6 empty] | OPEN | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 3290000 |  | #DIV/0! | 0 | 90% | 2961000 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| THIRD PARTY | [6 empty] | OPEN
90a | Murrayfield Pitch Relocation - Flood prevention scheme | Third Party | Project |  |  | 3355000 | Infraco | OPEN |  | 3000000 | [5 empty] | 1915600 | 1915600 | 5 | 100% | 1915600 | 0% | 0 |  |  | From Infraco Normalisation item 9 (in part) - NOW OMITTED FROM NORMALISATIONS | Comments made by various individuals suggests that a compromise has been reached with SRU. Await final confirmation from?
90b | Murrayfield Pitch Relocation - mods only to Waranders Club House | Third Party | Project |  |  |  | Infraco | OPEN | [7 empty] | 500000 | 500000 | 6 | 100% | 500000 | 0% | 0 |  |  | From Infraco Normalisation item 9 (in part) Remaining allowance in Normalisation Item 9 required to meet temporary pitch move commitment to SRU. L. Murphy to confirm if this scope will be required.
| THIRD PARTY TOTAL | [6 empty] | OPEN | 0 | 3000000 |  |  | 0 | 0 | 0 | 2415600 | 2415600 |  | 100% | 2415600 | 0% | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TRACTION POWER | [6 empty] | OPEN
104 | Network Reinforcement - not to be paid for by ETN | Traction Power | Project - 31.1.16 |  | AD/BE |  | Infraco | OPEN | [5 empty] | 0 | 0 | 1973000 | 1363000 | 5 |  | 0 | 100% | 1363000 |  |  | Sign Off Sheet has £2.2m achieved & £2.45m estimate Letter gone to SP asking confirmation of Tram liability in £s. Will be concluded at end of Oct. Latest figures based on SP verbal w/c 12/11 | Argument that ETN alone should not be penalised for upgrading SP network when there are significant other developments ongoing in the City. Adjusted to reflect difference between original QRA provision and works estimate. | 610000 | [9 empty] | Meeting held with SP. Update awaited
| TRACTION POWER TOTAL | [6 empty] | OPEN | 0 | 0 |  |  | 0 | 0 | 0 | 1973000 | 1363000 |  | 0% | 0 | 100% | 1363000 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TRAMS | [6 empty] | OPEN
119 | Reduce fleet size - delete 1 tram from spare capacity and accept risk to lower performance | Trams | Project - 5.1.17 |  | AR |  | Tramco | OPEN |  |  |  |  | 0 | 500000 | 0 | 500000 | 500000 | 3 | 20% | 100000 | 0% | 0 |  |  |  | Opportunity of last resort
| TRAMS TOTAL | [6 empty] | OPEN | 0 | 0 |  |  | 0 | 500000 | 0 | 500000 | 500000 |  | 20% | 100000 | 0% | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| OVERALL TOTALS | [6 empty] | OPEN | 0 | 10700000 |  |  | 2920000 | 500000 | 182351.435 | 8323600 | 12863600 |  | 57.33% | 4771600 | 35.45% | 4560000 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| NOTE: Financial Impact calculated on average Max/Min impact multiplied by the probability of success | [13 empty] | 3602351.435
DEFINITIONS
| BANKED' | Items offered by bidders or developed by project team.
| IN PROGRESS' | Potential for further saving (undisclosed)
| CLOSED' | No Value / Dead
| REJECTED' | Value exists but not attainable
| OPEN' | Active Item under review
Rev 27_11.10.7 - updated to include Geoff's assessemnt of category 1s

## Summary P10
EDINBURGH TRAM 1A Full consolidation
1 |  | Period | Proj Mgr | 04/05/06 | 2006-04-01 | 2006-05-01 | 2006-06-01 | 2006-07-01 | 2006-08-01 | 2006-09-01 | 2006-10-01 | 2006-11-01 | 2006-12-01 | 2007-01-01 | 2007-02-01 | 2007-03-01 | 06/07 | Cumulative | 1 - 07/08 | 2 - 07/08 | 3 - 07/08 | 4 - 07/08 | 5 - 07/08 | 6 - 07/08 | 7 - 07/08 | 8 - 07/08 | 9 - 07/08 | 10 - 07/08 | 11 - 07/08 | 12 - 07/08 | 13 - 07/08 | 07/08 | Cumulative | 1 - 08/09 | 2 - 08/09 | 3 - 08/09 | 4 - 08/09 | 5 - 08/09 | 6 - 08/09 | 7 - 08/09 | 8 - 08/09 | 9 - 08/09 | 10 - 08/09 | 11 - 08/09 | 12 - 08/09 | 13 - 08/09 | 08/09 | Cumulative | 1 - 09/10 | 2 - 09/10 | 3 - 09/10 | 4 - 09/10 | 5 - 09/10 | 6 - 09/10 | 7 - 09/10 | 8 - 09/10 | 9 - 09/10 | 10 - 09/10 | 11 - 09/10 | 12 - 09/10 | 13 - 09/10 | 09/10 | Cumulative | 1 - 10/11 | 2 - 10/11 | 3 - 10/11 | 4 - 10/11 | 5 - 10/11 | 6 - 10/11 | 7 - 10/11 | 8 - 10/11 | 9 - 10/11 | 10 - 10/11 | 11 - 10/11 | 12 - 10/11 | 13 - 10/11 | 10/11 | Cumulative | 1 - 11/12 | 2 - 11/12 | 3 - 11/12 | 4 - 11/12 | 5 - 11/12 | 6 - 11/12 | 7 - 11/12 | 8 - 11/12 | 9 - 11/12 | 10 - 11/12 | 11 - 11/12 | 12 - 11/12 | 13 - 11/12 | 11/12 | AFC P10 | AFC P9 | AFC P10 v P9 | 0708 P9 | 0708 P10 v P9 | AFC P8 | AFC P9 v P8 | 0708 P11-13 | 0809 Onwards | Infraco | Tramco | MUDFA | Realloc/ | Other | Predicted
2 |  |  |  |  | 2006-05-01 | 2006-06-01 | 2006-07-01 | 2006-08-01 | 2006-09-01 | 2006-10-01 | 2006-11-01 | 2006-12-01 | 2007-01-01 | 2007-02-01 | 2007-03-01 | 1 - 07/08 |  |  | 2 - 07/08 | 3 - 07/08 | 4 - 07/08 | 5 - 07/08 | 6 - 07/08 | 7 - 07/08 | 8 - 07/08 | 9 - 07/08 | 10 - 07/08 | 11 - 07/08 | 12 - 07/08 | 13 - 07/08 | 1 - 08/09 |  |  | 2 - 08/09 | 3 - 08/09 | 4 - 08/09 | 5 - 08/09 | 6 - 08/09 | 7 - 08/09 | 8 - 08/09 | 9 - 08/09 | 10 - 08/09 | 11 - 08/09 | 12 - 08/09 | 13 - 08/09 | 1 - 09/10 |  |  | 2 - 09/10 | 3 - 09/10 | 4 - 09/10 | 5 - 09/10 | 6 - 09/10 | 7 - 09/10 | 8 - 09/10 | 9 - 09/10 | 10 - 09/10 | 11 - 09/10 | 12 - 09/10 | 13 - 09/10 | 1 - 10/11 |  |  | 2 - 10/11 | 3 - 10/11 | 4 - 10/11 | 5 - 10/11 | 6 - 10/11 | 7 - 10/11 | 8 - 10/11 | 9 - 10/11 | 10 - 10/11 | 11 - 10/11 | 12 - 10/11 | 13 - 10/11 | 1 - 11/12 |  |  | 2 - 11/12 | 3 - 11/12 | 4 - 11/12 | 5 - 11/12 | 6 - 11/12 | 7 - 11/12 | 8 - 11/12 | 9 - 11/12 | 10 - 11/12 | 11 - 11/12 | 12 - 11/12 | 13 - 11/12
3 |  | Period end |  | 2006-03-31 | 2006-04-30 | 2006-05-31 | 2006-06-30 | 2006-07-31 | 2006-08-31 | 2006-09-30 | 2006-10-31 | 30/44/06 | 2006-12-31 | 2007-01-31 | 2007-02-28 | 2007-03-31 | 2007-03-31 |  | 2007-04-28 | 2007-05-26 | 2007-06-23 | 2007-07-21 | 2007-08-18 | 2007-09-15 | 2007-10-13 | 2007-11-10 | 2007-12-08 | 2008-01-05 | 2008-02-02 | 2008-03-01 | 2008-03-31 | 2008-03-31 |  | 2008-04-26 | 2008-05-24 | 2008-06-21 | 2008-07-19 | 2008-08-16 | 2008-09-13 | 2008-10-11 | 2008-11-08 | 2008-12-06 | 2009-01-03 | 2009-01-31 | 2009-02-28 | 2009-03-31 | 2009-03-31 |  | 2009-04-25 | 2009-05-23 | 2009-06-20 | 2009-07-18 | 2009-08-15 | 2009-09-12 | 2009-10-10 | 2009-11-07 | 2009-12-05 | 2010-01-02 | 2010-01-30 | 2010-02-27 | 2010-03-31 | 2010-01-31 |  | 2010-05-01 | 2010-05-29 | 2010-06-26 | 2010-07-24 | 2010-08-21 | 2010-09-18 | 2010-10-16 | 2010-11-13 | 2010-12-11 | 2011-01-08 | 2011-02-05 | 2011-03-05 | 2011-03-31 | 2011-03-31 |  | 2011-04-30 | 2011-05-28 | 2011-06-18 | 2011-07-16 | 2011-08-13 | 2011-09-10 | 2011-10-08 | 2011-11-05 | 2011-12-03 | 2011-12-31 | 2012-01-28 | 2012-02-25 | 2012-03-31 | 2012-03-31 | [9 empty] | Fin Close | Fin Close | Fin Close | Restate | Fin Close | Control Budget
4 |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90
5
1706 | 10 - 07/08 | FORECAST THIS PERIOD
1707
1708 | T01.01 | Project management Staff Costs | C McLauchlan | 1456288.59 | 162852.0783 | 162852.0783 | 215115 | 261366 | 256200.8145 | 269949.194 | 270000 | 270000 | 335403 | 195121 | 408571 | 543908 | 3351338.165 | 4807626.755 | 395023.7086 | 406954 | 425187 | 429810 | 437210 | 323708 | 641724 | 520821 | 598967 | 552993.795 | 548868.795 | 548868.795 | 550131.795 | 6380267.8886 | 11187894.6437 | 522798.0095 | 522798.0095 | 522798.0095 | 522798.0095 | 522798.0095 | 522798.0095 | 480173.6105 | 480173.6105 | 480173.6105 | 480173.6105 | 436879.6491 | 436879.6491 | 436879.6491 | 6368121.4464 | 17556016.09 | 357266 | 357266 | 357266 | 357266 | 357266 | 357266 | 355015 | 355015 | 364196 | 364196 | 364196 | 364196 | 364196 | 4674606 | 22230622.09 | 364196 | 364196 | 364196 | 364196 | 364196 | 364196 | 382433 | 382433 | 166793 | 0 | 0 | 0 | 0 | 3116835 | 25347457.09 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 25347457.09 | 25866806.3822 | -519349.2922 | 6459432.6272 | -79164.7385 | 26171910.4636 | -305104.0814 | 1647869.385 | 14159562.4464 | 583353 |  |  | 561111 |  | 26491921.09 |  | Email SMcG to SB/CMcL -13/1/08
1709 | T01.02 | Recruitment Fees | C McLaughlan | 1: 38611.75; 7: 8375; 11: 46351; 12: 22675; 13: 25925; 14: 103326; 15: 141937.75; 16: 56666.6666; 19: 10303; 22: 10303; 24: 15853; 25: 12363; 26: 12363; 27: 12363; 28: 8876; 29: 139090.6666; 30: 281028.4166; 31: 35700; 32: 11000; 33: 6500; 34: 3803; 44: 57003; 45: 338031.4166; 46: 37485; 59: 37485; 60: 375516.4166; 61: 39359.25; 74: 39359.25; 75: 414875.6666; 76: 41326.95; 89: 41326.95; 90: 456202.6166 | 456202.6166 | 0 | 139090.6666 | 0 | 456202.6166 | 0 | 33602 | 175174.2 | [5 empty] | 456202.6166 |  | Review by PM
1710 | T01.03 | Travel & Subsistence / Conference | C McLaughlan | 25629.24 | 3000 | 3000 | 8883 | 6176 | 5000 | 6496 | -8114 | 10000 | 5000 |  | 817 | 5885 | 46143 | 71772.24 | 4803.87 | 4659.97 | 4776.19 | 4720.84 |  | 4776.97 | 4797.94 | 7587.73 | 9223.14 | 12571.71 | 3499.86 | 3240.52 | 5116.1 | 69774.84 | 141547.08 | 5011.0769 | 5011.0769 | 5011.0769 | 5011.0769 | 5011.0769 | 5011.0769 | 5011.0769 | 5011.0769 | 5011.0769 | 5011.0769 | 5011.0769 | 5011.0769 | 5011.0769 | 65144 | 206691.08 | 5215.6154 | 5215.6154 | 5215.6154 | 5215.6154 | 5215.6154 | 5215.6154 | 5215.6154 | 5215.6154 | 5215.6154 | 5215.6154 | 5215.6154 | 5215.6154 | 5215.6154 | 67803 | 274494.08 | 5429.4615 | 5429.4615 | 5429.4615 | 5429.4615 | 5429.4615 | 5429.4615 | 5429.4615 | 5429.4615 | 5429.4615 | 5429.4615 | 5429.4615 | 5429.4615 | 5429.4615 | 70583 | 345077.08 | 3015.5 | 2457.5 | 1786.5 | 1786.5 | 1641.5 | [8 empty] | 10687.5 | 355764.58 | 354145.08 | 1619.5 | 60749.84 | 9025 | 354145.08 | 0 | 11856.48 | 214217.5 | [5 empty] | 355764.58 |  | Issue of policy outstanding
1711 | T01.04 | Allocations from central O/H | Various | 910013.9336 | 75298.7943 | 73710.1831 | 116748 | 188591 | 150809 | 150809 | 163186 | 150809 | 150809 | 228623 | 150809 | 96000 | 1696201.9773 | 2606215.9109 | 156605.4615 | 162453 | 160460 | 156605.4615 | 201692 | 103605 | 65292 | 65292 | 173168 | 79346 | 79346 | 79346 | 79346 | 1562556.9231 | 4168772.834 | 32610.5385 | 32610.5385 | 32610.5385 | 32610.5385 | 32610.5385 | 32610.5385 | 32610.5385 | 32610.5385 | 32610.5385 | 32610.5385 | 32610.5385 | 32610.5385 | 32610.5385 | 423937.001 | 4592709.835 | 27889.6154 | 27889.6154 | 27889.6154 | 27889.6154 | 27889.6154 | 27889.6154 | 27889.6154 | 27889.6154 | 27889.6154 | 27889.6154 | 27889.6154 | 27889.6154 | 27889.6154 | 362565.0005 | 4955274.8355 | 29284.0962 | 29284.0962 | 29284.0962 | 29284.0962 | 29284.0962 | 29284.0962 | 29284.0962 | 29284.0962 | 29284.0962 | 29284.0962 | 29284.0962 | 29284.0962 | 29284.0962 | 380693.2512 | 5335968.0867 | 36901.301 | 36901.301 | 36901.301 | 36901.301 | 36901.301 | 36901.301 | 36901.301 | 36901.301 | 36901.301 | 36901.301 | 36901.301 | 36901.301 | 36901.301 | 479716.9127 | 5815684.9994 | 5815695.9994 | -11 | 1642556.9231 | -80000 | 5728879.9994 | 86816 | 238038 | 1646912.1654 |  |  |  | 207426 |  | 6023110.9994 |  | Email SMcG to SB/CMcL - 13/1/08
1712 | T01.05 | IT & Software Costs / fitout | S Healy | 214591.66 | 307000 | 90000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 35191 | 73196 | 561387 | 775978.66 | 34393.6154 | 46091 | 363784.6154 | 289669.6154 |  | 23385 |  |  | -136036 | 68018 | 68018 | 10000 | 10000 | 777323.8462 | 1553302.5062 | 31893 | 31893 | 31893 | 31893 | 31893 | 31893 | 31893 | 31893 | 31893 | 31893 | 31893 | 31893 | 31893 | 414609 | 1967911.5062 | 32877 | 32877 | 32877 | 32877 | 32877 | 32877 | 32877 | 32877 | 32877 | 32877 | 32877 | 32877 | 32877 | 427401 | 2395312.5062 | 34495 | 34495 | 34495 | 34495 | 34495 | 34495 | 34495 | 34495 | 34495 | 34495 | 34495 | 34495 | 34495 | 448435 | 2843747.5062 | 30612 | 30612 | 30612 | 30612 | 30612 | 30612 | 30612 | 30612 | 30612 | 30612 | 30612 | 30612 | 30612 | 397956 | 3241703.5062 | 3313983.5062 | -72280 | 777323.8462 | 0 | 3313983.5062 | 0 | 88018 | 1688401 |  |  |  | 104005 |  | 3345708.5062 |  | Email SMcG to SH cc JMcE/SB/CMcL - 13/1/08
1713 | T01.06 | Citypoint - rent,rates,s/c | P Diamond | 29174 | 20000 | 20000 | 20000 | 20000 | 20000 | 20249 | 19751 | 20000 | 20000 | 20000 | 20000 | 40634 | 260634 | 289808 | 67447 | 45114 | 45114 | 45114 | 45114 | 45114 | 45114 | 45114 | 17903 | 44572 | 44572 | 44572 | 44572 | 579436 | 869244 | 22438.2232 | 22438.2232 | 22438.2232 | 22438.2232 | 22438.2232 | 22438.2232 | 22438.2232 | 22438.2232 | 22438.2232 | 22438.2232 | 22438.2232 | 22438.2232 | 22438.2232 | 291696.9012 | 1160940.9012 | 22869.8458 | 22869.8458 | 22869.8458 | 22869.8458 | 22869.8458 | 22869.8458 | 22869.8458 | 22869.8458 | 22869.8458 | 22869.8458 | 22869.8458 | 22869.8458 | 22869.8458 | 297307.9951 | 1458248.8963 | 23323.0497 | 23323.0497 | 23323.0497 | 23323.0497 | 23323.0497 | 23323.0497 | 23323.0497 | 23323.0497 | 23323.0497 | 23323.0497 | 23323.0497 | 23323.0497 | 23323.0497 | 303199.6459 | 1761448.5422 | 37057.6829 | 37057.6829 | 37057.6829 | 37057.6829 | 37057.6829 | 37057.6829 | 37057.6829 | 37057.6829 | 37057.6829 | 37057.6829 | 37057.6829 | 37057.6829 | 37057.6829 | 481749.8779 | 2243198.4201 | 2243198.4201 | 0 | 579436 | 0 | 2272577.4201 | -29379 | 133716 | 1373954.4201 | [5 empty] | 2243198.4201 |  | Email SMcG to SB/CMcL - 13/1/08
1714 | T01.07 | Recovered from SDS |  | 1: 0; 2: -13000; 3: -4000; 4: -4000; 5: 21000; 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
1715 | T01.08 | Short Term Contractors | C McLaughlan | 1: 85542; 2: 50000; 3: 50000; 4: 11262; 14: 111262; 15: 196804; 29: 0; 30: 196804; 44: 0; 45: 196804; 59: 0; 60: 196804; 74: 0; 75: 196804; 89: 0; 90: 196804 | 196804 | 0 | 0 | 0 | 196804 | 0 | 0 | 0 |  |  |  | -196804 |  | 0 |  | Budget reallocated to T01.01
1716 | T01.09 | City Point Overheads | Various |  | 4000 | 4000 | 1323 | 4000 | 4000 | 4125 | 4000 | 4000 | 4000 | -14107 | 2000 | -1746 | 19595 | 19595 | 3076.9231 |  |  | 3355.9231 | 500 | [5 empty] | 954 | 954 | 955 | 9795.8462 | 29390.8462 | 5587 | 5587 | 5587 | 5587 | 5587 | 5587 | 2731 | 3230.7692 | 3230.7692 | 3230.7692 | 3230.7692 | 3230.7692 | 3230.7692 | 55637.6154 | 85028.4615 | 3392.3077 | 3392.3077 | 3392.3077 | 3392.3077 | 3392.3077 | 3392.3077 | 3392.3077 | 3392.3077 | 3392.3077 | 3392.3077 | 3392.3077 | 3392.3077 | 3392.3077 | 44100 | 129128.4615 | 3561.9231 | 3561.9231 | 3561.9231 | 3561.9231 | 3561.9231 | 3561.9231 | 3561.9231 | 3561.9231 | 3561.9231 | 3561.9231 | 3561.9231 | 3561.9231 | 3561.9231 | 46305 | 175433.4615 | 4721.7692 | 4721.7692 | 4721.7692 | 4721.7692 | 4721.7692 | 4721.7692 | 4721.7692 | 4721.7692 | 4721.7692 | 4721.7692 | 4721.7692 | 4721.7692 | 4721.7692 | 61383 | 236816.4615 | 236817.4615 | -1 | 18364.8462 | -8569 | 236817.4615 | 0 | 2863 | 207425.6154 |  |  |  | -207425.6154 |  | 29390.8462 |  | Budget for 0809 onwards reallocated to T01.04
1717 | T01.10 | Active Risk Manager | M | [7 empty] | 23344 | 23344 | 21588 | -5190 | 6799 |  | 69885 | 69885 | [7 empty] | 11229 |  |  | 10239 |  |  | 21468 | 91353 | 1733.9231 | 1733.9231 | 1733.9231 | 1733.9231 | 1733.9231 | 1733.9231 | 1733.9231 | 1733.9231 | 1733.9231 | 1733.9231 | 1733.9231 | 1733.9231 | 1733.9231 | 22541 | 113894 | 1820.6154 | 1820.6154 | 1820.6154 | 1820.6154 | 1820.6154 | 1820.6154 | 1820.6154 | 1820.6154 | 1820.6154 | 1820.6154 | 1820.6154 | 1820.6154 | 1820.6154 | 23668 | 137562 | 1911.6923 | 1911.6923 | 1911.6923 | 1911.6923 | 1911.6923 | 1911.6923 | 1911.6923 | 1911.6923 | 1911.6923 | 1911.6923 | 1911.6923 | 1911.6923 | 1911.6923 | 24852 | 162414 | 2534.1538 | 2534.1538 | 2534.1538 | 2534.1538 | 2534.1538 | 2534.1538 | 2534.1538 | 2534.1538 | 2534.1538 | 2534.1538 | 2534.1538 | 2534.1538 | 2534 | 32943.8462 | 195357.8462 | 195358 | -0.15385 | 21468 | 0 | 195358 | 0 | 10239 | 104004.8462 |  |  |  | -104005 |  | 91352.8462 |  | Budget for 0809 onwards reallocated to T01.05
1718 | T01.11 | Archaeological supervisor | S Clark | 14: 0; 15: 0; 29: 0; 30: 0; 31: 5011.0769; 32: 5011.0769; 33: 5011.0769; 34: 5011.0769; 35: 5011.0769; 36: 5011.0769; 37: 5011.0769; 38: 5011.0769; 39: 5011.0769; 40: 5011.0769; 41: 5011.0769; 42: 5011.0769; 43: 5011.0769; 44: 65144; 45: 65144; 46: 4966.2308; 47: 4966.2308; 48: 4966.2308; 49: 4966.2308; 50: 4966.2308; 51: 4966.2308; 52: 4966.2308; 53: 4966.2308; 54: 4966.2308; 55: 4966.2308; 56: 4966.2308; 57: 4966.2308; 58: 4966.2308; 59: 64561; 60: 129705; 61: 4936.6154; 62: 4936.6154; 63: 4936.6154; 64: 4936.6154; 65: 4936.6154; 66: 4936.6154; 67: 4936.6154; 68: 4936.6154; 69: 4936.6154; 70: 4936.6154; 71: 4936.6154; 72: 4936.6154; 73: 4936.6154; 74: 64176; 75: 193881; 89: 0; 90: 193881 | 193881 | 0 | 0 | 0 | 193881 | 0 | 0 | 193881 | [5 empty] | 193881 |  | Review by PM
1719 | T01.12 | MUDFA Site Overheads |  | 14: 0; 15: 0; 20: 500; 21: 500; 22: 500; 23: 500; 24: 500; 25: 500; 26: 500; 27: 500; 28: 500; 29: 4500; 30: 4500; 31: 500; 32: 500; 33: 500; 34: 500; 35: 500; 36: 500; 37: 500; 44: 3500; 45: 8000; 59: 0; 60: 8000; 74: 0; 75: 8000; 89: 0; 90: 8000 | 8000 | 0 | 4500 | 0 | 8000 | 0 | 1500 | 3500 | [5 empty] | 8000
1728 | T01 | Total tie PM costs |  | 2759851.1736 | 609150.8726 | 399562.2613 | 376331 | 508133 | 443009.8145 | 467003.194 | 479167 | 485153 | 543800 | 477798 | 646862 | 783802 | 6219772.1424 | 8979623.3159 | 718017.2452 | 665271.97 | 999321.8054 | 939578.84 | 685016 | 501088.97 | 767730.94 | 650543.73 | 679578.14 | 770364.505 | 768360.655 | 699844.315 | 699496.895 | 9544214.0106 | 18523837.3266 | 663282.8481 | 638582.8481 | 634082.8481 | 631385.8481 | 627582.8481 | 627582.8481 | 582102.4491 | 582102.2183 | 582102.2183 | 582102.2183 | 538808.257 | 538808.257 | 538808.257 | 7767333.964 | 26291171.2905 | 493782.2304 | 456297.2304 | 456297.2304 | 456297.2304 | 456297.2304 | 456297.2304 | 454046.2304 | 454046.2304 | 463227.2304 | 463227.2304 | 463227.2304 | 463227.2304 | 463227.2304 | 5999496.9956 | 32290668.2861 | 506497.0882 | 467137.8382 | 467137.8382 | 467137.8382 | 467137.8382 | 467137.8382 | 485374.8382 | 485374.8382 | 269734.8382 | 102941.8382 | 102941.8382 | 102941.8382 | 102941.8382 | 4494438.1471 | 36785106.4332 | 156169.3569 | 114284.407 | 113613.407 | 113613.407 | 113468.407 | 111826.907 | 111826.907 | 111826.907 | 111826.907 | 111826.907 | 111826.907 | 111826.907 | 111826.7531 | 1505764.0867 | 38290870.5199 | 38880892.4659 | -590021.946 | 9702922.7492 | -158708.7385 | 39128559.5474 | -247667.0814 | 2167701.865 | 19767033.1934 | [5 empty] | 39238530.9046
1729 | 0 | 0
1730 | T02.01 | Core Team | A Richards | 386879.57 | 30000 | 30000 | -2661 | 50000 | 50000 | 50000 | 30200 | 30200 | 30200 | 30200 | 30200 | 30200 | 388539 | 775418.57 | 35527 | 35527 | 35527 | 27200 | 25769 | 27000 | 30000 | 36756 | 39364 | 39364 | 39364 | 39364 | 52014 | 462776 | 1238194.57 | 42097.47 | 44082.21 | 44970.12 | 46761.88 | 54195 | 54195 | 57734 | 60147 | 60147 | 60147 | 73653 | 87455 | 87455 | 773039.68 | 2011234.25 | 93001 | 93001 | 93001 | 97651 | 97651 | 97651 | 88398 | 88398 | 88398 | 88398 | 88398 | 94094 | 94094 | 1202134 | 3213368.25 | 124627 | 194977 | 304879 | 365009 | 407755 | 469931 | 512677 | 574658 | 622747 | 840532 | 0 | 0 | 0 | 4417792 | 7631160.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7631160.25 | 7631160.25 | 0 | 462776 | 0 | 7631160.25 | 0 | 130742 | 6392965.68 | [5 empty] | 7631160.25 |  | Review by PM confrims adequate
1731 | T02.02 | Retention | A Richards | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | [5 empty] | 0
1745 | T02 | Total DPOF |  | 386879.57 | 30000 | 30000 | -2661 | 50000 | 50000 | 50000 | 30200 | 30200 | 30200 | 30200 | 30200 | 30200 | 388539 | 775418.57 | 35527 | 35527 | 35527 | 27200 | 25769 | 27000 | 30000 | 36756 | 39364 | 39364 | 39364 | 39364 | 52014 | 462776 | 1238194.57 | 42097.47 | 44082.21 | 44970.12 | 46761.88 | 54195 | 54195 | 57734 | 60147 | 60147 | 60147 | 73653 | 87455 | 87455 | 773039.68 | 2011234.25 | 93001 | 93001 | 93001 | 97651 | 97651 | 97651 | 88398 | 88398 | 88398 | 88398 | 88398 | 94094 | 94094 | 1202134 | 3213368.25 | 124627 | 194977 | 304879 | 365009 | 407755 | 469931 | 512677 | 574658 | 622747 | 840532 | 0 | 0 | 0 | 4417792 | 7631160.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7631160.25 | 7631160.25 | 0 | 462776 | 0 | 7631160.25 | 0 | 130742 | 6392965.68 | [5 empty] | 7631160.25
1746 | 0 | 0
1747 | T03.01 | DLA-SDS | B Dawson | 1: 76499.47; 3: 1915; 4: 2646; 5: 27; 6: 0; 7: 371; 9: 1196; 10: 227; 11: 80; 12: 5000; 13: 0; 14: 11462; 15: 87961.47; 17: 96.76; 18: 0; 19: 0; 20: 5000; 23: 286; 24: 20209.56; 25: 7939.14; 29: 33531.46; 30: 121492.93; 44: 0; 45: 121492.93; 59: 0; 60: 121492.93; 74: 0; 75: 121492.93; 89: 0; 90: 121492.93 | 118553.79 | 2939.14 | 30592.32 | 2939.14 | 93344.23 | 25209.56 | 0 | 0 |  |  |  | -25209.56 | 25209.56 | 121492.93 | )
1748 | T03.02 | DLA-TSS | B Dawson | 1: 29835.86; 4: 0; 5: 0; 6: 0; 7: 0; 8: 0; 9: 2164; 10: 0; 11: 0; 12: 0; 13: 0; 14: 2164; 15: 31999.86; 16: 0; 17: 0; 18: 0; 19: 0; 20: 0; 24: -0.49; 25: 0; 29: -0.49; 30: 31999.37; 44: 0; 45: 31999.37; 59: 0; 60: 31999.37; 74: 0; 75: 31999.37; 89: 0; 90: 31999.37 | 31999.37 | 0 | -0.49 | 0 | 31999.86 | -0.49 | 0 | 0 |  |  |  | 0.49 | -0.49 | 31999.37 | )
1749 | T03.03 | DLA- Site Investigation | B Dawson | 1: 0; 4: 0; 5: 0; 6: 0; 7: 0; 8: 0; 9: 0; 10: 0; 11: 0; 12: 0; 13: 0; 14: 0; 15: 0; 16: 0; 17: 0; 18: 0; 19: 0; 20: 0; 24: 1116.25; 25: 0; 29: 1116.25; 30: 1116.25; 44: 0; 45: 1116.25; 59: 0; 60: 1116.25; 74: 0; 75: 1116.25; 89: 0; 90: 1116.25 | 1116.25 | 0 | 1116.25 | 0 | 0 | 1116.25 | 0 | 0 |  |  |  | -1116.25 | 1116.25 | 1116.25 | )
1750 | T03.04 | DLA-MUDFA | B Dawson | 1: 354360.76; 2: 7000; 3: 31085; 4: 59268; 5: 78604; 6: 5000; 7: 32179; 8: 5000; 9: 29928; 10: 7772; 11: 505; 12: 1000; 13: 8879; 14: 266220; 15: 620580.76; 16: 3000; 17: 5345.87; 18: 2732.52; 19: 11155.84; 20: 2376.72; 24: 16757.29; 25: -147.95; 26: 5000; 27: 5000; 28: 5000; 29: 56220.29; 30: 676801.05; 44: 0; 45: 676801.05; 59: 0; 60: 676801.05; 74: 0; 75: 676801.05; 89: 0; 90: 676801.05 | 681949 | -5147.95 | 61368.24 | -5147.95 | 645191.71 | 36757.29 | 15000 | 0 |  |  |  | -36757.29 | 36757.29 | 676801.05 | )
1751 | T03.05 | DLA-Network Rail / Scotrail | B Dawson | 1: 48665.11; 2: 0; 3: 1792; 4: 1577; 5: 6683; 6: 2500; 7: 4515; 8: 500; 9: -184; 10: 8259; 11: -1979; 12: 2000; 13: -942; 14: 24721; 15: 73386.11; 16: 1500; 17: 2422.04; 18: 699.19; 19: 1750; 20: 556.48; 21: 2000; 22: 2000; 23: 3000; 24: 10896.44; 25: 3194.72; 26: 5000; 27: 5000; 28: 5000; 29: 43018.87; 30: 116404.98; 31: 386.53; 32: 404.76; 33: 412.91; 34: 409.61; 35: 406.45; 36: 412.74; 37: 416.45; 38: 414.88; 39: 421.73; 40: 411.35; 41: 414.58; 42: 459; 43: 459; 44: 5429.99; 45: 121834.97; 59: 0; 60: 121834.97; 74: 0; 75: 121834.97; 89: 0; 90: 121834.97 | 118640.25 | 3194.72 | 39824.15 | 3194.72 | 92743.81 | 25896.44 | 15000 | 5429.99 |  |  |  | -25896.44 | 25896.44 | 121834.97 | )
1752 | T03.06 | DLA-JRC | B Dawson | 1: 27275.32; 4: 108; 5: 0; 6: 0; 7: 0; 8: 0; 9: 0; 10: 0; 11: 0; 12: 0; 13: 0; 14: 108; 15: 27383.32; 16: 0; 17: 0; 18: 0; 19: 0; 20: 0; 24: -0.5; 25: 0; 29: -0.5; 30: 27382.82; 44: 0; 45: 27382.82; 59: 0; 60: 27382.82; 74: 0; 75: 27382.82; 89: 0; 90: 27382.82 | 27382.82 | 0 | -0.5 | 0 | 27383.32 | -0.5 | 0 | 0 |  |  |  | 0.5 | -0.5 | 27382.82 | )
1753 | T03.07 | DLA-Infraco | B Dawson | 141282.71 | 65000 | 37383 | 4783 | 22985 | 55000 | 55905 | 55000 | 49192 | 24944 | 21040 | 60000 | 44401 | 495633 | 636915.71 | 37700 | 1182.08 | 10319.82 | 11750 | 9658.49 | 20000 | 10000 | 10000 | 140142.47 | 30589.11 | 30000 | 10000 |  | 321341.97 | 958257.68 | 1923 | 1923 | 1923 | 1923 | 1923 | 1923 | 1923 | 1923 | 1923 | 1923 | 1923 | 1923 | 1924 | 25000 | 983257.68 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 760 | 10000 | 993257.68 | [13 empty] | 0 | 993257.68 | [13 empty] | 0 | 993257.68 | 992668.57 | 589.11 | 320752.86 | 589.11 | 802526.1 | 190142.47 | 40000 | 35000 |  |  |  | -190142.47 | 490142.47 | 1293257.68 | ) | Assumes an additional £300k over and above
1754 | T03.08 | DLA-Vehicles & Driver supply contract | B Dawson | 1: 142160.42; 2: 40000; 3: 21089; 4: 13010; 5: 18588; 6: 5000; 7: 16481; 8: 30000; 9: 14394; 10: 33543; 11: -13036; 12: 30000; 13: -16977; 14: 192092; 15: 334252.42; 16: 35855; 17: 18935.58; 18: 23882.18; 19: 6295; 20: 12765.92; 23: 3300; 24: 24433.13; 25: -9321.58; 26: 600; 27: 600; 28: 600; 29: 117945.23; 30: 452197.65; 44: 0; 45: 452197.65; 59: 0; 60: 452197.65; 74: 0; 75: 452197.65; 89: 0; 90: 452197.65 | 462119.23 | -9921.58 | 127866.81 | -9921.58 | 440986.1 | 21133.13 | 1800 | 0 |  |  |  | -21133.13 | 21133.13 | 452197.65 | ) | the £364k addition to FBC budget being reported
1755 | T03.09 | DLA-BAA | B Dawson | 1: 1009.5; 3: 95; 4: 151; 5: 54; 6: 2500; 7: 132; 8: 500; 9: -2480; 10: 500; 11: 0; 12: 1000; 13: -1000; 14: 1452; 15: 2461.5; 16: 7500; 17: -6500; 18: -64.75; 19: 200; 20: -38.75; 24: 14040.33; 25: 3708.64; 29: 18845.47; 30: 21306.97; 44: 0; 45: 21306.97; 59: 0; 60: 21306.97; 74: 0; 75: 21306.97; 89: 0; 90: 21306.97 | 17598.33 | 3708.64 | 15136.83 | 3708.64 | 3558 | 14040.33 | 0 | 0 |  |  |  | -14040.33 | 14040.33 | 21306.97 | ) | in the PMs report based upon burn rate.
1756 | T03.10 | DLA-Land & Property (3rd parties) | B Dawson | 1: 5328.44; 2: 500; 4: 1841; 5: 3441; 6: 2000; 7: 647; 8: 500; 9: 4719; 10: 1269; 11: 681; 12: 2000; 13: -444; 14: 17154; 15: 22482.44; 16: 5000; 17: -4161.37; 18: -306.5; 19: 0; 20: 1000; 21: 1000; 22: 1000; 23: 2000; 24: 7931.67; 25: -4996.83; 26: 1500; 27: 0; 28: 0; 29: 9966.97; 30: 32449.41; 44: 0; 45: 32449.41; 59: 0; 60: 32449.41; 74: 0; 75: 32449.41; 89: 0; 90: 32449.41 | 39446.24 | -6996.83 | 16963.8 | -6996.83 | 33014.57 | 6431.67 | 1500 | 0 |  |  |  | -6431.67 | 6431.67 | 32449.41 | ) | PM needs support from DLA in delivering forecast
1757 | T03.11 | DLA-Ticketing Agreements | B Dawson | 1: 0; 4: 0; 5: 0; 6: 0; 7: 0; 8: 0; 9: 0; 10: 0; 11: 0; 12: 0; 13: 0; 14: 0; 15: 0; 16: 0; 17: 0; 18: 0; 19: 0; 20: 0; 24: 0; 25: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | )
1758 | T03.12 | DLA-DPOF | B Dawson | 1: 0; 3: 623; 4: 4521; 5: 2214; 6: 10000; 7: 8021; 8: 10000; 9: -13721; 10: -7196; 11: 4414; 12: 2500; 13: 14677; 14: 36053; 15: 36053; 16: 10000; 17: 6646.75; 18: 9111.54; 19: 516.5; 20: 4836.78; 21: 2000; 24: 10169.18; 25: 5998.18; 26: 5000; 27: 5000; 28: 5000; 29: 64278.93; 30: 100331.93; 44: 0; 45: 100331.93; 59: 0; 60: 100331.93; 74: 0; 75: 100331.93; 89: 0; 90: 100331.93 | 99333.75 | 998.18 | 63280.75 | 998.18 | 69164.57 | 30169.18 | 15000 | 0 |  |  |  | -30169.18 | 30169.18 | 100331.93 | )
1759 | T03.13 | DLA-Tram Netwk/Roads Interface | B Dawson | 1: 9163.01; 2: 500; 3: 586; 4: 3331; 5: 252; 6: 2000; 7: 3062; 8: 1000; 9: -2199; 10: -2438; 11: 0; 12: 500; 13: -500; 14: 6094; 15: 15257.01; 16: 0; 17: 0; 18: 0; 19: 250; 20: -37.15; 24: -499.41; 25: 0; 29: -286.56; 30: 14970.45; 44: 0; 45: 14970.45; 59: 0; 60: 14970.45; 74: 0; 75: 14970.45; 89: 0; 90: 14970.45 | 14970.45 | 0 | -286.56 | 0 | 15469.86 | -499.41 | 0 | 0 |  |  |  | 499.41 | -499.41 | 14970.45 | )
1760 | T03.14 | DLA-EARL interface | B Dawson | 1: 2413.16; 2: 2200; 3: 2760; 4: 134; 5: 0; 6: 1000; 7: 3400; 8: 1000; 9: 4017; 10: 2637; 11: 1484; 12: 1000; 13: 2725; 14: 22357; 15: 24770.16; 16: 3000; 17: -3000; 18: 2000; 19: 1600; 20: -31.89; 24: 10879.12; 25: 0; 29: 14447.23; 30: 39217.39; 44: 0; 45: 39217.39; 59: 0; 60: 39217.39; 74: 0; 75: 39217.39; 89: 0; 90: 39217.39 | 39217.39 | 0 | 14447.23 | 0 | 28338.27 | 10879.12 | 0 | 0 |  |  |  | -10879.12 | 10879.12 | 39217.39 | )
1761 | T03.15 | DLA-Commissioning Svcs Agmt | B Dawson | 2: 500; 3: 845; 4: 776; 5: 364; 6: 4500; 7: 1942; 8: 1500; 9: -4801; 11: 0; 12: 1000; 13: -1000; 14: 5626; 15: 5626; 16: 0; 17: 0; 18: 0; 19: 0; 20: 0; 24: 1266.48; 25: 0; 29: 1266.48; 30: 6892.48; 44: 0; 45: 6892.48; 59: 0; 60: 6892.48; 74: 0; 75: 6892.48; 89: 0; 90: 6892.48 | 6892.48 | 0 | 1266.48 | 0 | 5626 | 1266.48 | 0 | 0 |  |  |  | -1266.48 | 1266.48 | 6892.48 | )
1762 | T03.16 | OCIP | B Dawson | 5: 701; 6: 2000; 7: 0; 8: 2000; 9: -201; 10: 4483; 11: 7095; 12: 4000; 13: -7685; 14: 12393; 15: 12393; 16: 0; 17: 1074.16; 18: 1725.63; 19: 350; 20: 1130; 21: 500; 24: -3837.32; 25: 7854.59; 26: 3000; 29: 11797.06; 30: 24190.06; 44: 0; 45: 24190.06; 59: 0; 60: 24190.06; 74: 0; 75: 24190.06; 89: 0; 90: 24190.06 | 13335.47 | 10854.59 | 942.47 | 10854.59 | 17172.79 | -3837.32 | 3000 | 0 |  |  |  | 3837.32 | -3837.32 | 24190.06 | )
1763 | T03.17 | Infraco Enabling | B Dawson | 9: 0; 13: 0; 14: 0; 15: 0; 16: 0; 17: 0; 18: 0; 19: 0; 20: 0; 24: 7901.63; 25: 0; 29: 7901.63; 30: 7901.63; 44: 0; 45: 7901.63; 59: 0; 60: 7901.63; 74: 0; 75: 7901.63; 89: 0; 90: 7901.63 | 7901.63 | 0 | 7901.63 | 0 | 0 | 7901.63 | 0 | 0 |  |  |  | -7901.63 | 7901.63 | 7901.63 | )
1764 | T03.18 | HR Issues | B Dawson | 13: 1218; 14: 1218; 15: 1218; 17: 0; 18: 0; 19: 0; 20: 1000; 24: -1301.56; 25: -217.75; 29: -519.31; 30: 698.69; 44: 0; 45: 698.69; 59: 0; 60: 698.69; 74: 0; 75: 698.69; 89: 0; 90: 698.69 | 916.44 | -217.75 | -301.56 | -217.75 | 2218 | -1301.56 | 0 | 0 |  |  |  | 1301.56 | -1301.56 | 698.69 | )
1765 | T03.19 | 0 | B Dawson | 14: 0; 15: 0; 17: 0; 18: 0; 19: 0; 20: 0; 24: 0; 25: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | )
1766 | T03.19.01 | Ingliston Park & Ride | B Dawson | 13: 997; 14: 997; 15: 997; 17: 0; 18: 0; 19: 0; 20: 0; 24: -997.5; 25: 0; 29: -997.5; 30: -0.5; 44: 0; 45: -0.5; 59: 0; 60: -0.5; 74: 0; 75: -0.5; 89: 0; 90: -0.5 | -0.5 | 0 | -997.5 | 0 | 997 | -997.5 | 0 | 0 |  |  |  | 997.5 | -997.5 | -0.5 | )
1767 | T03.19.02 | Mass Earthworks | B Dawson | 13: 1136; 14: 1136; 15: 1136; 17: 0; 18: 0; 19: 0; 20: 0; 24: 0.06; 25: 0; 29: 0.06; 30: 1136.06; 44: 0; 45: 1136.06; 59: 0; 60: 1136.06; 74: 0; 75: 1136.06; 89: 0; 90: 1136.06 | 1136.06 | 0 | 0.06 | 5.4567e-14 | 1136 | 0.06 | 0 | 0 |  |  |  | 0.06 | -0.06 | 1136.06 | )
1776 | T03.20 | D&W-General Advice | B Dawson | 458319 | 10020 | 38691 | 19737 | 13146 | 15000 | 18300 | 8635 | 23080 | -7988 | 4000 | -615 | 21334 | 163340 | 621659 | 2800 | 2428 | 2000 | 3000 | 2500 | 1500 | 2700 | 1500 | 3375 | 500 | 3375 | 3375 | 3375 | 32428 | 654087 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 4077 | 41000.0769 | 695087.0769 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 40000 | 735087.0769 | [13 empty] | 0 | 735087.0769 | [13 empty] | 0 | 735087.0769 | 739962.0769 | -4875 | 37303 | -4875 | 739962.0769 | 0 | 10125 | 81000.0769 | [5 empty] | 735087.0769
1777 | T03.21 | D&W-TRO's | B Dawson |  | 9765 | 22653 | 885 | 5657 | 7000 | 9124 | 14888 | 29535 | -14377 | 14000 | 7568 | 29156 | 135854 | 135854 | 3070 | 33430 | 41564.429 | 36161.1712 | 7000 | 32000 | 16500 | 25000 | 32200 | 8000 | 42000 | 42000 | 41000 | 359925.6003 | 495779.6003 | 21277.1089 | 18477.1089 | 18477.1089 | 18477.1089 | 18477.1089 | 18477.1089 | 18477.1089 | 18477.1089 | 18477.1089 | 18477.1089 | 18477.1089 | 18477.1089 | 18477.1089 | 243002.4159 | 738782.0162 | 4861.5834 | 4861.5834 | 4861.5834 | 4861.5834 | 4861.5834 | 4861.5834 | 4861.5834 | 4861.5834 | 4861.5834 | 4861.5834 | 4861.5834 | 4861.5834 | 4861.5834 | 63200.5841 | 801982.6003 | [13 empty] | 0 | 801982.6003 | [13 empty] | 0 | 801982.6003 | 801982.6003 | 0 | 362725.6003 | -2800 | 801982.6003 | 0 | 125000 | 306203 | [5 empty] | 801982.6003
1778 | T03.22 | D&W-Property | B Dawson |  | 10270 | 18534 | 18970 | 18787 | 29000 | 20723 | 71785 | 66283 | 28864 | 49000 | 32052 | 40184 | 404452 | 404452 | 15800 | 15620 | 10000 | 15000 | 15000 | 20000 | 37000 | 30000 | 45000 | 16500 | 58950 | 58950 | 58950 | 396770 | 801222 | 10720.5385 | 10720.5385 | 10720.5385 | 10720.5385 | 10720.5385 | 10720.5385 | 10720.5385 | 10720.5385 | 10720.5385 | 10720.5385 | 10720.5385 | 10720.5385 | 10720.5385 | 139367 | 940589 | 4400 | 4400 | 4400 | 4400 | 4400 | 4400 | 4400 | 4400 | 4400 | 4400 | 4400 | 4400 | 4400 | 57200 | 997789 | [13 empty] | 0 | 997789 | [13 empty] | 0 | 997789 | 999439 | -1650 | 398420 | -1650 | 999439 | 0 | 176850 | 196567 | [5 empty] | 997789
1779 | T03.23 | D&W-Planning Monitoring | B Dawson |  | 7266 | 5838 | 906 | 5226 | 9000 | 13896 | 8488 | 16060 | -3134 | 11000 | 7282 | 11454 | 93282 | 93282 | 9600 | 2860 | 12000 | 6000 | 3000 | 2000 | 6100 | 10000 | 4475 | 5000 | 4475 | 4475 | 4475 | 74460 | 167742 | 5760 | 5760 | 5760 | 5760 | 5760 | 5760 | 5760 | 5760 | 5760 | 5760 | 5760 | 5760 | 5760 | 74880 | 242622 | 3840 | 3840 | 3840 | 3840 | 3840 | 3840 | 3840 | 3840 | 3840 | 3840 | 3840 | 3840 | 3840 | 49920 | 292542 | [13 empty] | 0 | 292542 | [13 empty] | 0 | 292542 | 286017 | 6525 | 67935 | 6525 | 286017 | 0 | 13425 | 124800 | [5 empty] | 292542
1780 | T03.24 | D&W-TDWG | B Dawson | 2: 11496; 3: 6814; 4: 4578; 5: 9430; 6: 11000; 7: 1038; 8: 3098; 9: 4772; 10: 6680; 11: 6000; 12: 5368; 13: 2196; 14: 72470; 15: 72470; 17: 8890; 18: 3500; 19: 1000; 20: 2000; 25: 0; 29: 15390; 30: 87860; 44: 0; 45: 87860; 59: 0; 60: 87860; 74: 0; 75: 87860; 89: 0; 90: 87860 | 87860 | 0 | 15390 | 0 | 87860 | 0 | 0 | 0 | [5 empty] | 87860
1781 | T03.25 | D&W -Public Realm | B Dawson | 3: 10296; 4: -10296; 5: 0; 6: 0; 7: 0; 8: 0; 11: 0; 12: 0; 13: 0; 14: 0; 15: 0; 25: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
1782 | T03.26 | D&W-Litigation | B Dawson | 3: 0; 4: 220; 5: 40; 6: 0; 7: 0; 8: 0; 11: 0; 12: 0; 13: -260; 14: 0; 15: 0; 25: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
1783 | T03.27 | D&W-Secondments | B Dawson | 2: 41465; 3: 41956; 4: 23531; 5: 30798; 6: 14400; 7: 0; 8: 0; 11: 0; 12: 0; 13: -27; 14: 152123; 15: 152123; 25: 0; 29: 0; 30: 152123; 44: 0; 45: 152123; 59: 0; 60: 152123; 74: 0; 75: 152123; 89: 0; 90: 152123 | 152123 | 0 | 0 | 0 | 152123 | 0 | 0 | 0 | [5 empty] | 152123
1792 | T03 | Total LEGALS |  | 1296312.76 | 205982 | 242955 | 150677 | 216997 | 176900 | 189736 | 213894 | 221754 | 84045 | 104284 | 161655 | 149522 | 2118401 | 3414713.76 | 134825 | 85269.87 | 119164.059 | 95028.5112 | 67716.6 | 81000 | 75300 | 85086 | 344156.83 | 74600.27 | 158900 | 134400 | 123400 | 1578847.1403 | 4993560.9003 | 43144.1005 | 40362.3305 | 40370.4805 | 40367.1805 | 40364.0205 | 40370.3105 | 40374.0205 | 40372.4505 | 40379.3005 | 40368.9205 | 40372.1505 | 40416.5705 | 41417.6474 | 528679.4829 | 5522240.3831 | 16948.5065 | 16948.5065 | 16948.5065 | 16948.5065 | 16948.5065 | 16948.5065 | 16948.5065 | 16948.5065 | 16948.5065 | 16948.5065 | 16948.5065 | 16948.5065 | 16938.5065 | 220320.5841 | 5742560.9672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5742560.9672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5742560.9672 | 5742560.6972 | 0.27 | 1581646.8703 | -2799.73 | 5378253.8672 | 364306.83 | 416700 | 749000.0669 | [5 empty] | 6042560.9672
1793 | 0 | 0
1794 | T04.01 | Design Services under SDS | D Sharp | 1: 3110000; 2: 305000; 3: 1214000; 4: 1784000; 5: 779659; 6: 713873; 7: 930275; 8: 861209; 9: 913968; 10: 825000; 11: 850000; 12: 1559832; 13: -2180864.75; 14: 8555951.25; 15: 11665951.25; 29: 0; 30: 11665951.25; 44: 0; 45: 11665951.25; 59: 0; 60: 11665951.25; 74: 0; 75: 11665951.25; 89: 0; 90: 11665951.25 | 11665951.25 | 0 | 0 | 0 | 11665951.25 | 0 | 0 | 0 | [5 empty] | 11665951.25
1795 | T04.01.01 | Overall Value Main Works ( Unallocated ) | D Sharp | [13 empty] | 0 | 0 | 393551 | 393551 | 380997 | 258554 | 135000 | -362500 | -679385 | 194459 | 89250 | 89250 | 173000 | 173000 | 1948000 | 3186727 | 3186727 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 24000 | 300000 | 3486727 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 24000 | 300000 | 3786727 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 24000 | 300000 | 4086727 | [13 empty] | 0 | 4086727 | 4086727 | 0 | 3186727 | 0 | 4086727 | 0 | 2294000 | 900000 | [5 empty] | 4086727
1796 | T04.01.02 | Section 1 Newhaven Road to Haymarket | D Sharp | 13: 1252075.1604; 14: 1252075.1604; 15: 1252075.1604; 16: 277184.6522; 17: 395860.2963; 18: 380584.3158; 19: 333729.7147; 20: -1048668.7944; 21: 117668.8251; 22: 465253.9596; 23: 123170.1509; 24: -63684.2757; 25: 318991.8727; 26: 46488.1541; 27: 12131.0656; 28: 18005.0553; 29: 1376714.9923; 30: 2628790.1526; 31: 280898.01; 44: 280898.01; 45: 2909688.1626; 59: 0; 60: 2909688.1626; 74: 0; 75: 2909688.1626; 89: 0; 90: 2909688.1626 | 2909688.17 | -0.0073968 | 1246290.2742 | 130424.7181 | 2909689.5364 | -1.3663 | 76624.2751 | 280898.01 | [5 empty] | 2909688.1626
1797 | T04.01.03 | Section 2 Haymarket Corridor | D Sharp | 13: 175977.52; 14: 175977.52; 15: 175977.52; 16: 26293.3439; 17: 34464.2022; 18: 3286.9085; 19: 1401.7698; 20: -3310.1244; 21: -27935.3059; 22: 30912; 23: 0; 24: -2831.6369; 25: -1543.6953; 26: 4875.1005; 27: 1455.8257; 28: 747.0684; 29: 67815.4565; 30: 243792.9765; 44: 0; 45: 243792.9765; 59: 0; 60: 243792.9765; 74: 0; 75: 243792.9765; 89: 0; 90: 243792.9765 | 240974.7016 | 2818.2749 | 64997.1816 | 2818.2749 | 242474.449 | -1499.7474 | 7077.9947 | 0 | [5 empty] | 243792.9765
1798 | T04.01.03 | Section 3 Haymarket to Granton Sq | D Sharp | 13: 907113.5614; 14: 907113.5614; 15: 907113.5614; 16: 772065.4714; 17: 244489.5581; 18: 137448.0914; 19: 81396.1404; 20: -7952.927; 21: -4682.3256; 22: -10607.3502; 23: -39138.9974; 24: -119949.67; 25: 159959.4647; 26: 42921.8501; 27: 9203; 28: 0; 29: 1265152.3058; 30: 2172265.8672; 44: 0; 45: 2172265.8672; 59: 0; 60: 2172265.8672; 74: 0; 75: 2172265.8672; 89: 0; 90: 2172265.8672 | 2172265.9201 | -0.052885 | 1265152.3587 | -0.052885 | 2173263.2232 | -997.3032 | 52124.8501 | 0 | [5 empty] | 2172265.8672
1799 | T04.01.04 | Section 3 1B deduction | D Sharp | 13: -1000000; 14: -1000000; 15: -1000000; 16: -354446; 17: -253486; 18: -191799; 19: -42171; 20: -16853; 29: -858755; 30: -1858755; 44: 0; 45: -1858755; 59: 0; 60: -1858755; 74: 0; 75: -1858755; 89: 0; 90: -1858755 | -1858755 | 0 | -858755 | 0 | -1858755 | 0 | 0 | 0 | [5 empty] | -1858755
1800 | T04.01.05 | Section 4 Granton Sq to Newhaven Rd | D Sharp | 14: 0; 15: 0; 16: 0; 17: 0; 18: 0; 19: 0; 20: 0; 21: 0; 22: 0; 23: 0; 24: 0; 25: 0; 26: 0; 27: 0; 28: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
1801 | T04.01.06 | Section 5 Roseburn Junction to Gogar | D Sharp | 13: 628551.6837; 14: 628551.6837; 15: 628551.6837; 16: 299507.205; 17: 193351.8763; 18: 202156.5343; 19: 75318.3259; 20: -206598.7164; 21: 299.4414; 22: 80699.9635; 23: 13804.4925; 24: -79999.3095; 25: 140489.358; 26: 56856.0333; 27: 42312.3793; 28: 6857.9098; 29: 825055.4933; 30: 1453607.1771; 31: 1237.173; 44: 1237.173; 45: 1454844.3501; 59: 0; 60: 1454844.3501; 74: 0; 75: 1454844.3501; 89: 0; 90: 1454844.3501 | 1454844.3501 | 0 | 824490.2211 | 565.2722 | 1454844.3501 | 0 | 106026.3224 | 1237.173 | [5 empty] | 1454844.3501
1802 | T04.01.07 | Section 6 Gogar Depot | D Sharp | 13: 94842.259; 14: 94842.259; 15: 94842.259; 16: 40323.1094; 17: 53412.6166; 18: 26288.8118; 19: 44847.2046; 20: 4267.2644; 21: 8969.3495; 22: 17745; 23: 0; 24: -9530.7; 25: 19276.8335; 26: 20233.0793; 27: 7219; 28: 887.6154; 29: 233939.1845; 30: 328781.4435; 31: 1684.1933; 44: 1684.1933; 45: 330465.6368; 59: 0; 60: 330465.6368; 74: 0; 75: 330465.6368; 89: 0; 90: 330465.6368 | 333465.5937 | -2999.9568 | 235937.5261 | -1998.3416 | 331417.5614 | 2048.0323 | 28339.6948 | 1684.1933 | [5 empty] | 330465.6368
1803 | T04.01.08 | Section 7 Gogar to Edinburgh Airport | D Sharp | 13: 224954.2006; 14: 224954.2006; 15: 224954.2006; 16: 137615.2978; 17: 46400.6534; 18: 54665.7698; 19: 8845.1246; 20: -48894.0475; 21: 28031.1228; 22: -8577.488; 23: -17065.1438; 24: -63273.8236; 25: -22147.7624; 26: 24365.1661; 27: 45978.7106; 28: 32309.3642; 29: 218252.944; 30: 443207.1446; 31: 42373; 44: 42373; 45: 485580.1446; 59: 0; 60: 485580.1446; 74: 0; 75: 485580.1446; 89: 0; 90: 485580.1446 | 485398.2737 | 181.8709 | 245685.0731 | -27432.1291 | 484948.1215 | 450.1522 | 102653.2409 | 42373 | [5 empty] | 485580.1446
1804 | T04.01.09 | Section 8 Ingliston West / Newbridge | D Sharp | 14: 0; 15: 0; 16: 0; 17: 0; 18: 0; 19: 0; 20: 0; 21: 0; 22: 0; 23: 0; 24: 0; 25: 0; 26: 0; 27: 0; 28: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
1805 | T04.01.10 | MUDFA / Utilities | D Sharp | 13: 348021.3636; 14: 348021.3636; 15: 348021.3636; 16: 68110.4591; 17: 36716.3996; 18: 25116.5767; 19: 37321.1992; 20: 24207.5764; 21: 13131.6601; 22: 0; 23: 0; 24: 0; 25: 0; 26: 0; 27: 0; 29: 204603.8711; 30: 552625.2348; 44: 0; 45: 552625.2348; 59: 0; 60: 552625.2348; 74: 0; 75: 552625.2348; 89: 0; 90: 552625.2348 | 552625.2348 | 0 | 204603.8711 | 0 | 552625.2348 | 0 | 0 | 0 | [5 empty] | 552625.2348
1806 | T04.02 | Site Investigation under SDS | D Sharp | 1: 190000; 2: 145000; 3: 210000; 4: 90000; 5: 105000; 6: 200000; 7: 210000; 8: 200000; 9: 40000; 10: 25000; 14: 1225000; 15: 1415000; 29: 0; 30: 1415000; 44: 0; 45: 1415000; 59: 0; 60: 1415000; 71: 75000; 72: 75000; 73: 75000; 74: 225000; 75: 1640000; 89: 0; 90: 1640000 | 1640000 | 0 | 0 | 0 | 1640000 | 0 | 0 | 225000 | [5 empty] | 1640000
1815 | T04 | Total SDS |  | 3300000 | 450000 | 1424000 | 1874000 | 884659 | 913873 | 1140275 | 1061209 | 953968 | 850000 | 850000 | 1559832 | 450670.9987 | 12412486.9987 | 15712486.9987 | 1660204.5388 | 1144760.6024 | 1018745.0083 | 799242.479 | -1168802.7687 | -227017.2327 | -103958.915 | 275229.5022 | -250019.4157 | 704276.0711 | 368739.3836 | 291299.9812 | 2006807.0132 | 6519506.2476 | 22231993.2463 | 349192.3764 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 24000 | 626192.3764 | 22858185.6227 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 24000 | 300000 | 23158185.6227 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 23000 | 98000 | 98000 | 99000 | 525000 | 23683185.6227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23683185.6227 | 23683185.494 | 0.1287 | 6415128.5059 | 104377.7417 | 23683185.7264 | -0.23238 | 2666846.378 | 1451192.3764 | [5 empty] | 23683185.6227 |  | Phase 1a only
1816 | 0 | 0
1817 | T05.01 | Integrated Transport Model | A Sim | 1: 365000; 2: 55000; 3: 42000; 4: 14614; 5: 86000; 6: 55000; 7: 140000; 8: 180000; 9: 8000; 10: 134156; 11: 97000; 12: 105000; 13: 29000; 14: 945770; 15: 1310770; 16: 55000; 17: 15000; 18: 47000; 19: 44000; 20: 58000; 21: 28000; 22: 27000; 23: 29439.315; 24: 35000; 25: 35000; 26: 35000; 27: 21038.8425; 28: 21038.8425; 29: 450517; 30: 1761287; 31: 4000; 32: 4000; 33: 4326; 34: 4157; 35: 35000; 36: 35000; 38: 25000; 44: 111483; 45: 1872770; 51: 15000; 52: 15000; 59: 30000; 60: 1902770; 66: 15000; 67: 15000; 74: 30000; 75: 1932770; 81: 15000; 82: 15000; 88: 120000; 89: 150000; 90: 2082770 | 2082770 | 0 | 450517 | 0 | 2082770 | 0 | 77077.685 | 321483 | [5 empty] | 2082770
1818 | T05.02 | Surveys (MM) | A Sim | 1: 147195.78; 2: 3000; 3: 10000; 4: 10000; 13: -4607; 14: 18393; 15: 165588.78; 29: 0; 30: 165588.78; 44: 0; 45: 165588.78; 59: 0; 60: 165588.78; 74: 0; 75: 165588.78; 89: 0; 90: 165588.78 | 165588.78 | 0 | 0 | 0 | 165588.78 | 0 | 0 | 0 | [5 empty] | 165588.78
1819 | T05.03 | Consultancy (Halcrow) | A Sim | 1: 9916.21; 14: 0; 15: 9916.21; 29: 0; 30: 9916.21; 44: 0; 45: 9916.21; 59: 0; 60: 9916.21; 74: 0; 75: 9916.21; 89: 0; 90: 9916.21 | 9916.21 | 0 | 0 | 0 | 9916.21 | 0 | 0 | 0 | [5 empty] | 9916.21
1827 | T05 | Total JRC |  | 522111.99 | 58000 | 52000 | 24614 | 86000 | 55000 | 140000 | 180000 | 8000 | 134156 | 97000 | 105000 | 24393 | 964163 | 1486274.99 | 55000 | 15000 | 47000 | 44000 | 58000 | 28000 | 27000 | 29439.315 | 35000 | 35000 | 35000 | 21038.8425 | 21038.8425 | 450517 | 1936791.99 | 4000 | 4000 | 4326 | 4157 | 35000 | 35000 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 111483 | 2048274.99 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 2078274.99 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 2108274.99 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 120000 | 150000 | 2258274.99 | 2258274.99 | 0 | 450517 | 0 | 2258274.99 | 0 | 77077.685 | 321483 | [5 empty] | 2258274.99
1828 | 0 | 0
1829 | T06.01 | Technical Services | S Clark | 1233000 | 280000 | 190000 | 240000 | 354000 | 191000 | 464000 | 467000 | 345000 | 401000 | 320000 | 330000 | 478261 | 4060261 | 5293261 | 214662.53 | 193947.47 | 216074 | 557000 | 164781 | 243637.7003 | 224243 | 219963 | 156685 | 193940.74 | 217978.74 | 199878.74 | 143791.24 | 2946583.1603 | 8239844.1603 | 58736 | 55943 | 27720 | 27720 | 27720 | 27720 | 31390 | 15264 | 16264 | 16264 | 16264 | 16264 | 16264 | 353533 | 8593377.1603 | 17264 | 17264 | 17264 | 17264 | 17264 | 17264 | 10494 | 10494 | 10494 | 10494 | 10494 | 10494 | 10494 | 177042 | 8770419.1603 | 10494 | 10494 | 10494 | 10494 | 10494 | 10494 | 11770 | 11770 | 11770 | 11770 | 11770 | 11770 | 11770 | 145354 | 8915773.1603 | 11770 | 11770 | 11770 | 11770 | 11770 | 11770 | [7 empty] | 70620 | 8986393.1603 | 8956284.7003 | 30108.46 | 2922490.7003 | 24092.46 | 8956284.7003 | 0 | 561648.72 | 746549 | [5 empty] | 8986393.1603 |  | Review by PM. We must have a plusible outturn profile for TSS and it must live within the
1830 | T06.02 | Land agreement/negotiations | S Clark | 1: 113000; 2: 0; 14: 0; 15: 113000; 29: 0; 30: 113000; 44: 0; 45: 113000; 59: 0; 60: 113000; 74: 0; 75: 113000; 89: 0; 90: 113000 | 113000 | 0 | 0 | 0 | 113000 | 0 | 0 | 0 | [5 empty] | 113000 |  | £747k budget available for 0809 onwards. Outturn for 0708 to be checked
1831 | T06.03 | TSS Second to CEC-Approvals support | D Fraser | 4: 3002; 5: 15539; 6: 16929; 7: 15984; 8: 18569; 9: 17216; 10: 4058; 11: 1084; 14: 92381; 15: 92381; 29: 0; 30: 92381; 44: 0; 45: 92381; 59: 0; 60: 92381; 74: 0; 75: 92381; 89: 0; 90: 92381 | 92381 | 0 | 0 | 0 | 92381 | 0 | 0 | 0 | [5 empty] | 92381
1832 | T06.04 | CEC | D Fraser | 3: 40000; 4: -3002; 5: 24461; 6: 33071; 7: 34016; 8: -98569; 9: 22784; 10: 5942; 11: 58916; 12: 85000; 13: -3000; 14: 199619; 15: 199619; 16: 120000; 17: 0; 18: 30554; 19: 66374; 20: 58240; 21: 46975; 22: 81553; 23: 36084; 24: 76186; 25: 9193; 26: 76186; 27: 76186; 28: 76190; 29: 753721; 30: 953340; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 44: 0; 45: 953340; 59: 0; 60: 953340; 74: 0; 75: 953340; 89: 0; 90: 953340 | 1020333 | -66993 | 820714 | -66993 | 1020333 | 0 | 228562 | 0 |  |  |  |  | 633708 | 1587048 |  | Anticipated we are fighting a losing battle with CEC requirement for 0809
1844 | T06 | Total TSS |  | 1346000 | 280000 | 230000 | 240000 | 394000 | 241000 | 514000 | 387000 | 385000 | 411000 | 380000 | 415000 | 475261 | 4352261 | 5698261 | 334662.53 | 193947.47 | 246628 | 623374 | 223021 | 290612.7003 | 305796 | 256047 | 232871 | 203133.74 | 294164.74 | 276064.74 | 219981.24 | 3700304.1603 | 9398565.1603 | 58736 | 55943 | 27720 | 27720 | 27720 | 27720 | 31390 | 15264 | 16264 | 16264 | 16264 | 16264 | 16264 | 353533 | 9752098.1603 | 17264 | 17264 | 17264 | 17264 | 17264 | 17264 | 10494 | 10494 | 10494 | 10494 | 10494 | 10494 | 10494 | 177042 | 9929140.1603 | 10494 | 10494 | 10494 | 10494 | 10494 | 10494 | 11770 | 11770 | 11770 | 11770 | 11770 | 11770 | 11770 | 145354 | 10074494.1603 | 11770 | 11770 | 11770 | 11770 | 11770 | 11770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70620 | 10145114.1603 | 10181998.7003 | -36884.54 | 3743204.7003 | -42900.54 | 10181998.7003 | 0 | 790210.72 | 746549 | [5 empty] | 10778822.1603
1845 | 0 | 0
1846 | T07.01 | Consultancies | Closed | 1: 20521.46; 13: 10583; 14: 10583; 15: 31104.46; 29: 0; 30: 31104.46; 44: 0; 45: 31104.46; 59: 0; 60: 31104.46; 74: 0; 75: 31104.46; 89: 0; 90: 31104.46 | 31104.46 | 0 | 0 | 0 | 31104.46 | 0 | 0 | 0 | [5 empty] | 31104.46
1856 | T07 | Total UTILITIES |  | 20521.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10583 | 10583 | 31104.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31104.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31104.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31104.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31104.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31104.46 | 31104.46 | 0 | 0 | 0 | 31104.46 | 0 | 0 | 0 | [5 empty] | 31104.46
1857 | 0 | 0
1858 | T08.01 | Tech. Advisors-Parl.Support | Closed | 1: 268642.76; 14: 0; 15: 268642.76; 29: 0; 30: 268642.76; 44: 0; 45: 268642.76; 59: 0; 60: 268642.76; 74: 0; 75: 268642.76; 89: 0; 90: 268642.76 | 268642.76 | 0 | 0 | 0 | 268642.76 | 0 | 0 | 0 | [5 empty] | 268642.76
1859 | T08.02 | Tech. Advisors-Parl.Support-PM | Closed | 1: 29382.99; 14: 0; 15: 29382.99; 29: 0; 30: 29382.99; 44: 0; 45: 29382.99; 59: 0; 60: 29382.99; 74: 0; 75: 29382.99; 89: 0; 90: 29382.99 | 29382.99 | 0 | 0 | 0 | 29382.99 | 0 | 0 | 0 | [5 empty] | 29382.99
1868 | T08 | Total DESIGN SUPPORT |  | 298025.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298025.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298025.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298025.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298025.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298025.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298025.75 | 298025.75 | 0 | 0 | 0 | 298025.75 | 0 | 0 | 0 | [5 empty] | 298025.75
1869 | 0 | 0
1870 | T09.01 | Network Rail Legal Costs | T Glazebrook | 14: 0; 29: 0; 44: 0; 59: 0; 74: 0; 89: 0 |  | 0 |  | 0 |  |  | 0 | 0 | [5 empty] | 0
1871 | T09.01.01 | Network Rail (PM) | T Glazebrook | 2: 0; 3: 0; 4: 22519; 5: 30000; 6: 15000; 7: 0; 8: 20000; 9: 20000; 10: 5756; 11: 15000; 12: 10000; 13: 10000; 14: 148275; 15: 148275; 16: 33626.13; 18: 38878.4; 19: 10968.18; 21: 14921; 24: 6342; 26: 18137; 27: 18284; 28: 11744; 29: 152900.71; 30: 301175.71; 31: 7988; 44: 7988; 45: 309163.71; 59: 0; 60: 309163.71; 74: 0; 75: 309163.71; 89: 0; 90: 309163.71 | 309163.71 | 0 | 160888.71 | -7988 | 309163.71 | 0 | 48165 | 7988 | [5 empty] | 309163.71
1872 | T09.01.02 | Network Rail (Legal) | T Glazebrook | 8: 10000; 9: 0; 10: -10000; 13: 7500; 14: 7500; 15: 7500; 29: 0; 30: 7500; 44: 0; 45: 7500; 59: 0; 60: 7500; 74: 0; 75: 7500; 89: 0; 90: 7500 | 7500 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | [5 empty] | 7500
1882 | T09 | Total 3RD PARTY NEGOTIATIONS |  | 0 | 0 | 0 | 22519 | 30000 | 15000 | 0 | 30000 | 20000 | -4244 | 15000 | 10000 | 17500 | 155775 | 155775 | 33626.13 | 0 | 38878.4 | 10968.18 | 0 | 14921 | 0 | 0 | 6342 | 0 | 18137 | 18284 | 11744 | 152900.71 | 308675.71 | 7988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7988 | 316663.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316663.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316663.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316663.71 | 316663.71 | 0 | 160888.71 | -7988 | 316663.71 | 0 | 48165 | 7988 | [5 empty] | 316663.71
1883 | 0 | 0
1884 | T10.01 | D&W (10.01 &11.01) | A Sim | 1: 25843; 14: 0; 15: 25843; 29: 0; 30: 25843; 44: 0; 45: 25843; 59: 0; 60: 25843; 74: 0; 75: 25843; 89: 0; 90: 25843 | 25843 | 0 | 0 | 0 | 25843 | 0 | 0 | 0 | [5 empty] | 25843
1885 | T10.02 | Advisors (Colliers / DV) | A Sim | 35624 | 2085 | 5000 | -1260 | 265 | 6000 | 6000 | -6500 | 5000 | -3125 | 2000 | 3330 | 4100 | 22895 | 58519 | 9149 | 4101 | 8750 | 4500 | 6650 | 10150 | 9490 | 6470 | 6650 | 8850 | 4000 | 4000 | 1210 | 83970 | 142489 | 4205.93 | 4404.23 | 4492.94 | 4459.74 | 4426.71 | 4495.22 | 3479.46 | 1804.51 | 1834.3 | 1789.42 | 1805.55 | 1999 | 1999 | 41196.01 | 183685.01 | 1603.33 | 1748.15 | 1779.18 | 1769.53 | 1754.97 | 1780.04 | 1799.03 | 787.81 | 821.58 | 774.26 | 790.19 | 975.15 | 1052.79 | 17436.01 | 201121.02 | [13 empty] | 0 | 201121.02 | [13 empty] | 0 | 201121.02 | 201061.02 | 60 | 83910 | 60 | 201061.02 | 0 | 9210 | 58632.02 | [5 empty] | 201121.02
1886 | T10.03 | Technical | A Sim | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
1887 | T10.04 | Advance Purchases 05/06 (Fees) | A Sim | 1: 60181; 14: 0; 15: 60181; 29: 0; 30: 60181; 44: 0; 45: 60181; 59: 0; 60: 60181; 74: 0; 75: 60181; 89: 0; 90: 60181 | 60181 | 0 | 0 | 0 | 60181 | 0 | 0 | 0 | [5 empty] | 60181
1888 | T10.05.01 | Advance Purchases (GVD) | A Sim | 14: 0; 15: 0; 16: 9076400; 17: -743923; 18: -1535149; 22: 1633944; 24: 1679546; 25: 1785000; 29: 11895818; 30: 11895818; 31: 1760000; 44: 1760000; 45: 13655818; 59: 0; 60: 13655818; 74: 0; 75: 13655818; 89: 0; 90: 13655818 | 11870818 | 1785000 | 10110818 | 1785000 | 11870818 | 0 | 0 | 1760000 | [5 empty] | 13655818
1889 | T10.05.02 | Advance Purchases (gifted / free issue) | A Sim | 14: 0; 15: 0; 16: 319935; 17: -27279; 18: 1785000; 19: 4512025; 20: -140163; 21: -473180; 25: -1785000; 28: 508989; 29: 4700327; 30: 4700327; 44: 0; 45: 4700327; 59: 0; 60: 4700327; 74: 0; 75: 4700327; 89: 0; 90: 4700327 | 6485327 | -1785000 | 6485327 | -1785000 | 6485327 | 0 | 508989 | 0 | [5 empty] | 4700327
1890 | T10.06.01 | Business Compo Primary payment | M Connelly | 14: 0; 15: 0; 19: 0; 21: 16000; 22: 88000; 23: 88000; 24: -74000; 25: -25000; 26: 20000; 27: 50000; 28: 50000; 29: 213000; 30: 213000; 31: 107769; 32: 107769; 33: 107769; 34: 107769; 35: 107769; 36: 107769; 37: 107769; 38: 107769; 39: 107769; 40: 107769; 41: 107769; 42: 107769; 43: 93772; 44: 1387000; 45: 1600000; 59: 0; 60: 1600000; 74: 0; 75: 1600000; 89: 0; 90: 1600000 | 1600000 | 0 | 470000 | -257000 | 1600000 | 0 | 120000 | 1387000 | [5 empty] | 1600000
1891 | T10.06.02 | Business Compo Enhanced payment | M Connelly | 14: 0; 15: 0; 19: 0; 29: 0; 30: 0; 42: 350000; 44: 350000; 45: 350000; 59: 0; 60: 350000; 74: 0; 75: 350000; 89: 0; 90: 350000 | 350000 | 0 | 0 | 0 | 350000 | 0 | 0 | 350000 | [5 empty] | 350000
1892 | T10.06.03 | Business Compo Admin | M Connelly | 14: 0; 15: 0; 19: 2000; 21: 2000; 22: 2000; 23: 2000; 24: 1230; 25: 1846; 26: 1846; 27: 1846; 28: 1846; 29: 16614; 30: 16614; 31: 1846; 32: 1846; 33: 1846; 34: 1846; 35: 1846; 36: 1846; 37: 1846; 38: 1846; 39: 1846; 40: 1846; 41: 1846; 42: 1846; 43: 1846; 44: 23998; 45: 40612; 46: 1846; 47: 1846; 48: 1846; 49: 1846; 50: 2004; 59: 9388; 60: 50000; 74: 0; 75: 50000; 89: 0; 90: 50000 | 50000 | 0 | 16614 | 0 | 50000 | 0 | 5538 | 33386 | [5 empty] | 50000
1900 | T10 | Total LAND & PROPERTY |  | 121648 | 2085 | 5000 | -1260 | 265 | 6000 | 6000 | -6500 | 5000 | -3125 | 2000 | 3330 | 4100 | 22895 | 144543 | 9405484 | -767101 | 258601 | 4518525 | -133513 | -445030 | 1733434 | 96470 | 1613426 | -14304 | 25846 | 55846 | 562045 | 16909729 | 17054272 | 1873820.93 | 114019.23 | 114107.94 | 114074.74 | 114041.71 | 114110.22 | 113094.46 | 111419.51 | 111449.3 | 111404.42 | 111420.55 | 461614 | 97617 | 3562194.01 | 20616466.01 | 3449.33 | 3594.15 | 3625.18 | 3615.53 | 3758.97 | 1780.04 | 1799.03 | 787.81 | 821.58 | 774.26 | 790.19 | 975.15 | 1052.79 | 26824.01 | 20643290.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20643290.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20643290.02 | 20643230.02 | 60 | 17166669 | -256940 | 20643230.02 | 0 | 643737 | 3589018.02 | [5 empty] | 20643290.02
1901 | 0 | 0
1902 | T11.01 | Legal | Closed | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | [5 empty] | 0
1903 | T11.02 | TRO's - Technnical | Closed | 1: 1312.95; 14: 0; 15: 1312.95; 29: 0; 30: 1312.95; 44: 0; 45: 1312.95; 59: 0; 60: 1312.95; 74: 0; 75: 1312.95; 89: 0; 90: 1312.95 | 1312.95 | 0 | 0 | 0 | 1312.95 | 0 | 0 | 0 | [5 empty] | 1312.95
1912 | T11 | Total TROs |  | 1312.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.95 | 1312.95 | 0 | 0 | 0 | 1312.95 | 0 | 0 | 0 | [5 empty] | 1312.95
1913 | 0 | 0
1914 | T12.01 | Fees / production Items - WS | C McLauchlan | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
1915 | T12.01.01 | PR fees | C McLauchlan | 1: 86876; 2: 18500; 3: 18500; 4: 18500; 5: 18500; 6: 15000; 7: 15000; 8: 15000; 9: 15000; 10: 15000; 11: 15000; 12: 15000; 13: 15000; 14: 194000; 15: 280876; 16: 41478.27; 17: 40235.83; 18: 16995; 19: 40764.7; 20: 15500; 23: -42353; 24: 7000; 25: 3000; 26: 3000; 27: 3000; 28: 3000; 29: 131620.8; 30: 412496.8; 44: 0; 45: 412496.8; 59: 0; 60: 412496.8; 74: 0; 75: 412496.8; 89: 0; 90: 412496.8 | 412496.8 | 0 | 131620.8 | 0 | 412496.8 | 0 | 9000 | 0 | [5 empty] | 412496.8 | )
1916 | T12.01.02 | PA fees | C McLauchlan | 2: 2000; 3: 2000; 4: 2000; 14: 6000; 15: 6000; 29: 0; 30: 6000; 44: 0; 45: 6000; 59: 0; 60: 6000; 74: 0; 75: 6000; 89: 0; 90: 6000 | 6000 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | [5 empty] | 6000 | )
1917 | T12.01.03 | Sundries | C McLauchlan | 2: 1850; 3: 1850; 4: 1850; 5: 1850; 7: 1500; 8: 2625; 9: 1500; 10: 1500; 11: 2943; 13: 3000; 14: 20468; 15: 20468; 29: 0; 30: 20468; 44: 0; 45: 20468; 59: 0; 60: 20468; 74: 0; 75: 20468; 89: 0; 90: 20468 | 20468 | 0 | 0 | 0 | 20468 | 0 | 0 | 0 | [5 empty] | 20468 | )
1918 | T12.01.04 | Production | C McLauchlan | 2: 4300; 3: 1164; 4: 11847; 5: 3095; 6: 60509; 7: 38550; 8: 19219; 9: 118088; 10: 7050; 12: 13550; 13: 41727; 14: 319099; 15: 319099; 29: 0; 30: 319099; 44: 0; 45: 319099; 59: 0; 60: 319099; 74: 0; 75: 319099; 89: 0; 90: 319099 | 319099 | 0 | 0 | 0 | 319099 | 0 | 0 | 0 | [5 empty] | 319099 | )
1919 | T12.01.05 | Outlook | C McLauchlan | 2: 2500; 14: 2500; 15: 2500; 29: 0; 30: 2500; 44: 0; 45: 2500; 59: 0; 60: 2500; 74: 0; 75: 2500; 89: 0; 90: 2500 | 2500 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | [5 empty] | 2500 | )
1920 | T12.01.06 | Branding / advertising | C McLauchlan | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | )
1921 | T12.02 | Fees / production Items - MH | C McLauchlan | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | )
1922 | T12.02.01 | PR fees | C McLauchlan |  |  |  |  | 11000 | 12538 | 12538 | 12538 | 12538 | 12538 | 11923 | 12538 | 12538 | 110689 | 110689 | 12595.9 | 12596 | 12596 |  |  |  |  | 75065 | 13000 | 7000 | 7000 | 7000 | 7000 | 153852.9 | 264541.9 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 130000 | 394541.9 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 130000 | 524541.9 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 130000 | 654541.9 | [13 empty] | 0 | 654541.9 | 654541.9 | 0 | 153852.9 | 0 | 654541.9 | 0 | 21000 | 390000 | [5 empty] | 654541.9 | )
1923 | T12.02.02 | PA fees | C McLauchlan | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | )
1924 | T12.02.03 | Sundries | C McLauchlan | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | )
1925 | T12.02.04 | Production | C McLauchlan | 7: 2000; 9: 4000; 10: 2000; 14: 8000; 15: 8000; 29: 0; 30: 8000; 44: 0; 45: 8000; 59: 0; 60: 8000; 74: 0; 75: 8000; 89: 0; 90: 8000 | 8000 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | [5 empty] | 8000 | )
1926 | T12.02.05 | Outlook | C McLauchlan |  |  |  |  | 2500 |  | 2500 |  | 2500 |  |  |  |  | 7500 | 7500 | [13 empty] | 0 | 7500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -45500 | -38000 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -45500 | -83500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -3500 | -45500 | -129000 | [13 empty] | 0 | -129000 | -129000 | 0 | 0 | 0 | -129000 | 0 | 0 | -136500 | [5 empty] | -129000 | )
1927 | T12.02.06 | Branding / advertising | C McLauchlan | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | )
1928 | T12.03 | Tram branding | C McLauchlan | 14: 0; 15: 0; 20: 12500; 21: 12500; 23: 4166.6667; 24: 4166.6667; 25: 4166.6667; 29: 37500; 30: 37500; 44: 0; 45: 37500; 59: 0; 60: 37500; 74: 0; 75: 37500; 89: 0; 90: 37500 | 37500 | 0 | 37500 | 0 | 37500 | 0 | 0 | 0 | [5 empty] | 37500 | )
1929 | T12.04 | PR Support | C McLauchlan | 14: 0; 15: 0; 21: 23000; 22: 9000; 23: -32000; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | )
1930 | T12.05 | Business development and marketing | C McLauchlan | 14: 0; 15: 0; 21: 6000; 22: 3000; 23: -9000; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | )
1931 | T12.06 | Media monitoring | C McLauchlan | [13 empty] | 0 | 0 | [5 empty] | 750 | 375 | 4915 | 375 | 375 | 375 | 375 | 375 | 7915 | 7915 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 4875 | 12790 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 4875 | 17665 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 4875 | 22540 | [13 empty] | 0 | 22540 | 22540 | 0 | 7915 | 0 | 22540 | 0 | 1125 | 14625 | [5 empty] | 22540 | ) | Refresh on scope/profile/esrtimating basis
1932 | T12.07 | Media training | C McLauchlan | [13 empty] | 0 | 0 | [5 empty] | 4000 | 0 | -4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 6500 | 6500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 6500 | 13000 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 6500 | 19500 | [13 empty] | 0 | 19500 | 19500 | 0 | 0 | 0 | 19500 | 0 | 0 | 19500 | [5 empty] | 19500 | ) | of all Comms/Stakeholder costs from 0809 = £1,092k
1933 | T12.08 | Promotional materials | C McLauchlan | [13 empty] | 0 | 0 | [5 empty] | 2000 | 1000 | -2580 | 600 | 600 | 600 | 600 | 600 | 3420 | 3420 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 24375 | 27795 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 24375 | 52170 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 24375 | 76545 | [13 empty] | 0 | 76545 | 76545 | 0 | 3420 | 0 | 76545 | 0 | 1800 | 73125 | [5 empty] | 76545 | )
1934 | T12.09 | Websites | C McLauchlan | [13 empty] | 0 | 0 | [5 empty] | 1000 | 500 | -1010 | 2000 | 500 | 500 | 500 | 500 | 4490 | 4490 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 26000 | 30490 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 26000 | 56490 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 26000 | 82490 | [13 empty] | 0 | 82490 | 82490 | 0 | 4490 | 0 | 82490 | 0 | 1500 | 78000 | [5 empty] | 82490 | )
1935 | T12.10 | Events | C McLauchlan | [13 empty] | 0 | 0 | [5 empty] | 2000 | 3000 | -5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 13000 | 13000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 13000 | 26000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 13000 | 39000 | [13 empty] | 0 | 39000 | 39000 | 0 | 0 | 0 | 39000 | 0 | 0 | 39000 | [5 empty] | 39000 | )
1936 | T12.11 | Advertising | C McLauchlan | [13 empty] | 0 | 0 | [5 empty] | 3000 | 1000 | -800 | 1500 | 1000 | 1000 | 1500 | 1000 | 9200 | 9200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 19500 | 28700 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 19500 | 48200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 19500 | 67700 | [13 empty] | 0 | 67700 | 67700 | 0 | 9200 | 0 | 67700 | 0 | 3500 | 58500 | [5 empty] | 67700 | )
1937 | T12.12 | Internal communications | C McLauchlan | [13 empty] | 0 | 0 | [5 empty] | 500 | 250 | 841 | 250 | 250 | 250 | 250 | 250 | 2841 | 2841 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 3250 | 6091 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 3250 | 9341 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 3250 | 12591 | [13 empty] | 0 | 12591 | 12591 | 0 | 2841 | 0 | 12591 | 0 | 750 | 9750 | [5 empty] | 12591 | )
1938 | T12.13 | S/H – Wider Community Consultations | M Connelly | [13 empty] | 0 | 0 | [6 empty] | 0 | 15145 | 15645 | -25830 | 11145 | 11645 | 11145 | 38895 | 38895 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 182000 | 220895 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 182000 | 402895 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 182000 | 584895 | [13 empty] | 0 | 584895 | 624370 | -39475 | 78370 | -39475 | 624370 | 0 | 33935 | 546000 | [5 empty] | 584895 | )
1939 | T12.14 | S/H – Events | M Connelly | 14: 0; 15: 0; 25: 4082; 29: 4082; 30: 4082; 44: 0; 45: 4082; 59: 0; 60: 4082; 74: 0; 75: 4082; 89: 0; 90: 4082 | 0 | 4082 | 0 | 4082 | 0 | 0 | 0 | 0 | [5 empty] | 4082 | )
1940 | T12.15 | S/H – Open for Business | M Connelly | 14: 0; 15: 0; 25: 19745; 29: 19745; 30: 19745; 44: 0; 45: 19745; 59: 0; 60: 19745; 74: 0; 75: 19745; 89: 0; 90: 19745 | 0 | 19745 | 0 | 19745 | 0 | 0 | 0 | 0 | [5 empty] | 19745 | )
1941 | T12.16 | S/H – Sundry Expenses | M Connelly | 14: 0; 15: 0; 25: 15648; 29: 15648; 30: 15648; 44: 0; 45: 15648; 59: 0; 60: 15648; 74: 0; 75: 15648; 89: 0; 90: 15648 | 0 | 15648 | 0 | 15648 | 0 | 0 | 0 | 0 | [5 empty] | 15648 | )
1944 | T12 | Total COMMS / MARKETING |  | 86876 | 29150 | 23514 | 34197 | 36945 | 88047 | 72088 | 49382 | 153626 | 38088 | 29866 | 41088 | 72265 | 668256 | 755132 | 54074.17 | 52831.83 | 29591 | 40764.7 | 28000 | 54750 | 18125 | 3389.6667 | 44536.6667 | 30536.6667 | 23870 | 24870 | 23870 | 429209.7 | 1184341.7 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 364000 | 1548341.7 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 364000 | 1912341.7 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 364000 | 2276341.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2276341.7 | 2276341.7 | 0 | 429209.7 | 0 | 2276341.7 | 0 | 72610 | 1092000 | [5 empty] | 2276341.7 | )
1945 | 0 | 0
1946 | T13.01 | Non Executive Board | A Richards | 1: 19947; 13: 14405; 14: 14405; 15: 34352; 29: 0; 30: 34352; 44: 0; 45: 34352; 59: 0; 60: 34352; 74: 0; 75: 34352; 89: 0; 90: 34352 | 34352 | 0 | 0 | 0 | 34352 | 0 | 0 | 0 | [5 empty] | 34352
1947 | T13.02 | Search Fees | A Richards | 1: 5000; 14: 0; 15: 5000; 29: 0; 30: 5000; 44: 0; 45: 5000; 59: 0; 60: 5000; 74: 0; 75: 5000; 89: 0; 90: 5000 | 5000 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | [5 empty] | 5000
1948 | T13.03 | Overheads | A Richards |  | 65000 | 65000 | 7875 | 65000 | 65000 | 52137 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 620012 | 620012 | 25083 | 48000 | 51000 | 73000 | 53000 | 93000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 560083 | 1180095 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 403000 | 1583095 | 44000 | 39000 | 49000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 522000 | 2105095 | 45000 | 40000 | 50000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 25000 | 59562 | 59562 | 59562 | 578686 | 2683781 | [13 empty] | 0 | 2683781 | 2683781 | 0 | 560083 | 0 | 2683781 | 0 | 93000 | 1503686 | [5 empty] | 2683781
1956 | T13 | Total TEL |  | 24947 | 65000 | 65000 | 7875 | 65000 | 65000 | 52137 | 50000 | 50000 | 50000 | 50000 | 50000 | 64405 | 634417 | 659364 | 25083 | 48000 | 51000 | 73000 | 53000 | 93000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 560083 | 1219447 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 31000 | 403000 | 1622447 | 44000 | 39000 | 49000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 522000 | 2144447 | 45000 | 40000 | 50000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 25000 | 59562 | 59562 | 59562 | 578686 | 2723133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2723133 | 2723133 | 0 | 560083 | 0 | 2723133 | 0 | 93000 | 1503686 | [5 empty] | 2723133
1957 | 0 | 0
1958 | T14.01 | Operator Consultancy | Closed | 1: 0; 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [5 empty] | 0
1959 | T14.02 | Financial Consultancy | G Bissett | 1: 53727; 2: 30000; 3: 20000; 4: 7196; 13: 13000; 14: 70196; 15: 123923; 25: 13500; 26: 20000; 29: 33500; 30: 157423; 44: 0; 45: 157423; 59: 0; 60: 157423; 74: 0; 75: 157423; 89: 0; 90: 157423 | 123923 | 33500 | 0 | 33500 | 123923 | 0 | 20000 | 0 | [5 empty] | 157423
1960 | T14.03 | WP1 modelling (FM) | Closed | 1: 39646.03; 13: -22462; 14: -22462; 15: 17184.03; 29: 0; 30: 17184.03; 44: 0; 45: 17184.03; 59: 0; 60: 17184.03; 74: 0; 75: 17184.03; 89: 0; 90: 17184.03 | 17184.03 | 0 | 0 | 0 | 17184.03 | 0 | 0 | 0 | [5 empty] | 17184.03
1961 | T14.04 | WP2 modelling (MVA) | Closed | 1: 10496.61; 4: 651.78; 14: 651.78; 15: 11148.39; 29: 0; 30: 11148.39; 44: 0; 45: 11148.39; 59: 0; 60: 11148.39; 74: 0; 75: 11148.39; 89: 0; 90: 11148.39 | 11148.39 | 0 | 0 | 0 | 11148.39 | 0 | 0 | 0 | [5 empty] | 11148.39
1968 | T14 | Total SERVICE INTEGRATION |  | 103869.64 | 30000 | 20000 | 7847.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9462 | 48385.78 | 152255.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13500 | 20000 | 0 | 0 | 33500 | 185755.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185755.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185755.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185755.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185755.42 | 152255.42 | 33500 | 0 | 33500 | 152255.42 | 0 | 20000 | 0 | [5 empty] | 185755.42
1969 | 0 | 0
1970 | T15.01 | INFRACO (PUK) | S McGarrity | 1: 73279.05; 2: 6000; 3: 6000; 4: 14229; 5: 6000; 6: 6000; 7: 6000; 8: 6000; 9: 6000; 10: 6000; 11: 6000; 12: 6000; 13: 10229; 14: 84458; 15: 157737.05; 16: 8020; 17: 5101; 18: 6222; 19: 8248.46; 20: 7268.61; 21: 5732.18; 22: 7691.34; 23: 26881; 24: 8410; 25: 10000; 29: 93574.59; 30: 251311.64; 44: 0; 45: 251311.64; 59: 0; 60: 251311.64; 74: 0; 75: 251311.64; 89: 0; 90: 251311.64 | 241311.64 | 10000 | 83574.59 | 10000 | 232902 | 8409.64 | 0 | 0 |  |  |  |  | 15000 | 266311.64 |  | Additional month fees to end P11 0708
1980 | T15 | Total PUK |  | 73279.05 | 6000 | 6000 | 14229 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 10229 | 84458 | 157737.05 | 8020 | 5101 | 6222 | 8248.46 | 7268.61 | 5732.18 | 7691.34 | 26881 | 8410 | 10000 | 0 | 0 | 0 | 93574.59 | 251311.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251311.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251311.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251311.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251311.64 | 241311.64 | 10000 | 83574.59 | 10000 | 232902 | 8409.64 | 0 | 0 | [5 empty] | 266311.64
1981 | 0 | 0
1982 | T16.01 | Financial advisor 05/06 | Closed | 1: 244340; 2: 0; 3: 20000; 4: 18246; 13: 2700; 14: 40946; 15: 285286; 29: 0; 30: 285286; 44: 0; 45: 285286; 59: 0; 60: 285286; 74: 0; 75: 285286; 89: 0; 90: 285286 | 285286 | 0 | 0 | 0 | 285286 | 0 | 0 | 0 | [5 empty] | 285286
1992 | T16 | Total FINANCIAL ADVISOR |  | 244340 | 0 | 20000 | 18246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2700 | 40946 | 285286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285286 | 285286 | 0 | 0 | 0 | 285286 |  | 0 | 0 | [5 empty] | 285286
1993 | 0 | 0
1994 | T17.01 | Insurance consultancy | T Kinloch | 36123 | 1700 | 1700 | 5757 | 3000 | 8540 | 4000 | 4500 | 8281 | 6000 | 6000 | 6000 | 8813 | 64291 | 100414 | 2500 | 3857.53 | 5000 | 6930 | 6090 | 3000 | 53676.43 | -33175 | 6635.0711 | 6635.0711 | 6635.0711 | 6635.0711 | 6635.07 | 81054.3144 | 181468.3144 | 4986.3014 | 4986.3014 | 4986.3014 | 4986.3014 | 4986.3014 | 4986.3014 | 4986.3014 | 4986.3014 | 4986.3014 | 4986.3014 | 4986.3014 | 4986.3014 | 5164.3836 | 65000 | 246468.3144 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4767.1233 | 60000 | 306468.3144 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4602.7397 | 4767.1233 | 60000 | 366468.3144 | [13 empty] | 0 | 366468.3144 | 366468.3155 | -0.00109 | 81054.3155 | -0.00109 | 366468.3155 | 0 | 19905.2122 | 185000 | [5 empty] | 366468.3144
1995 | T17.02 | OCIP | T Kinloch | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | -29000 | -10000 | -317724 | 11015.6992 | 21865.2535 | 78395.2356 | 78395.2356 | 128395.2356 | 361342.6596 | 361342.6596 | 81980.6234 | 81980.6234 | 96980.6234 | 81980.6234 | 81538.6234 | 81504.6234 | 81504.6234 | 81504.6234 | 81504.6234 | 81504.6234 | 80031.1838 | 80031.1838 | 230031.1838 | 1222077.785 | 1583420.4445 | 80031.1838 | 80031.1838 | 80031.1838 | 80031.1838 | 80031.1838 | 80031.1838 | 80031.1838 | 88272.942 | 103108.1069 | 103108.1069 | 103108.1069 | 103108.1069 | 228108.1069 | 1289031.7628 | 2872452.2073 | 103108.1069 | 103108.1069 | 103108.1069 | 103108.1069 | 102985.2349 | 102875.3448 | 102875.3448 | 94633.5866 | 79798.4217 | 79798.4217 | 68149.3924 | 0 | 125000 | 1168548.1744 | 4041000.3818 | [12 empty] | 100000 | 100000 | 4141000.3818 | 4141001.2588 | -0.87703 | 372326.6913 | -10984.0317 | 4141001.2588 | 0 | 285185.7068 | 3779657.7222 | [5 empty] | 4141000.3818
1996 | T17.03 | OCIP deduction only INFRACO | T Kinloch | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | 0
2004 | T17 | Total INSURANCE |  | 36123 | 1700 | 1700 | 5757 | 3000 | 8540 | 4000 | 4500 | 8281 | 6000 | 6000 | 6000 | 8813 | 64291 | 100414 | 2500 | 3857.53 | 5000 | 6930 | 406090 | -26000 | 43676.43 | -350899 | 17650.7703 | 28500.3246 | 85030.3067 | 85030.3067 | 135030.3056 | 442396.9739 | 542810.9739 | 86966.9247 | 86966.9247 | 101966.9247 | 86966.9247 | 86524.9247 | 86490.9247 | 86490.9247 | 86490.9247 | 86490.9247 | 86490.9247 | 85017.4852 | 85017.4852 | 235195.5673 | 1287077.785 | 1829888.7589 | 84633.9235 | 84633.9235 | 84633.9235 | 84633.9235 | 84633.9235 | 84633.9235 | 84633.9235 | 92875.6818 | 107710.8466 | 107710.8466 | 107710.8466 | 107710.8466 | 232875.2301 | 1349031.7628 | 3178920.5217 | 107710.8466 | 107710.8466 | 107710.8466 | 107710.8466 | 107587.9746 | 107478.0845 | 107478.0845 | 99236.3263 | 84401.1615 | 84401.1615 | 72752.1321 | 4602.7397 | 129767.1233 | 1228548.1744 | 4407468.6961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 4507468.6961 | 4507469.5742 | -0.87812 | 453381.0067 | -10984.0328 | 4507469.5742 | 0 | 305090.919 | 3964657.7222 | [5 empty] | 4507468.6961
2005 | 0 | 0
2006 | T18.01 | MUDFA | G Barclay | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | [5 empty] | 0
2007 | T18.01.01 | MUDFA main works | G Barclay | 8: 100000; 9: 210000; 10: 450000; 11: 83333; 12: 88333.3333; 13: 93333.3333; 14: 1024999.6667; 15: 1024999.6667; 16: 200000; 17: 200000; 18: 200000; 19: 1013106; 20: 1804821; 21: 2072491.1732; 22: 1976538; 23: -4387822; 24: 1534422; 25: 648919; 26: 1225931; 27: 1700144; 28: 1821203; 29: 10009753.1732; 30: 11034752.8399; 31: 2783310; 32: 2710140; 33: 2768761; 34: 2908071; 35: 2759661; 36: 2954600; 37: 2365261; 38: 2070894; 39: 1723530; 40: 718214; 41: 0; 42: 0; 43: 0; 44: 23762442; 45: 34797194.8399; 59: 0; 60: 34797194.8399; 74: 0; 75: 34797194.8399; 89: 0; 90: 34797194.8399 | 34797194.8399 | 0 | 10009753.1732 | 0 | 34855391.8399 | -58197 | 4747278 | 23762442 |  |  | -3000000 |  |  | 31797194.8399 | ) | Must identify what elements of MUDFA / Utilities
2008 | T18.01.02 | MUDFA adjustments | G Barclay | 14: 0; 15: 0; 16: 0; 17: 0; 18: 0; 19: 272060; 20: 351260.05; 21: 280124.68; 22: 283028.34; 23: 298125.16; 24: 370578; 25: 284589; 26: 300108; 27: 318497; 28: 194968; 29: 2953338.23; 30: 2953338.23; 31: 290459; 32: 304153.1; 33: 310279.4; 34: 308757.76; 35: 306842.06; 36: 311590.81; 37: 192506.87; 39: 0; 40: 0; 41: 0; 42: 0; 43: 0; 44: 2024589; 45: 4977927.23; 59: 0; 60: 4977927.23; 74: 0; 75: 4977927.23; 89: 0; 90: 4977927.23 | 4977927.23 | 0 | 2953338.23 | 0 | 5044729.24 | -66802.01 | 813573 | 2024589 | [5 empty] | 4977927.23 | ) | budget our £3m saving will come from - URGENT
2009 | T18.01.03 | 0 | G Barclay | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | 0 | )
2010 | T18.01.04 | 0 | G Barclay | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | 0 | )
2011 | T18.01.05 | 0 | G Barclay | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | 0 | )
2012 | T18.01.06 | 0 | G Barclay | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | 0 | )
2013 | T18.01.07 | 0 | G Barclay | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | 0 | )
2014 | T18.01.08 | 0 | G Barclay | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | 0 | )
2015 | T18.01.09 | 0 | G Barclay | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | 0 | )
2016 | T18.01.10 | 0 | G Barclay | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | 0 | )
2017 | T18.01.11 | 0 | G Barclay | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | 0 | )
2018 | T18.01.12 | 0 | G Barclay | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | 0 | )
2019 | T18.01.13 | 0 | G Barclay | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | 0 | )
2020 | T18.01.14 | 0 | G Barclay | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | 0 | )
2021 | T18.01.15 | Transfer to Infraco | G Barclay | 14: 0; 15: 0; 28: 125000; 29: 125000; 30: 125000; 44: 0; 45: 125000; 59: 0; 60: 125000; 74: 0; 75: 125000; 89: 0; 90: 125000 | 125000 | 0 | 125000 | 0 | 125000 | 0 | 125000 | 0 | [5 empty] | 125000 | )
2022 | T18.01 | Subtotal MUDFA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 210000 | 450000 | 83333 | 88333.3333 | 93333.3333 | 1024999.6667 | 1024999.6667 | 200000 | 200000 | 200000 | 1285166 | 2156081.05 | 2352615.8532 | 2259566.34 | -4089696.84 | 1905000 | 933508 | 1526039 | 2018641 | 2141171 | 13088091.4032 | 14113091.0699 | 3073769 | 3014293.1 | 3079040.4 | 3216828.76 | 3066503.06 | 3266190.81 | 2557767.87 | 2070894 | 1723530 | 718214 | 0 | 0 | 0 | 25787031 | 39900122.0699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39900122.0699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39900122.0699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39900122.0699 | 39900122.0699 | 0 | 13088091.4032 | 0 | 40025121.0799 | -124999.01 | 5685851 | 25787031 | [5 empty] | 36900122.0699 | )
2023 | T18.02 | Utilities | G Barclay | 1: 21485; 4: 10350; 5: 100000; 6: 25000; 8: 30000; 9: 690665; 10: 51146; 11: 42750; 12: 55523; 13: 97750; 14: 1103184; 15: 1124669; 16: 0; 17: 0; 18: 73747; 19: 149000; 20: 749686.77; 21: 925481; 22: 870925; 23: -1677490; 24: 384805; 25: 93633; 26: 296562; 27: 350000; 28: 485000; 29: 2701349.77; 30: 3826018.77; 31: 750000; 32: 750000; 33: 650000; 34: 538918.52; 35: 841564.13; 36: 856135.95; 37: 490719.4; 38: 400000; 39: 425000; 40: 425000; 41: 425000; 42: 412827; 43: 836030; 44: 7801195; 45: 11627213.77; 59: 0; 60: 11627213.77; 74: 0; 75: 11627213.77; 89: 0; 90: 11627213.77 | 11627213.77 | 0 | 2701349.77 | 0 | 11627213.77 | 0 | 1131562 | 7801195 | [5 empty] | 11627213.77 | )
2039 | T18.02 | Subtotal utilities |  | 21485 | 0 | 0 | 10350 | 100000 | 25000 | 0 | 30000 | 690665 | 51146 | 42750 | 55523 | 97750 | 1103184 | 1124669 | 0 | 0 | 73747 | 149000 | 749686.77 | 925481 | 870925 | -1677490 | 384805 | 93633 | 296562 | 350000 | 485000 | 2701349.77 | 3826018.77 | 750000 | 750000 | 650000 | 538918.52 | 841564.13 | 856135.95 | 490719.4 | 400000 | 425000 | 425000 | 425000 | 412827 | 836030 | 7801195 | 11627213.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11627213.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11627213.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11627213.77 | 11627213.77 | 0 | 2701349.77 | 0 | 11627213.77 | 0 | 1131562 | 7801195 | [5 empty] | 11627213.77 | )
2040 | T18 | Total MUDFA / Utilities |  | 21485 | 0 | 0 | 10350 | 100000 | 25000 | 0 | 130000 | 900665 | 501146 | 126083 | 143856.3333 | 191083.3333 | 2128183.6667 | 2149668.6667 | 200000 | 200000 | 273747 | 1434166 | 2905767.82 | 3278096.8532 | 3130491.34 | -5767186.84 | 2289805 | 1027141 | 1822601 | 2368641 | 2626171 | 15789441.1732 | 17939109.8399 | 3823769 | 3764293.1 | 3729040.4 | 3755747.28 | 3908067.19 | 4122326.76 | 3048487.27 | 2470894 | 2148530 | 1143214 | 425000 | 412827 | 836030 | 33588226 | 51527335.8399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51527335.8399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51527335.8399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51527335.8399 | 51527335.8399 | 0 | 15789441.1732 | 0 | 51652334.8499 | -124999.01 | 6817413 | 33588226 | [5 empty] | 48527335.8399 | ) | Pre tfr any scope to Infraco
2041 | 0 | 0
2042 | T19.01 | 0 | J McEwan | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | [5 empty] | 0
2043 | T19.01.01 | INFRACO main works | J McEwan | 14: 0; 15: 0; 27: 30040000; 28: 6200000; 29: 36240000; 30: 36240000; 31: 13187407.5218; 32: 8008851.4083; 33: 10553140.2156; 34: 12676414.0892; 35: 11110966.8988; 36: 6623942.4107; 37: 9793022.0377; 38: 9692891.9164; 39: 9961091.5877; 40: 7773253.9181; 41: 8546127.4618; 42: 9363046.3256; 43: 8241233.8012; 44: 125531389.593; 45: 161771389.593; 46: 7284143.4592; 47: 8091548.5377; 48: 6849383.9889; 49: 7365374.3701; 50: 3685255.531; 51: 4267420.1918; 52: 4833198; 53: 5391475.6465; 54: 1610273.2705; 55: 1788471.4084; 56: 1785763.9995; 57: 455200.7159; 58: 370706.7523; 59: 53778215.8719; 60: 215549605.4649; 61: 170706.7523; 62: 115929.4663; 63: 339420.7932; 64: 115929.4663; 65: 225484.0383; 66: 61152.1802; 67: 6374.8942; 68: 115929.4663; 69: 225484.0383; 70: 22333.8942; 71: 528829.869; 74: 1927574.8585; 75: 217477180.3234; 89: 0; 90: 217477180.3234 | 217477180.7414 | -0.41804 | 38740000 | -2500000 | 245372183.9233 | -27895003.1819 | 36240000 | 181237180.3234 | 6603252 |  |  |  |  | 224080432.3234
2044 | T19.01.02 | INFRACO adjustments | J McEwan | 14: 0; 15: 0; 29: 0; 30: 0; 31: -1845637.9913; 32: -1327360.9598; 33: -1749043.1038; 34: -2100947.6033; 35: -1841495.4823; 36: -1097830.651; 37: -1623063.5915; 38: -1606468.3512; 39: -1650918.8916; 40: -1288313.7987; 41: -1416407.3438; 42: -1551800.8168; 43: -1365875.261; 44: -20465163.8463; 45: -20465163.8463; 46: -1207250.2236; 47: -1341066.9128; 48: -1135194.6043; 49: -1220713.1703; 50: -610782.2544; 51: -707268.3301; 52: -386696.7101; 53: -893565.6218; 54: -266881.4496; 55: -296415.4289; 56: -295966.7118; 57: -75443.4848; 58: -61439.7303; 59: -8498684.6327; 60: -28963848.4789; 61: -61439.7303; 62: -52361.1212; 63: -89401.8462; 64: -52361.1212; 65: -70518.3393; 66: -43282.5122; 67: -34203.9031; 68: -52361.1212; 69: -70518.3393; 70: -34203.9031; 71: -87646.5409; 74: -648298.4782; 75: -29612146.9571; 89: 0; 90: -29612146.9571 | -29612146.9571 | 0 | 0 | 0 | -29612147 | 0.042859 | 0 | -29612146.9571 | 15794141 |  |  |  |  | -13818005.9571 |  | VE deducted in Weisbaden deal
2045 | T19.01.03 | INFRACO testing and commission | J McEwan | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 61: 200000; 62: 200000; 63: 200000; 64: 200000; 65: 200000; 66: 200000; 67: 200000; 68: 200000; 69: 200000; 70: 184041; 74: 1984041; 75: 1984041; 89: 0; 90: 1984041 | 1984041 | 0 | 0 | 0 | 0 | 1984041 | 0 | 1984041 | 413048 |  |  |  |  | 2397089 |  | Maintenance mobilisation + spare parts
2046 | T19.01.04 | Depot phase 1 works adjustment | J McEwan | 14: 0; 15: 0; 29: 0; 30: 0; 33: -21387171; 36: -10740284; 39: -11488624; 43: -4159677; 44: -47775756; 45: -47775756; 48: 6141828; 51: 10686234; 54: 14221552; 58: 13281059; 59: 44330673; 60: -3445083; 63: 8508799; 66: 460392; 69: 1418254; 73: -6942362; 74: 3445083; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | -4966630 | 4966630 | 0 | 0 | [5 empty] | 0
2047 | T19.01.05 | Piling A8 / retaining wall at depot | J McEwan | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | 0
2048 | T19.01.06 | Infraco early mobilisation | J McEwan | 14: 0; 15: 0; 26: 4080524; 27: 2919476; 29: 7000000; 30: 7000000; 44: 0; 45: 7000000; 59: 0; 60: 7000000; 74: 0; 75: 7000000; 89: 0; 90: 7000000 | 7000000 | 0 | 7000000 | 0 | 7000000 | 0 | 7000000 | 0 | [5 empty] | 7000000
2049 | T19.01.07 | Infraco funding adjustment | J McEwan | 14: 0; 15: 0; 27: -15500000; 29: -15500000; 30: -15500000; 33: 2250000; 36: 2250000; 39: 2250000; 42: 2250000; 44: 9000000; 45: -6500000; 48: 1625000; 51: 1625000; 54: 1625000; 57: 1625000; 59: 6500000; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | -18000000 | 2500000 |  | 0 | -15500000 | 15500000 | [5 empty] | 0
2050 | T19.01.08 | Non infrastructure works | J McEwan | 14: 0; 15: 0; 29: 0; 30: 0; 33: 7700000; 34: 900000; 40: 1600000; 44: 10200000; 45: 10200000; 48: 2500000; 53: 102332; 56: 1300000; 59: 3902332; 60: 14102332; 64: 2400000; 74: 2400000; 75: 16502332; 89: 0; 90: 16502332 | 16502332 | 0 | 0 | 0 | 0 | 16502332 | 0 | 16502332 | -13992648 |  |  |  |  | 2509684
2051 | T19.01.09 | Contingency | J McEwan | 14: 0; 15: 0; 29: 0; 30: 0; 31: 113900; 32: 113900; 33: 113900; 34: 113900; 35: 113900; 36: 113900; 37: 113900; 38: 113900; 39: 113900; 40: 113900; 41: 113900; 42: 113900; 43: 113900; 44: 1480700; 45: 1480700; 46: 113900; 47: 113900; 48: 113900; 49: 113900; 50: 113900; 51: 113900; 52: 113900; 53: 113900; 54: 113900; 55: 113900; 56: 113900; 57: 113900; 58: 113900; 59: 1480700; 60: 2961400; 61: 113900; 62: 113900; 63: 113900; 64: 113900; 65: 113900; 66: 113900; 67: 113900; 68: 113900; 69: 113900; 70: 113900; 71: 113900; 72: 113900; 73: 113800; 74: 1480600; 75: 4442000; 89: 0; 90: 4442000 | 4442000 | 0 | 0 | 0 | 0 | 4442000 | 0 | 4442000 | -442000 |  |  |  |  | 4000000 |  | Provision against VE £13.8m
2058 | T19.01 | Subtotal INFRACO |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4080524 | 17459476 | 6200000 | 27740000 | 27740000 | 11455669.5304 | 6795390.4486 | -2519173.8882 | 11589366.4859 | 9383371.4165 | -2850272.2403 | 8283858.4462 | 8200323.5652 | -814551.3039 | 8198840.1194 | 7243620.118 | 10175145.5088 | 2829581.5402 | 77971169.7468 | 105711169.7468 | 6190793.2357 | 6864381.6249 | 16094917.3846 | 6258561.1998 | 3188373.2766 | 15985285.8617 | 4560401.2899 | 4714142.0247 | 17303843.8209 | 1605955.9795 | 2903697.2878 | 2118657.2312 | 13704226.022 | 101493236.2392 | 207204405.9859 | 423167.022 | 377468.345 | 9072717.947 | 2777468.345 | 468865.6989 | 792161.6681 | 286070.9911 | 377468.345 | 1887119.6989 | 286070.9911 | 555083.3281 | 113900 | -6828562 | 10589000.3803 | 217793406.3662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217793406.3662 | 217793406.7843 | -0.41804 | 27740000 | 0 | 217793406.9233 | -0.13907 | 27740000 | 190053406.3662 | [5 empty] | 226169199.3662
2059 | T19.02 | Advance Works | S Clark | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | 0
2060 | T19.02.01 | SRU Murrayfield pitches | S Clark | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | 0
2061 | T19.02.02 | Relocate historic monuments | S Clark | 14: 0; 15: 0; 29: 0; 30: 0; 37: 42000; 44: 42000; 45: 42000; 59: 0; 60: 42000; 74: 0; 75: 42000; 89: 0; 90: 42000 | 42000 | 0 | 0 | 0 | 42000 | 0 | 0 | 42000 | -42000 |  |  |  |  | 0
2062 | T19.02.03 | Environ. impacts - badgers | S Clark | 14: 0; 15: 0; 17: 20000; 18: 5000; 20: -15000; 22: 2000; 26: 10000; 27: 10000; 29: 32000; 30: 32000; 44: 0; 45: 32000; 59: 0; 60: 32000; 74: 0; 75: 32000; 89: 0; 90: 32000 | 32000 | 0 | 32000 | 0 | 32000 | 0 | 20000 | 0 | [5 empty] | 32000
2063 | T19.02.04 | Invasive species | S Clark | 14: 0; 15: 0; 18: 37000; 20: 14642; 22: 25820; 28: 15000; 29: 92462; 30: 92462; 31: 15000; 33: 15000; 34: 15000; 36: 15000; 44: 60000; 45: 152462; 46: 25000; 48: 25000; 49: 25000; 51: 25000; 52: 25000; 53: 22538; 59: 147538; 60: 300000; 74: 0; 75: 300000; 89: 0; 90: 300000 | 300000 | 0 | 92462 | 0 | 300000 | 0 | 15000 | 207538 | [5 empty] | 300000
2075 | T19.02 | Subtotal advance works |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 42000 | 0 | -358 | 0 | 27820 | 0 | 0 | 0 | 10000 | 10000 | 15000 | 124462 | 124462 | 15000 | 0 | 15000 | 15000 | 0 | 15000 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 102000 | 226462 | 25000 | 0 | 25000 | 25000 | 0 | 25000 | 25000 | 22538 | 0 | 0 | 0 | 0 | 0 | 147538 | 374000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374000 | 374000 | 0 | 124462 | 0 | 374000 | 0 | 35000 | 249538 | [5 empty] | 332000
2076 | T19.03 | Depot advance works | G Barclay | 14: 0; 15: 0; 16: 134574; 29: 134574; 30: 134574; 44: 0; 45: 134574; 59: 0; 60: 134574; 74: 0; 75: 134574; 89: 0; 90: 134574 | 134574 | 0 | 134574 | 0 | 134574 | 0 | 0 | 0 | [5 empty] | 134574
2077 | T19.03.01 | Set up / mobilisation | G Barclay | 14: 0; 15: 0; 17: 179741; 29: 179741; 30: 179741; 44: 0; 45: 179741; 59: 0; 60: 179741; 74: 0; 75: 179741; 89: 0; 90: 179741 | 179741 | 0 | 179741 | 0 | 179741 | 0 | 0 | 0 | [5 empty] | 179741
2078 | T19.03.02 | Phase 1 (150,000m3) | G Barclay | 14: 0; 15: 0; 17: 405559; 18: 707000; 19: 1010441; 20: 569660; 21: 222025; 29: 2914685; 30: 2914685; 44: 0; 45: 2914685; 59: 0; 60: 2914685; 74: 0; 75: 2914685; 89: 0; 90: 2914685 | 2914685 | 0 | 2914685 | 0 | 2914685 | 0 | 0 | 0 | [5 empty] | 2914685
2079 | T19.03.03 | Phase 2 (100,000m3) | G Barclay | 14: 0; 15: 0; 20: 50000; 21: 894600; 22: 409889; 23: 224552; 25: 583353; 29: 2162394; 30: 2162394; 44: 0; 45: 2162394; 59: 0; 60: 2162394; 74: 0; 75: 2162394; 89: 0; 90: 2162394 | 1579041 | 583353 | 1579041 | 583353 | 1579041 | 0 | 0 | 0 | [5 empty] | 2162394
2080 | T19.03.04 | Phase 3 (55,000m3) | G Barclay | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
2092 | T19.03 | Subtotal depot advance works |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134574 | 585300 | 707000 | 1010441 | 619660 | 1116625 | 409889 | 224552 | 0 | 583353 | 0 | 0 | 0 | 5391394 | 5391394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5391394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5391394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5391394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5391394 | 4808041 | 583353 | 4808041 | 583353 | 4808041 | 0 | 0 | 0 | [5 empty] | 5391394
2093 | T19.04 | 0 |  | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [5 empty] | 0
2094 | T19.05 | 0 |  | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [5 empty] | 0
2095 | T19.06 | 0 |  | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [5 empty] | 0
2096 | T19.07 | 0 |  | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [5 empty] | 0
2097 | T19.08 | 0 |  | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 222975447.9233 |  | 0 | 0 | [5 empty] | 0
2098 | T19.09 | 0 |  | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | [5 empty] | 0
2099 | T19.10 | 0 |  | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [5 empty] | 0
2100 | T19 | Total INFRACO |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134574 | 605300 | 749000 | 1010441 | 619302 | 1116625 | 437709 | 224552 | 0 | 583353 | 4090524 | 17469476 | 6215000 | 33255856 | 33255856 | 11470669.5304 | 6795390.4486 | -2504173.8882 | 11604366.4859 | 9383371.4165 | -2835272.2403 | 8325858.4462 | 8200323.5652 | -814551.3039 | 8198840.1194 | 7243620.118 | 10175145.5088 | 2829581.5402 | 78073169.7468 | 111329025.7468 | 6215793.2357 | 6864381.6249 | 16119917.3846 | 6283561.1998 | 3188373.2766 | 16010285.8617 | 4585401.2899 | 4736680.0247 | 17303843.8209 | 1605955.9795 | 2903697.2878 | 2118657.2312 | 13704226.022 | 101640774.2392 | 212969799.9859 | 423167.022 | 377468.345 | 9072717.947 | 2777468.345 | 468865.6989 | 792161.6681 | 286070.9911 | 377468.345 | 1887119.6989 | 286070.9911 | 555083.3281 | 113900 | -6828562 | 10589000.3803 | 223558800.3662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223558800.3662 | 222975447.7843 | 583352.582 | 32672503 | 583353 | 222975447.9233 | -0.13907 | 27775000 | 190302944.3662 | [5 empty] | 231892593.3662 |  | Pre scope transfers to/from MUDFA and Tramco
2101 | 0 | 0
2102 | T20.01 | 0 | A Richards | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
2103 | T20.01.01 | TRAMCO | A Richards | 14: 0; 15: 0; 27: 4850000; 28: 4450000; 29: 9300000; 30: 9300000; 31: 3579057; 32: 11667.4266; 33: 11667.4266; 34: 11667.4266; 35: 11667.4266; 36: 11667.4266; 37: 11667.4266; 38: 11667.4266; 39: 11667.4; 40: 9875558.8; 41: 17113; 42: 17113; 43: 185463.4; 44: 13767644.586; 45: 23067644.586; 46: 686430.5; 47: 774476; 48: 1000535.2; 49: 2136019.5; 50: 1736976.4; 51: 1918157.5; 52: 2216774.9; 53: 2473759.7; 54: 2685128.3; 55: 1836165; 56: 2148355.1; 57: 2032115.9; 58: 1922290.9; 59: 23567184.9; 60: 46634829.486; 61: 1734570.7; 62: 1570697.6; 63: 1409717.9; 64: 1153518.3; 65: 731604.2; 66: 2399558.8; 67: 11667.4; 68: 5833.7; 73: -4531773; 74: 4485395.6; 75: 51120225.086; 89: 0; 90: 51120225.086 | 51120225.086 | 0 | 9300000 | 0 | 51148461.7583 | -28236.6724 | 9300000 | 41820225.086 |  | 5259300 |  |  |  | 56379525.086
2104 | T20.01.02 | TRAMCO adjustments | A Richards | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | -28236.1964 | 28236.1964 | 0 | 0 | [5 empty] | 0
2105 | T20.01.03 | Testing and commission | A Richards | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
2106 | T20.01.04 | Tramco early mobilisation | A Richards | 14: 0; 15: 0; 26: 100000; 27: 150000; 29: 250000; 30: 250000; 44: 0; 45: 250000; 59: 0; 60: 250000; 74: 0; 75: 250000; 89: 0; 90: 250000 | 250000 | 0 | 250000 | 0 | 250000 | 0 | 250000 | 0 | [5 empty] | 250000
2107 | T20.01.05 | Tramco funding adjustment | A Richards | 14: 0; 15: 0; 27: -4350000; 28: -4350000; 29: -8700000; 30: -8700000; 44: 0; 45: -8700000; 48: 2175000; 51: 2175000; 54: 2175000; 57: 2175000; 59: 8700000; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | -8700000 | 0 | 0 | 0 | -8700000 | 8700000 | [5 empty] | 0
2113 | T20 | Total TRAMCO |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 650000 | 100000 | 850000 | 850000 | 3579057 | 11667.4266 | 11667.4266 | 11667.4266 | 11667.4266 | 11667.4266 | 11667.4266 | 11667.4266 | 11667.4 | 9875558.8 | 17113 | 17113 | 185463.4 | 13767644.586 | 14617644.586 | 686430.5 | 774476 | 3175535.2 | 2136019.5 | 1736976.4 | 4093157.5 | 2216774.9 | 2473759.7 | 4860128.3 | 1836165 | 2148355.1 | 4207115.9 | 1922290.9 | 32267184.9 | 46884829.486 | 1734570.7 | 1570697.6 | 1409717.9 | 1153518.3 | 731604.2 | 2399558.8 | 11667.4 | 5833.7 | 0 | 0 | 0 | 0 | -4531773 | 4485395.6 | 51370225.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51370225.086 | 51370225.086 | 0 | 850000 | 0 | 51370225.5619 | -0.47591 | 850000 | 50520225.086 | [5 empty] | 56629525.086 |  | Pre any trf from Infraco re equipment
2114 | 0 | 0
2115 | T99.01 | Miscellaneous | M Thorne | 20762.74 | 5000 | 5000 | 26737 | 69 | 35000 | 12885 | 10000 | 10000 | 10000 | 10000 | -19056 | 11385 | 117020 | 137782.74 | 6455 | 898 | 20978 | 3322 |  |  |  |  | -17844 |  | 4461 | 4461 | 4461 | 27192 | 164974.74 | 2601 | 2601 | 2601 | 2601 | 2603 | 2601 | 2601 | 2601 | 2601 | 2601 | 2601 | 2601 | 2607 | 33821 | 198795.74 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 22100 | 220895.74 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 22100 | 242995.74 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 2220 | 22620 | 265615.74 | 265615.74 | 0 | 31653 | -4461 | 265616 | -0.26 | 13383 | 100641 | [5 empty] | 265615.74
2116 | T99.02 | Previous years | Closed | 1: 3093000; 14: 0; 15: 3093000; 29: 0; 30: 3093000; 44: 0; 45: 3093000; 59: 0; 60: 3093000; 74: 0; 75: 3093000; 89: 0; 90: 3093000 | 3093000 | 0 | 0 | 0 | 3093000 | 0 | 0 | 0 | [5 empty] | 3093000
2117 | T99.03 | 0 |  | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | 0
2118 | T99.04 | 0 |  | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | 0
2119 | T99.05 | 0 |  | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | 0
2120 | T99.06 | 0 |  | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | 0
2121 | T99.07 | 0 |  | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | 0
2122 | T99.08 | 0 |  | 14: 0; 15: 0; 29: 0; 30: 0; 44: 0; 45: 0; 59: 0; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | 0
2123 | T99.09 | High level TS adjust |  | 14: 0; 15: 0; 29: 0; 30: 0; 36: -1300000; 44: -1300000; 45: -1300000; 51: 1300000; 59: 1300000; 60: 0; 74: 0; 75: 0; 89: 0; 90: 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | 0
2124 | T99.10 | Risk |  | 14: 0; 15: 0; 28: 1500000; 29: 1500000; 30: 1500000; 31: 1813600; 32: 1813600; 33: 1813600; 34: 1810300; 35: 1762700; 36: 1671600; 37: 1401200; 38: 1142900; 39: 1061600; 40: 423200; 41: 405800; 42: 379700; 43: 8074255; 44: 23574055; 45: 25074055; 46: 373500; 47: 388800; 48: 388800; 49: 401400; 50: 401400; 51: 401400; 52: 379200; 53: 378400; 54: 378400; 55: 308600; 56: 308600; 57: 308600; 58: 12433645; 59: 16850745; 60: 41924800; 61: 308600; 62: 308600; 63: 308600; 64: 308600; 65: 275600; 66: 275600; 67: 275600; 68: 296500; 69: 296500; 70: 4395000; 74: 7049200; 75: 48974000; 89: 0; 90: 48974000 | 48974000 | 0 | 2500000 | -1000000 | 48974000 | 0 | 1500000 | 47474000 | -8917146 | -5259300 | 3000000 |  | -1313015 | 36484539 |  | Net tfr from risk allowance = £12.4m v £10m previosuly reported.
2125 | T99 | Total RISK / OTHER |  | 3113762.74 | 5000 | 5000 | 26737 | 69 | 35000 | 12885 | 10000 | 10000 | 10000 | 10000 | -19056 | 11385 | 117020 | 3230782.74 | 6455 | 898 | 20978 | 3322 | 0 | 0 | 0 | 0 | -17844 | 0 | 4461 | 4461 | 1504461 | 1527192 | 4757974.74 | 1816201 | 1816201 | 1816201 | 1812901 | 1765303 | 374201 | 1403801 | 1145501 | 1064201 | 425801 | 408401 | 382301 | 8076862 | 22307876 | 27065850.74 | 375200 | 390500 | 390500 | 403100 | 403100 | 1703100 | 380900 | 380100 | 380100 | 310300 | 310300 | 310300 | 12435345 | 18172845 | 45238695.74 | 310300 | 310300 | 310300 | 310300 | 277300 | 277300 | 277300 | 298200 | 298200 | 4396700 | 1700 | 1700 | 1700 | 7071300 | 52309995.74 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 1700 | 2220 | 22620 | 52332615.74 | 52332615.74 | 0 | 2531653 | -1004461 | 52332616 | -0.26 | 1513383 | 47574641 | [5 empty] | 39843154.74 |  | Increase includes £0.6m on depot excavation, £300k on IPR2 contingency,
2126 | 0 | 0 | [106 empty] | £0.7m on DLA and £0.6m CEC costs
2127 | T999 | TOTAL |  | 13757346.0836 | 1772067.8726 | 2524731.2613 | 2809458.78 | 2381068 | 2128369.8145 | 2654124.194 | 2624852 | 3237647 | 2657066 | 2184231 | 3159767.3333 | 2297450.332 | 30430833.5878 | 44188179.6713 | 12808052.614 | 2288664.2724 | 3899403.2727 | 9634789.1702 | 3776635.2613 | 4792779.4708 | 6503995.135 | -4402691.6261 | 5074276.9912 | 3536465.5774 | 7885998.0853 | 22169620.1854 | 14332059.2963 | 92300047.7059 | 136488227.3772 | 23877925.1801 | 13453508.5185 | 4102279.2517 | 18218115.7658 | 16135837.5364 | 2740392.2496 | 13782999.997 | 12831182.0953 | 3388679.8396 | 20622191.4029 | 9041669.5606 | 12298961.8214 | 13027694.4119 | 163521437.6309 | 300009665.0081 | 8081502.7261 | 8791096.4353 | 20457722.425 | 9589090.8902 | 6095003.307 | 22586118.0622 | 7944395.8803 | 8344089.9533 | 23321672.2844 | 4529973.823 | 6139921.1613 | 7419522.8647 | 28971543.679 | 162271653.4917 | 462281318.4998 | 3313366.6568 | 3129785.6298 | 11783957.5318 | 5282638.3298 | 2561744.7118 | 4630061.3908 | 1798338.3139 | 1943541.2095 | 3264972.6986 | 5798415.9908 | 929809.2985 | 420476.578 | -10927594.0385 | 33929514.3018 | 496210832.8016 | 169639.3569 | 127754.407 | 127083.407 | 127083.407 | 126938.407 | 140296.907 | 128526.907 | 113526.907 | 113526.907 | 113526.907 | 113526.907 | 113526.907 | 334046.7531 | 1849004.0867 | 498059836.8883 | 498059831.2718 | 5.6165 | 93053599.0055 | -753551.2996 | 498059782.0006 | 49.2712 | 44387677.567 | 361571609.5111 | 0 | 0 | 0 | 0.67465 | -0.29 | 498059837.273 |  | IE we have a £2.4m challenge to back to the same figures as reported to TPB
2128 | 0 | 0
2129 | 0 | Cumulative |  | 13757346.0836 | 15529413.9561 | 18054145.2174 | 20863603.9974 | 23244671.9974 | 25373041.812 | 28027166.0059 | 30652018.0059 | 33889665.0059 | 36546731.0059 | 38730962.0059 | 41890729.3393 | 44188179.6713 | 44188179.6713 | 44188179.6713 | 56996232.2853 | 59284896.5578 | 63184299.8305 | 72819089.0007 | 76595724.262 | 81388503.7328 | 87892498.8678 | 83489807.2416 | 88564084.2328 | 92100549.8103 | 99986547.8955 | 122156168.081 | 136488227.3772 | 136488227.3772 | 136488227.3772 | 160366152.5574 | 173819661.0759 | 177921940.3276 | 196140056.0934 | 212275893.6297 | 215016285.8793 | 228799285.8763 | 241630467.9716 | 245019147.8112 | 265641339.2142 | 274683008.7748 | 286981970.5962 | 300009665.0081 | 300009665.0081 | 300009665.0081 | 308091167.7342 | 316882264.1696 | 337339986.5945 | 346929077.4848 | 353024080.7918 | 375610198.8539 | 383554594.7342 | 391898684.6875 | 415220356.9719 | 419750330.7949 | 425890251.9561 | 433309774.8208 | 462281318.4998 | 462281318.4998 | 462281318.4998 | 465594685.1566 | 468724470.7864 | 480508428.3183 | 485791066.6481 | 488352811.3599 | 492982872.7507 | 494781211.0646 | 496724752.2742 | 499989724.9728 | 505788140.9636 | 506717950.2621 | 507138426.8401 | 496210832.8016 | 496210832.8016 | 496210832.8016 | 496380472.1585 | 496508226.5655 | 496635309.9725 | 496762393.3794 | 496889331.7864 | 497029628.6934 | 497158155.6003 | 497271682.5073 | 497385209.4143 | 497498736.3213 | 497612263.2282 | 497725790.1352 | 498059836.8883 | 498059836.8883 | 498059836.8883
2130
2131 |  | Difference from last month |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4209405.3457 | -3073056.3615 | 116667.889 | -753551.2996 | -753551.2996 | -753551.2996 | -717111.8593 | -591838.8059 | -451565.7526 | -285773.6992 | -108084.6458 | 58865.4075 | 183943.0618 | 361822.7162 | 539702.3705 | 731947.0248 | 879424.2782 | 1026901.5316 | 1174381.7851 | 1174381.7851 | #VALUE! | 1222133.3893 | 1269884.9936 | 692636.5979 | 740388.2022 | 788139.8064 | 210891.4107 | 2758642.5969 | 2806394.2012 | 2229145.8055 | 2276897.4098 | 2324649.014 | 1747400.6183 | 2795152.2226 | 2795152.2226 | #VALUE! | 2842903.8269 | 2890655.4311 | 2938407.0354 | 2986158.6397 | 3031293.2768 | 3076461.9139 | 3121630.551 | 3166799.188 | 2996327.8251 | 2666698.878 | 2402415.2704 | 2069982.2704 | 1737549.2704 | 1737549.2704 | 1737549.2704 | 1479758.2704 | 1232702.2704 | 989768.2704 | 778508.2704 | 579497.2704 | 378844.7704 | 321005.7704 | 267505.7704 | 214005.7704 | 160505.7704 | 107005.7704 | 53505.7704 | 5.6165 | 5.6165 | 5.5825 |  |  | -26446889.3199
1963143
|  |  |  | 1456289 | [10 empty] | 2807430 | 454973 | 3262403 | 4718692 | 301035 | 297653 | 417047 | 406356 | 349547 | 391035 | 370517 | 513142 | 476457 | 165915 | 1295010 |  |  | 4983714 | 9702406 | [13 empty] | 0 | 9702406 | [13 empty] | 0 | 9702406 | [13 empty] | 0 | 9702406 | [13 empty] | 0 | 9702406
|  |  |  | 1: 38612; 4: 6250; 6: 2125; 11: 46350; 12: 22676; 13: 28925; 14: 106326; 15: 144938; 16: 13162; 17: 5685; 18: 10850; 19: 15500; 21: 11875; 22: 12453; 23: 8550; 24: 12050; 25: 7050; 26: 5313; 29: 102488; 30: 247426; 44: 0; 45: 247426; 59: 0; 60: 247426; 74: 0; 75: 247426; 89: 0; 90: 247426 |  |  | 3010293
|  |  |  | 25629 | 603 | 3993 | 9908 | 6177 | 5582 | -15921 | 12956 | 7290 | 3722 | 2802 | 3146 | 5885 | 46143 | 71772 | 3525.27 | 1909.67 | 4971.4 | 4180.25 | 1999.38 | 4034 | 4871 | 10789 | 7449 | 14190 | 0 |  |  | 57918.97 | 129690.97 | [13 empty] | 0 | 129690.97 | [13 empty] | 0 | 129690.97 | [13 empty] | 0 | 129690.97 | [13 empty] | 0 | 129690.97
|  |  |  | 1: 910014; 2: 83788.3235; 3: 63304.2494; 4: 119161.305; 5: 253047.9308; 6: 151630.605; 7: 165422.8092; 8: 163186; 10: 357513; 11: 92339; 13: 246809; 14: 1696202.2229; 15: 2606216.2229; 16: 166684; 17: 153084; 18: 146092; 19: 215351; 20: 121466; 21: 68552; 23: 274598; 24: 47272; 26: 131420; 29: 1324519; 30: 3930735.2229; 44: 0; 45: 3930735.2229; 59: 0; 60: 3930735.2229; 74: 0; 75: 3930735.2229; 89: 0; 90: 3930735.2229 |  |  | 95016742.0055
|  |  |  | 214592 | [11 empty] | 556308.55 | 556308.55 | 770900.55 | 34394 | 36619 | 196803 | 201899 | 111736 | 27211 | 82304 | -64652 | 52 | 21420 | 46598 |  |  | 694384 | 1465284.55 | [13 empty] | 0 | 1465284.55 | [13 empty] | 0 | 1465284.55 | [13 empty] | 0 | 1465284.55 | [13 empty] | 0 | 1465284.55
|  |  |  | 1: 29174; 3: 8697; 4: 21037; 5: 78595; 6: -5080; 8: 330; 9: 6920; 10: 3131; 12: 67872; 13: 6831.15; 14: 188333.15; 15: 217507.15; 16: 75877; 17: 66733; 20: 61804; 22: 1897; 23: 228356; 24: 0; 25: 0; 26: 83354; 29: 518021; 30: 735528.15; 44: 0; 45: 735528.15; 59: 0; 60: 735528.15; 74: 0; 75: 735528.15; 89: 0; 90: 735528.15 |  |  | 3010293
[17 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 85542 | [12 empty] | 0 | 85542 | 0 | [12 empty] | 0 | 85542 | [13 empty] | 0 | 85542 | [13 empty] | 0 | 85542 | [13 empty] | 0 | 85542 | [13 empty] | 0 | 85542
[6 empty] | 400.11 | 8923 | 2536 | 2670 | 917 | 917 | 998 |  | 1834 | 252 | 148 | 19595.11 | 19595.11 | 0 | 0 | 516 | 599 | 1011 | 1644 | -72 |  |  | 386 | 2849 |  |  | 6933 | 26528.11 | [13 empty] | 0 | 26528.11 | [13 empty] | 0 | 26528.11 | [13 empty] | 0 | 26528.11 | [13 empty] | 0 | 26528.11
[11 empty] | 23344 | 32682 | 7060 | 6799 |  |  | 69885 | 69885 | 0 | [7 empty] | 1606 |  | 9623 |  |  | 11229 | 81114 | [13 empty] | 0 | 81114 | [13 empty] | 0 | 81114 | [13 empty] | 0 | 81114 | [13 empty] | 0 | 81114
[17 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 2759852 | 84391.3235 | 76394.3594 | 165279.305 | 340355.9308 | 156927.605 | 150418.8092 | 200733 | 47890 | 371426 | 150124 | 2901376 | 1299879.7 | 5945196.0329 | 8705048.0329 | 594677.27 | 561683.67 | 776279.4 | 843885.25 | 647563.38 | 504351 | 471970 | 970783 | 544886 | 208961 | 1574167 | 0 | 0 | 7699206.97 | 16404255.0029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16404255.0029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16404255.0029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16404255.0029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16404255.0029
|  |  |  | 386880 |  |  | 84511 |  | 75123 |  |  | 92262.09 |  | 100941 |  |  | 352837.09 | 739717.09 |  | 113667.37 |  |  | 109662.54 |  |  | 76535.61 | [5 empty] | 299865.52 | 1039582.61 | [13 empty] | 0 | 1039582.61 | [13 empty] | 0 | 1039582.61 | [13 empty] | 0 | 1039582.61 | [13 empty] | 0 | 1039582.61
[7 empty] | -1942.8 |  | -7512 |  |  | -9226.2 |  |  |  | 18681 | 0 | 0 |  | -11366.7 |  |  | -10966.3 |  |  | -7554.7 | [5 empty] | -29887.7 | -29887.7 | [13 empty] | 0 | -29887.7 | [13 empty] | 0 | -29887.7 | [13 empty] | 0 | -29887.7 | [13 empty] | 0 | -29887.7
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 386880 | 0 | 0 | 82568.2 | 0 | 67611 | 0 | 0 | 83035.89 | 0 | 100941 | 0 | 18681 | 352837.09 | 739717.09 | 0 | 102300.67 | 0 | 0 | 98696.24 | 0 | 0 | 68980.91 | 0 | 0 | 0 | 0 | 0 | 269977.82 | 1009694.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1009694.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1009694.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1009694.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1009694.91
|  |  |  | 76499.47 | 2741 | 1630 | 190 | 27 | 370.89 | 1195.95 | 0 | 227 | 80.63 | 0 | 0 | 10666.49 | 17128.96 | 93628.43 |  | 383.25 |  |  |  | 2403 | 6639.11 | 8609.52 | 4829.62 | 5000 |  |  |  | 27864.5 | 121492.93 | [13 empty] | 0 | 121492.93 | [13 empty] | 0 | 121492.93 | [13 empty] | 0 | 121492.93 | [13 empty] | 0 | 121492.93
|  |  |  | 29835.86 | 0 | 0 | 0 | 0 |  | 2163.51 | 0 | 0 | 0 | 0 | 0 | 0 | 2163.51 | 31999.37 | [13 empty] | 0 | 31999.37 | [13 empty] | 0 | 31999.37 | [13 empty] | 0 | 31999.37 | [13 empty] | 0 | 31999.37 | [13 empty] | 0 | 31999.37
|  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1116.25 | [9 empty] | 1116.25 | 1116.25 | [13 empty] | 0 | 1116.25 | [13 empty] | 0 | 1116.25 | [13 empty] | 0 | 1116.25 | [13 empty] | 0 | 1116.25
|  |  |  | 354360.76 | 7326 | 26428 | 63599 | 78604 | 32179.2 | 22007.85 | 17920 | 5772 | 1505.06 | 2437.08 | 7441.35 | -6062.55 | 259156.99 | 613517.75 |  | 13309.8 | 6846 | 4138 |  | 13602 | 2535.45 | 2604.79 | 247.26 | 5000 |  |  |  | 48283.3 | 661801.05 | [13 empty] | 0 | 661801.05 | [13 empty] | 0 | 661801.05 | [13 empty] | 0 | 661801.05 | [13 empty] | 0 | 661801.05
|  |  |  | 48665.11 | 0 | 1525 | 1844 | 6683 | 3515.33 | 1976.23 | 1339 | 4259 | 521.41 | 543.96 | 514.41 | -513.99 | 22207.35 | 70872.46 |  | 1073 | 2422 | 1699 |  | 2745 | 2898.8 | 12515.09 | 7179.63 |  |  |  |  | 30532.52 | 101404.98 | [13 empty] | 0 | 101404.98 | [13 empty] | 0 | 101404.98 | [13 empty] | 0 | 101404.98 | [13 empty] | 0 | 101404.98
|  |  |  | 27275.32 | 0 | 0 | 107.5 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107.5 | 27382.82 | [13 empty] | 0 | 27382.82 | [13 empty] | 0 | 27382.82 | [13 empty] | 0 | 27382.82 | [13 empty] | 0 | 27382.82 | [13 empty] | 0 | 27382.82
|  |  |  | 141282.71 | 62127 | 31593 | 13446 | 22985 | 40905.14 | 74819.19 | 69373 | 14944 | 9970.02 | 36357.64 | 59112.75 | -59066.78 | 376565.96 | 517848.67 |  | 104077 | 16882 | 30320 |  | 23546 | 64994.9 | 76036.8 | 34552.31 | 50000 |  |  |  | 400409.01 | 918257.68 | [13 empty] | 0 | 918257.68 | [13 empty] | 0 | 918257.68 | [13 empty] | 0 | 918257.68 | [13 empty] | 0 | 918257.68
|  |  |  | 142160.42 | 36632 | 16192 | 21275 | 18588 | 1480.84 | 11383.57 | 23010.35 | 23543.55 | 6963.34 | 8349.61 | 9674.1 | -11803.15 | 165289.21 | 307449.63 |  | 41199 | 19746 | 58649 |  | 15048 | 6127.6 | 1477.07 | 101.35 | 600 |  |  |  | 142948.02 | 450397.65 | [13 empty] | 0 | 450397.65 | [13 empty] | 0 | 450397.65 | [13 empty] | 0 | 450397.65 | [13 empty] | 0 | 450397.65
|  |  |  | 1009.5 | 0 | 81 | 165 | 54 | 131.67 | 20.6 | 0 | 0 | 0 | 0 | 0 | -0.99 | 451.28 | 1460.78 |  | 2580 | 935 |  |  | 161 | 5961.55 | 7673.64 |  | 2535 |  |  |  | 19846.19 | 21306.97 | [13 empty] | 0 | 21306.97 | [13 empty] | 0 | 21306.97 | [13 empty] | 0 | 21306.97 | [13 empty] | 0 | 21306.97
|  |  |  | 5328.44 | 0 | 0 | 2341 | 3441 | 1646.62 | 6004.12 | 215 | 269 | 680.83 | 56.21 | 499.89 | -513.87 | 14639.8 | 19968.24 |  | 645 | 339 | 194 |  | 4800 |  |  | 3003.17 | 2000 |  |  |  | 10981.17 | 30949.41 | [13 empty] | 0 | 30949.41 | [13 empty] | 0 | 30949.41 | [13 empty] | 0 | 30949.41 | [13 empty] | 0 | 30949.41
|  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 0 | 2365 | 2536 | 1098.83 | 1358 | 3020.7 | 1198.65 | 81 | 304 | 4413.94 | 6482.29 | 10694.92 | -6867.22 | 26686.11 | 26686.11 |  | 14718 | 9191 | 15657 |  | 5942 | 639.64 | 1343.77 | 6154.41 | 5000 |  |  |  | 58645.82 | 85331.93 | [13 empty] | 0 | 85331.93 | [13 empty] | 0 | 85331.93 | [13 empty] | 0 | 85331.93 | [13 empty] | 0 | 85331.93
|  |  |  | 9163.01 | 95 | 499 | 3823 | 252 | 61.81 | 183.63 | 618 | 62 | 0 |  | 0 | 0 | 5594.44 | 14757.45 | [5 empty] | 213 | [7 empty] | 213 | 14970.45 | [13 empty] | 0 | 14970.45 | [13 empty] | 0 | 14970.45 | [13 empty] | 0 | 14970.45 | [13 empty] | 0 | 14970.45
|  |  |  | 2413.16 | 2127 | 2349 | 618 | 0 | 3399.87 | 144.23 | 4873 | 2637 | 1483.56 | 535.35 | 3189.66 | -3189.44 | 18167.23 | 20580.39 |  | 15069 |  | 2800 |  | 768 | [7 empty] | 18637 | 39217.39 | [13 empty] | 0 | 39217.39 | [13 empty] | 0 | 39217.39 | [13 empty] | 0 | 39217.39 | [13 empty] | 0 | 39217.39
[5 empty] | 643 | 719 | 759 | 364 | 1442.35 | 188.13 | 511 | 0 | 0 | 0 | 0 | 2266 | 6892.48 | 6892.48 | [13 empty] | 0 | 6892.48 | [13 empty] | 0 | 6892.48 | [13 empty] | 0 | 6892.48 | [13 empty] | 0 | 6892.48 | [13 empty] | 0 | 6892.48
[8 empty] | 701 |  | 232.93 | 1566 | 1499 | 2079.32 | 5277.78 | 321.43 | -4320.74 | 7356.72 | 7356.72 |  | 562 | 74 | 2576 |  | 2420 | 96.75 | 2851.59 | 2753 | 2500 |  |  |  | 13833.34 | 21190.06 | [13 empty] | 0 | 21190.06 | [13 empty] | 0 | 21190.06 | [13 empty] | 0 | 21190.06 | [13 empty] | 0 | 21190.06
[8 empty] | 0 |  |  | 0 | 0 |  |  | 0 | 3950.63 | 3950.63 | 3950.63 |  | 3951 | [11 empty] | 3951 | 7901.63 | [13 empty] | 0 | 7901.63 | [13 empty] | 0 | 7901.63 | [13 empty] | 0 | 7901.63 | [13 empty] | 0 | 7901.63
[13 empty] | 1069.64 | 148.36 | 0 | -1218.19 | -0.19 | -0.19 | [6 empty] | 666.63 | 32.25 | [5 empty] | 698.88 | 698.69 | [13 empty] | 0 | 698.69 | [13 empty] | 0 | 698.69 | [13 empty] | 0 | 698.69 | [13 empty] | 0 | 698.69
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[15 empty] | 996.5 | -997 | -0.5 | -0.5 | [13 empty] | 0 | -0.5 | [13 empty] | 0 | -0.5 | [13 empty] | 0 | -0.5 | [13 empty] | 0 | -0.5 | [13 empty] | 0 | -0.5
[15 empty] | 1136.06 | -1136 | 0.06 | 0.06 | 1136 | [12 empty] | 1136 | 1136.06 | [13 empty] | 0 | 1136.06 | [13 empty] | 0 | 1136.06 | [13 empty] | 0 | 1136.06 | [13 empty] | 0 | 1136.06
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 458319 | 20177 | 25402 | 22928 | 13246 | 14300 | 12534.77 | 13095 | 10002 | 178 | 4664 | 2097 | 24716 | 163339.77 | 621658.77 | 3228 | 3314 | 3410 | 3050 | 3014 | 1764 | 2848 | 1002 | 560 |  |  |  |  | 22190 | 643848.77 | [13 empty] | 0 | 643848.77 | [13 empty] | 0 | 643848.77 | [13 empty] | 0 | 643848.77 | [13 empty] | 0 | 643848.77
[5 empty] | 11261 | 15199 | 6843 | 5657 | 7124 | 8888 | 12035 | 10623 | 5988 | 11951 | 11454 | 28831 | 135854 | 135854 | 3134 | 6583 | 5499 | 4132 | 4036 | 12811 | 12906 | 21907 | 16466 |  |  |  |  | 87474 | 223328 | [13 empty] | 0 | 223328 | [13 empty] | 0 | 223328 | [13 empty] | 0 | 223328 | [13 empty] | 0 | 223328
[5 empty] | 31301 | 22079 | 16517 | 18787 | 26723 | 19785.07 | 63283 | 66863.8 | 25569 | 45676 | 38801 | 29067 | 404451.87 | 404451.87 | 16420 | 12136 | 10039 | 14095 | 14245 | 23892 | 35355 | 30274 | 28097 |  |  |  |  | 184553 | 589004.87 | [13 empty] | 0 | 589004.87 | [13 empty] | 0 | 589004.87 | [13 empty] | 0 | 589004.87 | [13 empty] | 0 | 589004.87
[7 empty] | 5220 | 5226 | 10896 | 24348 | 6060 | 7866 | 9936 | 9408 | 7938 | 6384 | 93282 | 93282 | 5460 | 8130 | 10962 | 3876 | 2292 | 1194 | 5778 | 11004 | 12054 |  |  |  |  | 60750 | 154032 | [13 empty] | 0 | 154032 | [13 empty] | 0 | 154032 | [13 empty] | 0 | 154032 | [13 empty] | 0 | 154032
[5 empty] | 11598 | 6220 | 0 | 9430 | 7038 | 4098 | 2772 | 7680 | 3954 | 4260 | 8154 | 7266 | 72470 | 72470 | 5410 | 3162 | 3066 | 804 | 1074 | 0 | 0 | 0 | 0 |  |  |  |  | 13516 | 85986 | [13 empty] | 0 | 85986 | [13 empty] | 0 | 85986 | [13 empty] | 0 | 85986 | [13 empty] | 0 | 85986
[5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 21940 | 21940 | 21940 | [13 empty] | 0 | 21940 | [13 empty] | 0 | 21940 | [13 empty] | 0 | 21940 | [13 empty] | 0 | 21940 | [13 empty] | 0 | 21940
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[5 empty] | 48216 | 31094 | 27615 | 30798 | 14400 | [7 empty] | 152123 | 152123 | [13 empty] | 0 | 152123 | [13 empty] | 0 | 152123 | [13 empty] | 0 | 152123 | [13 empty] | 0 | 152123 | [13 empty] | 0 | 152123
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 1296312.76 | 236609 | 183546 | 188389.33 | 216201 | 168635.42 | 191172.43 | 216751.35 | 156551.35 | 74392.75 | 136147.28 | 162025.07 | 39397.2 | 1969818.18 | 3266130.94 | 34788 | 230892.05 | 89411 | 143106.25 | 24661 | 111309 | 147447.43 | 177331.52 | 115997.75 | 72635 | 0 | 0 | 0 | 1147579 | 4413709.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4413709.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4413709.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4413709.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4413709.94
|  |  |  | 3300000 | 210529 | 345526 | 2949964 | 0 | 0 | 725487 | 426636 | 707233 | 700586 | 697470 | 119046 |  | 7753413 | 11053413 | 291512 | 368762 | 523702 | 150095 |  | 663872 | 1824701 | [6 empty] | 3822644 | 14876057 | [13 empty] | 0 | 14876057 | [13 empty] | 0 | 14876057 | [13 empty] | 0 | 14876057 | [13 empty] | 0 | 14876057
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[15 empty] | 1225000 |  | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 3300000 | 210529 | 345526 | 2949964 | 0 | 0 | 725487 | 426636 | 707233 | 700586 | 697470 | 1344046 | 0 | 7753413 | 11053413 | 291512 | 368762 | 523702 | 150095 | 0 | 663872 | 1824701 | 0 | 0 | 0 | 0 | 0 | 0 | 3822644 | 14876057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14876057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14876057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14876057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14876057
|  |  |  | 260379 |  | 120041 | 46333 | 14614 |  |  | 195593 |  | 168460 | 140168 |  | 250410 | 935619 | 1195998 | 105083 | 24097 | 14866 | 46468 | 53378 | 58235 | 22122 | 27498 | [5 empty] | 351747 | 1547745 | [13 empty] | 0 | 1547745 | [13 empty] | 0 | 1547745 | [13 empty] | 0 | 1547745 | [13 empty] | 0 | 1547745
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 260379 | 0 | 120041 | 46333 | 14614 | 0 | 0 | 195593 | 0 | 168460 | 140168 | 0 | 250410 | 935619 | 1195998 | 105083 | 24097 | 14866 | 46468 | 53378 | 58235 | 22122 | 27498 | 0 | 0 | 0 | 0 | 0 | 351747 | 1547745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1547745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1547745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1547745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1547745
|  |  |  | 1233000 | [11 empty] | 3496006 | 3496006 | 4729006 | 713228 | 302570 | 329115 | 260253 | 216045 | 371906 | 189038 | 210017 |  |  | 357017 |  |  | 2949189 | 7678195 | [13 empty] | 0 | 7678195 | [13 empty] | 0 | 7678195 | [13 empty] | 0 | 7678195 | [13 empty] | 0 | 7678195
|  |  |  | 113000 | [12 empty] | 0 | 113000 | [13 empty] | 0 | 113000 | [13 empty] | 0 | 113000 | [13 empty] | 0 | 113000 | [13 empty] | 0 | 113000 | [13 empty] | 0 | 113000
[12 empty] | 6489 | 15365 | 1074 | 6035 |  | 92381 | 92381 | [13 empty] | 0 | 92381 | [13 empty] | 0 | 92381 | [13 empty] | 0 | 92381 | [13 empty] | 0 | 92381 | [13 empty] | 0 | 92381
[16 empty] | 50057 | 50057 | 50057 | 99047.1 | 29799.25 | 74299.16 | 61966 | 32764 |  | 126838 |  |  |  | 262557 |  |  | 687270.51 | 737327.51 | [13 empty] | 0 | 737327.51 | [13 empty] | 0 | 737327.51 | [13 empty] | 0 | 737327.51 | [13 empty] | 0 | 737327.51
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 1346000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6489 | 15365 | 1074 | 6035 | 3546063 | 3638444 | 4984444 | 812275.1 | 332369.25 | 403414.16 | 322219 | 248809 | 371906 | 315876 | 210017 | 0 | 0 | 619574 | 0 | 0 | 3636459.51 | 8620903.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8620903.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8620903.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8620903.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8620903.51
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 8672.16 | 8724.05 | 11206.78 | 11558.94 | 10842.41 | 19360 | 11757.65 | 11153.35 | 10484 | 10994 | 6012 |  | 120765.34 | 120765.34 | 20501 |  | 18014 | 22336 | 10968.18 | 11584 |  | 13120 | 28222 |  |  |  |  | 124745.18 | 245510.52 | [13 empty] | 0 | 245510.52 | [13 empty] | 0 | 245510.52 | [13 empty] | 0 | 245510.52 | [13 empty] | 0 | 245510.52
[15 empty] | 7500 |  | 7500 | 7500 | [9 empty] | 7500 |  |  |  | 7500 | 15000 | [13 empty] | 0 | 15000 | [13 empty] | 0 | 15000 | [13 empty] | 0 | 15000 | [13 empty] | 0 | 15000
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 0 | 8672.16 | 8724.05 | 11206.78 | 11558.94 | 10842.41 | 19360 | 11757.65 | 11153.35 | 10484 | 10994 | 13512 | 0 | 128265.34 | 128265.34 | 20501 | 0 | 18014 | 22336 | 10968.18 | 11584 | 0 | 13120 | 28222 | 7500 | 0 | 0 | 0 | 132245.18 | 260510.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260510.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260510.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260510.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260510.52
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 35624 | [12 empty] | 32204 | 67828 | 4817 | 1433 | 3501 | 3218 | 11586 | 10150 | 14264 | 12295 | [5 empty] | 61264 | 129092 | [13 empty] | 0 | 129092 | [13 empty] | 0 | 129092 | [13 empty] | 0 | 129092 | [13 empty] | 0 | 129092
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [7 empty] | 11000 | 23000 | 15000 | 44000 |  |  | 93000 | 93000 | [13 empty] | 0 | 93000 | [13 empty] | 0 | 93000 | [13 empty] | 0 | 93000 | [13 empty] | 0 | 93000
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 |  |  |  |  | 2000 | 2000 | 1538 | 1846 | 1846 | 1846.15 |  |  |  | 11076.15 | 11076.15 | [13 empty] | 0 | 11076.15 | [13 empty] | 0 | 11076.15 | [13 empty] | 0 | 11076.15 | [13 empty] | 0 | 11076.15
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 35624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32204 | 67828 | 4817 | 1433 | 3501 | 3218 | 13586 | 12150 | 15802 | 25141 | 24846 | 16846.15 | 44000 | 0 | 0 | 165340.15 | 233168.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233168.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233168.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233168.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233168.15
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 86876 | 18500 | 18500 | 18500 | 18500 | 15000 | 15000 | 15000 |  | 15000 | 15000 | 15000 | 15000 | 179000 | 265876 | 15000 | 15000 | 15000 | 15000 | 12000 | 8000 | 2253.11 | 13453 | 6116 | 8425 |  |  |  | 110247.11 | 376123.11 | [13 empty] | 0 | 376123.11 | [13 empty] | 0 | 376123.11 | [13 empty] | 0 | 376123.11 | [13 empty] | 0 | 376123.11
[5 empty] | 2000 | 2000 | 2000 | [9 empty] | 6000 | 6000 | [13 empty] | 0 | 6000 | [13 empty] | 0 | 6000 | [13 empty] | 0 | 6000 | [13 empty] | 0 | 6000 | [13 empty] | 0 | 6000
[5 empty] | 1850 | 1850 | 1850 | 1850 | 1500 |  |  | 2500 | 1500 | 975 |  |  | 13875 | 13875 | 1500 | 1500 | 1500 | 1500 | 1200 | 800 | [7 empty] | 8000 | 21875 | [13 empty] | 0 | 21875 | [13 empty] | 0 | 21875 | [13 empty] | 0 | 21875 | [13 empty] | 0 | 21875
[5 empty] | 3441.87 | 1940 | 11846 | 3094.39 | 59009 | 18011 | 30014.15 |  | 13720.15 | 9038 | 13873 | -169 | 163818.56 | 163818.56 | 5198.5 | 1290 | 692 | 690 | 1045 | [8 empty] | 8915.5 | 172734.06 | [13 empty] | 0 | 172734.06 | [13 empty] | 0 | 172734.06 | [13 empty] | 0 | 172734.06 | [13 empty] | 0 | 172734.06
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[7 empty] | 2054.28 | 440 | 30290 | 1207 |  |  | 85991.66 | 4830 |  | 54560 | 179372.94 | 179372.94 | [13 empty] | 0 | 179372.94 | [13 empty] | 0 | 179372.94 | [13 empty] | 0 | 179372.94 | [13 empty] | 0 | 179372.94 | [13 empty] | 0 | 179372.94
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[16 empty] | 103330 | 103330 | 103330 | 12537 | 12537.5 | 12537.5 | 2500 | 14515 |  | 12797.69 | 25212.5 | [5 empty] | 92637.19 | 195967.19 | [13 empty] | 0 | 195967.19 | [13 empty] | 0 | 195967.19 | [13 empty] | 0 | 195967.19 | [13 empty] | 0 | 195967.19
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 |  |  |  |  | 7500 |  |  | 14172.69 | 5227.7 | 7249 | 2851 |  |  | 37000.39 | 37000.39 | [13 empty] | 0 | 37000.39 | [13 empty] | 0 | 37000.39 | [13 empty] | 0 | 37000.39 | [13 empty] | 0 | 37000.39
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [7 empty] | 6040 | [5 empty] | 6040 | 6040 | [13 empty] | 0 | 6040 | [13 empty] | 0 | 6040 | [13 empty] | 0 | 6040 | [13 empty] | 0 | 6040
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [7 empty] | 420 | [5 empty] | 420 | 420 | [13 empty] | 0 | 420 | [13 empty] | 0 | 420 | [13 empty] | 0 | 420 | [13 empty] | 0 | 420
[17 empty] | 0 | 0 | [7 empty] | 490 | [5 empty] | 490 | 490 | [13 empty] | 0 | 490 | [13 empty] | 0 | 490 | [13 empty] | 0 | 490 | [13 empty] | 0 | 490
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [7 empty] | 3200 | 8372 | 15500 |  |  |  | 27072 | 27072 | [13 empty] | 0 | 27072 | [13 empty] | 0 | 27072 | [13 empty] | 0 | 27072 | [13 empty] | 0 | 27072
[17 empty] | 0 | 0 | [7 empty] | 1591 | 30 |  |  |  |  | 1621 | 1621 | [13 empty] | 0 | 1621 | [13 empty] | 0 | 1621 | [13 empty] | 0 | 1621 | [13 empty] | 0 | 1621
[17 empty] | 0 | 0 | [6 empty] | 132.5 |  | 1564.94 |  | 3262 |  |  | 4959.44 | 4959.44 | [13 empty] | 0 | 4959.44 | [13 empty] | 0 | 4959.44 | [13 empty] | 0 | 4959.44 | [13 empty] | 0 | 4959.44
[17 empty] | 0 | 0 | [8 empty] | 4082 |  |  |  |  | 4082 | 4082 | [13 empty] | 0 | 4082 | [13 empty] | 0 | 4082 | [13 empty] | 0 | 4082 | [13 empty] | 0 | 4082
[17 empty] | 0 | 0 | [9 empty] | 19745 |  |  |  | 19745 | 19745 | [13 empty] | 0 | 19745 | [13 empty] | 0 | 19745 | [13 empty] | 0 | 19745 | [13 empty] | 0 | 19745
[17 empty] | 0 | 0 |  |  |  |  | 95.36 | 929 |  |  | 14572 | 52 |  |  |  | 15648.36 | 15648.36 | [13 empty] | 0 | 15648.36 | [13 empty] | 0 | 15648.36 | [13 empty] | 0 | 15648.36 | [13 empty] | 0 | 15648.36
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 86876 | 25791.87 | 24290 | 36250.28 | 23884.39 | 105799 | 34218 | 45014.15 | 2500 | 116211.81 | 29843 | 28873 | 172721 | 645396.5 | 732272.5 | 34235.5 | 30327.5 | 29729.5 | 19690 | 36355.36 | 9729 | 15183.3 | 64579.19 | 39964.64 | 50971 | 6113 | 0 | 0 | 336877.99 | 1069150.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1069150.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1069150.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1069150.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1069150.49
|  |  |  | 19947 | [8 empty] | 14405 |  |  |  | 14405 | 34352 | [13 empty] | 0 | 34352 | [13 empty] | 0 | 34352 | [13 empty] | 0 | 34352 | [13 empty] | 0 | 34352 | [13 empty] | 0 | 34352
|  |  |  | 5000 | [12 empty] | 0 | 5000 | [13 empty] | 0 | 5000 | [13 empty] | 0 | 5000 | [13 empty] | 0 | 5000 | [13 empty] | 0 | 5000 | [13 empty] | 0 | 5000
[13 empty] | 468852 |  |  |  | 468852 | 468852 |  | 140867 |  |  | 201230 |  | 2522.32 | 158765 |  | 3514.79 |  |  |  | 506899.11 | 975751.11 | [13 empty] | 0 | 975751.11 | [13 empty] | 0 | 975751.11 | [13 empty] | 0 | 975751.11 | [13 empty] | 0 | 975751.11
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 24947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 483257 | 0 | 0 | 0 | 483257 | 508204 | 0 | 140867 | 0 | 0 | 201230 | 0 | 2522.32 | 158765 | 0 | 3514.79 | 0 | 0 | 0 | 506899.11 | 1015103.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1015103.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1015103.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1015103.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1015103.11
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [5 empty] | 13500 | [7 empty] | 13500 | 13500 | [13 empty] | 0 | 13500 | [13 empty] | 0 | 13500 | [13 empty] | 0 | 13500 | [13 empty] | 0 | 13500
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13500 | 13500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13500
|  |  |  | 73279 | [11 empty] | 84458 | 84458 | 157737 | 8020 | 5101 |  | 8248 | 7859 | 3568.75 | 15487.2 | 26881 | 8410 |  |  |  |  | 83574.95 | 241311.95 | [13 empty] | 0 | 241311.95 | [13 empty] | 0 | 241311.95 | [13 empty] | 0 | 241311.95 | [13 empty] | 0 | 241311.95
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 73279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84458 | 84458 | 157737 | 8020 | 5101 | 0 | 8248 | 7859 | 3568.75 | 15487.2 | 26881 | 8410 | 0 | 0 | 0 | 0 | 83574.95 | 241311.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241311.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241311.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241311.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241311.95
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 35660 | 2450 | 2256 | 4914 | 8540 | 3570 | 3296 |  | 6440 | 6915 | 6020 | 12390 | -376 | 56415 | 92075 | 3990 | 2380 | 3978 | 3780 | 6930 | 6090 | 57896.43 | 0 | [5 empty] | 85044.43 | 177119.43 | [13 empty] | 0 | 177119.43 | [13 empty] | 0 | 177119.43 | [13 empty] | 0 | 177119.43 | [13 empty] | 0 | 177119.43
[17 empty] | 0 | 0 | [5 empty] | 26188 |  | 414251.25 | 13550 |  | 1582420.35 |  |  | 2036409.6 | 2036409.6 | [10 empty] | 1101039.75 |  |  | 1101039.75 | 3137449.35 | [13 empty] | 0 | 3137449.35 | [13 empty] | 0 | 3137449.35 | [13 empty] | 0 | 3137449.35
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 35660 | 2450 | 2256 | 4914 | 8540 | 3570 | 3296 | 0 | 6440 | 6915 | 6020 | 12390 | -376 | 56415 | 92075 | 3990 | 2380 | 3978 | 3780 | 6930 | 32278 | 57896.43 | 414251.25 | 13550 | 0 | 1582420.35 | 0 | 0 | 2121454.03 | 2213529.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1101039.75 | 0 | 0 | 1101039.75 | 3314568.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3314568.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3314568.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3314568.78
[13 empty] | 734024 |  |  |  | 734024 | 734024 | 177636 |  | 1544751 |  | 1387955 | 1470172 | 2043539.12 | 3080644.39 | [5 empty] | 9704697.51 | 10438721.51 | [13 empty] | 0 | 10438721.51 | [13 empty] | 0 | 10438721.51 | [13 empty] | 0 | 10438721.51 | [13 empty] | 0 | 10438721.51
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 734024 | 0 | 0 | 0 | 734024 | 734024 | 177636 | 0 | 1544751 | 0 | 1387955 | 1470172 | 2043539.12 | 3080644.39 | 0 | 0 | 0 | 0 | 0 | 9704697.51 | 10438721.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10438721.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10438721.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10438721.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10438721.51
|  |  |  | 21485 |  | 10350 | 2640.5 |  |  |  | 18396 | 8032.1 | 2128.8 | 820373 | 20713 | 119175 | 1001808.4 | 1023293.4 | 24523 | 31214 | 47737 | 13764 |  | 94835 | 19081 | 4125 | [5 empty] | 235279 | 1258572.4 | [13 empty] | 0 | 1258572.4 | [13 empty] | 0 | 1258572.4 | [13 empty] | 0 | 1258572.4 | [13 empty] | 0 | 1258572.4
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 21485 | 0 | 10350 | 2640.5 | 0 | 0 | 0 | 18396 | 8032.1 | 2128.8 | 820373 | 20713 | 119175 | 1001808.4 | 1023293.4 | 24523 | 31214 | 47737 | 13764 | 0 | 94835 | 19081 | 4125 | 0 | 0 | 0 | 0 | 0 | 235279 | 1258572.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258572.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258572.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258572.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258572.4
|  |  |  | 21485 | 0 | 10350 | 2640.5 | 0 | 0 | 0 | 18396 | 8032.1 | 736152.8 | 820373 | 20713 | 119175 | 1735832.4 | 1757317.4 | 202159 | 31214 | 1592488 | 13764 | 1387955 | 1565007 | 2062620.12 | 3084769.39 | 0 | 0 | 0 | 0 | 0 | 9939976.51 | 11697293.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11697293.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11697293.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11697293.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11697293.91
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | 2191983.0248 | 977462.0248 | 900337.0248 | 900337.0248 | 850337.0248 | 1054337.0248 | 362798.5633 | 462798.5633 | 312798.5633 | 262798.5633 | 362798.5633 | 462798.5633 | 262798.5633 | 9364383.092 | 9364383.092 | 557131.3044 | [12 empty] | 557131.3044 | 9921514.3963
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2191983.0248 | 977462.0248 | 900337.0248 | 900337.0248 | 850337.0248 | 1054337.0248 | 362798.5633 | 462798.5633 | 312798.5633 | 262798.5633 | 362798.5633 | 462798.5633 | 262798.5633 | 9364383.092 | 9364383.092 | 557131.3044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 557131.3044 | 9921514.3963
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 |  |  |  |  | 6250 |  | 2650 |  |  |  | 3100 |  |  | 12000 | 12000 | [13 empty] | 0 | 12000 | [13 empty] | 0 | 12000 | [13 empty] | 0 | 12000 | [13 empty] | 0 | 12000
[17 empty] | 0 | 0 |  |  |  |  | 25820 |  | 25821 | 25820 |  |  | 0 |  |  | 77461 | 77461 | [13 empty] | 0 | 77461 | [13 empty] | 0 | 77461 | [13 empty] | 0 | 77461 | [13 empty] | 0 | 77461
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32070 | 0 | 28471 | 25820 | 0 | 0 | 3100 | 0 | 0 | 89461 | 89461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89461
[17 empty] | 0 | 0 |  | 133000 | [11 empty] | 133000 | 133000 | [13 empty] | 0 | 133000 | [13 empty] | 0 | 133000 | [13 empty] | 0 | 133000 | [13 empty] | 0 | 133000
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 |  |  | 1767366 | [10 empty] | 1767366 | 1767366 | [13 empty] | 0 | 1767366 | [13 empty] | 0 | 1767366 | [13 empty] | 0 | 1767366 | [13 empty] | 0 | 1767366
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133000 | 1767366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900366 | 1900366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900366
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133000 | 1767366 | 0 | 32070 | 0 | 28471 | 25820 | 0 | 0 | 3100 | 0 | 0 | 1989827 | 1989827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1989827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1989827 | 2191983.0248 | 977462.0248 | 900337.0248 | 900337.0248 | 850337.0248 | 1054337.0248 | 362798.5633 | 462798.5633 | 312798.5633 | 262798.5633 | 362798.5633 | 462798.5633 | 262798.5633 | 9364383.092 | 11354210.092 | 557131.3044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 557131.3044 | 11911341.3963
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 20762.74 | 5000 | 5000 | 26737 | 69 | 35000 | 12885 | 10000 | 10000 | 10000 | 10000 | -19056 | 11385 | 117020 | 137782.74 | 6703 | 649 | 6456 | [6 empty] | 0 |  |  |  | 13808 | 151590.74 | [13 empty] | 0 | 151590.74 | [13 empty] | 0 | 151590.74 | [13 empty] | 0 | 151590.74 | [13 empty] | 0 | 151590.74
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
[17 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0 | [13 empty] | 0 | 0
|  |  |  | 20762.74 | 5000 | 5000 | 26737 | 69 | 35000 | 12885 | 10000 | 10000 | 10000 | 10000 | -19056 | 11385 | 117020 | 137782.74 | 6703 | 649 | 6456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13808 | 151590.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151590.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151590.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151590.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151590.74
|  |  |  | 9648057.5 | 573443.3535 | 776127.4094 | 3514282.395 | 615223.2608 | 548385.435 | 1136837.2392 | 1124881.15 | 1039324.69 | 2693250.36 | 2103154.28 | 4469914.07 | 5541793.9 | 23878175.5429 | 33526233.0429 | 2118760.87 | 1965076.14 | 5229205.06 | 1576809.5 | 2770061.16 | 3357489.75 | 4980098.8 | 5267937.26 | 775876.39 | 360427.94 | 3829374.35 | 0 | 0 | 32231117.22 | 65757350.2629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1101039.75 | 0 | 0 | 1101039.75 | 66858390.0129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66858390.0129 | 2191983.0248 | 977462.0248 | 900337.0248 | 900337.0248 | 850337.0248 | 1054337.0248 | 362798.5633 | 462798.5633 | 312798.5633 | 262798.5633 | 362798.5633 | 462798.5633 | 262798.5633 | 9364383.092 | 76222773.1049 | 557131.3044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 557131.3044 | 76779904.4093
|  |  |  | 9648057.5 | 10221500.8535 | 10997628.2628 | 14511910.6578 | 15127133.9187 | 15675519.3537 | 16812356.5929 | 17937237.7429 | 18976562.4329 | 21669812.7929 | 23772967.0729 | 28242881.1429 | 33784675.0429 | 33462815.0429 | 28591846.0429 | 35581575.9129 | 37546652.0529 | 42775857.1129 | 44352666.6129 | 47122727.7729 | 50480217.5229 | 55460316.3229 | 60728253.5829 | 61504129.9729 | 61864557.9129 | 65693932.2629 | 65693932.2629 | 65693932.2629 | 65693932.2629 | 57873774.2629 | 65693932.2629 | 65693932.2629 | 65693932.2629 | 65693932.2629 | 65693932.2629 | 65693932.2629 | 65693932.2629 | 65693932.2629 | 65693932.2629 | 65693932.2629 | 66794972.0129 | 66794972.0129 | 66794972.0129 | 66794972.0129 | 58974814.0129 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  |  | 1456288.59 | 1619140.6683 | 1781992.7465 | 1997107.7465 | 2258473.7465 | 2514674.5611 | 2784623.755 | 3054623.755 | 3324623.755 | 3660026.755 | 3855147.755 | 4263718.755 | 4807626.755 | 4807626.755 | 4807626.755 | 5202650.4636 | 5609604.4636 | 6034791.4636 | 6464601.4636 | 6894411.4636 | 7343700.4636 | 7846536.4636 | 8336573.4636 | 8826610.4636 | 9316647.4636 | 9765441.4636 | 10211330.4636 | 10657219.4636 | 10657219.4636 | 10657219.4636 | 11040202.1548 | 11423184.846 | 11806167.5372 | 12189150.2284 | 12572132.9196 | 12965818.6108 | 13356789.302 | 13705326.9932 | 14053864.6844 | 14388037.3756 | 14722210.0668 | 15056382.758 | 15390555.4492 | 15390555.4492 | 15390555.4492 | 15711397.5952 | 16032239.7412 | 16353081.8872 | 16673924.0332 | 16994766.1792 | 17315608.3252 | 17635648.4712 | 17955688.6172 | 18284909.7632 | 18608888.9092 | 18932868.0552 | 19256847.2012 | 19580826.3472 | 19580826.3472 | 19580826.3472 | 19868007.3436 | 20155188.34 | 20442369.3364 | 20729550.3328 | 21016731.3292 | 21303912.3256 | 21610598.322 | 21917284.3184 | 22223970.3148 | 22530656.3112 | 22837342.3076 | 23144028.304 | 23450714.3004 | 23450714.3004 | 23450714.3004 | 23821645.6568 | 24181284.0132 | 24536129.3696 | 24859300.726 | 25170078.0824 | 25480855.4388 | 25568170.7952 | 25633690.1516 | 25699209.508 | 25764728.8644 | 25830248.2208 | 25895767.5772 | 25961286.9336 | 25961286.9336 | 25961286.9336
|  |  |  | 38611.75 | 38611.75 | 38611.75 | 38611.75 | 38611.75 | 38611.75 | 46986.75 | 46986.75 | 46986.75 | 46986.75 | 93337.75 | 116012.75 | 141937.75 | 141937.75 | 141937.75 | 198604.4167 | 198604.4167 | 198604.4167 | 208907.4167 | 219210.4167 | 229513.4167 | 239816.4167 | 250119.4167 | 262482.4167 | 274845.4167 | 287208.4167 | 299571.4167 | 311937.4167 | 311937.4167 | 311937.4167 | 347637.4167 | 347637.4167 | 347637.4167 | 347637.4167 | 347637.4167 | 347637.4167 | 347637.4167 | 347637.4167 | 347637.4167 | 347637.4167 | 347637.4167 | 347637.4167 | 347637.4167 | 347637.4167 | 347637.4167 | 385122.4167 | 385122.4167 | 385122.4167 | 385122.4167 | 385122.4167 | 385122.4167 | 385122.4167 | 385122.4167 | 385122.4167 | 385122.4167 | 385122.4167 | 385122.4167 | 385122.4167 | 385122.4167 | 385122.4167 | 424481.6667 | 424481.6667 | 424481.6667 | 424481.6667 | 424481.6667 | 424481.6667 | 424481.6667 | 424481.6667 | 424481.6667 | 424481.6667 | 424481.6667 | 424481.6667 | 424481.6667 | 424481.6667 | 424481.6667 | 465808.6167 | 465808.6167 | 465808.6167 | 465808.6167 | 465808.6167 | 465808.6167 | 465808.6167 | 465808.6167 | 465808.6167 | 465808.6167 | 465808.6167 | 465808.6167 | 465808.6167 | 465808.6167 | 465808.6167
|  |  |  | 25629.24 | 28629.24 | 31629.24 | 40512.24 | 46688.24 | 51688.24 | 58184.24 | 50070.24 | 60070.24 | 65070.24 | 65070.24 | 65887.24 | 71772.24 | 71772.24 | 71772.24 | 76576.11 | 81236.08 | 86012.27 | 90733.11 | 95426.27 | 100203.24 | 105001.18 | 109795.91 | 114647.05 | 119393.76 | 124202.62 | 129306.14 | 134422.24 | 134422.24 | 134422.24 | 139433.3169 | 144444.3938 | 149455.4708 | 154466.5477 | 159477.6246 | 164488.7015 | 169499.7785 | 174510.8554 | 179521.9323 | 184533.0092 | 189544.0862 | 194555.1631 | 199566.24 | 199566.24 | 199566.24 | 204781.8554 | 209997.4708 | 215213.0862 | 220428.7015 | 225644.3169 | 230859.9323 | 236075.5477 | 241291.1631 | 246506.7785 | 251722.3938 | 256938.0092 | 262153.6246 | 267369.24 | 267369.24 | 267369.24 | 272798.7015 | 278228.1631 | 283657.6246 | 289087.0862 | 294516.5477 | 299946.0092 | 305375.4708 | 310804.9323 | 316234.3938 | 321663.8554 | 327093.3169 | 332522.7785 | 337952.24 | 337952.24 | 337952.24 | 340967.74 | 343983.24 | 346998.74 | 350014.24 | 353029.74 | 356045.24 | 356045.24 | 356045.24 | 356045.24 | 356045.24 | 356045.24 | 356045.24 | 356045.24 | 356045.24 | 356045.24
|  |  |  | 910013.9336 | 985312.7279 | 1059022.9109 | 1175770.9109 | 1364361.9109 | 1515170.9109 | 1665979.9109 | 1829165.9109 | 1979974.9109 | 2130783.9109 | 2359406.9109 | 2510215.9109 | 2606215.9109 | 2606215.9109 | 2606215.9109 | 2762821.3725 | 2925274.3725 | 3085734.3725 | 3242339.834 | 3398945.2955 | 3555550.7571 | 3712156.2186 | 3868761.6801 | 4025367.1417 | 4181972.6032 | 4338578.0648 | 4495183.5263 | 4651788.9878 | 4651788.9878 | 4651788.9878 | 4678350.5264 | 4704912.0649 | 4731473.6035 | 4758035.142 | 4784596.6805 | 4811158.2191 | 4837719.7576 | 4864281.2961 | 4890842.8347 | 4917404.3732 | 4943965.9118 | 4970527.4503 | 4997088.9888 | 4997088.9888 | 4997088.9888 | 5024978.6043 | 5052868.2197 | 5080757.8351 | 5108647.4505 | 5136537.066 | 5164426.6814 | 5192316.2968 | 5220205.9122 | 5248095.5276 | 5275985.1431 | 5303874.7585 | 5331764.3739 | 5359653.9893 | 5359653.9893 | 5359653.9893 | 5388938.0856 | 5418222.1818 | 5447506.2781 | 5476790.3743 | 5506074.4706 | 5535358.5668 | 5564642.6631 | 5593926.7593 | 5623210.8556 | 5652494.9518 | 5681779.048 | 5711063.1443 | 5740347.2405 | 5740347.2405 | 5740347.2405 | 5771095.5415 | 5801843.8425 | 5832592.1435 | 5863340.4444 | 5894088.7454 | 5924837.0464 | 5955585.3474 | 5986333.6484 | 6017081.9493 | 6047830.2503 | 6078578.5513 | 6109326.8523 | 6140075.1532 | 6140075.1532 | 6140075.1532
|  |  |  | 214591.66 | 521591.66 | 611591.66 | 618591.66 | 625591.66 | 632591.66 | 639591.66 | 646591.66 | 653591.66 | 660591.66 | 667591.66 | 702782.66 | 775978.66 | 775978.66 | 775978.66 | 810372.2754 | 856463.2754 | 1220247.8908 | 1509917.5062 | 1533302.1215 | 1556686.7369 | 1580071.3523 | 1603455.9677 | 1626840.5831 | 1650225.1985 | 1673609.8138 | 1696994.4292 | 1720379.0446 | 1720379.0446 | 1720379.0446 | 1747961.7369 | 1775544.4292 | 1803127.1215 | 1830709.8138 | 1858292.5062 | 1885875.1985 | 1913457.8908 | 1941040.5831 | 1968623.2754 | 1996205.9677 | 2023788.66 | 2051371.3523 | 2078954.0446 | 2078954.0446 | 2078954.0446 | 2105626.0446 | 2132298.0446 | 2158970.0446 | 2185642.0446 | 2212314.0446 | 2238986.0446 | 2265658.0446 | 2292330.0446 | 2319002.0446 | 2345674.0446 | 2372346.0446 | 2399018.0446 | 2425690.0446 | 2425690.0446 | 2425690.0446 | 2453695.66 | 2481701.2754 | 2509706.8908 | 2537712.5062 | 2565718.1215 | 2593723.7369 | 2621729.3523 | 2649734.9677 | 2677740.5831 | 2705746.1985 | 2733751.8138 | 2761757.4292 | 2789763.0446 | 2789763.0446 | 2789763.0446 | 2824527.1215 | 2859291.1985 | 2894055.2754 | 2928819.3523 | 2963583.4292 | 2998347.5062 | 3033111.5831 | 3067875.66 | 3102639.7369 | 3137403.8138 | 3172167.8908 | 3206931.9677 | 3241696.0446 | 3241696.0446 | 3241696.0446
|  |  |  | 29174 | 49174 | 69174 | 89174 | 109174 | 129174 | 149423 | 169174 | 189174 | 209174 | 229174 | 249174 | 289808 | 289808 | 289808 | 357255 | 402369 | 447483 | 492597 | 537711 | 582825 | 627939 | 673053 | 718167 | 763281 | 808395 | 853509 | 898623 | 898623 | 898623 | 921061.2232 | 943499.4463 | 965937.6695 | 988375.8927 | 1010814.1158 | 1033252.339 | 1055690.5622 | 1078128.7854 | 1100567.0085 | 1123005.2317 | 1145443.4549 | 1167881.678 | 1190319.9012 | 1190319.9012 | 1190319.9012 | 1213189.747 | 1236059.5928 | 1258929.4385 | 1281799.2843 | 1304669.1301 | 1327538.9759 | 1350408.8216 | 1373278.6674 | 1396148.5132 | 1419018.359 | 1441888.2047 | 1464758.0505 | 1487627.8963 | 1487627.8963 | 1487627.8963 | 1510950.946 | 1534273.9957 | 1557597.0454 | 1580920.095 | 1604243.1447 | 1627566.1944 | 1650889.2441 | 1674212.2938 | 1697535.3435 | 1720858.3931 | 1744181.4428 | 1767504.4925 | 1790827.5422 | 1790827.5422 | 1790827.5422 | 1827885.2251 | 1864942.908 | 1902000.5909 | 1939058.2739 | 1976115.9568 | 2013173.6397 | 2050231.3226 | 2087289.0055 | 2124346.6884 | 2161404.3714 | 2198462.0543 | 2235519.7372 | 2272577.4201 | 2272577.4201 | 2272577.4201
|  |  |  | 0 | -13000 | -17000 | -21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 85542 | 135542 | 185542 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804
|  |  |  | 0 | 4000 | 8000 | 9323 | 13323 | 17323 | 21448 | 25448 | 29448 | 33448 | 19341 | 21341 | 19595 | 19595 | 19595 | 22671.9231 | 22671.9231 | 22671.9231 | 26027.8462 | 29383.7692 | 32739.6923 | 36095.6154 | 39451.5385 | 42807.4615 | 46163.3846 | 49519.3077 | 52875.2308 | 56239.1538 | 56239.1538 | 56239.1538 | 59469.9231 | 62700.6923 | 65931.4615 | 69162.2308 | 72393 | 75623.7692 | 78854.5385 | 82085.3077 | 85316.0769 | 88546.8462 | 91777.6154 | 95008.3846 | 98239.1538 | 98239.1538 | 98239.1538 | 101631.4615 | 105023.7692 | 108416.0769 | 111808.3846 | 115200.6923 | 118593 | 121985.3077 | 125377.6154 | 128769.9231 | 132162.2308 | 135554.5385 | 138946.8462 | 142339.1538 | 142339.1538 | 142339.1538 | 145901.0769 | 149463 | 153024.9231 | 156586.8462 | 160148.7692 | 163710.6923 | 167272.6154 | 170834.5385 | 174396.4615 | 177958.3846 | 181520.3077 | 185082.2308 | 188644.1538 | 188644.1538 | 188644.1538 | 193365.923 | 198087.6923 | 202809.4615 | 207531.2307 | 212253 | 216974.7692 | 221696.5384 | 226418.3077 | 231140.0769 | 235861.8461 | 240583.6154 | 245305.3846 | 250027.1538 | 250027.1538 | 250027.1538
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23344 | 46688 | 68276 | 63086 | 69885 | 69885 | 69885 | 69885 | 69885 | 69885 | 69885 | 69885 | 69885 | 69885 | 69885 | 81114 | 91353 | 91353 | 91353 | 91353 | 91353 | 91353 | 91353 | 93086.9231 | 94820.8462 | 96554.7692 | 98288.6923 | 100022.6154 | 101756.5385 | 103490.4615 | 105224.3846 | 106958.3077 | 108692.2308 | 110426.1538 | 112160.0769 | 113894 | 113894 | 113894 | 115714.6154 | 117535.2308 | 119355.8462 | 121176.4615 | 122997.0769 | 124817.6923 | 126638.3077 | 128458.9231 | 130279.5385 | 132100.1538 | 133920.7692 | 135741.3846 | 137562 | 137562 | 137562 | 139473.6923 | 141385.3846 | 143297.0769 | 145208.7692 | 147120.4615 | 149032.1538 | 150943.8462 | 152855.5385 | 154767.2308 | 156678.9231 | 158590.6154 | 160502.3077 | 162414 | 162414 | 162414 | 164948.1538 | 167482.3077 | 170016.4615 | 172550.6154 | 175084.7692 | 177618.9231 | 180153.0769 | 182687.2308 | 185221.3846 | 187755.5385 | 190289.6923 | 192823.8462 | 195358 | 195358 | 195358
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5011.0769 | 10022.1538 | 15033.2308 | 20044.3077 | 25055.3846 | 30066.4615 | 35077.5385 | 40088.6154 | 45099.6923 | 50110.7692 | 55121.8462 | 60132.9231 | 65144 | 65144 | 65144 | 70110.2308 | 75076.4615 | 80042.6923 | 85008.9231 | 89975.1538 | 94941.3846 | 99907.6154 | 104873.8462 | 109840.0769 | 114806.3077 | 119772.5385 | 124738.7692 | 129705 | 129705 | 129705 | 134641.6154 | 139578.2308 | 144514.8462 | 149451.4615 | 154388.0769 | 159324.6923 | 164261.3077 | 169197.9231 | 174134.5385 | 179071.1538 | 184007.7692 | 188944.3846 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 1000 | 1500 | 2000 | 2500 | 3000 | 3500 | 4000 | 4500 | 4500 | 4500 | 5000 | 5500 | 6000 | 6500 | 7000 | 7500 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 2759851.1736 | 3369002.0461 | 3768564.3074 | 4144895.3074 | 4653028.3074 | 5096038.122 | 5563041.3159 | 6042208.3159 | 6527361.3159 | 7071161.3159 | 7548959.3159 | 8195821.3159 | 8979623.3159 | 8979623.3159 | 8979623.3159 | 9697640.5612 | 10362912.5312 | 11362234.3366 | 12301813.1766 | 12975579.3366 | 13668908.3066 | 14415805.2466 | 15161128.9766 | 15907579.1166 | 16643685.8266 | 17338611.6866 | 18030927.2066 | 18723266.3066 | 18723266.3066 | 18723266.3066 | 19234018.298 | 19709070.2893 | 20184122.2807 | 20659174.2721 | 21134226.2634 | 21619981.2548 | 22103021.2462 | 22543128.2375 | 22983235.2289 | 23408977.2203 | 23834719.2117 | 24260461.203 | 24686203.1944 | 24686203.1944 | 24686203.1944 | 25137356.5708 | 25551024.9473 | 25964693.3237 | 26378361.7001 | 26792030.0765 | 27205698.453 | 27618564.8294 | 28031431.2058 | 28453478.5823 | 28870283.9587 | 29287089.3351 | 29703894.7116 | 30120700.088 | 30120700.088 | 30120700.088 | 30543692.788 | 30927326.238 | 31310959.6881 | 31694593.1381 | 32078226.5881 | 32461860.0381 | 32864998.4882 | 33268136.9382 | 33671275.3882 | 34074413.8382 | 34477552.2882 | 34880690.7383 | 35283829.1883 | 35283829.1883 | 35283829.1883 | 35808928.9786 | 36281408.8188 | 36749095.6591 | 37185108.4994 | 37608727.3397 | 38032346.18 | 38229487.5203 | 38404832.8606 | 38580178.2009 | 38755523.5412 | 38930868.8815 | 39106214.2218 | 39281559.5621 | 39281559.5621 | 39281559.5621
|  |  |  | 386879.57 | 416879.57 | 446879.57 | 444218.57 | 494218.57 | 544218.57 | 594218.57 | 624418.57 | 654618.57 | 684818.57 | 715018.57 | 745218.57 | 775418.57 | 775418.57 | 775418.57 | 810945.57 | 846472.57 | 881999.57 | 909199.57 | 934968.57 | 961968.57 | 991968.57 | 1028724.57 | 1068088.57 | 1107452.57 | 1146816.57 | 1186180.57 | 1238194.57 | 1238194.57 | 1238194.57 | 1280292.04 | 1324374.25 | 1369344.37 | 1416106.25 | 1470301.25 | 1524496.25 | 1582230.25 | 1642377.25 | 1702524.25 | 1762671.25 | 1836324.25 | 1923779.25 | 2011234.25 | 2011234.25 | 2011234.25 | 2104235.25 | 2197236.25 | 2290237.25 | 2387888.25 | 2485539.25 | 2583190.25 | 2671588.25 | 2759986.25 | 2848384.25 | 2936782.25 | 3025180.25 | 3119274.25 | 3213368.25 | 3213368.25 | 3213368.25 | 3337995.25 | 3532972.25 | 3837851.25 | 4202860.25 | 4610615.25 | 5080546.25 | 5593223.25 | 6167881.25 | 6790628.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 386879.57 | 416879.57 | 446879.57 | 444218.57 | 494218.57 | 544218.57 | 594218.57 | 624418.57 | 654618.57 | 684818.57 | 715018.57 | 745218.57 | 775418.57 | 775418.57 | 775418.57 | 810945.57 | 846472.57 | 881999.57 | 909199.57 | 934968.57 | 961968.57 | 991968.57 | 1028724.57 | 1068088.57 | 1107452.57 | 1146816.57 | 1186180.57 | 1238194.57 | 1238194.57 | 1238194.57 | 1280292.04 | 1324374.25 | 1369344.37 | 1416106.25 | 1470301.25 | 1524496.25 | 1582230.25 | 1642377.25 | 1702524.25 | 1762671.25 | 1836324.25 | 1923779.25 | 2011234.25 | 2011234.25 | 2011234.25 | 2104235.25 | 2197236.25 | 2290237.25 | 2387888.25 | 2485539.25 | 2583190.25 | 2671588.25 | 2759986.25 | 2848384.25 | 2936782.25 | 3025180.25 | 3119274.25 | 3213368.25 | 3213368.25 | 3213368.25 | 3337995.25 | 3532972.25 | 3837851.25 | 4202860.25 | 4610615.25 | 5080546.25 | 5593223.25 | 6167881.25 | 6790628.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25
|  |  |  | 76499.47 | 76499.47 | 78414.47 | 81060.47 | 81087.47 | 81087.47 | 81458.47 | 81458.47 | 82654.47 | 82881.47 | 82961.47 | 87961.47 | 87961.47 | 87961.47 | 87961.47 | 87961.47 | 88058.23 | 88058.23 | 88058.23 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72 | 93344.72
|  |  |  | 29835.86 | 29835.86 | 29835.86 | 29835.86 | 29835.86 | 29835.86 | 29835.86 | 29835.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 354360.76 | 361360.76 | 392445.76 | 451713.76 | 530317.76 | 535317.76 | 567496.76 | 572496.76 | 602424.76 | 610196.76 | 610701.76 | 611701.76 | 620580.76 | 620580.76 | 620580.76 | 623580.76 | 628926.63 | 631659.15 | 642814.99 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 645191.71
|  |  |  | 48665.11 | 48665.11 | 50457.11 | 52034.11 | 58717.11 | 61217.11 | 65732.11 | 66232.11 | 66048.11 | 74307.11 | 72328.11 | 74328.11 | 73386.11 | 73386.11 | 73386.11 | 74886.11 | 77308.15 | 78007.34 | 79757.34 | 80313.82 | 82313.82 | 84313.82 | 87313.82 | 87313.82 | 87313.82 | 87313.82 | 87313.82 | 87313.82 | 87313.82 | 87313.82 | 87700.35 | 88105.11 | 88518.02 | 88927.63 | 89334.08 | 89746.82 | 90163.27 | 90578.15 | 90999.88 | 91411.23 | 91825.81 | 92284.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81 | 92743.81
|  |  |  | 27275.32 | 27275.32 | 27275.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32
|  |  |  | 141282.71 | 206282.71 | 243665.71 | 248448.71 | 271433.71 | 326433.71 | 382338.71 | 437338.71 | 486530.71 | 511474.71 | 532514.71 | 592514.71 | 636915.71 | 636915.71 | 636915.71 | 674615.71 | 675797.79 | 686117.61 | 697867.61 | 707526.1 | 727526.1 | 737526.1 | 747526.1 | 757526.1 | 757526.1 | 767526.1 | 767526.1 | 767526.1 | 767526.1 | 767526.1 | 769449.1 | 771372.1 | 773295.1 | 775218.1 | 777141.1 | 779064.1 | 780987.1 | 782910.1 | 784833.1 | 786756.1 | 788679.1 | 790602.1 | 792526.1 | 792526.1 | 792526.1 | 793296.1 | 794066.1 | 794836.1 | 795606.1 | 796376.1 | 797146.1 | 797916.1 | 798686.1 | 799456.1 | 800226.1 | 800996.1 | 801766.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1 | 802526.1
|  |  |  | 142160.42 | 182160.42 | 203249.42 | 216259.42 | 234847.42 | 239847.42 | 256328.42 | 286328.42 | 300722.42 | 334265.42 | 321229.42 | 351229.42 | 334252.42 | 334252.42 | 334252.42 | 370107.42 | 389043 | 412925.18 | 419220.18 | 431986.1 | 431986.1 | 431986.1 | 435286.1 | 438586.1 | 439186.1 | 439786.1 | 440386.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1 | 440986.1
|  |  |  | 1009.5 | 1009.5 | 1104.5 | 1255.5 | 1309.5 | 3809.5 | 3941.5 | 4441.5 | 1961.5 | 2461.5 | 2461.5 | 3461.5 | 2461.5 | 2461.5 | 2461.5 | 9961.5 | 3461.5 | 3396.75 | 3596.75 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558 | 3558
|  |  |  | 5328.44 | 5828.44 | 5828.44 | 7669.44 | 11110.44 | 13110.44 | 13757.44 | 14257.44 | 18976.44 | 20245.44 | 20926.44 | 22926.44 | 22482.44 | 22482.44 | 22482.44 | 27482.44 | 23321.07 | 23014.57 | 23014.57 | 24014.57 | 25014.57 | 26014.57 | 28014.57 | 29514.57 | 31514.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57 | 33014.57
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 623 | 5144 | 7358 | 17358 | 25379 | 35379 | 21658 | 14462 | 18876 | 21376 | 36053 | 36053 | 36053 | 46053 | 52699.75 | 61811.29 | 62327.79 | 67164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57 | 69164.57
|  |  |  | 9163.01 | 9663.01 | 10249.01 | 13580.01 | 13832.01 | 15832.01 | 18894.01 | 19894.01 | 17695.01 | 15257.01 | 15257.01 | 15757.01 | 15257.01 | 15257.01 | 15257.01 | 15257.01 | 15257.01 | 15257.01 | 15507.01 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 15469.86
|  |  |  | 2413.16 | 4613.16 | 7373.16 | 7507.16 | 7507.16 | 8507.16 | 11907.16 | 12907.16 | 16924.16 | 19561.16 | 21045.16 | 22045.16 | 24770.16 | 24770.16 | 24770.16 | 27770.16 | 24770.16 | 26770.16 | 28370.16 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 28338.27
|  |  |  | 0 | 500 | 1345 | 2121 | 2485 | 6985 | 8927 | 10427 | 5626 | 5626 | 5626 | 6626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626
|  |  |  | 0 | 0 | 0 | 0 | 701 | 2701 | 2701 | 4701 | 4500 | 8983 | 16078 | 20078 | 12393 | 12393 | 12393 | 12393 | 13467.16 | 15192.79 | 15542.79 | 16672.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79 | 17172.79
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1218 | 1218 | 1218 | 1218 | 1218 | 1218 | 1218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218 | 2218
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 458319 | 468339 | 507030 | 526767 | 539913 | 554913 | 573213 | 581848 | 604928 | 596940 | 600940 | 600325 | 621659 | 621659 | 621659 | 624459 | 626887 | 628887 | 631887 | 634387 | 635887 | 639262 | 642637 | 646012 | 649387 | 652762 | 656137 | 659512 | 659512 | 659512 | 662588.9231 | 665665.8462 | 668742.7692 | 671819.6923 | 674896.6154 | 677973.5385 | 681050.4615 | 684127.3846 | 687204.3077 | 690281.2308 | 693358.1538 | 696435.0769 | 699512 | 699512 | 699512 | 702588.9231 | 705665.8462 | 708742.7692 | 711819.6923 | 714896.6154 | 717973.5385 | 721050.4615 | 724127.3846 | 727204.3077 | 730281.2308 | 733358.1538 | 736435.0769 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512 | 739512
|  |  |  | 0 | 9765 | 32418 | 33303 | 38960 | 45960 | 55084 | 69972 | 99507 | 85130 | 99130 | 106698 | 135854 | 135854 | 135854 | 138924 | 172354 | 213918.429 | 250079.6003 | 257079.6003 | 289079.6003 | 305579.6003 | 337779.6003 | 369979.6003 | 402179.6003 | 434379.6003 | 466579.6003 | 498779.6003 | 498779.6003 | 498779.6003 | 517256.7092 | 535733.8181 | 554210.927 | 572688.036 | 591165.1449 | 609642.2538 | 628119.3627 | 646596.4716 | 665073.5805 | 683550.6895 | 702027.7984 | 720504.9073 | 738982.0162 | 738982.0162 | 738982.0162 | 743843.5996 | 748705.183 | 753566.7664 | 758428.3498 | 763289.9332 | 768151.5166 | 773013.0999 | 777874.6833 | 782736.2667 | 787597.8501 | 792459.4335 | 797321.0169 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003 | 802182.6003
|  |  |  | 0 | 10270 | 28804 | 47774 | 66561 | 95561 | 116284 | 188069 | 254352 | 283216 | 332216 | 364268 | 404452 | 404452 | 404452 | 420252 | 435872 | 445872 | 460872 | 475872 | 495872 | 540872 | 585872 | 630872 | 675872 | 720872 | 765872 | 810872 | 810872 | 810872 | 821592.5385 | 832313.0769 | 843033.6154 | 853754.1538 | 864474.6923 | 875195.2308 | 885915.7692 | 896636.3077 | 907356.8462 | 918077.3846 | 928797.9231 | 939518.4615 | 950239 | 950239 | 950239 | 954639 | 959039 | 963439 | 967839 | 972239 | 976639 | 981039 | 985439 | 989839 | 994239 | 998639 | 1003039 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439 | 1007439
|  |  |  | 0 | 7266 | 13104 | 14010 | 19236 | 28236 | 42132 | 50620 | 66680 | 63546 | 74546 | 81828 | 93282 | 93282 | 93282 | 102882 | 105742 | 117742 | 123742 | 126742 | 128742 | 133217 | 137692 | 142167 | 146642 | 151117 | 155592 | 160067 | 160067 | 160067 | 165827 | 171587 | 177347 | 183107 | 188867 | 194627 | 200387 | 206147 | 211907 | 217667 | 223427 | 229187 | 234947 | 234947 | 234947 | 238787 | 242627 | 246467 | 250307 | 254147 | 257987 | 261827 | 265667 | 269507 | 273347 | 277187 | 281027 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867 | 284867
|  |  |  | 0 | 11496 | 18310 | 22888 | 32318 | 43318 | 44356 | 47454 | 52226 | 58906 | 64906 | 70274 | 72470 | 72470 | 72470 | 72470 | 81360 | 84860 | 85860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860
|  |  |  | 0 | 0 | 10296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 220 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 41465 | 83421 | 106952 | 137750 | 152150 | 152150 | 152150 | 152150 | 152150 | 152150 | 152150 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1296312.76 | 1502294.76 | 1745249.76 | 1895926.76 | 2112923.76 | 2289823.76 | 2479559.76 | 2693453.76 | 2915207.76 | 2999252.76 | 3103536.76 | 3265191.76 | 3414713.76 | 3414713.76 | 3414713.76 | 3549538.76 | 3634808.63 | 3753972.689 | 3849001.2003 | 3917004.2903 | 3998004.2903 | 4080354.2903 | 4183704.2903 | 4283554.2903 | 4371204.2903 | 4468354.2903 | 4554004.2903 | 4639654.2903 | 4639654.2903 | 4639654.2903 | 4679998.3907 | 4720360.7212 | 4760731.2017 | 4801098.3821 | 4841462.4026 | 4881832.713 | 4922206.7335 | 4962579.1839 | 5002958.4844 | 5043327.4048 | 5083699.5553 | 5124116.1258 | 5164533.6962 | 5164533.6962 | 5164533.6962 | 5181482.2027 | 5198430.7092 | 5215379.2156 | 5232327.7221 | 5249276.2286 | 5266224.735 | 5283173.2415 | 5300121.748 | 5317070.2544 | 5334018.7609 | 5350967.2674 | 5367915.7738 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803 | 5384854.2803
|  |  |  | 3110000 | 3415000 | 4629000 | 6413000 | 7192659 | 7906532 | 8836807 | 9698016 | 10611984 | 11436984 | 12286984 | 13846816 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 393551 | 787102 | 1168099 | 1426653 | 1561653 | 1199153 | 519768 | 714227 | 953477 | 1192727 | 1215727 | 1238727 | 1261727 | 1261727 | 1261727 | 3209727 | 3232727 | 3255727 | 3278727 | 3301727 | 3324727 | 3347727 | 3370727 | 3393727 | 3416727 | 3439727 | 3462727 | 3486727 | 3486727 | 3486727 | 3509727 | 3532727 | 3555727 | 3578727 | 3601727 | 3624727 | 3647727 | 3670727 | 3693727 | 3716727 | 3739727 | 3762727 | 3786727 | 3786727 | 3786727 | 3809727 | 3832727 | 3855727 | 3878727 | 3901727 | 3924727 | 3947727 | 3970727 | 3993727 | 4016727 | 4039727 | 4062727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1252075.1604 | 1252075.1604 | 1252075.1604 | 1529259.8126 | 1925120.1088 | 2305704.4246 | 2639434.1393 | 1590765.345 | 1708434.17 | 2299514.0222 | 2471767.8411 | 2487936.1244 | 2535895.6193 | 2630960.1867 | 2735442.3756 | 2838624.7552 | 2838624.7552 | 2838624.7552 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463 | 2910605.5463
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175977.52 | 175977.52 | 175977.52 | 202270.8639 | 236735.0661 | 240021.9746 | 241423.7444 | 238113.62 | 210178.3141 | 234395.9689 | 235217.1862 | 235358.3095 | 235358.3095 | 240222.5585 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208 | 241438.6208
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 907113.5614 | 907113.5614 | 907113.5614 | 1679179.0328 | 1923668.5909 | 2061116.6823 | 2142512.8226 | 2134559.8957 | 2129877.57 | 2146808.4225 | 2169084.1535 | 2171401.6467 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446 | 2171927.2446
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1000000 | -1000000 | -1000000 | -1354446 | -1607932 | -1799731 | -1841902 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 628551.6837 | 628551.6837 | 628551.6837 | 928058.8887 | 1121410.765 | 1323567.2993 | 1398885.6251 | 1192286.9087 | 1192586.3501 | 1309232.123 | 1373657.1208 | 1419382.2707 | 1437852.5303 | 1449075.105 | 1452888.454 | 1454827.1174 | 1454827.1174 | 1454827.1174 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457 | 1455404.457
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94842.259 | 94842.259 | 94842.259 | 135165.3684 | 188577.985 | 214866.7968 | 259714.0014 | 263981.2658 | 272950.6153 | 301402.2086 | 325328.415 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219 | 330146.2219
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224954.2006 | 224954.2006 | 224954.2006 | 362569.4984 | 408970.1518 | 463635.9216 | 472481.0462 | 423586.9987 | 451618.1215 | 475447.6072 | 483662.3667 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357 | 486814.3357
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348021.3636 | 348021.3636 | 348021.3636 | 416131.8227 | 452848.2224 | 477964.799 | 515285.9982 | 539493.5746 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348
|  |  |  | 190000 | 335000 | 545000 | 635000 | 740000 | 940000 | 1150000 | 1350000 | 1390000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1490000 | 1565000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 3300000 | 3750000 | 5174000 | 7048000 | 7932659 | 8846532 | 9986807 | 11048016 | 12001984 | 12851984 | 13701984 | 15261816 | 15712486.9987 | 15712486.9987 | 15712486.9987 | 17372691.5375 | 18517452.14 | 19536197.1482 | 20335439.6272 | 19166636.8585 | 18939619.6258 | 19061389.8371 | 19547765.5681 | 19859337.3937 | 20165542.7461 | 20299694.1372 | 20432205.7374 | 20560326.7805 | 20560326.7805 | 20560326.7805 | 22580884.9111 | 22603884.9111 | 22626884.9111 | 22649884.9111 | 22672884.9111 | 22695884.9111 | 22718884.9111 | 22741884.9111 | 22764884.9111 | 22787884.9111 | 22810884.9111 | 22833884.9111 | 22857884.9111 | 22857884.9111 | 22857884.9111 | 22880884.9111 | 22903884.9111 | 22926884.9111 | 22949884.9111 | 22972884.9111 | 22995884.9111 | 23018884.9111 | 23041884.9111 | 23064884.9111 | 23087884.9111 | 23110884.9111 | 23133884.9111 | 23157884.9111 | 23157884.9111 | 23157884.9111 | 23180884.9111 | 23203884.9111 | 23226884.9111 | 23249884.9111 | 23272884.9111 | 23295884.9111 | 23318884.9111 | 23341884.9111 | 23364884.9111 | 23387884.9111 | 23485884.9111 | 23583884.9111 | 23682884.9111 | 23682884.9111 | 23682884.9111 | 23682884.9111 | 23682884.9111 | 23682884.9111 | 23682884.9111 | 23682884.9111 | 23682884.9111 | 23682884.9111 | 23682884.9111 | 23682884.9111 | 23682884.9111 | 23682884.9111 | 23682884.9111 | 23682884.9111 | 23682884.9111 | 23682884.9111
|  |  |  | 365000 | 420000 | 462000 | 476614 | 562614 | 617614 | 757614 | 937614 | 945614 | 1079770 | 1176770 | 1281770 | 1310770 | 1310770 | 1310770 | 1365770 | 1380770 | 1427770 | 1471770 | 1529770 | 1557770 | 1612770 | 1667770 | 1721770 | 1765770 | 1769770 | 1773770 | 1777770 | 1777770 | 1777770 | 1777770 | 1777770 | 1777770 | 1777770 | 1812770 | 1847770 | 1847770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1887770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1917770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1947770 | 1962770 | 1962770 | 1962770 | 1962770 | 1962770 | 1962770 | 2082770 | 2082770 | 2082770
|  |  |  | 147195.78 | 150195.78 | 160195.78 | 170195.78 | 170195.78 | 170195.78 | 170195.78 | 170195.78 | 170195.78 | 170195.78 | 170195.78 | 170195.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78
|  |  |  | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 522111.99 | 580111.99 | 632111.99 | 656725.99 | 742725.99 | 797725.99 | 937725.99 | 1117725.99 | 1125725.99 | 1259881.99 | 1356881.99 | 1461881.99 | 1486274.99 | 1486274.99 | 1486274.99 | 1541274.99 | 1556274.99 | 1603274.99 | 1647274.99 | 1705274.99 | 1733274.99 | 1788274.99 | 1843274.99 | 1897274.99 | 1941274.99 | 1945274.99 | 1949274.99 | 1953274.99 | 1953274.99 | 1953274.99 | 1953274.99 | 1953274.99 | 1953274.99 | 1953274.99 | 1988274.99 | 2023274.99 | 2023274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2063274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2093274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2123274.99 | 2138274.99 | 2138274.99 | 2138274.99 | 2138274.99 | 2138274.99 | 2138274.99 | 2258274.99 | 2258274.99 | 2258274.99
|  |  |  | 1233000 | 1513000 | 1703000 | 1943000 | 2297000 | 2488000 | 2952000 | 3419000 | 3764000 | 4165000 | 4485000 | 4815000 | 5293261 | 5293261 | 5293261 | 5507923.53 | 5701871 | 5917945 | 6474945 | 6639726 | 6883363.7003 | 7107655.5902 | 7327619.552 | 7537527.6039 | 7734159.7744 | 7912489.6863 | 8090773.9731 | 8269026.3849 | 8269026.3849 | 8269026.3849 | 8296746.3849 | 8324466.3849 | 8352186.3849 | 8379906.3849 | 8407626.3849 | 8435346.3849 | 8466736.3849 | 8482000.3849 | 8498264.3849 | 8514528.3849 | 8530792.3849 | 8547056.3849 | 8563320.3849 | 8563320.3849 | 8563320.3849 | 8580584.3849 | 8597848.3849 | 8615112.3849 | 8632376.3849 | 8649640.3849 | 8666904.3849 | 8677398.3849 | 8687892.3849 | 8698386.3849 | 8708880.3849 | 8719374.3849 | 8729868.3849 | 8740362.3849 | 8740362.3849 | 8740362.3849 | 8750856.3849 | 8761350.3849 | 8771844.3849 | 8782338.3849 | 8792832.3849 | 8803326.3849 | 8815096.3849 | 8826866.3849 | 8838636.3849 | 8850406.3849 | 8862176.3849 | 8873946.3849 | 8885716.3849 | 8885716.3849 | 8885716.3849 | 8897486.3849 | 8909256.3849 | 8921026.3849 | 8932796.3849 | 8944566.3849 | 8956336.3849 | 8956336.3849 | 8956336.3849 | 8956336.3849 | 8956336.3849 | 8956336.3849 | 8956336.3849 | 8956336.3849 | 8956336.3849 | 8956336.3849
|  |  |  | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000
|  |  |  | 0 | 0 | 0 | 3002 | 18541 | 35470 | 51454 | 70023 | 87239 | 91297 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381
|  |  |  | 0 | 0 | 40000 | 36998 | 61459 | 94530 | 128546 | 29977 | 52761 | 58703 | 117619 | 202619 | 199619 | 199619 | 199619 | 319619 | 319619 | 350173 | 416547 | 474787 | 521762 | 597948 | 674134 | 750320 | 826506 | 902692 | 978878 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068 | 1055068
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1346000 | 1626000 | 1856000 | 2096000 | 2490000 | 2731000 | 3245000 | 3632000 | 4017000 | 4428000 | 4808000 | 5223000 | 5698261 | 5698261 | 5698261 | 6032923.53 | 6226871 | 6473499 | 7096873 | 7319894 | 7610506.7003 | 7910984.5902 | 8207134.552 | 8493228.6039 | 8766046.7744 | 9020562.6863 | 9275032.9731 | 9529475.3849 | 9529475.3849 | 9529475.3849 | 9557195.3849 | 9584915.3849 | 9612635.3849 | 9640355.3849 | 9668075.3849 | 9695795.3849 | 9727185.3849 | 9742449.3849 | 9758713.3849 | 9774977.3849 | 9791241.3849 | 9807505.3849 | 9823769.3849 | 9823769.3849 | 9823769.3849 | 9841033.3849 | 9858297.3849 | 9875561.3849 | 9892825.3849 | 9910089.3849 | 9927353.3849 | 9937847.3849 | 9948341.3849 | 9958835.3849 | 9969329.3849 | 9979823.3849 | 9990317.3849 | 10000811.3849 | 10000811.3849 | 10000811.3849 | 10011305.3849 | 10021799.3849 | 10032293.3849 | 10042787.3849 | 10053281.3849 | 10063775.3849 | 10075545.3849 | 10087315.3849 | 10099085.3849 | 10110855.3849 | 10122625.3849 | 10134395.3849 | 10146165.3849 | 10146165.3849 | 10146165.3849 | 10157935.3849 | 10169705.3849 | 10181475.3849 | 10193245.3849 | 10205015.3849 | 10216785.3849 | 10216785.3849 | 10216785.3849 | 10216785.3849 | 10216785.3849 | 10216785.3849 | 10216785.3849 | 10216785.3849 | 10216785.3849 | 10216785.3849
|  |  |  | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46
|  |  |  | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76
|  |  |  | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75
|  |  |  | 0 | 0 | 0 | 22519 | 52519 | 67519 | 67519 | 87519 | 107519 | 113275 | 128275 | 138275 | 148275 | 148275 | 148275 | 181901.13 | 181901.13 | 220779.53 | 231747.71 | 231747.71 | 246668.71 | 264805.71 | 283089.71 | 301175.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 22519 | 52519 | 67519 | 67519 | 97519 | 117519 | 113275 | 128275 | 138275 | 155775 | 155775 | 155775 | 189401.13 | 189401.13 | 228279.53 | 239247.71 | 239247.71 | 254168.71 | 272305.71 | 290589.71 | 308675.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71
|  |  |  | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843
|  |  |  | 35624 | 37709 | 42709 | 41449 | 41714 | 47714 | 53714 | 47214 | 52214 | 49089 | 51089 | 54419 | 58519 | 58519 | 58519 | 67668 | 71769 | 80519 | 85019 | 91669 | 101819 | 106719 | 111619 | 118269 | 122769 | 127269 | 131769 | 136269 | 136269 | 136269 | 140474.93 | 144879.16 | 149372.1 | 153831.84 | 158258.55 | 162753.77 | 166233.23 | 168037.74 | 169872.04 | 171661.46 | 173467.01 | 175466.01 | 177465.01 | 177465.01 | 177465.01 | 179068.34 | 180816.49 | 182595.67 | 184365.2 | 186120.17 | 187900.21 | 189699.24 | 191487.05 | 193308.63 | 195082.89 | 196873.08 | 198848.23 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02 | 200901.02
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9076400 | 8332477 | 6797328 | 6797328 | 6797328 | 6797328 | 8431272 | 8431272 | 8431272 | 8431272 | 8431272 | 10110818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319935 | 292656 | 2077656 | 6589681 | 6449518 | 5976338 | 5976338 | 5976338 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 104000 | 192000 | 280000 | 368000 | 456000 | 544000 | 632000 | 632000 | 632000 | 720000 | 808000 | 896000 | 984000 | 1072000 | 1160000 | 1248000 | 1336000 | 1424000 | 1512000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 4000 | 6000 | 8000 | 10000 | 12000 | 14000 | 16000 | 18000 | 18000 | 18000 | 20000 | 22000 | 24000 | 26000 | 28000 | 30000 | 32000 | 34000 | 36000 | 38000 | 40000 | 42000 | 44000 | 44000 | 44000 | 46000 | 48000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 121648 | 123733 | 128733 | 127473 | 127738 | 133738 | 139738 | 133238 | 138238 | 135113 | 137113 | 140443 | 144543 | 144543 | 144543 | 9550027 | 8782926 | 9041527 | 13560052 | 13426539 | 12981509 | 14710353 | 14805253 | 15410892 | 15505392 | 15599892 | 17373938 | 19228438 | 19228438 | 19228438 | 19322643.93 | 19417048.16 | 19511541.1 | 19606000.84 | 19700427.55 | 19794922.77 | 19888402.23 | 19980206.74 | 20072041.04 | 20163830.46 | 20255636.01 | 20609635.01 | 20613634.01 | 20613634.01 | 20613634.01 | 20617237.34 | 20620985.49 | 20624764.67 | 20626534.2 | 20628289.17 | 20630069.21 | 20631868.24 | 20633656.05 | 20635477.63 | 20637251.89 | 20639042.08 | 20641017.23 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02 | 20643070.02
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 86876 | 105376 | 123876 | 142376 | 160876 | 175876 | 190876 | 205876 | 220876 | 235876 | 250876 | 265876 | 280876 | 280876 | 280876 | 322354.27 | 362590.1 | 379585.1 | 420349.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8 | 435849.8
|  |  |  | 0 | 2000 | 4000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000
|  |  |  | 0 | 1850 | 3700 | 5550 | 7400 | 7400 | 8900 | 11525 | 13025 | 14525 | 17468 | 17468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468
|  |  |  | 0 | 4300 | 5464 | 17311 | 20406 | 80915 | 119465 | 138684 | 256772 | 263822 | 263822 | 277372 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099
|  |  |  | 0 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 11000 | 23538 | 36076 | 48614 | 61152 | 73690 | 85613 | 98151 | 110689 | 110689 | 110689 | 123284.9 | 135880.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 6000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000
|  |  |  | 0 | 0 | 0 | 0 | 2500 | 2500 | 5000 | 5000 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 25000 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000 | 32000 | 34500 | 38000 | 41500 | 42500 | 43500 | 44500 | 44500 | 44500 | 48000 | 51500 | 55000 | 58500 | 62000 | 65500 | 69000 | 72500 | 76000 | 79500 | 83000 | 86500 | 90000 | 90000 | 90000 | 93500 | 97000 | 100500 | 104000 | 107500 | 111000 | 114500 | 118000 | 121500 | 125000 | 128500 | 132000 | 135500 | 135500 | 135500 | 139000 | 142500 | 146000 | 149500 | 153000 | 156500 | 160000 | 163500 | 167000 | 170500 | 174000 | 177500 | 181000 | 181000 | 181000 | 181000 | 181000 | 181000 | 181000 | 181000 | 181000 | 181000 | 181000 | 181000 | 181000 | 181000 | 181000 | 181000 | 181000 | 181000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 9000 | 12000 | 15000 | 18000 | 21000 | 24000 | 27000 | 27000 | 27000 | 30000 | 33000 | 36000 | 39000 | 42000 | 45000 | 48000 | 51000 | 54000 | 57000 | 60000 | 63000 | 66000 | 66000 | 66000 | 69000 | 72000 | 75000 | 78000 | 81000 | 84000 | 87000 | 90000 | 93000 | 96000 | 99000 | 102000 | 105000 | 105000 | 105000 | 108000 | 111000 | 114000 | 117000 | 120000 | 123000 | 126000 | 129000 | 132000 | 135000 | 138000 | 141000 | 144000 | 144000 | 144000 | 144000 | 144000 | 144000 | 144000 | 144000 | 144000 | 144000 | 144000 | 144000 | 144000 | 144000 | 144000 | 144000 | 144000 | 144000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1125 | 1500 | 1875 | 2250 | 2625 | 3000 | 3375 | 3375 | 3375 | 3750 | 4125 | 4500 | 4875 | 5250 | 5625 | 6000 | 6375 | 6750 | 7125 | 7500 | 7875 | 8250 | 8250 | 8250 | 8625 | 9000 | 9375 | 9750 | 10125 | 10500 | 10875 | 11250 | 11625 | 12000 | 12375 | 12750 | 13125 | 13125 | 13125 | 13500 | 13875 | 14250 | 14625 | 15000 | 15375 | 15750 | 16125 | 16500 | 16875 | 17250 | 17625 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5500 | 6000 | 6500 | 7000 | 7500 | 8000 | 8500 | 9000 | 9500 | 10000 | 10500 | 11000 | 11500 | 11500 | 11500 | 12000 | 12500 | 13000 | 13500 | 14000 | 14500 | 15000 | 15500 | 16000 | 16500 | 17000 | 17500 | 18000 | 18000 | 18000 | 18500 | 19000 | 19500 | 20000 | 20500 | 21000 | 21500 | 22000 | 22500 | 23000 | 23500 | 24000 | 24500 | 24500 | 24500 | 24500 | 24500 | 24500 | 24500 | 24500 | 24500 | 24500 | 24500 | 24500 | 24500 | 24500 | 24500 | 24500 | 24500 | 24500
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 3000 | 4000 | 5000 | 6000 | 7000 | 8000 | 9000 | 9000 | 9000 | 10875 | 12750 | 14625 | 16500 | 18375 | 20250 | 22125 | 24000 | 25875 | 27750 | 29625 | 31500 | 33375 | 33375 | 33375 | 35250 | 37125 | 39000 | 40875 | 42750 | 44625 | 46500 | 48375 | 50250 | 52125 | 54000 | 55875 | 57750 | 57750 | 57750 | 59625 | 61500 | 63375 | 65250 | 67125 | 69000 | 70875 | 72750 | 74625 | 76500 | 78375 | 80250 | 82125 | 82125 | 82125 | 82125 | 82125 | 82125 | 82125 | 82125 | 82125 | 82125 | 82125 | 82125 | 82125 | 82125 | 82125 | 82125 | 82125 | 82125
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1500 | 3500 | 5500 | 6000 | 6500 | 7000 | 7500 | 7500 | 7500 | 9500 | 11500 | 13500 | 15500 | 17500 | 19500 | 21500 | 23500 | 25500 | 27500 | 29500 | 31500 | 33500 | 33500 | 33500 | 35500 | 37500 | 39500 | 41500 | 43500 | 45500 | 47500 | 49500 | 51500 | 53500 | 55500 | 57500 | 59500 | 59500 | 59500 | 61500 | 63500 | 65500 | 67500 | 69500 | 71500 | 73500 | 75500 | 77500 | 79500 | 81500 | 83500 | 85500 | 85500 | 85500 | 85500 | 85500 | 85500 | 85500 | 85500 | 85500 | 85500 | 85500 | 85500 | 85500 | 85500 | 85500 | 85500 | 85500 | 85500
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 5000 | 6000 | 7000 | 8000 | 9000 | 10000 | 11000 | 11000 | 11000 | 12000 | 13000 | 14000 | 15000 | 16000 | 17000 | 18000 | 19000 | 20000 | 21000 | 22000 | 23000 | 24000 | 24000 | 24000 | 25000 | 26000 | 27000 | 28000 | 29000 | 30000 | 31000 | 32000 | 33000 | 34000 | 35000 | 36000 | 37000 | 37000 | 37000 | 38000 | 39000 | 40000 | 41000 | 42000 | 43000 | 44000 | 45000 | 46000 | 47000 | 48000 | 49000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 4000 | 5000 | 6500 | 7500 | 8500 | 10000 | 11000 | 11000 | 11000 | 12500 | 14000 | 15500 | 17000 | 18500 | 20000 | 21500 | 23000 | 24500 | 26000 | 27500 | 29000 | 30500 | 30500 | 30500 | 32000 | 33500 | 35000 | 36500 | 38000 | 39500 | 41000 | 42500 | 44000 | 45500 | 47000 | 48500 | 50000 | 50000 | 50000 | 51500 | 53000 | 54500 | 56000 | 57500 | 59000 | 60500 | 62000 | 63500 | 65000 | 66500 | 68000 | 69500 | 69500 | 69500 | 69500 | 69500 | 69500 | 69500 | 69500 | 69500 | 69500 | 69500 | 69500 | 69500 | 69500 | 69500 | 69500 | 69500 | 69500
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 750 | 1000 | 1250 | 1500 | 1750 | 2000 | 2250 | 2250 | 2250 | 2500 | 2750 | 3000 | 3250 | 3500 | 3750 | 4000 | 4250 | 4500 | 4750 | 5000 | 5250 | 5500 | 5500 | 5500 | 5750 | 6000 | 6250 | 6500 | 6750 | 7000 | 7250 | 7500 | 7750 | 8000 | 8250 | 8500 | 8750 | 8750 | 8750 | 9000 | 9250 | 9500 | 9750 | 10000 | 10250 | 10500 | 10750 | 11000 | 11250 | 11500 | 11750 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18125 | 30250 | 42875 | 53500 | 61625 | 70250 | 78375 | 78375 | 78375 | 92375 | 106375 | 120375 | 134375 | 148375 | 162375 | 176375 | 190375 | 204375 | 218375 | 232375 | 246375 | 260375 | 260375 | 260375 | 274375 | 288375 | 302375 | 316375 | 330375 | 344375 | 358375 | 372375 | 386375 | 400375 | 414375 | 428375 | 442375 | 442375 | 442375 | 456375 | 470375 | 484375 | 498375 | 512375 | 526375 | 540375 | 554375 | 568375 | 582375 | 596375 | 610375 | 624375 | 624375 | 624375 | 624375 | 624375 | 624375 | 624375 | 624375 | 624375 | 624375 | 624375 | 624375 | 624375 | 624375 | 624375 | 624375 | 624375 | 624375
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 86876 | 116026 | 139540 | 173737 | 210682 | 298729 | 370817 | 420199 | 573825 | 611913 | 641779 | 682867 | 755132 | 755132 | 755132 | 809206.17 | 862038 | 891629 | 932393.7 | 960393.7 | 1015143.7 | 1063893.7 | 1088143.7 | 1113393.7 | 1134643.7 | 1150893.7 | 1168143.7 | 1184393.7 | 1184393.7 | 1184393.7 | 1212393.7 | 1240393.7 | 1268393.7 | 1296393.7 | 1324393.7 | 1352393.7 | 1380393.7 | 1408393.7 | 1436393.7 | 1464393.7 | 1492393.7 | 1520393.7 | 1548393.7 | 1548393.7 | 1548393.7 | 1576393.7 | 1604393.7 | 1632393.7 | 1660393.7 | 1688393.7 | 1716393.7 | 1744393.7 | 1772393.7 | 1800393.7 | 1828393.7 | 1856393.7 | 1884393.7 | 1912393.7 | 1912393.7 | 1912393.7 | 1940393.7 | 1968393.7 | 1996393.7 | 2024393.7 | 2052393.7 | 2080393.7 | 2108393.7 | 2136393.7 | 2164393.7 | 2192393.7 | 2220393.7 | 2248393.7 | 2276393.7 | 2276393.7 | 2276393.7 | 2276393.7 | 2276393.7 | 2276393.7 | 2276393.7 | 2276393.7 | 2276393.7 | 2276393.7 | 2276393.7 | 2276393.7 | 2276393.7 | 2276393.7 | 2276393.7 | 2276393.7 | 2276393.7 | 2276393.7
|  |  |  | 19947 | 19947 | 19947 | 19947 | 19947 | 19947 | 19947 | 19947 | 19947 | 19947 | 19947 | 19947 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352
|  |  |  | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000
|  |  |  | 0 | 65000 | 130000 | 137875 | 202875 | 267875 | 320012 | 370012 | 420012 | 470012 | 520012 | 570012 | 620012 | 620012 | 620012 | 645095 | 693095 | 744095 | 817095 | 870095 | 963095 | 994095 | 1025095 | 1056095 | 1087095 | 1118095 | 1149095 | 1180095 | 1180095 | 1180095 | 1211095 | 1242095 | 1273095 | 1304095 | 1335095 | 1366095 | 1397095 | 1428095 | 1459095 | 1490095 | 1521095 | 1552095 | 1583095 | 1583095 | 1583095 | 1627095 | 1666095 | 1715095 | 1754095 | 1793095 | 1832095 | 1871095 | 1910095 | 1949095 | 1988095 | 2027095 | 2066095 | 2105095 | 2105095 | 2105095 | 2150095 | 2190095 | 2240095 | 2280095 | 2320095 | 2360095 | 2400095 | 2440095 | 2480095 | 2505095 | 2564657 | 2624219 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 24947 | 89947 | 154947 | 162822 | 227822 | 292822 | 344959 | 394959 | 444959 | 494959 | 544959 | 594959 | 659364 | 659364 | 659364 | 684447 | 732447 | 783447 | 856447 | 909447 | 1002447 | 1033447 | 1064447 | 1095447 | 1126447 | 1157447 | 1188447 | 1219447 | 1219447 | 1219447 | 1250447 | 1281447 | 1312447 | 1343447 | 1374447 | 1405447 | 1436447 | 1467447 | 1498447 | 1529447 | 1560447 | 1591447 | 1622447 | 1622447 | 1622447 | 1666447 | 1705447 | 1754447 | 1793447 | 1832447 | 1871447 | 1910447 | 1949447 | 1988447 | 2027447 | 2066447 | 2105447 | 2144447 | 2144447 | 2144447 | 2189447 | 2229447 | 2279447 | 2319447 | 2359447 | 2399447 | 2439447 | 2479447 | 2519447 | 2544447 | 2604009 | 2663571 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 53727 | 83727 | 103727 | 110923 | 110923 | 110923 | 110923 | 110923 | 110923 | 110923 | 110923 | 110923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923
|  |  |  | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03
|  |  |  | 10496.61 | 10496.61 | 10496.61 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 103869.64 | 133869.64 | 153869.64 | 161717.42 | 161717.42 | 161717.42 | 161717.42 | 161717.42 | 161717.42 | 161717.42 | 161717.42 | 161717.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42
|  |  |  | 73279.05 | 79279.05 | 85279.05 | 99508.05 | 105508.05 | 111508.05 | 117508.05 | 123508.05 | 129508.05 | 135508.05 | 141508.05 | 147508.05 | 157737.05 | 157737.05 | 157737.05 | 165757.05 | 170858.05 | 177080.05 | 185328.51 | 192597.12 | 198329.3 | 204086.64 | 209840.13 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 73279.05 | 79279.05 | 85279.05 | 99508.05 | 105508.05 | 111508.05 | 117508.05 | 123508.05 | 129508.05 | 135508.05 | 141508.05 | 147508.05 | 157737.05 | 157737.05 | 157737.05 | 165757.05 | 170858.05 | 177080.05 | 185328.51 | 192597.12 | 198329.3 | 204086.64 | 209840.13 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31 | 215661.31
|  |  |  | 244340 | 244340 | 264340 | 282586 | 282586 | 282586 | 282586 | 282586 | 282586 | 282586 | 282586 | 282586 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 244340 | 244340 | 264340 | 282586 | 282586 | 282586 | 282586 | 282586 | 282586 | 282586 | 282586 | 282586 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286
|  |  |  | 36123 | 37823 | 39523 | 45280 | 48280 | 56820 | 60820 | 65320 | 73601 | 79601 | 85601 | 91601 | 100414 | 100414 | 100414 | 102914 | 106771.53 | 111771.53 | 118701.53 | 124791.53 | 127791.53 | 181467.96 | 181467.96 | 181467.96 | 181467.96 | 181467.96 | 181467.96 | 181467.96 | 181467.96 | 181467.96 | 246467.96 | 246467.96 | 246467.96 | 246467.96 | 246467.96 | 246467.96 | 246467.96 | 246467.96 | 246467.96 | 246467.96 | 246467.96 | 246467.96 | 246467.96 | 246467.96 | 246467.96 | 306467.96 | 306467.96 | 306467.96 | 306467.96 | 306467.96 | 306467.96 | 306467.96 | 306467.96 | 306467.96 | 306467.96 | 306467.96 | 306467.96 | 306467.96 | 306467.96 | 306467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96 | 366467.96
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 371000 | 361000 | 361000 | 361000 | 361000 | 361000 | 2526000 | 2576000 | 2576000 | 2576000 | 2576000 | 2576000 | 2576000 | 2576000 | 2576000 | 2576000 | 2576000 | 2576000 | 2576000 | 2576000 | 3641000 | 3641000 | 3791000 | 3791000 | 3791000 | 3791000 | 3791000 | 3791000 | 3791000 | 3791000 | 3791000 | 3791000 | 3791000 | 3791000 | 3791000 | 3791000 | 3791000 | 3916000 | 3916000 | 3916000 | 3916000 | 3916000 | 3916000 | 3916000 | 3916000 | 3916000 | 3916000 | 3916000 | 3916000 | 3916000 | 3916000 | 3916000 | 4041000 | 4041000 | 4041000 | 4041000 | 4041000 | 4041000 | 4041000 | 4041000 | 4041000 | 4041000 | 4041000 | 4041000 | 4041000 | 4041000 | 4041000 | 4141000 | 4141000 | 4141000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 36123 | 37823 | 39523 | 45280 | 48280 | 56820 | 60820 | 65320 | 73601 | 79601 | 85601 | 91601 | 100414 | 100414 | 100414 | 102914 | 106771.53 | 111771.53 | 118701.53 | 524791.53 | 498791.53 | 542467.96 | 542467.96 | 542467.96 | 542467.96 | 542467.96 | 2707467.96 | 2757467.96 | 2757467.96 | 2757467.96 | 2822467.96 | 2822467.96 | 2822467.96 | 2822467.96 | 2822467.96 | 2822467.96 | 2822467.96 | 2822467.96 | 2822467.96 | 2822467.96 | 3887467.96 | 3887467.96 | 4037467.96 | 4037467.96 | 4037467.96 | 4097467.96 | 4097467.96 | 4097467.96 | 4097467.96 | 4097467.96 | 4097467.96 | 4097467.96 | 4097467.96 | 4097467.96 | 4097467.96 | 4097467.96 | 4097467.96 | 4222467.96 | 4222467.96 | 4222467.96 | 4282467.96 | 4282467.96 | 4282467.96 | 4282467.96 | 4282467.96 | 4282467.96 | 4282467.96 | 4282467.96 | 4282467.96 | 4282467.96 | 4282467.96 | 4282467.96 | 4407467.96 | 4407467.96 | 4407467.96 | 4407467.96 | 4407467.96 | 4407467.96 | 4407467.96 | 4407467.96 | 4407467.96 | 4407467.96 | 4407467.96 | 4407467.96 | 4407467.96 | 4407467.96 | 4407467.96 | 4507467.96 | 4507467.96 | 4507467.96
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 310000 | 760000 | 843333 | 931666.3333 | 1024999.6667 | 1024999.6667 | 1024999.6667 | 1224999.6667 | 1424999.6667 | 1624999.6667 | 2638105.6667 | 4442926.6667 | 6515417.8399 | 8691955.8399 | 11716776.5935 | 14034536.4191 | 16289678.8814 | 18501052.5584 | 20812251.5773 | 22830390.5773 | 22830390.5773 | 22830390.5773 | 24675668.6473 | 26607944.9373 | 28579141.4873 | 30522864.9073 | 32195983.4873 | 33898864.6173 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873 | 34855392.5873
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272060 | 623320.05 | 903444.73 | 1186473.07 | 1484598.23 | 1786230.75 | 2081566.3 | 2381674.58 | 2700171.85 | 3020140.24 | 3020140.24 | 3020140.24 | 3310599.24 | 3614752.34 | 3925031.74 | 4233789.5 | 4540631.56 | 4852222.37 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24 | 5044729.24
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 310000 | 760000 | 843333 | 931666.3333 | 1024999.6667 | 1024999.6667 | 1024999.6667 | 1224999.6667 | 1424999.6667 | 1624999.6667 | 2910165.6667 | 5066246.7167 | 7418862.5699 | 9878428.9099 | 13201374.8235 | 15820767.1691 | 18371245.1814 | 20882727.1384 | 23512423.4273 | 25850530.8173 | 25850530.8173 | 25850530.8173 | 27986267.8873 | 30222697.2773 | 32504173.2273 | 34756654.4073 | 36736615.0473 | 38751086.9873 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273 | 39900121.8273
|  |  |  | 21485 | 21485 | 21485 | 31835 | 131835 | 156835 | 156835 | 186835 | 877500 | 928646 | 971396 | 1026919 | 1124669 | 1124669 | 1124669 | 1124669 | 1124669 | 1198416 | 1347416 | 2097102.77 | 3022583.77 | 3768508.77 | 4808991.14 | 5682302.71 | 6404766.13 | 7074675.81 | 7785633.87 | 8499875.81 | 8499875.81 | 8499875.81 | 8499875.81 | 8499875.81 | 8499875.81 | 9138794.33 | 10080358.46 | 11036494.41 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 21485 | 21485 | 21485 | 31835 | 131835 | 156835 | 156835 | 186835 | 877500 | 928646 | 971396 | 1026919 | 1124669 | 1124669 | 1124669 | 1124669 | 1124669 | 1198416 | 1347416 | 2097102.77 | 3022583.77 | 3768508.77 | 4808991.14 | 5682302.71 | 6404766.13 | 7074675.81 | 7785633.87 | 8499875.81 | 8499875.81 | 8499875.81 | 8499875.81 | 8499875.81 | 8499875.81 | 9138794.33 | 10080358.46 | 11036494.41 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81 | 11627213.81
|  |  |  | 21485 | 21485 | 21485 | 31835 | 131835 | 156835 | 156835 | 286835 | 1187500 | 1688646 | 1814729 | 1958585.3333 | 2149668.6667 | 2149668.6667 | 2149668.6667 | 2349668.6667 | 2549668.6667 | 2823415.6667 | 4257581.6667 | 7163349.4867 | 10441446.3399 | 13646937.6799 | 18010365.9635 | 21503069.8791 | 24776011.3114 | 27957402.9484 | 31298057.2973 | 34350406.6273 | 34350406.6273 | 34350406.6273 | 36486143.6973 | 38722573.0873 | 41004049.0373 | 43895448.7373 | 46816973.5073 | 49787581.3973 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373 | 51527335.6373
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2033370 | 4089485 | 6100109 | 8570145 | 12086509 | 14577126 | 14577126 | 14577126 | 24670309 | 31503276 | 34919759.3333 | 41154581.21 | 47389403.0867 | 53624224.9633 | 59829706.27 | 66077187.5767 | 72324668.8833 | 80945015.8933 | 89565362.9033 | 98185709.9133 | 106806056.9233 | 106806056.9233 | 106806056.9233 | 116874171.9233 | 126942286.9233 | 137010401.9233 | 147996548.0567 | 158982694.19 | 169968840.3233 | 180435940.21 | 190902951.0967 | 201369961.9833 | 208608907.9683 | 215847853.9533 | 223086799.9383 | 230325745.9233 | 230325745.9233 | 230325745.9233 | 234264634.6567 | 238203523.39 | 242142412.1233 | 243490978.96 | 244839545.7967 | 246188112.6333 | 246584706.3 | 246981299.9667 | 247377893.6333 | 247405553.9233 | 247405553.9233 | 247405553.9233 | 247405553.9233 | 247405553.9233 | 247405553.9233 | 247405553.9233 | 247405553.9233 | 247405553.9233 | 247405553.9233 | 247405553.9233 | 247405553.9233 | 247405553.9233 | 247405553.9233 | 247405553.9233 | 247405553.9233 | 247405553.9233 | 247405553.9233 | 247405553.9233 | 247405553.9233 | 247405553.9233
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340000 | 340000 | 340000 | -4026336 | -4026336 | -4028747 | -4028747 | -4028747 | -4028747 | -4028747 | -4028747 | -6477560 | -6477560 | -6477560 | -6477560 | -10982761 | -10982761 | -10982761 | -10982761 | -10982761 | -14929140 | -14929140 | -14929140 | -19235358 | -19235358 | -19235358 | -23338092 | -23338092 | -23338092 | -23338092 | -27121340 | -27121340 | -27121340 | -27121340 | -27121340 | -28743652 | -28743652 | -28743652 | -29350641 | -29350641 | -29350641 | -29584487 | -29612147 | -29612147 | -29612147 | -29612147 | -29612147 | -29612147 | -29612147 | -29612147 | -29612147 | -29612147 | -29612147 | -29612147 | -29612147 | -29612147 | -29612147 | -29612147 | -29612147 | -29612147 | -29612147 | -29612147 | -29612147
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 400000 | 600000 | 800000 | 1000000 | 1200000 | 1400000 | 1600000 | 1800000 | 1984041 | 1984041 | 1984041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2033370 | -4089485 | -6100109 | -8570145 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000 | -5000000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1500000 | 3000000 | 5000000 | 20275000 | 42275000 | 42275000 | 42275000 | 42275000 | 40387000 | 39443000 | 38499000 | 37555000 | 36611000 | 35667000 | 34723000 | 33779000 | 32835000 | 31891000 | 30947000 | 30000000 | 30000000 | 30000000 | 28385000 | 26770000 | 25155000 | 23540000 | 21925000 | 20310000 | 18695000 | 17080000 | 15465000 | 13850000 | 12235000 | 10620000 | 9000000 | 9000000 | 9000000 | 8693000 | 8386000 | 8079000 | 7772000 | 7465000 | 7158000 | 6851000 | 6544000 | 6237000 | 5930000 | 5623000 | 5316000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1500000 | 3000000 | 5000000 | 27361509 | 52192126 | 52192126 | 52192126 | 57918973 | 62863940 | 65334012.3333 | 70624834.21 | 75915656.0867 | 81206477.9633 | 86467959.27 | 91771440.5767 | 94626108.8833 | 102302455.8933 | 109978802.9033 | 117655149.9133 | 120823295.9233 | 120823295.9233 | 120823295.9233 | 129276410.9233 | 137729525.9233 | 142236261.9233 | 151607408.0567 | 160978554.19 | 166043482.3233 | 174895582.21 | 183747593.0967 | 188496869.9833 | 194120815.9683 | 199744761.9533 | 205368707.9383 | 207204405.9233 | 207204405.9233 | 207204405.9233 | 211036294.6567 | 214868183.39 | 217077760.1233 | 218319326.96 | 219560893.7967 | 220195471.6333 | 220485065.3 | 220774658.9667 | 220830406.6333 | 220707447.9233 | 220400447.9233 | 220093447.9233 | 217793406.9233 | 217793406.9233 | 217793406.9233 | 217793406.9233 | 217793406.9233 | 217793406.9233 | 217793406.9233 | 217793406.9233 | 217793406.9233 | 217793406.9233 | 217793406.9233 | 217793406.9233 | 217793406.9233 | 217793406.9233 | 217793406.9233 | 217793406.9233 | 217793406.9233 | 217793406.9233
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 25000 | 25000 | 10000 | 10000 | 14000 | 14000 | 27000 | 27000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37000 | 37000 | 51642 | 51642 | 77462 | 77462 | 77462 | 77462 | 77462 | 92462 | 92462 | 92462 | 92462 | 107462 | 107462 | 122462 | 137462 | 137462 | 152462 | 152462 | 152462 | 152462 | 152462 | 152462 | 152462 | 152462 | 152462 | 152462 | 177462 | 177462 | 202462 | 227462 | 227462 | 252462 | 277462 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 62000 | 62000 | 61642 | 61642 | 91462 | 91462 | 104462 | 104462 | 109462 | 124462 | 124462 | 124462 | 124462 | 139462 | 139462 | 154462 | 169462 | 169462 | 184462 | 226462 | 226462 | 226462 | 226462 | 226462 | 226462 | 226462 | 226462 | 226462 | 251462 | 251462 | 276462 | 301462 | 301462 | 326462 | 351462 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405559 | 1112559 | 2123000 | 2692660 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685 | 2860685
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 944600 | 1354489 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134574 | 719874 | 1426874 | 2437315 | 3056975 | 4119600 | 4529489 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041 | 4754041
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134574 | 739874 | 1488874 | 2499315 | 3118617 | 4181242 | 4620951 | 5345503 | 6358503 | 7858503 | 9863503 | 32240012 | 57070629 | 57070629 | 57070629 | 62812476 | 67757443 | 70242515.3333 | 75548337.21 | 80839159.0867 | 86144980.9633 | 91448462.27 | 96751943.5767 | 99606611.8833 | 107282958.8933 | 114959305.9033 | 122635652.9133 | 125803798.9233 | 125803798.9233 | 125803798.9233 | 134281913.9233 | 142735028.9233 | 147266764.9233 | 156662911.0567 | 166034057.19 | 171123985.3233 | 180001085.21 | 188875634.0967 | 193624910.9833 | 199248856.9683 | 204872802.9533 | 210496748.9383 | 212332446.9233 | 212332446.9233 | 212332446.9233 | 216164335.6567 | 219996224.39 | 222205801.1233 | 223447367.96 | 224688934.7967 | 225323512.6333 | 225613106.3 | 225902699.9667 | 225958447.6333 | 225835488.9233 | 225528488.9233 | 225221488.9233 | 222921447.9233 | 222921447.9233 | 222921447.9233 | 222921447.9233 | 222921447.9233 | 222921447.9233 | 222921447.9233 | 222921447.9233 | 222921447.9233 | 222921447.9233 | 222921447.9233 | 222921447.9233 | 222921447.9233 | 222921447.9233 | 222921447.9233 | 222921447.9233 | 222921447.9233 | 222921447.9233
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14118.0982 | 28236.1964 | 42354.2947 | 212445.2947 | 12880429.2947 | 12906214.8195 | 12906214.8195 | 12906214.8195 | 12921411.7706 | 12933079.1971 | 12944746.6237 | 12956414.0503 | 12968081.4769 | 12979748.9034 | 12991416.33 | 13003083.7566 | 13014751.1566 | 22890309.9566 | 22907422.9566 | 22924535.9566 | 23109999.3566 | 23109999.3566 | 23109999.3566 | 23796429.8566 | 24570905.8566 | 25571441.0566 | 27707460.5566 | 29444436.9566 | 31362594.4566 | 33579369.3566 | 36053129.0566 | 38738257.3566 | 40574422.3566 | 42722777.4566 | 44754893.3566 | 46677184.2566 | 46677184.2566 | 46677184.2566 | 48411754.9566 | 49982452.5566 | 51392170.4566 | 52545688.7566 | 53277292.9566 | 55676851.7566 | 55688519.1566 | 55694352.8566 | 55694352.8566 | 55694352.8566 | 55694352.8566 | 55694352.8566 | 51162579.8566 | 51162579.8566 | 51162579.8566 | 51162579.8566 | 51162579.8566 | 51162579.8566 | 51162579.8566 | 51162579.8566 | 51162579.8566 | 51162579.8566 | 51162579.8566 | 51162579.8566 | 51162579.8566 | 51162579.8566 | 51162579.8566 | 51162579.8566 | 51162579.8566 | 51162579.8566
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14118.0982 | -28236.1964 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947 | -42354.2947
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 250000 | 420091 | 13088075 | 13113860.5248 | 13113860.5248 | 13113860.5248 | 13129057.4759 | 13140724.9025 | 13152392.329 | 13164059.7556 | 13175727.1822 | 13187394.6088 | 13199062.0353 | 13210729.4619 | 13222396.8619 | 23097955.6619 | 23115068.6619 | 23132181.6619 | 23317645.0619 | 23317645.0619 | 23317645.0619 | 24004075.5619 | 24778551.5619 | 25779086.7619 | 27915106.2619 | 29652082.6619 | 31570240.1619 | 33787015.0619 | 36260774.7619 | 38945903.0619 | 40782068.0619 | 42930423.1619 | 44962539.0619 | 46884829.9619 | 46884829.9619 | 46884829.9619 | 48619400.6619 | 50190098.2619 | 51599816.1619 | 52753334.4619 | 53484938.6619 | 55884497.4619 | 55896164.8619 | 55901998.5619 | 55901998.5619 | 55901998.5619 | 55901998.5619 | 55901998.5619 | 51370225.5619 | 51370225.5619 | 51370225.5619 | 51370225.5619 | 51370225.5619 | 51370225.5619 | 51370225.5619 | 51370225.5619 | 51370225.5619 | 51370225.5619 | 51370225.5619 | 51370225.5619 | 51370225.5619 | 51370225.5619 | 51370225.5619 | 51370225.5619 | 51370225.5619 | 51370225.5619
|  |  |  | 20762.74 | 25762.74 | 30762.74 | 57499.74 | 57568.74 | 92568.74 | 105453.74 | 115453.74 | 125453.74 | 135453.74 | 145453.74 | 126397.74 | 137782.74 | 137782.74 | 137782.74 | 144237.74 | 145135.74 | 166113.74 | 169435.74 | 169435.74 | 169435.74 | 169435.74 | 170335.74 | 171235.74 | 172235.74 | 173235.74 | 175035.74 | 177595.74 | 177595.74 | 177595.74 | 179325.74 | 181055.74 | 182785.74 | 184515.74 | 186245.74 | 187975.74 | 189705.74 | 191435.74 | 193165.74 | 194895.74 | 196625.74 | 198355.74 | 200085.74 | 200085.74 | 200085.74 | 201815.74 | 203545.74 | 205275.74 | 207005.74 | 208735.74 | 210465.74 | 212195.74 | 213925.74 | 215655.74 | 217385.74 | 219115.74 | 220845.74 | 222575.74 | 222575.74 | 222575.74 | 224305.74 | 226035.74 | 227765.74 | 229495.74 | 231225.74 | 232955.74 | 234685.74 | 236415.74 | 238145.74 | 239875.74 | 241605.74 | 243335.74 | 245065.74 | 245065.74 | 245065.74 | 246795.74 | 248525.74 | 250255.74 | 251985.74 | 253715.74 | 255445.74 | 257175.74 | 258905.74 | 260635.74 | 262365.74 | 264095.74 | 265825.74 | 267873.74 | 267873.74 | 267873.74
|  |  |  | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2435909 | 5855245 | 9385046 | 11965991 | 11965991 | 11965991 | 12759549.13 | 13610729.45 | 14448306.3 | 15603320.68 | 16932791.65 | 18254894.77 | 19387082.39 | 20276763.87 | 21200793.16 | 22189886.74 | 23312815 | 24618161 | 26074055 | 26074055 | 26074055 | 27214489.17 | 28756423.55 | 30338598 | 32456218.13 | 34633073.03 | 36561679.2 | 38462917.48 | 40410768.83 | 42306293.25 | 43904297.64 | 45409530.67 | 46873936.78 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48443358.99 | 48973999.99 | 48973999.99 | 48973999.99
|  |  |  | 3113762.74 | 3118762.74 | 3123762.74 | 3150499.74 | 3150568.74 | 3185568.74 | 3198453.74 | 3208453.74 | 3218453.74 | 3228453.74 | 3238453.74 | 3219397.74 | 3230782.74 | 3230782.74 | 3230782.74 | 3237237.74 | 3238135.74 | 3259113.74 | 3262435.74 | 3262435.74 | 3262435.74 | 3262435.74 | 3263335.74 | 3264235.74 | 5701144.74 | 9121480.74 | 12653081.74 | 15236586.74 | 15236586.74 | 15236586.74 | 16031874.87 | 16884785.19 | 17724092.04 | 18880836.42 | 20212037.39 | 21535870.51 | 22669788.13 | 23561199.61 | 24486958.9 | 25477782.48 | 26602440.74 | 27909516.74 | 29367140.74 | 29367140.74 | 29367140.74 | 30509304.91 | 32052969.29 | 33636873.74 | 35756223.87 | 37934808.77 | 39865144.94 | 41768113.22 | 43717694.57 | 45614948.99 | 47214683.38 | 48721646.41 | 50187782.52 | 51758934.73 | 51758934.73 | 51758934.73 | 51760664.73 | 51762394.73 | 51764124.73 | 51765854.73 | 51767584.73 | 51769314.73 | 51771044.73 | 51772774.73 | 51774504.73 | 51776234.73 | 51777964.73 | 51779694.73 | 51781424.73 | 51781424.73 | 51781424.73 | 51783154.73 | 51784884.73 | 51786614.73 | 51788344.73 | 51790074.73 | 51791804.73 | 51793534.73 | 51795264.73 | 51796994.73 | 51798724.73 | 51800454.73 | 51802184.73 | 52334873.73 | 52334873.73 | 52334873.73
|  |  |  | 13757346.0836 | 15529413.9561 | 18054145.2174 | 20863603.9974 | 23244671.9974 | 25373041.812 | 28027166.0059 | 30652018.0059 | 33889665.0059 | 36546731.0059 | 38730962.0059 | 41890729.3393 | 44188179.6713 | 44188179.6713 | 44188179.6713 | 56676613.2854 | 58965277.5579 | 62834126.8305 | 72402542.0008 | 76109973.9121 | 80994018.3828 | 87775692.534 | 94685529.7305 | 102189393.8436 | 111190126.5088 | 121332802.3088 | 168445158.0648 | 202105731.4744 | 202105731.4744 | 202105731.4744 | 213653478.248 | 222463073.1464 | 228845201.2381 | 238977195.4132 | 249341168.1783 | 259772634.0133 | 268749472.0784 | 275710727.2434 | 280233553.8319 | 299492594.5537 | 310105549.5156 | 320111962.0874 | 325730073.0592 | 325730073.0592 | 325730073.0592 | 336773752.9421 | 348179638.355 | 355940475.0679 | 370229292.2441 | 384153286.5304 | 393744020.2566 | 407376369.2362 | 421294753.8657 | 431256122.9353 | 440940388.4532 | 450844088.6411 | 460596603.669 | 466682129.4369 | 466682129.4369 | 466682129.4369 | 472964432.5702 | 479048853.3536 | 483469884.437 | 486716836.0237 | 489584619.5103 | 493590544.597 | 494927121.1137 | 496304844.9304 | 497490978.0471 | 498701189.7871 | 498996390.2371 | 499291590.6872 | 493187977.1372 | 493187977.1372 | 493187977.1372 | 493726576.9275 | 494212556.7677 | 494693743.608 | 495143256.4483 | 495580375.2886 | 496032494.1289 | 496246365.4692 | 496423440.8095 | 496600516.1498 | 496777591.4901 | 496954666.8304 | 497131742.1707 | 498059776.511 | 498059776.511 | 498059776.511
|  |  |  | 1456288.59 | 1619140.6683 | 1781992.7465 | 1997107.7465 | 2258473.7465 | 2514674.5611 | 2784623.755 | 3054623.755 | 3324623.755 | 3660026.755 | 3855147.755 | 4263718.755 | 4807626.755 | 4807626.755 | 4807626.755 | 5202650.4636 | 5609604.4636 | 6034791.4636 | 6464601.4636 | 6901811.4636 | 7225519.4636 | 7867243.4636 | 8388064.4636 | 8987031.4636 | 9560132.1933 | 10129107.9229 | 10698083.6526 | 11267059.3822 | 11267059.3822 | 11267059.3822 | 11685657.3822 | 12102995.3822 | 12520333.3822 | 12900008.3822 | 13267346.3822 | 13645387.3822 | 14019820.3822 | 14341451.3822 | 14663082.3822 | 14970348.3822 | 15277614.3822 | 15584880.3822 | 15892146.3822 | 15892146.3822 | 15892146.3822 | 16199412.3822 | 16506678.3822 | 16813944.3822 | 17121210.3822 | 17428476.3822 | 17735742.3822 | 18040757.3822 | 18345772.3822 | 18659968.3822 | 18974164.3822 | 19288360.3822 | 19602556.3822 | 19916752.3822 | 19916752.3822 | 19916752.3822 | 20230948.3822 | 20545144.3822 | 20859340.3822 | 21173536.3822 | 21487732.3822 | 21801928.3822 | 22134361.3822 | 22466794.3822 | 22799227.3822 | 23131660.3822 | 23464093.3822 | 23796526.3822 | 24128959.3822 | 24128959.3822 | 24128959.3822 | 24387343.3822 | 24634434.3822 | 24876732.3822 | 25087356.3822 | 25285586.3822 | 25483816.3822 | 25542248.3822 | 25596341.3822 | 25650434.3822 | 25704527.3822 | 25758620.3822 | 25812713.3822 | 25866806.3822 | 25866806.3822 | 25866806.3822
|  |  |  | 38611.75 | 38611.75 | 38611.75 | 38611.75 | 38611.75 | 38611.75 | 46986.75 | 46986.75 | 46986.75 | 46986.75 | 93337.75 | 116012.75 | 141937.75 | 141937.75 | 141937.75 | 198604.4166 | 198604.4166 | 198604.4166 | 208907.4166 | 208907.4166 | 208907.4166 | 219210.4166 | 219210.4166 | 235063.4166 | 247426.4166 | 259789.4166 | 272152.4166 | 281028.4166 | 281028.4166 | 281028.4166 | 316728.4166 | 327728.4166 | 334228.4166 | 338031.4166 | 338031.4166 | 338031.4166 | 338031.4166 | 338031.4166 | 338031.4166 | 338031.4166 | 338031.4166 | 338031.4166 | 338031.4166 | 338031.4166 | 338031.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 414875.6666 | 414875.6666 | 414875.6666 | 414875.6666 | 414875.6666 | 414875.6666 | 414875.6666 | 414875.6666 | 414875.6666 | 414875.6666 | 414875.6666 | 414875.6666 | 414875.6666 | 414875.6666 | 414875.6666 | 456202.6166 | 456202.6166 | 456202.6166 | 456202.6166 | 456202.6166 | 456202.6166 | 456202.6166 | 456202.6166 | 456202.6166 | 456202.6166 | 456202.6166 | 456202.6166 | 456202.6166 | 456202.6166 | 456202.6166
|  |  |  | 25629.24 | 28629.24 | 31629.24 | 40512.24 | 46688.24 | 51688.24 | 58184.24 | 50070.24 | 60070.24 | 65070.24 | 65070.24 | 65887.24 | 71772.24 | 71772.24 | 71772.24 | 76576.11 | 81236.08 | 86012.27 | 90733.11 | 90733.11 | 95510.08 | 100308.02 | 107895.75 | 117118.89 | 120665.6 | 124165.46 | 127405.98 | 132522.08 | 132522.08 | 132522.08 | 137533.1569 | 142544.2338 | 147555.3108 | 152566.3877 | 157577.4646 | 162588.5415 | 167599.6185 | 172610.6954 | 177621.7723 | 182632.8492 | 187643.9262 | 192655.0031 | 197666.08 | 197666.08 | 197666.08 | 202881.6954 | 208097.3108 | 213312.9262 | 218528.5415 | 223744.1569 | 228959.7723 | 234175.3877 | 239391.0031 | 244606.6185 | 249822.2338 | 255037.8492 | 260253.4646 | 265469.08 | 265469.08 | 265469.08 | 270898.5415 | 276328.0031 | 281757.4646 | 287186.9262 | 292616.3877 | 298045.8492 | 303475.3108 | 308904.7723 | 314334.2338 | 319763.6954 | 325193.1569 | 330622.6185 | 336052.08 | 336052.08 | 336052.08 | 339067.58 | 342083.08 | 345098.58 | 348114.08 | 351129.58 | 354145.08 | 354145.08 | 354145.08 | 354145.08 | 354145.08 | 354145.08 | 354145.08 | 354145.08 | 354145.08 | 354145.08
|  |  |  | 910013.9336 | 985312.7279 | 1059022.9109 | 1175770.9109 | 1364361.9109 | 1515170.9109 | 1665979.9109 | 1829165.9109 | 1979974.9109 | 2130783.9109 | 2359406.9109 | 2510215.9109 | 2606215.9109 | 2606215.9109 | 2606215.9109 | 2762821.3725 | 2925274.3725 | 3085734.3725 | 3242339.834 | 3444031.834 | 3547636.834 | 3612928.834 | 3678220.834 | 3851388.834 | 3950734.834 | 4050080.834 | 4149426.834 | 4248772.834 | 4248772.834 | 4248772.834 | 4281383.3725 | 4313993.9111 | 4346604.4496 | 4379214.9881 | 4411825.5267 | 4444436.0652 | 4477046.6038 | 4509657.1423 | 4542267.6808 | 4574878.2194 | 4607488.7579 | 4640099.2965 | 4672709.835 | 4672709.835 | 4672709.835 | 4700599.4504 | 4728489.0658 | 4756378.6813 | 4784268.2967 | 4812157.9121 | 4840047.5275 | 4867937.143 | 4895826.7584 | 4923716.3738 | 4951605.9892 | 4979495.6046 | 5007385.2201 | 5035274.8355 | 5035274.8355 | 5035274.8355 | 5064558.9317 | 5093843.028 | 5123127.1242 | 5152411.2205 | 5181695.3167 | 5210979.413 | 5240263.5092 | 5269547.6055 | 5298831.7017 | 5328115.798 | 5357399.8942 | 5386683.9904 | 5415968.0867 | 5415968.0867 | 5415968.0867 | 5446716.3877 | 5477464.6886 | 5508212.9896 | 5538961.2906 | 5569709.5916 | 5600457.8926 | 5631206.1935 | 5661954.4945 | 5692702.7955 | 5723451.0965 | 5754199.3974 | 5784947.6984 | 5815695.9994 | 5815695.9994 | 5815695.9994
|  |  |  | 214591.66 | 521591.66 | 611591.66 | 618591.66 | 625591.66 | 632591.66 | 639591.66 | 646591.66 | 653591.66 | 660591.66 | 667591.66 | 702782.66 | 775978.66 | 775978.66 | 775978.66 | 810372.2754 | 856463.2754 | 1220247.8908 | 1509917.5062 | 1509917.5062 | 1533302.5062 | 1533302.5062 | 1533302.5062 | 1397266.5062 | 1465284.5062 | 1533302.5062 | 1543302.5062 | 1553302.5062 | 1553302.5062 | 1553302.5062 | 1585195.5062 | 1617088.5062 | 1648981.5062 | 1680874.5062 | 1712767.5062 | 1744660.5062 | 1776553.5062 | 1808446.5062 | 1840339.5062 | 1872232.5062 | 1904125.5062 | 1936018.5062 | 1967911.5062 | 1967911.5062 | 1967911.5062 | 2000788.5062 | 2033665.5062 | 2066542.5062 | 2099419.5062 | 2132296.5062 | 2165173.5062 | 2198050.5062 | 2230927.5062 | 2263804.5062 | 2296681.5062 | 2329558.5062 | 2362435.5062 | 2395312.5062 | 2395312.5062 | 2395312.5062 | 2429807.5062 | 2464302.5062 | 2498797.5062 | 2533292.5062 | 2567787.5062 | 2602282.5062 | 2636777.5062 | 2671272.5062 | 2705767.5062 | 2740262.5062 | 2774757.5062 | 2809252.5062 | 2843747.5062 | 2843747.5062 | 2843747.5062 | 2879919.5062 | 2916091.5062 | 2952263.5062 | 2988435.5062 | 3024607.5062 | 3060779.5062 | 3096951.5062 | 3133123.5062 | 3169295.5062 | 3205467.5062 | 3241639.5062 | 3277811.5062 | 3313983.5062 | 3313983.5062 | 3313983.5062
|  |  |  | 29174 | 49174 | 69174 | 89174 | 109174 | 129174 | 149423 | 169174 | 189174 | 209174 | 229174 | 249174 | 289808 | 289808 | 289808 | 357255 | 402369 | 447483 | 492597 | 537711 | 582825 | 627939 | 673053 | 690956 | 735528 | 780100 | 824672 | 869244 | 869244 | 869244 | 891682.2232 | 914120.4463 | 936558.6695 | 958996.8927 | 981435.1158 | 1003873.339 | 1026311.5622 | 1048749.7854 | 1071188.0085 | 1093626.2317 | 1116064.4549 | 1138502.678 | 1160940.9012 | 1160940.9012 | 1160940.9012 | 1183810.747 | 1206680.5928 | 1229550.4385 | 1252420.2843 | 1275290.1301 | 1298159.9759 | 1321029.8216 | 1343899.6674 | 1366769.5132 | 1389639.359 | 1412509.2047 | 1435379.0505 | 1458248.8963 | 1458248.8963 | 1458248.8963 | 1481571.946 | 1504894.9957 | 1528218.0454 | 1551541.095 | 1574864.1447 | 1598187.1944 | 1621510.2441 | 1644833.2938 | 1668156.3435 | 1691479.3931 | 1714802.4428 | 1738125.4925 | 1761448.5422 | 1761448.5422 | 1761448.5422 | 1798506.2251 | 1835563.908 | 1872621.5909 | 1909679.2739 | 1946736.9568 | 1983794.6397 | 2020852.3226 | 2057910.0055 | 2094967.6884 | 2132025.3714 | 2169083.0543 | 2206140.7372 | 2243198.4201 | 2243198.4201 | 2243198.4201
|  |  |  | 0 | -13000 | -17000 | -21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 85542 | 135542 | 185542 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804
|  |  |  | 0 | 4000 | 8000 | 9323 | 13323 | 17323 | 21448 | 25448 | 29448 | 33448 | 19341 | 21341 | 19595 | 19595 | 19595 | 22671.9231 | 22671.9231 | 22671.9231 | 26027.8462 | 26527.8462 | 26527.8462 | 26527.8462 | 26527.8462 | 26527.8462 | 29383.8462 | 32239.8462 | 35095.8462 | 37959.8462 | 37959.8462 | 37959.8462 | 43546.8462 | 49133.8462 | 54720.8462 | 57451.8462 | 60182.8462 | 62913.8462 | 65644.8462 | 68875.6154 | 72106.3846 | 75337.1538 | 78567.9231 | 81798.6923 | 85029.4615 | 85029.4615 | 85029.4615 | 88421.7692 | 91814.0769 | 95206.3846 | 98598.6923 | 101991 | 105383.3077 | 108775.6154 | 112167.9231 | 115560.2308 | 118952.5385 | 122344.8462 | 125737.1538 | 129129.4615 | 129129.4615 | 129129.4615 | 132691.3846 | 136253.3077 | 139815.2308 | 143377.1538 | 146939.0769 | 150501 | 154062.9231 | 157624.8462 | 161186.7692 | 164748.6923 | 168310.6154 | 171872.5385 | 175434.4615 | 175434.4615 | 175434.4615 | 180156.2307 | 184878 | 189599.7692 | 194321.5384 | 199043.3077 | 203765.0769 | 208486.8461 | 213208.6154 | 217930.3846 | 222652.1538 | 227373.923 | 232095.6923 | 236817.4615 | 236817.4615 | 236817.4615
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23344 | 46688 | 68276 | 63086 | 69885 | 69885 | 69885 | 69885 | 69885 | 69885 | 69885 | 69885 | 69885 | 69885 | 69885 | 81114 | 81114 | 91353 | 91353 | 91353 | 91353 | 91353 | 91353 | 93086.9231 | 94820.8462 | 96554.7692 | 98288.6923 | 100022.6154 | 101756.5385 | 103490.4615 | 105224.3846 | 106958.3077 | 108692.2308 | 110426.1538 | 112160.0769 | 113894 | 113894 | 113894 | 115714.6154 | 117535.2308 | 119355.8462 | 121176.4615 | 122997.0769 | 124817.6923 | 126638.3077 | 128458.9231 | 130279.5385 | 132100.1538 | 133920.7692 | 135741.3846 | 137562 | 137562 | 137562 | 139473.6923 | 141385.3846 | 143297.0769 | 145208.7692 | 147120.4615 | 149032.1538 | 150943.8462 | 152855.5385 | 154767.2308 | 156678.9231 | 158590.6154 | 160502.3077 | 162414 | 162414 | 162414 | 164948.1538 | 167482.3077 | 170016.4615 | 172550.6154 | 175084.7692 | 177618.9231 | 180153.0769 | 182687.2308 | 185221.3846 | 187755.5385 | 190289.6923 | 192823.8462 | 195358 | 195358 | 195358
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5011.0769 | 10022.1538 | 15033.2308 | 20044.3077 | 25055.3846 | 30066.4615 | 35077.5385 | 40088.6154 | 45099.6923 | 50110.7692 | 55121.8462 | 60132.9231 | 65144 | 65144 | 65144 | 70110.2308 | 75076.4615 | 80042.6923 | 85008.9231 | 89975.1538 | 94941.3846 | 99907.6154 | 104873.8462 | 109840.0769 | 114806.3077 | 119772.5385 | 124738.7692 | 129705 | 129705 | 129705 | 134641.6154 | 139578.2308 | 144514.8462 | 149451.4615 | 154388.0769 | 159324.6923 | 164261.3077 | 169197.9231 | 174134.5385 | 179071.1538 | 184007.7692 | 188944.3846 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 1000 | 1500 | 2000 | 2500 | 3000 | 3500 | 4000 | 4500 | 4500 | 4500 | 5000 | 5500 | 6000 | 6500 | 7000 | 7500 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 2759851.1736 | 3369002.0461 | 3768564.3074 | 4144895.3074 | 4653028.3074 | 5096038.122 | 5563041.3159 | 6042208.3159 | 6527361.3159 | 7071161.3159 | 7548959.3159 | 8195821.3159 | 8979623.3159 | 8979623.3159 | 8979623.3159 | 9697640.5611 | 10362912.5311 | 11362234.3365 | 12301813.1765 | 12986829.1765 | 13487918.1465 | 14255649.0865 | 14906192.8165 | 15585770.9565 | 16400312.3962 | 17200442.9858 | 17942296.2355 | 18682546.0651 | 18682546.0651 | 18682546.0651 | 19241628.9037 | 19774751.7424 | 20303374.581 | 20788781.4196 | 21258048.2582 | 21738018.0969 | 22214379.9355 | 22637939.5434 | 23061499.1512 | 23470693.7591 | 23879888.367 | 24289082.9748 | 24698277.5827 | 24698277.5827 | 24698277.5827 | 25142059.8131 | 25548357.0435 | 25954654.274 | 26360951.5044 | 26767248.7348 | 27173545.9653 | 27577592.1957 | 27981638.4261 | 28394865.6566 | 28808092.887 | 29221320.1174 | 29634547.3478 | 30047774.5783 | 30047774.5783 | 30047774.5783 | 30504271.6665 | 30921409.5048 | 31338547.343 | 31755685.1812 | 32172823.0195 | 32589960.8577 | 33025335.6959 | 33460710.5342 | 33896085.3724 | 34331460.2107 | 34766835.0489 | 35202209.8871 | 35637584.7254 | 35637584.7254 | 35637584.7254 | 36051545.0823 | 36412885.4893 | 36769432.8963 | 37094306.3032 | 37406785.7102 | 37719265.1172 | 37888931.0241 | 38054257.9311 | 38219584.8381 | 38384911.745 | 38550238.652 | 38715565.559 | 38880892.4659 | 38880892.4659 | 38880892.4659
|  |  |  | 386879.57 | 416879.57 | 446879.57 | 444218.57 | 494218.57 | 544218.57 | 594218.57 | 624418.57 | 654618.57 | 684818.57 | 715018.57 | 745218.57 | 775418.57 | 775418.57 | 775418.57 | 810945.57 | 846472.57 | 881999.57 | 909199.57 | 934968.57 | 961968.57 | 991968.57 | 1028724.57 | 1068088.57 | 1107452.57 | 1146816.57 | 1186180.57 | 1238194.57 | 1238194.57 | 1238194.57 | 1280292.04 | 1324374.25 | 1369344.37 | 1416106.25 | 1470301.25 | 1524496.25 | 1582230.25 | 1642377.25 | 1702524.25 | 1762671.25 | 1836324.25 | 1923779.25 | 2011234.25 | 2011234.25 | 2011234.25 | 2104235.25 | 2197236.25 | 2290237.25 | 2387888.25 | 2485539.25 | 2583190.25 | 2671588.25 | 2759986.25 | 2848384.25 | 2936782.25 | 3025180.25 | 3119274.25 | 3213368.25 | 3213368.25 | 3213368.25 | 3337995.25 | 3532972.25 | 3837851.25 | 4202860.25 | 4610615.25 | 5080546.25 | 5593223.25 | 6167881.25 | 6790628.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 386879.57 | 416879.57 | 446879.57 | 444218.57 | 494218.57 | 544218.57 | 594218.57 | 624418.57 | 654618.57 | 684818.57 | 715018.57 | 745218.57 | 775418.57 | 775418.57 | 775418.57 | 810945.57 | 846472.57 | 881999.57 | 909199.57 | 934968.57 | 961968.57 | 991968.57 | 1028724.57 | 1068088.57 | 1107452.57 | 1146816.57 | 1186180.57 | 1238194.57 | 1238194.57 | 1238194.57 | 1280292.04 | 1324374.25 | 1369344.37 | 1416106.25 | 1470301.25 | 1524496.25 | 1582230.25 | 1642377.25 | 1702524.25 | 1762671.25 | 1836324.25 | 1923779.25 | 2011234.25 | 2011234.25 | 2011234.25 | 2104235.25 | 2197236.25 | 2290237.25 | 2387888.25 | 2485539.25 | 2583190.25 | 2671588.25 | 2759986.25 | 2848384.25 | 2936782.25 | 3025180.25 | 3119274.25 | 3213368.25 | 3213368.25 | 3213368.25 | 3337995.25 | 3532972.25 | 3837851.25 | 4202860.25 | 4610615.25 | 5080546.25 | 5593223.25 | 6167881.25 | 6790628.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25
|  |  |  | 76499.47 | 76499.47 | 78414.47 | 81060.47 | 81087.47 | 81087.47 | 81458.47 | 81458.47 | 82654.47 | 82881.47 | 82961.47 | 87961.47 | 87961.47 | 87961.47 | 87961.47 | 87961.47 | 88058.23 | 88058.23 | 88058.23 | 93058.23 | 93058.23 | 93058.23 | 93344.23 | 113553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79 | 118553.79
|  |  |  | 29835.86 | 29835.86 | 29835.86 | 29835.86 | 29835.86 | 29835.86 | 29835.86 | 29835.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25
|  |  |  | 354360.76 | 361360.76 | 392445.76 | 451713.76 | 530317.76 | 535317.76 | 567496.76 | 572496.76 | 602424.76 | 610196.76 | 610701.76 | 611701.76 | 620580.76 | 620580.76 | 620580.76 | 623580.76 | 628926.63 | 631659.15 | 642814.99 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 661949 | 666949 | 671949 | 676949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949 | 681949
|  |  |  | 48665.11 | 48665.11 | 50457.11 | 52034.11 | 58717.11 | 61217.11 | 65732.11 | 66232.11 | 66048.11 | 74307.11 | 72328.11 | 74328.11 | 73386.11 | 73386.11 | 73386.11 | 74886.11 | 77308.15 | 78007.34 | 79757.34 | 80313.82 | 82313.82 | 84313.82 | 87313.82 | 98210.26 | 98210.26 | 103210.26 | 108210.26 | 113210.26 | 113210.26 | 113210.26 | 113596.79 | 114001.55 | 114414.46 | 114824.07 | 115230.52 | 115643.26 | 116059.71 | 116474.59 | 116896.32 | 117307.67 | 117722.25 | 118181.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25 | 118640.25
|  |  |  | 27275.32 | 27275.32 | 27275.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82
|  |  |  | 141282.71 | 206282.71 | 243665.71 | 248448.71 | 271433.71 | 326433.71 | 382338.71 | 437338.71 | 486530.71 | 511474.71 | 532514.71 | 592514.71 | 636915.71 | 636915.71 | 636915.71 | 674615.71 | 675797.79 | 686117.61 | 697867.61 | 707526.1 | 727526.1 | 737526.1 | 747526.1 | 887668.57 | 937668.57 | 947668.57 | 957668.57 | 957668.57 | 957668.57 | 957668.57 | 959591.57 | 961514.57 | 963437.57 | 965360.57 | 967283.57 | 969206.57 | 971129.57 | 973052.57 | 974975.57 | 976898.57 | 978821.57 | 980744.57 | 982668.57 | 982668.57 | 982668.57 | 983438.57 | 984208.57 | 984978.57 | 985748.57 | 986518.57 | 987288.57 | 988058.57 | 988828.57 | 989598.57 | 990368.57 | 991138.57 | 991908.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57 | 992668.57
|  |  |  | 142160.42 | 182160.42 | 203249.42 | 216259.42 | 234847.42 | 239847.42 | 256328.42 | 286328.42 | 300722.42 | 334265.42 | 321229.42 | 351229.42 | 334252.42 | 334252.42 | 334252.42 | 370107.42 | 389043 | 412925.18 | 419220.18 | 431986.1 | 431986.1 | 431986.1 | 435286.1 | 459719.23 | 460319.23 | 460919.23 | 461519.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23 | 462119.23
|  |  |  | 1009.5 | 1009.5 | 1104.5 | 1255.5 | 1309.5 | 3809.5 | 3941.5 | 4441.5 | 1961.5 | 2461.5 | 2461.5 | 3461.5 | 2461.5 | 2461.5 | 2461.5 | 9961.5 | 3461.5 | 3396.75 | 3596.75 | 3558 | 3558 | 3558 | 3558 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33 | 17598.33
|  |  |  | 5328.44 | 5828.44 | 5828.44 | 7669.44 | 11110.44 | 13110.44 | 13757.44 | 14257.44 | 18976.44 | 20245.44 | 20926.44 | 22926.44 | 22482.44 | 22482.44 | 22482.44 | 27482.44 | 23321.07 | 23014.57 | 23014.57 | 24014.57 | 25014.57 | 26014.57 | 28014.57 | 35946.24 | 37946.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24 | 39446.24
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 623 | 5144 | 7358 | 17358 | 25379 | 35379 | 21658 | 14462 | 18876 | 21376 | 36053 | 36053 | 36053 | 46053 | 52699.75 | 61811.29 | 62327.79 | 67164.57 | 69164.57 | 69164.57 | 69164.57 | 79333.75 | 84333.75 | 89333.75 | 94333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75 | 99333.75
|  |  |  | 9163.01 | 9663.01 | 10249.01 | 13580.01 | 13832.01 | 15832.01 | 18894.01 | 19894.01 | 17695.01 | 15257.01 | 15257.01 | 15757.01 | 15257.01 | 15257.01 | 15257.01 | 15257.01 | 15257.01 | 15257.01 | 15507.01 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45
|  |  |  | 2413.16 | 4613.16 | 7373.16 | 7507.16 | 7507.16 | 8507.16 | 11907.16 | 12907.16 | 16924.16 | 19561.16 | 21045.16 | 22045.16 | 24770.16 | 24770.16 | 24770.16 | 27770.16 | 24770.16 | 26770.16 | 28370.16 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39
|  |  |  | 0 | 500 | 1345 | 2121 | 2485 | 6985 | 8927 | 10427 | 5626 | 5626 | 5626 | 6626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48
|  |  |  | 0 | 0 | 0 | 0 | 701 | 2701 | 2701 | 4701 | 4500 | 8983 | 16078 | 20078 | 12393 | 12393 | 12393 | 12393 | 13467.16 | 15192.79 | 15542.79 | 16672.79 | 17172.79 | 17172.79 | 17172.79 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47 | 13335.47
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1218 | 1218 | 1218 | 1218 | 1218 | 1218 | 1218 | 2218 | 2218 | 2218 | 2218 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44 | 916.44
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 458319 | 468339 | 507030 | 526767 | 539913 | 554913 | 573213 | 581848 | 604928 | 596940 | 600940 | 600325 | 621659 | 621659 | 621659 | 624459 | 626887 | 628887 | 631887 | 634387 | 635887 | 638587 | 640087 | 643462 | 646837 | 650212 | 653587 | 658962 | 658962 | 658962 | 662038.9231 | 665115.8462 | 668192.7692 | 671269.6923 | 674346.6154 | 677423.5385 | 680500.4615 | 683577.3846 | 686654.3077 | 689731.2308 | 692808.1538 | 695885.0769 | 699962.0769 | 699962.0769 | 699962.0769 | 703039 | 706115.9231 | 709192.8462 | 712269.7692 | 715346.6923 | 718423.6154 | 721500.5385 | 724577.4615 | 727654.3846 | 730731.3077 | 733808.2308 | 736885.1538 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769 | 739962.0769
|  |  |  | 0 | 9765 | 32418 | 33303 | 38960 | 45960 | 55084 | 69972 | 99507 | 85130 | 99130 | 106698 | 135854 | 135854 | 135854 | 138924 | 172354 | 213918.429 | 250079.6003 | 257079.6003 | 289079.6003 | 305579.6003 | 330579.6003 | 362779.6003 | 394979.6003 | 427179.6003 | 459379.6003 | 498579.6003 | 498579.6003 | 498579.6003 | 517056.7092 | 535533.8181 | 554010.927 | 572488.036 | 590965.1449 | 609442.2538 | 627919.3627 | 646396.4716 | 664873.5805 | 683350.6895 | 701827.7984 | 720304.9073 | 738782.0162 | 738782.0162 | 738782.0162 | 743643.5996 | 748505.183 | 753366.7664 | 758228.3498 | 763089.9332 | 767951.5166 | 772813.0999 | 777674.6833 | 782536.2667 | 787397.8501 | 792259.4335 | 797121.0169 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003
|  |  |  | 0 | 10270 | 28804 | 47774 | 66561 | 95561 | 116284 | 188069 | 254352 | 283216 | 332216 | 364268 | 404452 | 404452 | 404452 | 420252 | 435872 | 445872 | 460872 | 475872 | 495872 | 532872 | 562872 | 607872 | 652872 | 697872 | 742872 | 802872 | 802872 | 802872 | 813592.5385 | 824313.0769 | 835033.6154 | 845754.1538 | 856474.6923 | 867195.2308 | 877915.7692 | 888636.3077 | 899356.8462 | 910077.3846 | 920797.9231 | 931518.4615 | 942239 | 942239 | 942239 | 946639 | 951039 | 955439 | 959839 | 964239 | 968639 | 973039 | 977439 | 981839 | 986239 | 990639 | 995039 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439 | 999439
|  |  |  | 0 | 7266 | 13104 | 14010 | 19236 | 28236 | 42132 | 50620 | 66680 | 63546 | 74546 | 81828 | 93282 | 93282 | 93282 | 102882 | 105742 | 117742 | 123742 | 126742 | 128742 | 134842 | 144842 | 149317 | 153792 | 156267 | 158742 | 161217 | 161217 | 161217 | 166977 | 172737 | 178497 | 184257 | 190017 | 195777 | 201537 | 207297 | 213057 | 218817 | 224577 | 230337 | 236097 | 236097 | 236097 | 239937 | 243777 | 247617 | 251457 | 255297 | 259137 | 262977 | 266817 | 270657 | 274497 | 278337 | 282177 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017 | 286017
|  |  |  | 0 | 11496 | 18310 | 22888 | 32318 | 43318 | 44356 | 47454 | 52226 | 58906 | 64906 | 70274 | 72470 | 72470 | 72470 | 72470 | 81360 | 84860 | 85860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860
|  |  |  | 0 | 0 | 10296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 220 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 41465 | 83421 | 106952 | 137750 | 152150 | 152150 | 152150 | 152150 | 152150 | 152150 | 152150 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1296312.76 | 1502294.76 | 1745249.76 | 1895926.76 | 2112923.76 | 2289823.76 | 2479559.76 | 2693453.76 | 2915207.76 | 2999252.76 | 3103536.76 | 3265191.76 | 3414713.76 | 3414713.76 | 3414713.76 | 3549538.76 | 3634808.63 | 3753972.689 | 3849001.2003 | 3916717.8003 | 3997717.8003 | 4073017.8003 | 4158103.8003 | 4502260.6303 | 4654910.6303 | 4765060.6303 | 4873710.6303 | 4996360.6303 | 4996360.6303 | 4996360.6303 | 5036704.7307 | 5077067.0612 | 5117437.5417 | 5157804.7221 | 5198168.7426 | 5238539.053 | 5278913.0735 | 5319285.5239 | 5359664.8244 | 5400033.7448 | 5440405.8953 | 5480822.4658 | 5522240.1131 | 5522240.1131 | 5522240.1131 | 5539188.6196 | 5556137.1261 | 5573085.6325 | 5590034.139 | 5606982.6455 | 5623931.1519 | 5640879.6584 | 5657828.1649 | 5674776.6713 | 5691725.1778 | 5708673.6843 | 5725622.1907 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972 | 5742560.6972
|  |  |  | 3110000 | 3415000 | 4629000 | 6413000 | 7192659 | 7906532 | 8836807 | 9698016 | 10611984 | 11436984 | 12286984 | 13846816 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 393551 | 787102 | 1168099 | 1426653 | 1561653 | 1199153 | 519768 | 714227 | 803477 | 1042727 | 1215727 | 1238727 | 3186727 | 3186727 | 3186727 | 3209727 | 3232727 | 3255727 | 3278727 | 3301727 | 3324727 | 3347727 | 3370727 | 3393727 | 3416727 | 3439727 | 3462727 | 3486727 | 3486727 | 3486727 | 3509727 | 3532727 | 3555727 | 3578727 | 3601727 | 3624727 | 3647727 | 3670727 | 3693727 | 3716727 | 3739727 | 3762727 | 3786727 | 3786727 | 3786727 | 3809727 | 3832727 | 3855727 | 3878727 | 3901727 | 3924727 | 3947727 | 3970727 | 3993727 | 4016727 | 4039727 | 4062727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1252075.1604 | 1252075.1604 | 1252075.1604 | 1529259.8126 | 1925120.1088 | 2305704.4246 | 2639434.1393 | 1590765.345 | 1708434.17 | 2173688.1297 | 2296858.2806 | 2233174.0049 | 2424625.7326 | 2465714.3551 | 2483746.393 | 2498365.4345 | 2498365.4345 | 2498365.4345 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17 | 2909688.17
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175977.52 | 175977.52 | 175977.52 | 202270.8639 | 236735.0661 | 240021.9746 | 241423.7444 | 238113.62 | 210178.3141 | 241090.3141 | 241090.3141 | 238258.6772 | 239880.6772 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016 | 240974.7016
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 907113.5614 | 907113.5614 | 907113.5614 | 1679179.0328 | 1923668.5909 | 2061116.6823 | 2142512.8226 | 2134559.8957 | 2129877.57 | 2119270.2199 | 2080131.2224 | 1960181.5524 | 2082356.9226 | 2114633.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201 | 2172265.9201
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1000000 | -1000000 | -1000000 | -1354446 | -1607932 | -1799731 | -1841902 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 628551.6837 | 628551.6837 | 628551.6837 | 928058.8887 | 1121410.765 | 1323567.2993 | 1398885.6251 | 1192286.9087 | 1192586.3501 | 1273286.3136 | 1287090.8061 | 1207091.4966 | 1292522.6823 | 1377378.5222 | 1443718.1448 | 1453041.9048 | 1453041.9048 | 1453041.9048 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94842.259 | 94842.259 | 94842.259 | 135165.3684 | 188577.985 | 214866.7968 | 259714.0014 | 263981.2658 | 272950.6153 | 290695.6153 | 290695.6153 | 281164.9152 | 294884.316 | 322032.7597 | 329364.2913 | 330779.7851 | 330779.7851 | 330779.7851 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937 | 333465.5937
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224954.2006 | 224954.2006 | 224954.2006 | 362569.4984 | 408970.1518 | 463635.9216 | 472481.0462 | 423586.9987 | 451618.1215 | 443040.6335 | 425975.4897 | 362701.6662 | 367048.474 | 405483.4068 | 433691.4068 | 470639.2737 | 470639.2737 | 470639.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737 | 485398.2737
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348021.3636 | 348021.3636 | 348021.3636 | 416131.8227 | 452848.2224 | 477964.799 | 515285.9982 | 539493.5746 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348
|  |  |  | 190000 | 335000 | 545000 | 635000 | 740000 | 940000 | 1150000 | 1350000 | 1390000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1490000 | 1565000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 3300000 | 3750000 | 5174000 | 7048000 | 7932659 | 8846532 | 9986807 | 11048016 | 12001984 | 12851984 | 13701984 | 15261816 | 15712486.9987 | 15712486.9987 | 15712486.9987 | 17372691.5375 | 18517452.14 | 19536197.1482 | 20335439.6272 | 19166636.8585 | 18939619.6258 | 18835660.7108 | 19110890.213 | 18860870.7973 | 19518867.2894 | 19916766.1503 | 20117309.3424 | 22127615.5046 | 22127615.5046 | 22127615.5046 | 22581185.494 | 22604185.494 | 22627185.494 | 22650185.494 | 22673185.494 | 22696185.494 | 22719185.494 | 22742185.494 | 22765185.494 | 22788185.494 | 22811185.494 | 22834185.494 | 22858185.494 | 22858185.494 | 22858185.494 | 22881185.494 | 22904185.494 | 22927185.494 | 22950185.494 | 22973185.494 | 22996185.494 | 23019185.494 | 23042185.494 | 23065185.494 | 23088185.494 | 23111185.494 | 23134185.494 | 23158185.494 | 23158185.494 | 23158185.494 | 23181185.494 | 23204185.494 | 23227185.494 | 23250185.494 | 23273185.494 | 23296185.494 | 23319185.494 | 23342185.494 | 23365185.494 | 23388185.494 | 23486185.494 | 23584185.494 | 23683185.494 | 23683185.494 | 23683185.494 | 23683185.494 | 23683185.494 | 23683185.494 | 23683185.494 | 23683185.494 | 23683185.494 | 23683185.494 | 23683185.494 | 23683185.494 | 23683185.494 | 23683185.494 | 23683185.494 | 23683185.494 | 23683185.494 | 23683185.494
|  |  |  | 365000 | 420000 | 462000 | 476614 | 562614 | 617614 | 757614 | 937614 | 945614 | 1079770 | 1176770 | 1281770 | 1310770 | 1310770 | 1310770 | 1365770 | 1380770 | 1427770 | 1471770 | 1529770 | 1557770 | 1584770 | 1614209.315 | 1649209.315 | 1684209.315 | 1719209.315 | 1740248.1575 | 1761287 | 1761287 | 1761287 | 1765287 | 1769287 | 1773613 | 1777770 | 1812770 | 1847770 | 1847770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1887770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1917770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1947770 | 1962770 | 1962770 | 1962770 | 1962770 | 1962770 | 1962770 | 2082770 | 2082770 | 2082770
|  |  |  | 147195.78 | 150195.78 | 160195.78 | 170195.78 | 170195.78 | 170195.78 | 170195.78 | 170195.78 | 170195.78 | 170195.78 | 170195.78 | 170195.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78
|  |  |  | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 522111.99 | 580111.99 | 632111.99 | 656725.99 | 742725.99 | 797725.99 | 937725.99 | 1117725.99 | 1125725.99 | 1259881.99 | 1356881.99 | 1461881.99 | 1486274.99 | 1486274.99 | 1486274.99 | 1541274.99 | 1556274.99 | 1603274.99 | 1647274.99 | 1705274.99 | 1733274.99 | 1760274.99 | 1789714.305 | 1824714.305 | 1859714.305 | 1894714.305 | 1915753.1475 | 1936791.99 | 1936791.99 | 1936791.99 | 1940791.99 | 1944791.99 | 1949117.99 | 1953274.99 | 1988274.99 | 2023274.99 | 2023274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2063274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2093274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2123274.99 | 2138274.99 | 2138274.99 | 2138274.99 | 2138274.99 | 2138274.99 | 2138274.99 | 2258274.99 | 2258274.99 | 2258274.99
|  |  |  | 1233000 | 1513000 | 1703000 | 1943000 | 2297000 | 2488000 | 2952000 | 3419000 | 3764000 | 4165000 | 4485000 | 4815000 | 5293261 | 5293261 | 5293261 | 5507923.53 | 5701871 | 5917945 | 6474945 | 6639726 | 6883363.7003 | 7107606.7003 | 7327569.7003 | 7484254.7003 | 7680886.7003 | 7859215.7003 | 8037499.7003 | 8215751.7003 | 8215751.7003 | 8215751.7003 | 8268471.7003 | 8324414.7003 | 8352134.7003 | 8379854.7003 | 8407574.7003 | 8435294.7003 | 8466684.7003 | 8481948.7003 | 8498212.7003 | 8514476.7003 | 8530740.7003 | 8547004.7003 | 8563268.7003 | 8563268.7003 | 8563268.7003 | 8580532.7003 | 8597796.7003 | 8615060.7003 | 8632324.7003 | 8649588.7003 | 8666852.7003 | 8677346.7003 | 8687840.7003 | 8698334.7003 | 8708828.7003 | 8719322.7003 | 8729816.7003 | 8740310.7003 | 8740310.7003 | 8740310.7003 | 8750804.7003 | 8761298.7003 | 8771792.7003 | 8782286.7003 | 8792780.7003 | 8803274.7003 | 8815044.7003 | 8826814.7003 | 8838584.7003 | 8850354.7003 | 8862124.7003 | 8873894.7003 | 8885664.7003 | 8885664.7003 | 8885664.7003 | 8897434.7003 | 8909204.7003 | 8920974.7003 | 8932744.7003 | 8944514.7003 | 8956284.7003 | 8956284.7003 | 8956284.7003 | 8956284.7003 | 8956284.7003 | 8956284.7003 | 8956284.7003 | 8956284.7003 | 8956284.7003 | 8956284.7003
|  |  |  | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000
|  |  |  | 0 | 0 | 0 | 3002 | 18541 | 35470 | 51454 | 70023 | 87239 | 91297 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381
|  |  |  | 0 | 0 | 40000 | 36998 | 61459 | 94530 | 128546 | 29977 | 52761 | 58703 | 117619 | 202619 | 199619 | 199619 | 199619 | 319619 | 319619 | 350173 | 416547 | 474787 | 521762 | 603315 | 639399 | 715585 | 791771 | 867957 | 944143 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333 | 1020333
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1346000 | 1626000 | 1856000 | 2096000 | 2490000 | 2731000 | 3245000 | 3632000 | 4017000 | 4428000 | 4808000 | 5223000 | 5698261 | 5698261 | 5698261 | 6032923.53 | 6226871 | 6473499 | 7096873 | 7319894 | 7610506.7003 | 7916302.7003 | 8172349.7003 | 8405220.7003 | 8678038.7003 | 8932553.7003 | 9187023.7003 | 9441465.7003 | 9441465.7003 | 9441465.7003 | 9494185.7003 | 9550128.7003 | 9577848.7003 | 9605568.7003 | 9633288.7003 | 9661008.7003 | 9692398.7003 | 9707662.7003 | 9723926.7003 | 9740190.7003 | 9756454.7003 | 9772718.7003 | 9788982.7003 | 9788982.7003 | 9788982.7003 | 9806246.7003 | 9823510.7003 | 9840774.7003 | 9858038.7003 | 9875302.7003 | 9892566.7003 | 9903060.7003 | 9913554.7003 | 9924048.7003 | 9934542.7003 | 9945036.7003 | 9955530.7003 | 9966024.7003 | 9966024.7003 | 9966024.7003 | 9976518.7003 | 9987012.7003 | 9997506.7003 | 10008000.7003 | 10018494.7003 | 10028988.7003 | 10040758.7003 | 10052528.7003 | 10064298.7003 | 10076068.7003 | 10087838.7003 | 10099608.7003 | 10111378.7003 | 10111378.7003 | 10111378.7003 | 10123148.7003 | 10134918.7003 | 10146688.7003 | 10158458.7003 | 10170228.7003 | 10181998.7003 | 10181998.7003 | 10181998.7003 | 10181998.7003 | 10181998.7003 | 10181998.7003 | 10181998.7003 | 10181998.7003 | 10181998.7003 | 10181998.7003
|  |  |  | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46
|  |  |  | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76
|  |  |  | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75
|  |  |  | 0 | 0 | 0 | 22519 | 52519 | 67519 | 67519 | 87519 | 107519 | 113275 | 128275 | 138275 | 148275 | 148275 | 148275 | 181901.13 | 181901.13 | 220779.53 | 231747.71 | 231747.71 | 246668.71 | 246668.71 | 246668.71 | 253010.71 | 271147.71 | 289431.71 | 301175.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 22519 | 52519 | 67519 | 67519 | 97519 | 117519 | 113275 | 128275 | 138275 | 155775 | 155775 | 155775 | 189401.13 | 189401.13 | 228279.53 | 239247.71 | 239247.71 | 254168.71 | 254168.71 | 254168.71 | 260510.71 | 278647.71 | 296931.71 | 308675.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71
|  |  |  | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843
|  |  |  | 35624 | 37709 | 42709 | 41449 | 41714 | 47714 | 53714 | 47214 | 52214 | 49089 | 51089 | 54419 | 58519 | 58519 | 58519 | 67668 | 71769 | 80519 | 85019 | 91669 | 101819 | 111309 | 117779 | 124429 | 128929 | 133429 | 137929 | 142429 | 142429 | 142429 | 146634.93 | 151039.16 | 155532.1 | 159991.84 | 164418.55 | 168913.77 | 172393.23 | 174197.74 | 176032.04 | 177821.46 | 179627.01 | 181626.01 | 183625.01 | 183625.01 | 183625.01 | 185228.34 | 186976.49 | 188755.67 | 190525.2 | 192280.17 | 194060.21 | 195859.24 | 196647.05 | 197468.63 | 198242.89 | 199033.08 | 200008.23 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02 | 201061.02
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9076400 | 8332477 | 6797328 | 6797328 | 6797328 | 6797328 | 8431272 | 8431272 | 10110818 | 10110818 | 10110818 | 10110818 | 10110818 | 10110818 | 10110818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818 | 11870818
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319935 | 292656 | 2077656 | 6589681 | 6449518 | 5976338 | 5976338 | 5976338 | 5976338 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327 | 6485327
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 104000 | 192000 | 118000 | 206000 | 294000 | 382000 | 470000 | 470000 | 470000 | 558000 | 646000 | 734000 | 822000 | 910000 | 998000 | 1086000 | 1174000 | 1262000 | 1350000 | 1438000 | 1526000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 4000 | 6000 | 8000 | 9230 | 11076 | 12922 | 14768 | 16614 | 16614 | 16614 | 18460 | 20306 | 22152 | 23998 | 25844 | 27690 | 29536 | 31382 | 33228 | 35074 | 36920 | 38766 | 40612 | 40612 | 40612 | 42458 | 44304 | 46150 | 47996 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 121648 | 123733 | 128733 | 127473 | 127738 | 133738 | 139738 | 133238 | 138238 | 135113 | 137113 | 140443 | 144543 | 144543 | 144543 | 9550027 | 8782926 | 9041527 | 13560052 | 13426539 | 12981509 | 14714943 | 14811413 | 16424839 | 17028174 | 17122520 | 17216866 | 17311212 | 17311212 | 17311212 | 19165263.93 | 19259514.16 | 19353853.1 | 19448158.84 | 19542431.55 | 19636772.77 | 19730098.23 | 19821748.74 | 19913429.04 | 20005064.46 | 20096716.01 | 20538561.01 | 20616406.01 | 20616406.01 | 20616406.01 | 20619855.34 | 20623449.49 | 20627074.67 | 20630690.2 | 20634449.17 | 20636229.21 | 20638028.24 | 20638816.05 | 20639637.63 | 20640411.89 | 20641202.08 | 20642177.23 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02 | 20643230.02
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 86876 | 105376 | 123876 | 142376 | 160876 | 175876 | 190876 | 205876 | 220876 | 235876 | 250876 | 265876 | 280876 | 280876 | 280876 | 322354.27 | 362590.1 | 379585.1 | 420349.8 | 435849.8 | 435849.8 | 435849.8 | 393496.8 | 400496.8 | 403496.8 | 406496.8 | 409496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8
|  |  |  | 0 | 2000 | 4000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000
|  |  |  | 0 | 1850 | 3700 | 5550 | 7400 | 7400 | 8900 | 11525 | 13025 | 14525 | 17468 | 17468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468
|  |  |  | 0 | 4300 | 5464 | 17311 | 20406 | 80915 | 119465 | 138684 | 256772 | 263822 | 263822 | 277372 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099
|  |  |  | 0 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 11000 | 23538 | 36076 | 48614 | 61152 | 73690 | 85613 | 98151 | 110689 | 110689 | 110689 | 123284.9 | 135880.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 223541.9 | 236541.9 | 243541.9 | 250541.9 | 257541.9 | 264541.9 | 264541.9 | 264541.9 | 274541.9 | 284541.9 | 294541.9 | 304541.9 | 314541.9 | 324541.9 | 334541.9 | 344541.9 | 354541.9 | 364541.9 | 374541.9 | 384541.9 | 394541.9 | 394541.9 | 394541.9 | 404541.9 | 414541.9 | 424541.9 | 434541.9 | 444541.9 | 454541.9 | 464541.9 | 474541.9 | 484541.9 | 494541.9 | 504541.9 | 514541.9 | 524541.9 | 524541.9 | 524541.9 | 534541.9 | 544541.9 | 554541.9 | 564541.9 | 574541.9 | 584541.9 | 594541.9 | 604541.9 | 614541.9 | 624541.9 | 634541.9 | 644541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 6000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000
|  |  |  | 0 | 0 | 0 | 0 | 2500 | 2500 | 5000 | 5000 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 4000 | 500 | -3000 | -6500 | -10000 | -13500 | -17000 | -20500 | -24000 | -27500 | -31000 | -34500 | -38000 | -38000 | -38000 | -41500 | -45000 | -48500 | -52000 | -55500 | -59000 | -62500 | -66000 | -69500 | -73000 | -76500 | -80000 | -83500 | -83500 | -83500 | -87000 | -90500 | -94000 | -97500 | -101000 | -104500 | -108000 | -111500 | -115000 | -118500 | -122000 | -125500 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 25000 | 25000 | 29166.6667 | 33333.3333 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1125 | 6040 | 6415 | 6790 | 7165 | 7540 | 7915 | 7915 | 7915 | 8290 | 8665 | 9040 | 9415 | 9790 | 10165 | 10540 | 10915 | 11290 | 11665 | 12040 | 12415 | 12790 | 12790 | 12790 | 13165 | 13540 | 13915 | 14290 | 14665 | 15040 | 15415 | 15790 | 16165 | 16540 | 16915 | 17290 | 17665 | 17665 | 17665 | 18040 | 18415 | 18790 | 19165 | 19540 | 19915 | 20290 | 20665 | 21040 | 21415 | 21790 | 22165 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 1000 | 1500 | 2000 | 2500 | 3000 | 3500 | 4000 | 4500 | 5000 | 5500 | 6000 | 6500 | 6500 | 6500 | 7000 | 7500 | 8000 | 8500 | 9000 | 9500 | 10000 | 10500 | 11000 | 11500 | 12000 | 12500 | 13000 | 13000 | 13000 | 13500 | 14000 | 14500 | 15000 | 15500 | 16000 | 16500 | 17000 | 17500 | 18000 | 18500 | 19000 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 3000 | 420 | 1020 | 1620 | 2220 | 2820 | 3420 | 3420 | 3420 | 5295 | 7170 | 9045 | 10920 | 12795 | 14670 | 16545 | 18420 | 20295 | 22170 | 24045 | 25920 | 27795 | 27795 | 27795 | 29670 | 31545 | 33420 | 35295 | 37170 | 39045 | 40920 | 42795 | 44670 | 46545 | 48420 | 50295 | 52170 | 52170 | 52170 | 54045 | 55920 | 57795 | 59670 | 61545 | 63420 | 65295 | 67170 | 69045 | 70920 | 72795 | 74670 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1500 | 490 | 2490 | 2990 | 3490 | 3990 | 4490 | 4490 | 4490 | 6490 | 8490 | 10490 | 12490 | 14490 | 16490 | 18490 | 20490 | 22490 | 24490 | 26490 | 28490 | 30490 | 30490 | 30490 | 32490 | 34490 | 36490 | 38490 | 40490 | 42490 | 44490 | 46490 | 48490 | 50490 | 52490 | 54490 | 56490 | 56490 | 56490 | 58490 | 60490 | 62490 | 64490 | 66490 | 68490 | 70490 | 72490 | 74490 | 76490 | 78490 | 80490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 2000 | 3000 | 4000 | 5000 | 6000 | 7000 | 8000 | 9000 | 10000 | 11000 | 12000 | 13000 | 13000 | 13000 | 14000 | 15000 | 16000 | 17000 | 18000 | 19000 | 20000 | 21000 | 22000 | 23000 | 24000 | 25000 | 26000 | 26000 | 26000 | 27000 | 28000 | 29000 | 30000 | 31000 | 32000 | 33000 | 34000 | 35000 | 36000 | 37000 | 38000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 4000 | 3200 | 4700 | 5700 | 6700 | 8200 | 9200 | 9200 | 9200 | 10700 | 12200 | 13700 | 15200 | 16700 | 18200 | 19700 | 21200 | 22700 | 24200 | 25700 | 27200 | 28700 | 28700 | 28700 | 30200 | 31700 | 33200 | 34700 | 36200 | 37700 | 39200 | 40700 | 42200 | 43700 | 45200 | 46700 | 48200 | 48200 | 48200 | 49700 | 51200 | 52700 | 54200 | 55700 | 57200 | 58700 | 60200 | 61700 | 63200 | 64700 | 66200 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 750 | 1591 | 1841 | 2091 | 2341 | 2591 | 2841 | 2841 | 2841 | 3091 | 3341 | 3591 | 3841 | 4091 | 4341 | 4591 | 4841 | 5091 | 5341 | 5591 | 5841 | 6091 | 6091 | 6091 | 6341 | 6591 | 6841 | 7091 | 7341 | 7591 | 7841 | 8091 | 8341 | 8591 | 8841 | 9091 | 9341 | 9341 | 9341 | 9591 | 9841 | 10091 | 10341 | 10591 | 10841 | 11091 | 11341 | 11591 | 11841 | 12091 | 12341 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15145 | 30790 | 44435 | 55580 | 67225 | 78370 | 78370 | 78370 | 92370 | 106370 | 120370 | 134370 | 148370 | 162370 | 176370 | 190370 | 204370 | 218370 | 232370 | 246370 | 260370 | 260370 | 260370 | 274370 | 288370 | 302370 | 316370 | 330370 | 344370 | 358370 | 372370 | 386370 | 400370 | 414370 | 428370 | 442370 | 442370 | 442370 | 456370 | 470370 | 484370 | 498370 | 512370 | 526370 | 540370 | 554370 | 568370 | 582370 | 596370 | 610370 | 624370 | 624370 | 624370 | 624370 | 624370 | 624370 | 624370 | 624370 | 624370 | 624370 | 624370 | 624370 | 624370 | 624370 | 624370 | 624370 | 624370 | 624370
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 86876 | 116026 | 139540 | 173737 | 210682 | 298729 | 370817 | 420199 | 573825 | 611913 | 641779 | 682867 | 755132 | 755132 | 755132 | 809206.17 | 862038 | 891629 | 932393.7 | 960393.7 | 1015143.7 | 1033268.7 | 1036658.3667 | 1081195.0333 | 1111731.7 | 1135601.7 | 1160471.7 | 1184341.7 | 1184341.7 | 1184341.7 | 1212341.7 | 1240341.7 | 1268341.7 | 1296341.7 | 1324341.7 | 1352341.7 | 1380341.7 | 1408341.7 | 1436341.7 | 1464341.7 | 1492341.7 | 1520341.7 | 1548341.7 | 1548341.7 | 1548341.7 | 1576341.7 | 1604341.7 | 1632341.7 | 1660341.7 | 1688341.7 | 1716341.7 | 1744341.7 | 1772341.7 | 1800341.7 | 1828341.7 | 1856341.7 | 1884341.7 | 1912341.7 | 1912341.7 | 1912341.7 | 1940341.7 | 1968341.7 | 1996341.7 | 2024341.7 | 2052341.7 | 2080341.7 | 2108341.7 | 2136341.7 | 2164341.7 | 2192341.7 | 2220341.7 | 2248341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7
|  |  |  | 19947 | 19947 | 19947 | 19947 | 19947 | 19947 | 19947 | 19947 | 19947 | 19947 | 19947 | 19947 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352
|  |  |  | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000
|  |  |  | 0 | 65000 | 130000 | 137875 | 202875 | 267875 | 320012 | 370012 | 420012 | 470012 | 520012 | 570012 | 620012 | 620012 | 620012 | 645095 | 693095 | 744095 | 817095 | 870095 | 963095 | 994095 | 1025095 | 1056095 | 1087095 | 1118095 | 1149095 | 1180095 | 1180095 | 1180095 | 1211095 | 1242095 | 1273095 | 1304095 | 1335095 | 1366095 | 1397095 | 1428095 | 1459095 | 1490095 | 1521095 | 1552095 | 1583095 | 1583095 | 1583095 | 1627095 | 1666095 | 1715095 | 1754095 | 1793095 | 1832095 | 1871095 | 1910095 | 1949095 | 1988095 | 2027095 | 2066095 | 2105095 | 2105095 | 2105095 | 2150095 | 2190095 | 2240095 | 2280095 | 2320095 | 2360095 | 2400095 | 2440095 | 2480095 | 2505095 | 2564657 | 2624219 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 24947 | 89947 | 154947 | 162822 | 227822 | 292822 | 344959 | 394959 | 444959 | 494959 | 544959 | 594959 | 659364 | 659364 | 659364 | 684447 | 732447 | 783447 | 856447 | 909447 | 1002447 | 1033447 | 1064447 | 1095447 | 1126447 | 1157447 | 1188447 | 1219447 | 1219447 | 1219447 | 1250447 | 1281447 | 1312447 | 1343447 | 1374447 | 1405447 | 1436447 | 1467447 | 1498447 | 1529447 | 1560447 | 1591447 | 1622447 | 1622447 | 1622447 | 1666447 | 1705447 | 1754447 | 1793447 | 1832447 | 1871447 | 1910447 | 1949447 | 1988447 | 2027447 | 2066447 | 2105447 | 2144447 | 2144447 | 2144447 | 2189447 | 2229447 | 2279447 | 2319447 | 2359447 | 2399447 | 2439447 | 2479447 | 2519447 | 2544447 | 2604009 | 2663571 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 53727 | 83727 | 103727 | 110923 | 110923 | 110923 | 110923 | 110923 | 110923 | 110923 | 110923 | 110923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923
|  |  |  | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03
|  |  |  | 10496.61 | 10496.61 | 10496.61 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 103869.64 | 133869.64 | 153869.64 | 161717.42 | 161717.42 | 161717.42 | 161717.42 | 161717.42 | 161717.42 | 161717.42 | 161717.42 | 161717.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42
|  |  |  | 73279.05 | 79279.05 | 85279.05 | 99508.05 | 105508.05 | 111508.05 | 117508.05 | 123508.05 | 129508.05 | 135508.05 | 141508.05 | 147508.05 | 157737.05 | 157737.05 | 157737.05 | 165757.05 | 170858.05 | 177080.05 | 185328.51 | 192597.12 | 198329.3 | 206020.64 | 232901.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 73279.05 | 79279.05 | 85279.05 | 99508.05 | 105508.05 | 111508.05 | 117508.05 | 123508.05 | 129508.05 | 135508.05 | 141508.05 | 147508.05 | 157737.05 | 157737.05 | 157737.05 | 165757.05 | 170858.05 | 177080.05 | 185328.51 | 192597.12 | 198329.3 | 206020.64 | 232901.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64 | 241311.64
|  |  |  | 244340 | 244340 | 264340 | 282586 | 282586 | 282586 | 282586 | 282586 | 282586 | 282586 | 282586 | 282586 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 244340 | 244340 | 264340 | 282586 | 282586 | 282586 | 282586 | 282586 | 282586 | 282586 | 282586 | 282586 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286
|  |  |  | 36123 | 37823 | 39523 | 45280 | 48280 | 56820 | 60820 | 65320 | 73601 | 79601 | 85601 | 91601 | 100414 | 100414 | 100414 | 102914 | 106771.53 | 111771.53 | 118701.53 | 124791.53 | 127791.53 | 181467.96 | 148292.96 | 154928.0311 | 161563.1022 | 168198.1733 | 174833.2444 | 181468.3155 | 181468.3155 | 181468.3155 | 186454.6168 | 191440.9182 | 196427.2196 | 201413.5209 | 206399.8223 | 211386.1237 | 216372.425 | 221358.7264 | 226345.0278 | 231331.3291 | 236317.6305 | 241303.9319 | 246468.3155 | 246468.3155 | 246468.3155 | 251071.0552 | 255673.7949 | 260276.5346 | 264879.2744 | 269482.0141 | 274084.7538 | 278687.4935 | 283290.2333 | 287892.973 | 292495.7127 | 297098.4524 | 301701.1922 | 306468.3155 | 306468.3155 | 306468.3155 | 311071.0552 | 315673.7949 | 320276.5346 | 324879.2744 | 329482.0141 | 334084.7538 | 338687.4935 | 343290.2333 | 347892.973 | 352495.7127 | 357098.4524 | 361701.1922 | 366468.3155 | 366468.3155 | 366468.3155 | 366468.3155 | 366468.3155 | 366468.3155 | 366468.3155 | 366468.3155 | 366468.3155 | 366468.3155 | 366468.3155 | 366468.3155 | 366468.3155 | 366468.3155 | 366468.3155 | 366468.3155 | 366468.3155 | 366468.3155
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 371000 | 361000 | 43276 | 54291.6992 | 75487.9528 | 157767.5323 | 240047.1118 | 372326.6913 | 372326.6913 | 372326.6913 | 454606.2708 | 536885.8503 | 619165.4298 | 701445.0093 | 783724.5888 | 866004.1684 | 948283.7479 | 1030563.3274 | 1112842.9069 | 1195122.4864 | 1277402.0659 | 1359681.6454 | 1591961.2249 | 1591961.2249 | 1591961.2249 | 1674240.8044 | 1756520.3839 | 1838799.9635 | 1921079.543 | 2003359.1225 | 2085638.702 | 2167918.2815 | 2258439.6192 | 2363796.1218 | 2469152.6244 | 2574509.127 | 2679865.6296 | 2910222.1322 | 2910222.1322 | 2910222.1322 | 3015578.6348 | 3120935.1374 | 3226291.6399 | 3331648.1425 | 3439498.7404 | 3547205.4481 | 3654912.1558 | 3754377.1053 | 3839006.8899 | 3916001.2588 | 3916001.2588 | 3916001.2588 | 4041001.2588 | 4041001.2588 | 4041001.2588 | 4041001.2588 | 4041001.2588 | 4041001.2588 | 4041001.2588 | 4041001.2588 | 4041001.2588 | 4041001.2588 | 4041001.2588 | 4041001.2588 | 4041001.2588 | 4041001.2588 | 4041001.2588 | 4141001.2588 | 4141001.2588 | 4141001.2588
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 36123 | 37823 | 39523 | 45280 | 48280 | 56820 | 60820 | 65320 | 73601 | 79601 | 85601 | 91601 | 100414 | 100414 | 100414 | 102914 | 106771.53 | 111771.53 | 118701.53 | 524791.53 | 498791.53 | 542467.96 | 191568.96 | 209219.7303 | 237051.0549 | 325965.7055 | 414880.3561 | 553795.0067 | 553795.0067 | 553795.0067 | 641060.8876 | 728326.7685 | 815592.6494 | 902858.5303 | 990124.4111 | 1077390.292 | 1164656.1729 | 1251922.0538 | 1339187.9347 | 1426453.8155 | 1513719.6964 | 1600985.5773 | 1838429.5404 | 1838429.5404 | 1838429.5404 | 1925311.8596 | 2012194.1788 | 2099076.4981 | 2185958.8173 | 2272841.1366 | 2359723.4558 | 2446605.775 | 2541729.8525 | 2651689.0948 | 2761648.3371 | 2871607.5794 | 2981566.8218 | 3216690.4476 | 3216690.4476 | 3216690.4476 | 3326649.6899 | 3436608.9323 | 3546568.1746 | 3656527.4169 | 3768980.7544 | 3881290.2019 | 3993599.6493 | 4097667.3385 | 4186899.8629 | 4268496.9715 | 4273099.7112 | 4277702.451 | 4407469.5742 | 4407469.5742 | 4407469.5742 | 4407469.5742 | 4407469.5742 | 4407469.5742 | 4407469.5742 | 4407469.5742 | 4407469.5742 | 4407469.5742 | 4407469.5742 | 4407469.5742 | 4407469.5742 | 4407469.5742 | 4407469.5742 | 4507469.5742 | 4507469.5742 | 4507469.5742
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 310000 | 760000 | 843333 | 931666.3333 | 1024999.6667 | 1024999.6667 | 1024999.6667 | 1224999.6667 | 1424999.6667 | 1624999.6667 | 2638105.6667 | 4442926.6667 | 6515417.8399 | 8491955.8399 | 4104133.8399 | 5638555.8399 | 5992647.8399 | 7218578.8399 | 8918722.8399 | 11034752.8399 | 11034752.8399 | 11034752.8399 | 13818062.8399 | 16528202.8399 | 19296963.8399 | 22205034.8399 | 24964695.8399 | 27919295.8399 | 30284556.8399 | 32355450.8399 | 34078980.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272060 | 623320.05 | 903444.73 | 1186473.07 | 1484598.23 | 1855176.23 | 2139765.23 | 2439873.23 | 2758370.23 | 2953338.23 | 2953338.23 | 2953338.23 | 3243797.23 | 3547950.33 | 3858229.73 | 4166987.49 | 4473829.55 | 4785420.36 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 310000 | 760000 | 843333 | 931666.3333 | 1024999.6667 | 1024999.6667 | 1024999.6667 | 1224999.6667 | 1424999.6667 | 1624999.6667 | 2910165.6667 | 5066246.7167 | 7418862.5699 | 9678428.9099 | 5588732.0699 | 7493732.0699 | 8132413.0699 | 9658452.0699 | 11677093.0699 | 14113091.0699 | 14113091.0699 | 14113091.0699 | 17186860.0699 | 20201153.1699 | 23280193.5699 | 26497022.3299 | 29563525.3899 | 32829716.1999 | 35387484.0699 | 37458378.0699 | 39181908.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699
|  |  |  | 21485 | 21485 | 21485 | 31835 | 131835 | 156835 | 156835 | 186835 | 877500 | 928646 | 971396 | 1026919 | 1124669 | 1124669 | 1124669 | 1124669 | 1124669 | 1198416 | 1347416 | 2097102.77 | 3022583.77 | 3893508.77 | 2216018.77 | 2600823.77 | 2829818.77 | 3076018.77 | 3376018.77 | 3826018.77 | 3826018.77 | 3826018.77 | 4576018.77 | 5326018.77 | 5976018.77 | 6514937.29 | 7356501.42 | 8212637.37 | 8703356.77 | 9103356.77 | 9528356.77 | 9953356.77 | 10378356.77 | 10791183.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 21485 | 21485 | 21485 | 31835 | 131835 | 156835 | 156835 | 186835 | 877500 | 928646 | 971396 | 1026919 | 1124669 | 1124669 | 1124669 | 1124669 | 1124669 | 1198416 | 1347416 | 2097102.77 | 3022583.77 | 3893508.77 | 2216018.77 | 2600823.77 | 2829818.77 | 3076018.77 | 3376018.77 | 3826018.77 | 3826018.77 | 3826018.77 | 4576018.77 | 5326018.77 | 5976018.77 | 6514937.29 | 7356501.42 | 8212637.37 | 8703356.77 | 9103356.77 | 9528356.77 | 9953356.77 | 10378356.77 | 10791183.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77
|  |  |  | 21485 | 21485 | 21485 | 31835 | 131835 | 156835 | 156835 | 286835 | 1187500 | 1688646 | 1814729 | 1958585.3333 | 2149668.6667 | 2149668.6667 | 2149668.6667 | 2349668.6667 | 2549668.6667 | 2823415.6667 | 4257581.6667 | 7163349.4867 | 10441446.3399 | 13571937.6799 | 7804750.8399 | 10094555.8399 | 10962231.8399 | 12734470.8399 | 15053111.8399 | 17939109.8399 | 17939109.8399 | 17939109.8399 | 21762878.8399 | 25527171.9399 | 29256212.3399 | 33011959.6199 | 36920026.8099 | 41042353.5699 | 44090840.8399 | 46561734.8399 | 48710264.8399 | 49853478.8399 | 50278478.8399 | 50691305.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32540000 | 38740000 | 38740000 | 38740000 | 51927407.5218 | 59936258.9301 | 70489399.1457 | 83165813.2349 | 94276780.1337 | 100900722.5444 | 110693744.5821 | 120386636.4985 | 130347728.0862 | 138120982.0044 | 146667109.4662 | 156030155.7918 | 164271389.593 | 164271389.593 | 164271389.593 | 171555533.0523 | 179647081.5899 | 186496465.5788 | 193861839.9489 | 197547095.4799 | 201814515.6718 | 204147714.0898 | 209539189.7363 | 211149463.0068 | 212937934.4152 | 214723698.4147 | 215178899.1307 | 215549605.8829 | 215549605.8829 | 215549605.8829 | 215720312.6352 | 215836242.1014 | 216175662.8946 | 216291592.3609 | 216517076.3991 | 216578228.5794 | 216584603.4736 | 216700532.9399 | 216926016.9782 | 216948350.8724 | 217477180.7414 | 217477180.7414 | 217477180.7414 | 217477180.7414 | 217477180.7414 | 217477180.7414 | 217477180.7414 | 217477180.7414 | 217477180.7414 | 217477180.7414 | 217477180.7414 | 217477180.7414 | 217477180.7414 | 217477180.7414 | 217477180.7414 | 217477180.7414 | 217477180.7414 | 217477180.7414 | 217477180.7414 | 217477180.7414
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1845637.9913 | -3172998.9511 | -4922042.0549 | -7022989.6582 | -8864485.1405 | -9962315.7915 | -11585379.3831 | -13191847.7343 | -14842766.6259 | -16131080.4246 | -17547487.7684 | -19099288.5852 | -20465163.8463 | -20465163.8463 | -20465163.8463 | -21672414.0698 | -23013480.9826 | -24148675.5868 | -25369388.7571 | -25980171.0116 | -26687439.3417 | -27074136.0518 | -27967701.6736 | -28234583.1232 | -28530998.5521 | -28826965.2639 | -28902408.7487 | -28963848.4789 | -28963848.4789 | -28963848.4789 | -29025288.2092 | -29077649.3305 | -29167051.1767 | -29219412.2979 | -29289930.6372 | -29333213.1494 | -29367417.0525 | -29419778.1738 | -29490296.5131 | -29524500.4162 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 400000 | 600000 | 800000 | 1000000 | 1200000 | 1400000 | 1600000 | 1800000 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21387171 | -21387171 | -21387171 | -32127455 | -32127455 | -32127455 | -43616079 | -43616079 | -43616079 | -43616079 | -47775756 | -47775756 | -47775756 | -47775756 | -47775756 | -41633928 | -41633928 | -41633928 | -30947694 | -30947694 | -30947694 | -16726142 | -16726142 | -16726142 | -16726142 | -3445083 | -3445083 | -3445083 | -3445083 | -3445083 | 5063716 | 5063716 | 5063716 | 5524108 | 5524108 | 5524108 | 6942362 | 6942362 | 6942362 | 6942362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4080524 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18000000 | -18000000 | -18000000 | -18000000 | -18000000 | -18000000 | -15750000 | -15750000 | -15750000 | -13500000 | -13500000 | -13500000 | -11250000 | -11250000 | -11250000 | -9000000 | -9000000 | -9000000 | -9000000 | -9000000 | -9000000 | -6750000 | -6750000 | -6750000 | -4500000 | -4500000 | -4500000 | -2250000 | -2250000 | -2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7700000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 10200000 | 10200000 | 10200000 | 10200000 | 10200000 | 10200000 | 10200000 | 10200000 | 12700000 | 12700000 | 12700000 | 12700000 | 12700000 | 12802332 | 12802332 | 12802332 | 14102332 | 14102332 | 14102332 | 14102332 | 14102332 | 14102332 | 14102332 | 14102332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113900 | 227800 | 341700 | 455600 | 569500 | 683400 | 797300 | 911200 | 1025100 | 1139000 | 1252900 | 1366800 | 1480700 | 1480700 | 1480700 | 1594600 | 1708500 | 1822400 | 1936300 | 2050200 | 2164100 | 2278000 | 2391900 | 2505800 | 2619700 | 2733600 | 2847500 | 2961400 | 2961400 | 2961400 | 3075300 | 3189200 | 3303100 | 3417000 | 3530900 | 3644800 | 3758700 | 3872600 | 3986500 | 4100400 | 4214300 | 4328200 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4080524 | 7000000 | 21540000 | 27740000 | 27740000 | 27740000 | 39195669.5304 | 45991059.979 | 43471886.0908 | 55061252.5767 | 64444623.9932 | 61594351.7529 | 69878210.199 | 78078533.7642 | 77263982.4603 | 85462822.5797 | 92706442.6978 | 102881588.2066 | 105711169.7468 | 105711169.7468 | 105711169.7468 | 111901962.9825 | 118766344.6074 | 135486261.992 | 141744823.1918 | 144933196.4684 | 161543482.3301 | 163603884.038 | 168318026.0627 | 186246869.8836 | 187852825.8631 | 190756523.1508 | 193500180.382 | 207204406.404 | 207204406.404 | 207204406.404 | 207627573.426 | 208005041.771 | 217077759.718 | 219855228.063 | 220324093.7619 | 221116255.43 | 221402326.4211 | 221779794.7661 | 223666914.465 | 223952985.4561 | 224508068.7843 | 224621968.7843 | 217793406.7843 | 217793406.7843 | 217793406.7843 | 217793406.7843 | 217793406.7843 | 217793406.7843 | 217793406.7843 | 217793406.7843 | 217793406.7843 | 217793406.7843 | 217793406.7843 | 217793406.7843 | 217793406.7843 | 217793406.7843 | 217793406.7843 | 217793406.7843 | 217793406.7843 | 217793406.7843
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 25000 | 25000 | 10000 | 10000 | 12000 | 12000 | 12000 | 22000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37000 | 37000 | 51642 | 51642 | 77462 | 77462 | 77462 | 77462 | 77462 | 77462 | 92462 | 92462 | 92462 | 107462 | 107462 | 122462 | 137462 | 137462 | 152462 | 152462 | 152462 | 152462 | 152462 | 152462 | 152462 | 152462 | 152462 | 152462 | 177462 | 177462 | 202462 | 227462 | 227462 | 252462 | 277462 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 62000 | 62000 | 61642 | 61642 | 89462 | 89462 | 89462 | 99462 | 109462 | 109462 | 124462 | 124462 | 124462 | 139462 | 139462 | 154462 | 169462 | 169462 | 184462 | 226462 | 226462 | 226462 | 226462 | 226462 | 226462 | 226462 | 226462 | 226462 | 251462 | 251462 | 276462 | 301462 | 301462 | 326462 | 351462 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405559 | 1112559 | 2123000 | 2692660 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 944600 | 1354489 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041 | 1579041
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134574 | 719874 | 1426874 | 2437315 | 3056975 | 4173600 | 4583489 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041 | 4808041
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134574 | 739874 | 1488874 | 2499315 | 3118617 | 4235242 | 4672951 | 4897503 | 4897503 | 8988027 | 11917503 | 26457503 | 32672503 | 32672503 | 32672503 | 44143172.5304 | 50938562.979 | 48434389.0908 | 60038755.5767 | 69422126.9932 | 66586854.7529 | 74912713.199 | 83113036.7642 | 82298485.4603 | 90497325.5797 | 97740945.6978 | 107916091.2066 | 110745672.7468 | 110745672.7468 | 110745672.7468 | 116961465.9825 | 123825847.6074 | 140570764.992 | 146854326.1918 | 150042699.4684 | 166677985.3301 | 168763387.038 | 173500067.0627 | 191428910.8836 | 193034866.8631 | 195938564.1508 | 198682221.382 | 212386447.404 | 212386447.404 | 212386447.404 | 212809614.426 | 213187082.771 | 222259800.718 | 225037269.063 | 225506134.7619 | 226298296.43 | 226584367.4211 | 226961835.7661 | 228848955.465 | 229135026.4561 | 229690109.7843 | 229804009.7843 | 222975447.7843 | 222975447.7843 | 222975447.7843 | 222975447.7843 | 222975447.7843 | 222975447.7843 | 222975447.7843 | 222975447.7843 | 222975447.7843 | 222975447.7843 | 222975447.7843 | 222975447.7843 | 222975447.7843 | 222975447.7843 | 222975447.7843 | 222975447.7843 | 222975447.7843 | 222975447.7843
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4850000 | 9300000 | 9300000 | 9300000 | 12879057 | 12890724.4266 | 12902391.8531 | 12914059.2797 | 12925726.7063 | 12937394.1328 | 12949061.5594 | 12960728.986 | 12972396.386 | 22847955.186 | 22865068.186 | 22882181.186 | 23067644.586 | 23067644.586 | 23067644.586 | 23754075.086 | 24528551.086 | 25529086.286 | 27665105.786 | 29402082.186 | 31320239.686 | 33537014.586 | 36010774.286 | 38695902.586 | 40532067.586 | 42680422.686 | 44712538.586 | 46634829.486 | 46634829.486 | 46634829.486 | 48369400.186 | 49940097.786 | 51349815.686 | 52503333.986 | 53234938.186 | 55634496.986 | 55646164.386 | 55651998.086 | 55651998.086 | 55651998.086 | 55651998.086 | 55651998.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4350000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -6525000 | -6525000 | -6525000 | -4350000 | -4350000 | -4350000 | -2175000 | -2175000 | -2175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 250000 | 750000 | 850000 | 850000 | 850000 | 4429057 | 4440724.4266 | 4452391.8531 | 4464059.2797 | 4475726.7063 | 4487394.1328 | 4499061.5594 | 4510728.986 | 4522396.386 | 14397955.186 | 14415068.186 | 14432181.186 | 14617644.586 | 14617644.586 | 14617644.586 | 15304075.086 | 16078551.086 | 19254086.286 | 21390105.786 | 23127082.186 | 27220239.686 | 29437014.586 | 31910774.286 | 36770902.586 | 38607067.586 | 40755422.686 | 44962538.586 | 46884829.486 | 46884829.486 | 46884829.486 | 48619400.186 | 50190097.786 | 51599815.686 | 52753333.986 | 53484938.186 | 55884496.986 | 55896164.386 | 55901998.086 | 55901998.086 | 55901998.086 | 55901998.086 | 55901998.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086
|  |  |  | 20762.74 | 25762.74 | 30762.74 | 57499.74 | 57568.74 | 92568.74 | 105453.74 | 115453.74 | 125453.74 | 135453.74 | 145453.74 | 126397.74 | 137782.74 | 137782.74 | 137782.74 | 144237.74 | 145135.74 | 166113.74 | 169435.74 | 169435.74 | 169435.74 | 169435.74 | 169435.74 | 151591.74 | 156052.74 | 160513.74 | 164974.74 | 169435.74 | 169435.74 | 169435.74 | 171693.74 | 173951.74 | 176209.74 | 178467.74 | 180725.74 | 182983.74 | 185241.74 | 187499.74 | 189757.74 | 192015.74 | 194273.74 | 196531.74 | 198795.74 | 198795.74 | 198795.74 | 200495.74 | 202195.74 | 203895.74 | 205595.74 | 207295.74 | 208995.74 | 210695.74 | 212395.74 | 214095.74 | 215795.74 | 217495.74 | 219195.74 | 220895.74 | 220895.74 | 220895.74 | 222595.74 | 224295.74 | 225995.74 | 227695.74 | 229395.74 | 231095.74 | 232795.74 | 234495.74 | 236195.74 | 237895.74 | 239595.74 | 241295.74 | 242995.74 | 242995.74 | 242995.74 | 244695.74 | 246395.74 | 248095.74 | 249795.74 | 251495.74 | 253195.74 | 254895.74 | 256595.74 | 258295.74 | 259995.74 | 261695.74 | 263395.74 | 265615.74 | 265615.74 | 265615.74
|  |  |  | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1300000 | -1300000 | -1300000 | -1300000 | -1300000 | -1300000 | -1300000 | -1300000 | -1300000 | -1300000 | -1300000 | -1300000 | -1300000 | -1300000 | -1300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 2500000 | 2500000 | 4313600 | 6127200 | 7940800 | 9751100 | 11513800 | 13185400 | 14586600 | 15729500 | 16791100 | 17214300 | 17620100 | 17999800 | 26074055 | 26074055 | 26074055 | 26447555 | 26836355 | 27225155 | 27626555 | 28027955 | 28429355 | 28808555 | 29186955 | 29565355 | 29873955 | 30182555 | 30491155 | 41924800 | 41924800 | 41924800 | 42233400 | 42542000 | 42850600 | 43159200 | 43434800 | 43710400 | 43986000 | 44282500 | 44579000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000
|  |  |  | 3113762.74 | 3118762.74 | 3123762.74 | 3150499.74 | 3150568.74 | 3185568.74 | 3198453.74 | 3208453.74 | 3218453.74 | 3228453.74 | 3238453.74 | 3219397.74 | 3230782.74 | 3230782.74 | 3230782.74 | 3237237.74 | 3238135.74 | 3259113.74 | 3262435.74 | 3262435.74 | 3262435.74 | 3262435.74 | 3262435.74 | 3244591.74 | 3249052.74 | 3253513.74 | 3257974.74 | 5762435.74 | 5762435.74 | 5762435.74 | 7578293.74 | 9394151.74 | 11210009.74 | 13022567.74 | 14787525.74 | 15161383.74 | 16564841.74 | 17709999.74 | 18773857.74 | 19199315.74 | 19607373.74 | 19989331.74 | 28065850.74 | 28065850.74 | 28065850.74 | 28441050.74 | 28831550.74 | 29222050.74 | 29625150.74 | 30028250.74 | 31731350.74 | 32112250.74 | 32492350.74 | 32872450.74 | 33182750.74 | 33493050.74 | 33803350.74 | 45238695.74 | 45238695.74 | 45238695.74 | 45548995.74 | 45859295.74 | 46169595.74 | 46479895.74 | 46757195.74 | 47034495.74 | 47311795.74 | 47609995.74 | 47908195.74 | 52304895.74 | 52306595.74 | 52308295.74 | 52309995.74 | 52309995.74 | 52309995.74 | 52311695.74 | 52313395.74 | 52315095.74 | 52316795.74 | 52318495.74 | 52320195.74 | 52321895.74 | 52323595.74 | 52325295.74 | 52326995.74 | 52328695.74 | 52330395.74 | 52332615.74 | 52332615.74 | 52332615.74
|  |  |  | 13757346.0836 | 15529413.9561 | 18054145.2174 | 20863603.9974 | 23244671.9974 | 25373041.812 | 28027166.0059 | 30652018.0059 | 33889665.0059 | 36546731.0059 | 38730962.0059 | 41890729.3393 | 44188179.6713 | 44188179.6713 | 44188179.6713 | 56996232.2853 | 59284896.5578 | 63184299.8305 | 72819089.0007 | 76595724.262 | 81388503.7328 | 87892498.8678 | 83489807.2416 | 88564084.2328 | 96309955.1559 | 103059604.257 | 122039500.1919 | 137241778.6769 | 137241778.6769 | 137241778.6769 | 161083264.4167 | 174411499.8818 | 178373506.0801 | 196425829.7926 | 212383978.2756 | 214957420.4718 | 228615342.8145 | 241268645.2554 | 244479445.4407 | 264909392.1893 | 273803584.4966 | 285955069.0646 | 298835283.2231 | 298835283.2231 | 298835283.2231 | 306869034.3449 | 315612379.1759 | 336647349.9967 | 346188689.2826 | 352235940.9853 | 375399307.4432 | 380795952.1373 | 389092290.4863 | 412991211.1664 | 417473433.3851 | 423565602.9421 | 431562374.2025 | 459486166.2772 | 459486166.2772 | 459486166.2772 | 462751781.3297 | 465833815.3553 | 477570021.2828 | 482804908.0084 | 485321518.0831 | 489906410.8369 | 491659580.5137 | 493557953.0861 | 496993397.1476 | 503121442.0856 | 504315534.9917 | 505068444.5697 | 494473283.5312 | 494473283.5312 | 494473283.5312 | 494900713.8881 | 495275524.2951 | 495645541.7021 | 495983885.109 | 496309834.516 | 496650783.923 | 496837149.83 | 497004176.7369 | 497171203.6439 | 497338230.5509 | 497505257.4578 | 497672284.3648 | 498059831.2718 | 498059831.2718 | 498059831.2718
|  |  |  | 1456288.59 | 1619140.6683 | 1781992.7465 | 1997107.7465 | 2258473.7465 | 2514674.5611 | 2784623.755 | 3054623.755 | 3324623.755 | 3660026.755 | 3855147.755 | 4263718.755 | 4807626.755 | 4807626.755 | 4807626.755 | 5202650.4636 | 5609604.4636 | 6034791.4636 | 6464601.4636 | 6901811.4636 | 7225519.4636 | 7867243.4636 | 8388064.4636 | 8987031.4636 | 9540025.2586 | 10088894.0536 | 10637762.8487 | 11187894.6437 | 11187894.6437 | 11187894.6437 | 11710692.6532 | 12233490.6627 | 12756288.6722 | 13279086.6817 | 13801884.6912 | 14324682.7007 | 14804856.3112 | 15285029.9217 | 15765203.5322 | 16245377.1426 | 16682256.7918 | 17119136.4409 | 17556016.09 | 17556016.09 | 17556016.09 | 17913282.09 | 18270548.09 | 18627814.09 | 18985080.09 | 19342346.09 | 19699612.09 | 20054627.09 | 20409642.09 | 20773838.09 | 21138034.09 | 21502230.09 | 21866426.09 | 22230622.09 | 22230622.09 | 22230622.09 | 22594818.09 | 22959014.09 | 23323210.09 | 23687406.09 | 24051602.09 | 24415798.09 | 24798231.09 | 25180664.09 | 25347457.09 | 25347457.09 | 25347457.09 | 25347457.09 | 25347457.09 | 25347457.09 | 25347457.09 | 25347457.09 | 25347457.09 | 25347457.09 | 25347457.09 | 25347457.09 | 25347457.09 | 25347457.09 | 25347457.09 | 25347457.09 | 25347457.09 | 25347457.09 | 25347457.09 | 25347457.09 | 25347457.09 | 25347457.09
|  |  |  | 38611.75 | 38611.75 | 38611.75 | 38611.75 | 38611.75 | 38611.75 | 46986.75 | 46986.75 | 46986.75 | 46986.75 | 93337.75 | 116012.75 | 141937.75 | 141937.75 | 141937.75 | 198604.4166 | 198604.4166 | 198604.4166 | 208907.4166 | 208907.4166 | 208907.4166 | 219210.4166 | 219210.4166 | 235063.4166 | 247426.4166 | 259789.4166 | 272152.4166 | 281028.4166 | 281028.4166 | 281028.4166 | 316728.4166 | 327728.4166 | 334228.4166 | 338031.4166 | 338031.4166 | 338031.4166 | 338031.4166 | 338031.4166 | 338031.4166 | 338031.4166 | 338031.4166 | 338031.4166 | 338031.4166 | 338031.4166 | 338031.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 375516.4166 | 414875.6666 | 414875.6666 | 414875.6666 | 414875.6666 | 414875.6666 | 414875.6666 | 414875.6666 | 414875.6666 | 414875.6666 | 414875.6666 | 414875.6666 | 414875.6666 | 414875.6666 | 414875.6666 | 414875.6666 | 456202.6166 | 456202.6166 | 456202.6166 | 456202.6166 | 456202.6166 | 456202.6166 | 456202.6166 | 456202.6166 | 456202.6166 | 456202.6166 | 456202.6166 | 456202.6166 | 456202.6166 | 456202.6166 | 456202.6166
|  |  |  | 25629.24 | 28629.24 | 31629.24 | 40512.24 | 46688.24 | 51688.24 | 58184.24 | 50070.24 | 60070.24 | 65070.24 | 65070.24 | 65887.24 | 71772.24 | 71772.24 | 71772.24 | 76576.11 | 81236.08 | 86012.27 | 90733.11 | 90733.11 | 95510.08 | 100308.02 | 107895.75 | 117118.89 | 129690.6 | 133190.46 | 136430.98 | 141547.08 | 141547.08 | 141547.08 | 146558.1569 | 151569.2338 | 156580.3108 | 161591.3877 | 166602.4646 | 171613.5415 | 176624.6185 | 181635.6954 | 186646.7723 | 191657.8492 | 196668.9262 | 201680.0031 | 206691.08 | 206691.08 | 206691.08 | 211906.6954 | 217122.3108 | 222337.9262 | 227553.5415 | 232769.1569 | 237984.7723 | 243200.3877 | 248416.0031 | 253631.6185 | 258847.2338 | 264062.8492 | 269278.4646 | 274494.08 | 274494.08 | 274494.08 | 279923.5415 | 285353.0031 | 290782.4646 | 296211.9262 | 301641.3877 | 307070.8492 | 312500.3108 | 317929.7723 | 323359.2338 | 328788.6954 | 334218.1569 | 339647.6185 | 345077.08 | 345077.08 | 345077.08 | 348092.58 | 350550.08 | 352336.58 | 354123.08 | 355764.58 | 355764.58 | 355764.58 | 355764.58 | 355764.58 | 355764.58 | 355764.58 | 355764.58 | 355764.58 | 355764.58 | 355764.58
|  |  |  | 910013.9336 | 985312.7279 | 1059022.9109 | 1175770.9109 | 1364361.9109 | 1515170.9109 | 1665979.9109 | 1829165.9109 | 1979974.9109 | 2130783.9109 | 2359406.9109 | 2510215.9109 | 2606215.9109 | 2606215.9109 | 2606215.9109 | 2762821.3725 | 2925274.3725 | 3085734.3725 | 3242339.834 | 3444031.834 | 3547636.834 | 3612928.834 | 3678220.834 | 3851388.834 | 3930734.834 | 4010080.834 | 4089426.834 | 4168772.834 | 4168772.834 | 4168772.834 | 4201383.3725 | 4233993.9111 | 4266604.4496 | 4299214.9881 | 4331825.5267 | 4364436.0652 | 4397046.6038 | 4429657.1423 | 4462267.6808 | 4494878.2194 | 4527488.7579 | 4560099.2965 | 4592709.835 | 4592709.835 | 4592709.835 | 4620599.4504 | 4648489.0658 | 4676378.6813 | 4704268.2967 | 4732157.9121 | 4760047.5275 | 4787937.143 | 4815826.7584 | 4843716.3738 | 4871605.9892 | 4899495.6046 | 4927385.2201 | 4955274.8355 | 4955274.8355 | 4955274.8355 | 4984558.9317 | 5013843.028 | 5043127.1242 | 5072411.2205 | 5101695.3167 | 5130979.413 | 5160263.5092 | 5189547.6055 | 5218831.7017 | 5248115.798 | 5277399.8942 | 5306683.9904 | 5335968.0867 | 5335968.0867 | 5335968.0867 | 5372869.3877 | 5409770.6886 | 5446671.9896 | 5483573.2906 | 5520474.5916 | 5557375.8926 | 5594277.1935 | 5631178.4945 | 5668079.7955 | 5704981.0965 | 5741882.3974 | 5778783.6984 | 5815684.9994 | 5815684.9994 | 5815684.9994
|  |  |  | 214591.66 | 521591.66 | 611591.66 | 618591.66 | 625591.66 | 632591.66 | 639591.66 | 646591.66 | 653591.66 | 660591.66 | 667591.66 | 702782.66 | 775978.66 | 775978.66 | 775978.66 | 810372.2754 | 856463.2754 | 1220247.8908 | 1509917.5062 | 1509917.5062 | 1533302.5062 | 1533302.5062 | 1533302.5062 | 1397266.5062 | 1465284.5062 | 1533302.5062 | 1543302.5062 | 1553302.5062 | 1553302.5062 | 1553302.5062 | 1585195.5062 | 1617088.5062 | 1648981.5062 | 1680874.5062 | 1712767.5062 | 1744660.5062 | 1776553.5062 | 1808446.5062 | 1840339.5062 | 1872232.5062 | 1904125.5062 | 1936018.5062 | 1967911.5062 | 1967911.5062 | 1967911.5062 | 2000788.5062 | 2033665.5062 | 2066542.5062 | 2099419.5062 | 2132296.5062 | 2165173.5062 | 2198050.5062 | 2230927.5062 | 2263804.5062 | 2296681.5062 | 2329558.5062 | 2362435.5062 | 2395312.5062 | 2395312.5062 | 2395312.5062 | 2429807.5062 | 2464302.5062 | 2498797.5062 | 2533292.5062 | 2567787.5062 | 2602282.5062 | 2636777.5062 | 2671272.5062 | 2705767.5062 | 2740262.5062 | 2774757.5062 | 2809252.5062 | 2843747.5062 | 2843747.5062 | 2843747.5062 | 2874359.5062 | 2904971.5062 | 2935583.5062 | 2966195.5062 | 2996807.5062 | 3027419.5062 | 3058031.5062 | 3088643.5062 | 3119255.5062 | 3149867.5062 | 3180479.5062 | 3211091.5062 | 3241703.5062 | 3241703.5062 | 3241703.5062
|  |  |  | 29174 | 49174 | 69174 | 89174 | 109174 | 129174 | 149423 | 169174 | 189174 | 209174 | 229174 | 249174 | 289808 | 289808 | 289808 | 357255 | 402369 | 447483 | 492597 | 537711 | 582825 | 627939 | 673053 | 690956 | 735528 | 780100 | 824672 | 869244 | 869244 | 869244 | 891682.2232 | 914120.4463 | 936558.6695 | 958996.8927 | 981435.1158 | 1003873.339 | 1026311.5622 | 1048749.7854 | 1071188.0085 | 1093626.2317 | 1116064.4549 | 1138502.678 | 1160940.9012 | 1160940.9012 | 1160940.9012 | 1183810.747 | 1206680.5928 | 1229550.4385 | 1252420.2843 | 1275290.1301 | 1298159.9759 | 1321029.8216 | 1343899.6674 | 1366769.5132 | 1389639.359 | 1412509.2047 | 1435379.0505 | 1458248.8963 | 1458248.8963 | 1458248.8963 | 1481571.946 | 1504894.9957 | 1528218.0454 | 1551541.095 | 1574864.1447 | 1598187.1944 | 1621510.2441 | 1644833.2938 | 1668156.3435 | 1691479.3931 | 1714802.4428 | 1738125.4925 | 1761448.5422 | 1761448.5422 | 1761448.5422 | 1798506.2251 | 1835563.908 | 1872621.5909 | 1909679.2739 | 1946736.9568 | 1983794.6397 | 2020852.3226 | 2057910.0055 | 2094967.6884 | 2132025.3714 | 2169083.0543 | 2206140.7372 | 2243198.4201 | 2243198.4201 | 2243198.4201
|  |  |  | 0 | -13000 | -17000 | -21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 85542 | 135542 | 185542 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804 | 196804
|  |  |  | 0 | 4000 | 8000 | 9323 | 13323 | 17323 | 21448 | 25448 | 29448 | 33448 | 19341 | 21341 | 19595 | 19595 | 19595 | 22671.9231 | 22671.9231 | 22671.9231 | 26027.8462 | 26527.8462 | 26527.8462 | 26527.8462 | 26527.8462 | 26527.8462 | 26527.8462 | 27481.8462 | 28435.8462 | 29390.8462 | 29390.8462 | 29390.8462 | 34977.8462 | 40564.8462 | 46151.8462 | 51738.8462 | 57325.8462 | 62912.8462 | 65643.8462 | 68874.6154 | 72105.3846 | 75336.1538 | 78566.9231 | 81797.6923 | 85028.4615 | 85028.4615 | 85028.4615 | 88420.7692 | 91813.0769 | 95205.3846 | 98597.6923 | 101990 | 105382.3077 | 108774.6154 | 112166.9231 | 115559.2308 | 118951.5385 | 122343.8462 | 125736.1538 | 129128.4615 | 129128.4615 | 129128.4615 | 132690.3846 | 136252.3077 | 139814.2308 | 143376.1538 | 146938.0769 | 150500 | 154061.9231 | 157623.8462 | 161185.7692 | 164747.6923 | 168309.6154 | 171871.5385 | 175433.4615 | 175433.4615 | 175433.4615 | 180155.2307 | 184877 | 189598.7692 | 194320.5384 | 199042.3077 | 203764.0769 | 208485.8461 | 213207.6154 | 217929.3846 | 222651.1538 | 227372.923 | 232094.6923 | 236816.4615 | 236816.4615 | 236816.4615
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23344 | 46688 | 68276 | 63086 | 69885 | 69885 | 69885 | 69885 | 69885 | 69885 | 69885 | 69885 | 69885 | 69885 | 69885 | 81114 | 81114 | 81114 | 91353 | 91353 | 91353 | 91353 | 91353 | 93086.9231 | 94820.8462 | 96554.7692 | 98288.6923 | 100022.6154 | 101756.5385 | 103490.4615 | 105224.3846 | 106958.3077 | 108692.2308 | 110426.1538 | 112160.0769 | 113894 | 113894 | 113894 | 115714.6154 | 117535.2308 | 119355.8462 | 121176.4615 | 122997.0769 | 124817.6923 | 126638.3077 | 128458.9231 | 130279.5385 | 132100.1538 | 133920.7692 | 135741.3846 | 137562 | 137562 | 137562 | 139473.6923 | 141385.3846 | 143297.0769 | 145208.7692 | 147120.4615 | 149032.1538 | 150943.8462 | 152855.5385 | 154767.2308 | 156678.9231 | 158590.6154 | 160502.3077 | 162414 | 162414 | 162414 | 164948.1538 | 167482.3077 | 170016.4615 | 172550.6154 | 175084.7692 | 177618.9231 | 180153.0769 | 182687.2308 | 185221.3846 | 187755.5385 | 190289.6923 | 192823.8462 | 195357.8462 | 195357.8462 | 195357.8462
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5011.0769 | 10022.1538 | 15033.2308 | 20044.3077 | 25055.3846 | 30066.4615 | 35077.5385 | 40088.6154 | 45099.6923 | 50110.7692 | 55121.8462 | 60132.9231 | 65144 | 65144 | 65144 | 70110.2308 | 75076.4615 | 80042.6923 | 85008.9231 | 89975.1538 | 94941.3846 | 99907.6154 | 104873.8462 | 109840.0769 | 114806.3077 | 119772.5385 | 124738.7692 | 129705 | 129705 | 129705 | 134641.6154 | 139578.2308 | 144514.8462 | 149451.4615 | 154388.0769 | 159324.6923 | 164261.3077 | 169197.9231 | 174134.5385 | 179071.1538 | 184007.7692 | 188944.3846 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881 | 193881
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 1000 | 1500 | 2000 | 2500 | 3000 | 3500 | 4000 | 4500 | 4500 | 4500 | 5000 | 5500 | 6000 | 6500 | 7000 | 7500 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 2759851.1736 | 3369002.0461 | 3768564.3074 | 4144895.3074 | 4653028.3074 | 5096038.122 | 5563041.3159 | 6042208.3159 | 6527361.3159 | 7071161.3159 | 7548959.3159 | 8195821.3159 | 8979623.3159 | 8979623.3159 | 8979623.3159 | 9697640.5611 | 10362912.5311 | 11362234.3365 | 12301813.1765 | 12986829.1765 | 13487918.1465 | 14255649.0865 | 14906192.8165 | 15585770.9565 | 16356135.4615 | 17124496.1165 | 17824340.4316 | 18523837.3266 | 18523837.3266 | 18523837.3266 | 19187120.1747 | 19825703.0228 | 20459785.871 | 21091171.7191 | 21718754.5673 | 22346337.4154 | 22928439.8645 | 23510542.0829 | 24092644.3012 | 24674746.5195 | 25213554.7765 | 25752363.0335 | 26291171.2905 | 26291171.2905 | 26291171.2905 | 26784953.521 | 27241250.7514 | 27697547.9818 | 28153845.2122 | 28610142.4427 | 29066439.6731 | 29520485.9035 | 29974532.134 | 30437759.3644 | 30900986.5948 | 31364213.8253 | 31827441.0557 | 32290668.2861 | 32290668.2861 | 32290668.2861 | 32797165.3744 | 33264303.2126 | 33731441.0508 | 34198578.8891 | 34665716.7273 | 35132854.5656 | 35618229.4038 | 36103604.242 | 36373339.0803 | 36476280.9185 | 36579222.7567 | 36682164.595 | 36785106.4332 | 36785106.4332 | 36785106.4332 | 36941275.7902 | 37055560.1971 | 37169173.6041 | 37282787.0111 | 37396255.418 | 37508082.325 | 37619909.232 | 37731736.1389 | 37843563.0459 | 37955389.9529 | 38067216.8599 | 38179043.7668 | 38290870.5199 | 38290870.5199 | 38290870.5199
|  |  |  | 386879.57 | 416879.57 | 446879.57 | 444218.57 | 494218.57 | 544218.57 | 594218.57 | 624418.57 | 654618.57 | 684818.57 | 715018.57 | 745218.57 | 775418.57 | 775418.57 | 775418.57 | 810945.57 | 846472.57 | 881999.57 | 909199.57 | 934968.57 | 961968.57 | 991968.57 | 1028724.57 | 1068088.57 | 1107452.57 | 1146816.57 | 1186180.57 | 1238194.57 | 1238194.57 | 1238194.57 | 1280292.04 | 1324374.25 | 1369344.37 | 1416106.25 | 1470301.25 | 1524496.25 | 1582230.25 | 1642377.25 | 1702524.25 | 1762671.25 | 1836324.25 | 1923779.25 | 2011234.25 | 2011234.25 | 2011234.25 | 2104235.25 | 2197236.25 | 2290237.25 | 2387888.25 | 2485539.25 | 2583190.25 | 2671588.25 | 2759986.25 | 2848384.25 | 2936782.25 | 3025180.25 | 3119274.25 | 3213368.25 | 3213368.25 | 3213368.25 | 3337995.25 | 3532972.25 | 3837851.25 | 4202860.25 | 4610615.25 | 5080546.25 | 5593223.25 | 6167881.25 | 6790628.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 386879.57 | 416879.57 | 446879.57 | 444218.57 | 494218.57 | 544218.57 | 594218.57 | 624418.57 | 654618.57 | 684818.57 | 715018.57 | 745218.57 | 775418.57 | 775418.57 | 775418.57 | 810945.57 | 846472.57 | 881999.57 | 909199.57 | 934968.57 | 961968.57 | 991968.57 | 1028724.57 | 1068088.57 | 1107452.57 | 1146816.57 | 1186180.57 | 1238194.57 | 1238194.57 | 1238194.57 | 1280292.04 | 1324374.25 | 1369344.37 | 1416106.25 | 1470301.25 | 1524496.25 | 1582230.25 | 1642377.25 | 1702524.25 | 1762671.25 | 1836324.25 | 1923779.25 | 2011234.25 | 2011234.25 | 2011234.25 | 2104235.25 | 2197236.25 | 2290237.25 | 2387888.25 | 2485539.25 | 2583190.25 | 2671588.25 | 2759986.25 | 2848384.25 | 2936782.25 | 3025180.25 | 3119274.25 | 3213368.25 | 3213368.25 | 3213368.25 | 3337995.25 | 3532972.25 | 3837851.25 | 4202860.25 | 4610615.25 | 5080546.25 | 5593223.25 | 6167881.25 | 6790628.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25 | 7631160.25
|  |  |  | 76499.47 | 76499.47 | 78414.47 | 81060.47 | 81087.47 | 81087.47 | 81458.47 | 81458.47 | 82654.47 | 82881.47 | 82961.47 | 87961.47 | 87961.47 | 87961.47 | 87961.47 | 87961.47 | 88058.23 | 88058.23 | 88058.23 | 93058.23 | 93058.23 | 93058.23 | 93344.23 | 113553.79 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93 | 121492.93
|  |  |  | 29835.86 | 29835.86 | 29835.86 | 29835.86 | 29835.86 | 29835.86 | 29835.86 | 29835.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.86 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37 | 31999.37
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25 | 1116.25
|  |  |  | 354360.76 | 361360.76 | 392445.76 | 451713.76 | 530317.76 | 535317.76 | 567496.76 | 572496.76 | 602424.76 | 610196.76 | 610701.76 | 611701.76 | 620580.76 | 620580.76 | 620580.76 | 623580.76 | 628926.63 | 631659.15 | 642814.99 | 645191.71 | 645191.71 | 645191.71 | 645191.71 | 661949 | 661801.05 | 666801.05 | 671801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05 | 676801.05
|  |  |  | 48665.11 | 48665.11 | 50457.11 | 52034.11 | 58717.11 | 61217.11 | 65732.11 | 66232.11 | 66048.11 | 74307.11 | 72328.11 | 74328.11 | 73386.11 | 73386.11 | 73386.11 | 74886.11 | 77308.15 | 78007.34 | 79757.34 | 80313.82 | 82313.82 | 84313.82 | 87313.82 | 98210.26 | 101404.98 | 106404.98 | 111404.98 | 116404.98 | 116404.98 | 116404.98 | 116791.51 | 117196.27 | 117609.18 | 118018.79 | 118425.24 | 118837.98 | 119254.43 | 119669.31 | 120091.04 | 120502.39 | 120916.97 | 121375.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97 | 121834.97
|  |  |  | 27275.32 | 27275.32 | 27275.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27383.32 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82 | 27382.82
|  |  |  | 141282.71 | 206282.71 | 243665.71 | 248448.71 | 271433.71 | 326433.71 | 382338.71 | 437338.71 | 486530.71 | 511474.71 | 532514.71 | 592514.71 | 636915.71 | 636915.71 | 636915.71 | 674615.71 | 675797.79 | 686117.61 | 697867.61 | 707526.1 | 727526.1 | 737526.1 | 747526.1 | 887668.57 | 918257.68 | 948257.68 | 958257.68 | 958257.68 | 958257.68 | 958257.68 | 960180.68 | 962103.68 | 964026.68 | 965949.68 | 967872.68 | 969795.68 | 971718.68 | 973641.68 | 975564.68 | 977487.68 | 979410.68 | 981333.68 | 983257.68 | 983257.68 | 983257.68 | 984027.68 | 984797.68 | 985567.68 | 986337.68 | 987107.68 | 987877.68 | 988647.68 | 989417.68 | 990187.68 | 990957.68 | 991727.68 | 992497.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68 | 993257.68
|  |  |  | 142160.42 | 182160.42 | 203249.42 | 216259.42 | 234847.42 | 239847.42 | 256328.42 | 286328.42 | 300722.42 | 334265.42 | 321229.42 | 351229.42 | 334252.42 | 334252.42 | 334252.42 | 370107.42 | 389043 | 412925.18 | 419220.18 | 431986.1 | 431986.1 | 431986.1 | 435286.1 | 459719.23 | 450397.65 | 450997.65 | 451597.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65 | 452197.65
|  |  |  | 1009.5 | 1009.5 | 1104.5 | 1255.5 | 1309.5 | 3809.5 | 3941.5 | 4441.5 | 1961.5 | 2461.5 | 2461.5 | 3461.5 | 2461.5 | 2461.5 | 2461.5 | 9961.5 | 3461.5 | 3396.75 | 3596.75 | 3558 | 3558 | 3558 | 3558 | 17598.33 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97 | 21306.97
|  |  |  | 5328.44 | 5828.44 | 5828.44 | 7669.44 | 11110.44 | 13110.44 | 13757.44 | 14257.44 | 18976.44 | 20245.44 | 20926.44 | 22926.44 | 22482.44 | 22482.44 | 22482.44 | 27482.44 | 23321.07 | 23014.57 | 23014.57 | 24014.57 | 25014.57 | 26014.57 | 28014.57 | 35946.24 | 30949.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41 | 32449.41
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 623 | 5144 | 7358 | 17358 | 25379 | 35379 | 21658 | 14462 | 18876 | 21376 | 36053 | 36053 | 36053 | 46053 | 52699.75 | 61811.29 | 62327.79 | 67164.57 | 69164.57 | 69164.57 | 69164.57 | 79333.75 | 85331.93 | 90331.93 | 95331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93 | 100331.93
|  |  |  | 9163.01 | 9663.01 | 10249.01 | 13580.01 | 13832.01 | 15832.01 | 18894.01 | 19894.01 | 17695.01 | 15257.01 | 15257.01 | 15757.01 | 15257.01 | 15257.01 | 15257.01 | 15257.01 | 15257.01 | 15257.01 | 15507.01 | 15469.86 | 15469.86 | 15469.86 | 15469.86 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45 | 14970.45
|  |  |  | 2413.16 | 4613.16 | 7373.16 | 7507.16 | 7507.16 | 8507.16 | 11907.16 | 12907.16 | 16924.16 | 19561.16 | 21045.16 | 22045.16 | 24770.16 | 24770.16 | 24770.16 | 27770.16 | 24770.16 | 26770.16 | 28370.16 | 28338.27 | 28338.27 | 28338.27 | 28338.27 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39 | 39217.39
|  |  |  | 0 | 500 | 1345 | 2121 | 2485 | 6985 | 8927 | 10427 | 5626 | 5626 | 5626 | 6626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 5626 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48 | 6892.48
|  |  |  | 0 | 0 | 0 | 0 | 701 | 2701 | 2701 | 4701 | 4500 | 8983 | 16078 | 20078 | 12393 | 12393 | 12393 | 12393 | 13467.16 | 15192.79 | 15542.79 | 16672.79 | 17172.79 | 17172.79 | 17172.79 | 13335.47 | 21190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06 | 24190.06
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63 | 7901.63
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1218 | 1218 | 1218 | 1218 | 1218 | 1218 | 1218 | 2218 | 2218 | 2218 | 2218 | 916.44 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69 | 698.69
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06 | 1136.06
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 458319 | 468339 | 507030 | 526767 | 539913 | 554913 | 573213 | 581848 | 604928 | 596940 | 600940 | 600325 | 621659 | 621659 | 621659 | 624459 | 626887 | 628887 | 631887 | 634387 | 635887 | 638587 | 640087 | 643462 | 643962 | 647337 | 650712 | 654087 | 654087 | 654087 | 657163.9231 | 660240.8462 | 663317.7692 | 666394.6923 | 669471.6154 | 672548.5385 | 675625.4615 | 678702.3846 | 681779.3077 | 684856.2308 | 687933.1538 | 691010.0769 | 695087.0769 | 695087.0769 | 695087.0769 | 698164 | 701240.9231 | 704317.8462 | 707394.7692 | 710471.6923 | 713548.6154 | 716625.5385 | 719702.4615 | 722779.3846 | 725856.3077 | 728933.2308 | 732010.1538 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769 | 735087.0769
|  |  |  | 0 | 9765 | 32418 | 33303 | 38960 | 45960 | 55084 | 69972 | 99507 | 85130 | 99130 | 106698 | 135854 | 135854 | 135854 | 138924 | 172354 | 213918.429 | 250079.6003 | 257079.6003 | 289079.6003 | 305579.6003 | 330579.6003 | 362779.6003 | 370779.6003 | 412779.6003 | 454779.6003 | 495779.6003 | 495779.6003 | 495779.6003 | 517056.7092 | 535533.8181 | 554010.927 | 572488.036 | 590965.1449 | 609442.2538 | 627919.3627 | 646396.4716 | 664873.5805 | 683350.6895 | 701827.7984 | 720304.9073 | 738782.0162 | 738782.0162 | 738782.0162 | 743643.5996 | 748505.183 | 753366.7664 | 758228.3498 | 763089.9332 | 767951.5166 | 772813.0999 | 777674.6833 | 782536.2667 | 787397.8501 | 792259.4335 | 797121.0169 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003 | 801982.6003
|  |  |  | 0 | 10270 | 28804 | 47774 | 66561 | 95561 | 116284 | 188069 | 254352 | 283216 | 332216 | 364268 | 404452 | 404452 | 404452 | 420252 | 435872 | 445872 | 460872 | 475872 | 495872 | 532872 | 562872 | 607872 | 624372 | 683322 | 742272 | 801222 | 801222 | 801222 | 811942.5385 | 822663.0769 | 833383.6154 | 844104.1538 | 854824.6923 | 865545.2308 | 876265.7692 | 886986.3077 | 897706.8462 | 908427.3846 | 919147.9231 | 929868.4615 | 940589 | 940589 | 940589 | 944989 | 949389 | 953789 | 958189 | 962589 | 966989 | 971389 | 975789 | 980189 | 984589 | 988989 | 993389 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789 | 997789
|  |  |  | 0 | 7266 | 13104 | 14010 | 19236 | 28236 | 42132 | 50620 | 66680 | 63546 | 74546 | 81828 | 93282 | 93282 | 93282 | 102882 | 105742 | 117742 | 123742 | 126742 | 128742 | 134842 | 144842 | 149317 | 154317 | 158792 | 163267 | 167742 | 167742 | 167742 | 173502 | 179262 | 185022 | 190782 | 196542 | 202302 | 208062 | 213822 | 219582 | 225342 | 231102 | 236862 | 242622 | 242622 | 242622 | 246462 | 250302 | 254142 | 257982 | 261822 | 265662 | 269502 | 273342 | 277182 | 281022 | 284862 | 288702 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542 | 292542
|  |  |  | 0 | 11496 | 18310 | 22888 | 32318 | 43318 | 44356 | 47454 | 52226 | 58906 | 64906 | 70274 | 72470 | 72470 | 72470 | 72470 | 81360 | 84860 | 85860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860 | 87860
|  |  |  | 0 | 0 | 10296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 220 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 41465 | 83421 | 106952 | 137750 | 152150 | 152150 | 152150 | 152150 | 152150 | 152150 | 152150 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123 | 152123
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1296312.76 | 1502294.76 | 1745249.76 | 1895926.76 | 2112923.76 | 2289823.76 | 2479559.76 | 2693453.76 | 2915207.76 | 2999252.76 | 3103536.76 | 3265191.76 | 3414713.76 | 3414713.76 | 3414713.76 | 3549538.76 | 3634808.63 | 3753972.689 | 3849001.2003 | 3916717.8003 | 3997717.8003 | 4073017.8003 | 4158103.8003 | 4502260.6303 | 4576860.9003 | 4735760.9003 | 4870160.9003 | 4993560.9003 | 4993560.9003 | 4993560.9003 | 5036705.0007 | 5077067.3312 | 5117437.8117 | 5157804.9921 | 5198169.0126 | 5238539.323 | 5278913.3435 | 5319285.7939 | 5359665.0944 | 5400034.0148 | 5440406.1653 | 5480822.7358 | 5522240.3831 | 5522240.3831 | 5522240.3831 | 5539188.8896 | 5556137.3961 | 5573085.9025 | 5590034.409 | 5606982.9155 | 5623931.4219 | 5640879.9284 | 5657828.4349 | 5674776.9413 | 5691725.4478 | 5708673.9543 | 5725622.4607 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672 | 5742560.9672
|  |  |  | 3110000 | 3415000 | 4629000 | 6413000 | 7192659 | 7906532 | 8836807 | 9698016 | 10611984 | 11436984 | 12286984 | 13846816 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25 | 11665951.25
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 393551 | 787102 | 1168099 | 1426653 | 1561653 | 1199153 | 519768 | 714227 | 803477 | 892727 | 1065727 | 1238727 | 3186727 | 3186727 | 3186727 | 3209727 | 3232727 | 3255727 | 3278727 | 3301727 | 3324727 | 3347727 | 3370727 | 3393727 | 3416727 | 3439727 | 3462727 | 3486727 | 3486727 | 3486727 | 3509727 | 3532727 | 3555727 | 3578727 | 3601727 | 3624727 | 3647727 | 3670727 | 3693727 | 3716727 | 3739727 | 3762727 | 3786727 | 3786727 | 3786727 | 3809727 | 3832727 | 3855727 | 3878727 | 3901727 | 3924727 | 3947727 | 3970727 | 3993727 | 4016727 | 4039727 | 4062727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727 | 4086727
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1252075.1604 | 1252075.1604 | 1252075.1604 | 1529259.8126 | 1925120.1088 | 2305704.4246 | 2639434.1393 | 1590765.345 | 1708434.17 | 2173688.1297 | 2296858.2806 | 2233174.0049 | 2552165.8775 | 2598654.0317 | 2610785.0973 | 2628790.1526 | 2628790.1526 | 2628790.1526 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626 | 2909688.1626
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175977.52 | 175977.52 | 175977.52 | 202270.8639 | 236735.0661 | 240021.9746 | 241423.7444 | 238113.62 | 210178.3141 | 241090.3141 | 241090.3141 | 238258.6772 | 236714.9819 | 241590.0824 | 243045.9081 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765 | 243792.9765
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 907113.5614 | 907113.5614 | 907113.5614 | 1679179.0328 | 1923668.5909 | 2061116.6823 | 2142512.8226 | 2134559.8957 | 2129877.57 | 2119270.2199 | 2080131.2224 | 1960181.5524 | 2120141.017 | 2163062.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672 | 2172265.8672
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1000000 | -1000000 | -1000000 | -1354446 | -1607932 | -1799731 | -1841902 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755 | -1858755
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 628551.6837 | 628551.6837 | 628551.6837 | 928058.8887 | 1121410.765 | 1323567.2993 | 1398885.6251 | 1192286.9087 | 1192586.3501 | 1273286.3136 | 1287090.8061 | 1207091.4966 | 1347580.8546 | 1404436.888 | 1446749.2673 | 1453607.1771 | 1453607.1771 | 1453607.1771 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501 | 1454844.3501
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94842.259 | 94842.259 | 94842.259 | 135165.3684 | 188577.985 | 214866.7968 | 259714.0014 | 263981.2658 | 272950.6153 | 290695.6153 | 290695.6153 | 281164.9152 | 300441.7487 | 320674.8281 | 327893.8281 | 328781.4435 | 328781.4435 | 328781.4435 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368 | 330465.6368
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224954.2006 | 224954.2006 | 224954.2006 | 362569.4984 | 408970.1518 | 463635.9216 | 472481.0462 | 423586.9987 | 451618.1215 | 443040.6335 | 425975.4897 | 362701.6662 | 340553.9037 | 364919.0699 | 410897.7804 | 443207.1446 | 443207.1446 | 443207.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446 | 485580.1446
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348021.3636 | 348021.3636 | 348021.3636 | 416131.8227 | 452848.2224 | 477964.799 | 515285.9982 | 539493.5746 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348 | 552625.2348
|  |  |  | 190000 | 335000 | 545000 | 635000 | 740000 | 940000 | 1150000 | 1350000 | 1390000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1415000 | 1490000 | 1565000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000 | 1640000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 3300000 | 3750000 | 5174000 | 7048000 | 7932659 | 8846532 | 9986807 | 11048016 | 12001984 | 12851984 | 13701984 | 15261816 | 15712486.9987 | 15712486.9987 | 15712486.9987 | 17372691.5375 | 18517452.14 | 19536197.1482 | 20335439.6272 | 19166636.8585 | 18939619.6258 | 18835660.7108 | 19110890.213 | 18860870.7973 | 19565146.8684 | 19933886.2519 | 20225186.2332 | 22231993.2463 | 22231993.2463 | 22231993.2463 | 22581185.6227 | 22604185.6227 | 22627185.6227 | 22650185.6227 | 22673185.6227 | 22696185.6227 | 22719185.6227 | 22742185.6227 | 22765185.6227 | 22788185.6227 | 22811185.6227 | 22834185.6227 | 22858185.6227 | 22858185.6227 | 22858185.6227 | 22881185.6227 | 22904185.6227 | 22927185.6227 | 22950185.6227 | 22973185.6227 | 22996185.6227 | 23019185.6227 | 23042185.6227 | 23065185.6227 | 23088185.6227 | 23111185.6227 | 23134185.6227 | 23158185.6227 | 23158185.6227 | 23158185.6227 | 23181185.6227 | 23204185.6227 | 23227185.6227 | 23250185.6227 | 23273185.6227 | 23296185.6227 | 23319185.6227 | 23342185.6227 | 23365185.6227 | 23388185.6227 | 23486185.6227 | 23584185.6227 | 23683185.6227 | 23683185.6227 | 23683185.6227 | 23683185.6227 | 23683185.6227 | 23683185.6227 | 23683185.6227 | 23683185.6227 | 23683185.6227 | 23683185.6227 | 23683185.6227 | 23683185.6227 | 23683185.6227 | 23683185.6227 | 23683185.6227 | 23683185.6227 | 23683185.6227 | 23683185.6227
|  |  |  | 365000 | 420000 | 462000 | 476614 | 562614 | 617614 | 757614 | 937614 | 945614 | 1079770 | 1176770 | 1281770 | 1310770 | 1310770 | 1310770 | 1365770 | 1380770 | 1427770 | 1471770 | 1529770 | 1557770 | 1584770 | 1614209.315 | 1649209.315 | 1684209.315 | 1719209.315 | 1740248.1575 | 1761287 | 1761287 | 1761287 | 1765287 | 1769287 | 1773613 | 1777770 | 1812770 | 1847770 | 1847770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1872770 | 1887770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1902770 | 1917770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1932770 | 1947770 | 1962770 | 1962770 | 1962770 | 1962770 | 1962770 | 1962770 | 2082770 | 2082770 | 2082770
|  |  |  | 147195.78 | 150195.78 | 160195.78 | 170195.78 | 170195.78 | 170195.78 | 170195.78 | 170195.78 | 170195.78 | 170195.78 | 170195.78 | 170195.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78 | 165588.78
|  |  |  | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21 | 9916.21
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 522111.99 | 580111.99 | 632111.99 | 656725.99 | 742725.99 | 797725.99 | 937725.99 | 1117725.99 | 1125725.99 | 1259881.99 | 1356881.99 | 1461881.99 | 1486274.99 | 1486274.99 | 1486274.99 | 1541274.99 | 1556274.99 | 1603274.99 | 1647274.99 | 1705274.99 | 1733274.99 | 1760274.99 | 1789714.305 | 1824714.305 | 1859714.305 | 1894714.305 | 1915753.1475 | 1936791.99 | 1936791.99 | 1936791.99 | 1940791.99 | 1944791.99 | 1949117.99 | 1953274.99 | 1988274.99 | 2023274.99 | 2023274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2048274.99 | 2063274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2078274.99 | 2093274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2108274.99 | 2123274.99 | 2138274.99 | 2138274.99 | 2138274.99 | 2138274.99 | 2138274.99 | 2138274.99 | 2258274.99 | 2258274.99 | 2258274.99
|  |  |  | 1233000 | 1513000 | 1703000 | 1943000 | 2297000 | 2488000 | 2952000 | 3419000 | 3764000 | 4165000 | 4485000 | 4815000 | 5293261 | 5293261 | 5293261 | 5507923.53 | 5701871 | 5917945 | 6474945 | 6639726 | 6883363.7003 | 7107606.7003 | 7327569.7003 | 7484254.7003 | 7678195.4403 | 7896174.1803 | 8096052.9203 | 8239844.1603 | 8239844.1603 | 8239844.1603 | 8298580.1603 | 8354523.1603 | 8382243.1603 | 8409963.1603 | 8437683.1603 | 8465403.1603 | 8496793.1603 | 8512057.1603 | 8528321.1603 | 8544585.1603 | 8560849.1603 | 8577113.1603 | 8593377.1603 | 8593377.1603 | 8593377.1603 | 8610641.1603 | 8627905.1603 | 8645169.1603 | 8662433.1603 | 8679697.1603 | 8696961.1603 | 8707455.1603 | 8717949.1603 | 8728443.1603 | 8738937.1603 | 8749431.1603 | 8759925.1603 | 8770419.1603 | 8770419.1603 | 8770419.1603 | 8780913.1603 | 8791407.1603 | 8801901.1603 | 8812395.1603 | 8822889.1603 | 8833383.1603 | 8845153.1603 | 8856923.1603 | 8868693.1603 | 8880463.1603 | 8892233.1603 | 8904003.1603 | 8915773.1603 | 8915773.1603 | 8915773.1603 | 8927543.1603 | 8939313.1603 | 8951083.1603 | 8962853.1603 | 8974623.1603 | 8986393.1603 | 8986393.1603 | 8986393.1603 | 8986393.1603 | 8986393.1603 | 8986393.1603 | 8986393.1603 | 8986393.1603 | 8986393.1603 | 8986393.1603
|  |  |  | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000
|  |  |  | 0 | 0 | 0 | 3002 | 18541 | 35470 | 51454 | 70023 | 87239 | 91297 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381 | 92381
|  |  |  | 0 | 0 | 40000 | 36998 | 61459 | 94530 | 128546 | 29977 | 52761 | 58703 | 117619 | 202619 | 199619 | 199619 | 199619 | 319619 | 319619 | 350173 | 416547 | 474787 | 521762 | 603315 | 639399 | 715585 | 724778 | 800964 | 877150 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340 | 953340
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1346000 | 1626000 | 1856000 | 2096000 | 2490000 | 2731000 | 3245000 | 3632000 | 4017000 | 4428000 | 4808000 | 5223000 | 5698261 | 5698261 | 5698261 | 6032923.53 | 6226871 | 6473499 | 7096873 | 7319894 | 7610506.7003 | 7916302.7003 | 8172349.7003 | 8405220.7003 | 8608354.4403 | 8902519.1803 | 9178583.9203 | 9398565.1603 | 9398565.1603 | 9398565.1603 | 9457301.1603 | 9513244.1603 | 9540964.1603 | 9568684.1603 | 9596404.1603 | 9624124.1603 | 9655514.1603 | 9670778.1603 | 9687042.1603 | 9703306.1603 | 9719570.1603 | 9735834.1603 | 9752098.1603 | 9752098.1603 | 9752098.1603 | 9769362.1603 | 9786626.1603 | 9803890.1603 | 9821154.1603 | 9838418.1603 | 9855682.1603 | 9866176.1603 | 9876670.1603 | 9887164.1603 | 9897658.1603 | 9908152.1603 | 9918646.1603 | 9929140.1603 | 9929140.1603 | 9929140.1603 | 9939634.1603 | 9950128.1603 | 9960622.1603 | 9971116.1603 | 9981610.1603 | 9992104.1603 | 10003874.1603 | 10015644.1603 | 10027414.1603 | 10039184.1603 | 10050954.1603 | 10062724.1603 | 10074494.1603 | 10074494.1603 | 10074494.1603 | 10086264.1603 | 10098034.1603 | 10109804.1603 | 10121574.1603 | 10133344.1603 | 10145114.1603 | 10145114.1603 | 10145114.1603 | 10145114.1603 | 10145114.1603 | 10145114.1603 | 10145114.1603 | 10145114.1603 | 10145114.1603 | 10145114.1603
|  |  |  | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 20521.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46 | 31104.46
|  |  |  | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76 | 268642.76
|  |  |  | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99 | 29382.99
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75 | 298025.75
|  |  |  | 0 | 0 | 0 | 22519 | 52519 | 67519 | 67519 | 87519 | 107519 | 113275 | 128275 | 138275 | 148275 | 148275 | 148275 | 181901.13 | 181901.13 | 220779.53 | 231747.71 | 231747.71 | 246668.71 | 246668.71 | 246668.71 | 253010.71 | 253010.71 | 271147.71 | 289431.71 | 301175.71 | 301175.71 | 301175.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71 | 309163.71
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 22519 | 52519 | 67519 | 67519 | 97519 | 117519 | 113275 | 128275 | 138275 | 155775 | 155775 | 155775 | 189401.13 | 189401.13 | 228279.53 | 239247.71 | 239247.71 | 254168.71 | 254168.71 | 254168.71 | 260510.71 | 260510.71 | 278647.71 | 296931.71 | 308675.71 | 308675.71 | 308675.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71 | 316663.71
|  |  |  | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843 | 25843
|  |  |  | 35624 | 37709 | 42709 | 41449 | 41714 | 47714 | 53714 | 47214 | 52214 | 49089 | 51089 | 54419 | 58519 | 58519 | 58519 | 67668 | 71769 | 80519 | 85019 | 91669 | 101819 | 111309 | 117779 | 124429 | 133279 | 137279 | 141279 | 142489 | 142489 | 142489 | 146694.93 | 151099.16 | 155592.1 | 160051.84 | 164478.55 | 168973.77 | 172453.23 | 174257.74 | 176092.04 | 177881.46 | 179687.01 | 181686.01 | 183685.01 | 183685.01 | 183685.01 | 185288.34 | 187036.49 | 188815.67 | 190585.2 | 192340.17 | 194120.21 | 195919.24 | 196707.05 | 197528.63 | 198302.89 | 199093.08 | 200068.23 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02 | 201121.02
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181 | 60181
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9076400 | 8332477 | 6797328 | 6797328 | 6797328 | 6797328 | 8431272 | 8431272 | 10110818 | 11895818 | 11895818 | 11895818 | 11895818 | 11895818 | 11895818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818 | 13655818
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319935 | 292656 | 2077656 | 6589681 | 6449518 | 5976338 | 5976338 | 5976338 | 5976338 | 4191338 | 4191338 | 4191338 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327 | 4700327
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 104000 | 192000 | 118000 | 93000 | 113000 | 163000 | 213000 | 213000 | 213000 | 320769 | 428538 | 536307 | 644076 | 751845 | 859614 | 967383 | 1075152 | 1182921 | 1290690 | 1398459 | 1506228 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 4000 | 6000 | 8000 | 9230 | 11076 | 12922 | 14768 | 16614 | 16614 | 16614 | 18460 | 20306 | 22152 | 23998 | 25844 | 27690 | 29536 | 31382 | 33228 | 35074 | 36920 | 38766 | 40612 | 40612 | 40612 | 42458 | 44304 | 46150 | 47996 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 121648 | 123733 | 128733 | 127473 | 127738 | 133738 | 139738 | 133238 | 138238 | 135113 | 137113 | 140443 | 144543 | 144543 | 144543 | 9550027 | 8782926 | 9041527 | 13560052 | 13426539 | 12981509 | 14714943 | 14811413 | 16424839 | 16410535 | 16436381 | 16492227 | 17054272 | 17054272 | 17054272 | 18928092.93 | 19042112.16 | 19156220.1 | 19270294.84 | 19384336.55 | 19498446.77 | 19611541.23 | 19722960.74 | 19834410.04 | 19945814.46 | 20057235.01 | 20518849.01 | 20616466.01 | 20616466.01 | 20616466.01 | 20619915.34 | 20623509.49 | 20627134.67 | 20630750.2 | 20634509.17 | 20636289.21 | 20638088.24 | 20638876.05 | 20639697.63 | 20640471.89 | 20641262.08 | 20642237.23 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02 | 20643290.02
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95 | 1312.95
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 86876 | 105376 | 123876 | 142376 | 160876 | 175876 | 190876 | 205876 | 220876 | 235876 | 250876 | 265876 | 280876 | 280876 | 280876 | 322354.27 | 362590.1 | 379585.1 | 420349.8 | 435849.8 | 435849.8 | 435849.8 | 393496.8 | 400496.8 | 403496.8 | 406496.8 | 409496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8 | 412496.8
|  |  |  | 0 | 2000 | 4000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000
|  |  |  | 0 | 1850 | 3700 | 5550 | 7400 | 7400 | 8900 | 11525 | 13025 | 14525 | 17468 | 17468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468 | 20468
|  |  |  | 0 | 4300 | 5464 | 17311 | 20406 | 80915 | 119465 | 138684 | 256772 | 263822 | 263822 | 277372 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099 | 319099
|  |  |  | 0 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 11000 | 23538 | 36076 | 48614 | 61152 | 73690 | 85613 | 98151 | 110689 | 110689 | 110689 | 123284.9 | 135880.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 148476.9 | 223541.9 | 236541.9 | 243541.9 | 250541.9 | 257541.9 | 264541.9 | 264541.9 | 264541.9 | 274541.9 | 284541.9 | 294541.9 | 304541.9 | 314541.9 | 324541.9 | 334541.9 | 344541.9 | 354541.9 | 364541.9 | 374541.9 | 384541.9 | 394541.9 | 394541.9 | 394541.9 | 404541.9 | 414541.9 | 424541.9 | 434541.9 | 444541.9 | 454541.9 | 464541.9 | 474541.9 | 484541.9 | 494541.9 | 504541.9 | 514541.9 | 524541.9 | 524541.9 | 524541.9 | 534541.9 | 544541.9 | 554541.9 | 564541.9 | 574541.9 | 584541.9 | 594541.9 | 604541.9 | 614541.9 | 624541.9 | 634541.9 | 644541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9 | 654541.9
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 6000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000
|  |  |  | 0 | 0 | 0 | 0 | 2500 | 2500 | 5000 | 5000 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 4000 | 500 | -3000 | -6500 | -10000 | -13500 | -17000 | -20500 | -24000 | -27500 | -31000 | -34500 | -38000 | -38000 | -38000 | -41500 | -45000 | -48500 | -52000 | -55500 | -59000 | -62500 | -66000 | -69500 | -73000 | -76500 | -80000 | -83500 | -83500 | -83500 | -87000 | -90500 | -94000 | -97500 | -101000 | -104500 | -108000 | -111500 | -115000 | -118500 | -122000 | -125500 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000 | -129000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 25000 | 25000 | 29166.6667 | 33333.3333 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500 | 37500
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1125 | 6040 | 6415 | 6790 | 7165 | 7540 | 7915 | 7915 | 7915 | 8290 | 8665 | 9040 | 9415 | 9790 | 10165 | 10540 | 10915 | 11290 | 11665 | 12040 | 12415 | 12790 | 12790 | 12790 | 13165 | 13540 | 13915 | 14290 | 14665 | 15040 | 15415 | 15790 | 16165 | 16540 | 16915 | 17290 | 17665 | 17665 | 17665 | 18040 | 18415 | 18790 | 19165 | 19540 | 19915 | 20290 | 20665 | 21040 | 21415 | 21790 | 22165 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540 | 22540
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 1000 | 1500 | 2000 | 2500 | 3000 | 3500 | 4000 | 4500 | 5000 | 5500 | 6000 | 6500 | 6500 | 6500 | 7000 | 7500 | 8000 | 8500 | 9000 | 9500 | 10000 | 10500 | 11000 | 11500 | 12000 | 12500 | 13000 | 13000 | 13000 | 13500 | 14000 | 14500 | 15000 | 15500 | 16000 | 16500 | 17000 | 17500 | 18000 | 18500 | 19000 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 3000 | 420 | 1020 | 1620 | 2220 | 2820 | 3420 | 3420 | 3420 | 5295 | 7170 | 9045 | 10920 | 12795 | 14670 | 16545 | 18420 | 20295 | 22170 | 24045 | 25920 | 27795 | 27795 | 27795 | 29670 | 31545 | 33420 | 35295 | 37170 | 39045 | 40920 | 42795 | 44670 | 46545 | 48420 | 50295 | 52170 | 52170 | 52170 | 54045 | 55920 | 57795 | 59670 | 61545 | 63420 | 65295 | 67170 | 69045 | 70920 | 72795 | 74670 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545 | 76545
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1500 | 490 | 2490 | 2990 | 3490 | 3990 | 4490 | 4490 | 4490 | 6490 | 8490 | 10490 | 12490 | 14490 | 16490 | 18490 | 20490 | 22490 | 24490 | 26490 | 28490 | 30490 | 30490 | 30490 | 32490 | 34490 | 36490 | 38490 | 40490 | 42490 | 44490 | 46490 | 48490 | 50490 | 52490 | 54490 | 56490 | 56490 | 56490 | 58490 | 60490 | 62490 | 64490 | 66490 | 68490 | 70490 | 72490 | 74490 | 76490 | 78490 | 80490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490 | 82490
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 2000 | 3000 | 4000 | 5000 | 6000 | 7000 | 8000 | 9000 | 10000 | 11000 | 12000 | 13000 | 13000 | 13000 | 14000 | 15000 | 16000 | 17000 | 18000 | 19000 | 20000 | 21000 | 22000 | 23000 | 24000 | 25000 | 26000 | 26000 | 26000 | 27000 | 28000 | 29000 | 30000 | 31000 | 32000 | 33000 | 34000 | 35000 | 36000 | 37000 | 38000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 4000 | 3200 | 4700 | 5700 | 6700 | 8200 | 9200 | 9200 | 9200 | 10700 | 12200 | 13700 | 15200 | 16700 | 18200 | 19700 | 21200 | 22700 | 24200 | 25700 | 27200 | 28700 | 28700 | 28700 | 30200 | 31700 | 33200 | 34700 | 36200 | 37700 | 39200 | 40700 | 42200 | 43700 | 45200 | 46700 | 48200 | 48200 | 48200 | 49700 | 51200 | 52700 | 54200 | 55700 | 57200 | 58700 | 60200 | 61700 | 63200 | 64700 | 66200 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700 | 67700
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 750 | 1591 | 1841 | 2091 | 2341 | 2591 | 2841 | 2841 | 2841 | 3091 | 3341 | 3591 | 3841 | 4091 | 4341 | 4591 | 4841 | 5091 | 5341 | 5591 | 5841 | 6091 | 6091 | 6091 | 6341 | 6591 | 6841 | 7091 | 7341 | 7591 | 7841 | 8091 | 8341 | 8591 | 8841 | 9091 | 9341 | 9341 | 9341 | 9591 | 9841 | 10091 | 10341 | 10591 | 10841 | 11091 | 11341 | 11591 | 11841 | 12091 | 12341 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591 | 12591
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15145 | 30790 | 4960 | 16105 | 27750 | 38895 | 38895 | 38895 | 52895 | 66895 | 80895 | 94895 | 108895 | 122895 | 136895 | 150895 | 164895 | 178895 | 192895 | 206895 | 220895 | 220895 | 220895 | 234895 | 248895 | 262895 | 276895 | 290895 | 304895 | 318895 | 332895 | 346895 | 360895 | 374895 | 388895 | 402895 | 402895 | 402895 | 416895 | 430895 | 444895 | 458895 | 472895 | 486895 | 500895 | 514895 | 528895 | 542895 | 556895 | 570895 | 584895 | 584895 | 584895 | 584895 | 584895 | 584895 | 584895 | 584895 | 584895 | 584895 | 584895 | 584895 | 584895 | 584895 | 584895 | 584895 | 584895 | 584895
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082 | 4082
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745 | 19745
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648 | 15648
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 86876 | 116026 | 139540 | 173737 | 210682 | 298729 | 370817 | 420199 | 573825 | 611913 | 641779 | 682867 | 755132 | 755132 | 755132 | 809206.17 | 862038 | 891629 | 932393.7 | 960393.7 | 1015143.7 | 1033268.7 | 1036658.3667 | 1081195.0333 | 1111731.7 | 1135601.7 | 1160471.7 | 1184341.7 | 1184341.7 | 1184341.7 | 1212341.7 | 1240341.7 | 1268341.7 | 1296341.7 | 1324341.7 | 1352341.7 | 1380341.7 | 1408341.7 | 1436341.7 | 1464341.7 | 1492341.7 | 1520341.7 | 1548341.7 | 1548341.7 | 1548341.7 | 1576341.7 | 1604341.7 | 1632341.7 | 1660341.7 | 1688341.7 | 1716341.7 | 1744341.7 | 1772341.7 | 1800341.7 | 1828341.7 | 1856341.7 | 1884341.7 | 1912341.7 | 1912341.7 | 1912341.7 | 1940341.7 | 1968341.7 | 1996341.7 | 2024341.7 | 2052341.7 | 2080341.7 | 2108341.7 | 2136341.7 | 2164341.7 | 2192341.7 | 2220341.7 | 2248341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7 | 2276341.7
|  |  |  | 19947 | 19947 | 19947 | 19947 | 19947 | 19947 | 19947 | 19947 | 19947 | 19947 | 19947 | 19947 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352 | 34352
|  |  |  | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000
|  |  |  | 0 | 65000 | 130000 | 137875 | 202875 | 267875 | 320012 | 370012 | 420012 | 470012 | 520012 | 570012 | 620012 | 620012 | 620012 | 645095 | 693095 | 744095 | 817095 | 870095 | 963095 | 994095 | 1025095 | 1056095 | 1087095 | 1118095 | 1149095 | 1180095 | 1180095 | 1180095 | 1211095 | 1242095 | 1273095 | 1304095 | 1335095 | 1366095 | 1397095 | 1428095 | 1459095 | 1490095 | 1521095 | 1552095 | 1583095 | 1583095 | 1583095 | 1627095 | 1666095 | 1715095 | 1754095 | 1793095 | 1832095 | 1871095 | 1910095 | 1949095 | 1988095 | 2027095 | 2066095 | 2105095 | 2105095 | 2105095 | 2150095 | 2190095 | 2240095 | 2280095 | 2320095 | 2360095 | 2400095 | 2440095 | 2480095 | 2505095 | 2564657 | 2624219 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781 | 2683781
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 24947 | 89947 | 154947 | 162822 | 227822 | 292822 | 344959 | 394959 | 444959 | 494959 | 544959 | 594959 | 659364 | 659364 | 659364 | 684447 | 732447 | 783447 | 856447 | 909447 | 1002447 | 1033447 | 1064447 | 1095447 | 1126447 | 1157447 | 1188447 | 1219447 | 1219447 | 1219447 | 1250447 | 1281447 | 1312447 | 1343447 | 1374447 | 1405447 | 1436447 | 1467447 | 1498447 | 1529447 | 1560447 | 1591447 | 1622447 | 1622447 | 1622447 | 1666447 | 1705447 | 1754447 | 1793447 | 1832447 | 1871447 | 1910447 | 1949447 | 1988447 | 2027447 | 2066447 | 2105447 | 2144447 | 2144447 | 2144447 | 2189447 | 2229447 | 2279447 | 2319447 | 2359447 | 2399447 | 2439447 | 2479447 | 2519447 | 2544447 | 2604009 | 2663571 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133 | 2723133
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 53727 | 83727 | 103727 | 110923 | 110923 | 110923 | 110923 | 110923 | 110923 | 110923 | 110923 | 110923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 123923 | 137423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423 | 157423
|  |  |  | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 39646.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03 | 17184.03
|  |  |  | 10496.61 | 10496.61 | 10496.61 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39 | 11148.39
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 103869.64 | 133869.64 | 153869.64 | 161717.42 | 161717.42 | 161717.42 | 161717.42 | 161717.42 | 161717.42 | 161717.42 | 161717.42 | 161717.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 152255.42 | 165755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42 | 185755.42
|  |  |  | 73279.05 | 79279.05 | 85279.05 | 99508.05 | 105508.05 | 111508.05 | 117508.05 | 123508.05 | 129508.05 | 135508.05 | 141508.05 | 147508.05 | 157737.05 | 157737.05 | 157737.05 | 165757.05 | 170858.05 | 177080.05 | 185328.51 | 192597.12 | 198329.3 | 206020.64 | 232901.64 | 241311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 73279.05 | 79279.05 | 85279.05 | 99508.05 | 105508.05 | 111508.05 | 117508.05 | 123508.05 | 129508.05 | 135508.05 | 141508.05 | 147508.05 | 157737.05 | 157737.05 | 157737.05 | 165757.05 | 170858.05 | 177080.05 | 185328.51 | 192597.12 | 198329.3 | 206020.64 | 232901.64 | 241311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64 | 251311.64
|  |  |  | 244340 | 244340 | 264340 | 282586 | 282586 | 282586 | 282586 | 282586 | 282586 | 282586 | 282586 | 282586 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 244340 | 244340 | 264340 | 282586 | 282586 | 282586 | 282586 | 282586 | 282586 | 282586 | 282586 | 282586 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286 | 285286
|  |  |  | 36123 | 37823 | 39523 | 45280 | 48280 | 56820 | 60820 | 65320 | 73601 | 79601 | 85601 | 91601 | 100414 | 100414 | 100414 | 102914 | 106771.53 | 111771.53 | 118701.53 | 124791.53 | 127791.53 | 181467.96 | 148292.96 | 154928.0311 | 161563.1022 | 168198.1733 | 174833.2444 | 181468.3144 | 181468.3144 | 181468.3144 | 186454.6157 | 191440.9171 | 196427.2185 | 201413.5198 | 206399.8212 | 211386.1226 | 216372.4239 | 221358.7253 | 226345.0267 | 231331.3281 | 236317.6294 | 241303.9308 | 246468.3144 | 246468.3144 | 246468.3144 | 251071.0541 | 255673.7938 | 260276.5335 | 264879.2733 | 269482.013 | 274084.7527 | 278687.4924 | 283290.2322 | 287892.9719 | 292495.7116 | 297098.4513 | 301701.1911 | 306468.3144 | 306468.3144 | 306468.3144 | 311071.0541 | 315673.7938 | 320276.5335 | 324879.2733 | 329482.013 | 334084.7527 | 338687.4924 | 343290.2322 | 347892.9719 | 352495.7116 | 357098.4513 | 361701.1911 | 366468.3144 | 366468.3144 | 366468.3144 | 366468.3144 | 366468.3144 | 366468.3144 | 366468.3144 | 366468.3144 | 366468.3144 | 366468.3144 | 366468.3144 | 366468.3144 | 366468.3144 | 366468.3144 | 366468.3144 | 366468.3144 | 366468.3144 | 366468.3144
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 371000 | 361000 | 43276 | 54291.6992 | 76156.9528 | 154552.1884 | 232947.424 | 361342.6596 | 361342.6596 | 361342.6596 | 443323.2829 | 525303.9063 | 622284.5296 | 704265.153 | 785803.7764 | 867308.3997 | 948813.0231 | 1030317.6464 | 1111822.2698 | 1193326.8932 | 1273358.0769 | 1353389.2607 | 1583420.4445 | 1583420.4445 | 1583420.4445 | 1663451.6283 | 1743482.8121 | 1823513.9959 | 1903545.1797 | 1983576.3634 | 2063607.5472 | 2143638.731 | 2231911.673 | 2335019.7799 | 2438127.8868 | 2541235.9936 | 2644344.1005 | 2872452.2073 | 2872452.2073 | 2872452.2073 | 2975560.3142 | 3078668.4211 | 3181776.5279 | 3284884.6348 | 3387869.8697 | 3490745.2145 | 3593620.5593 | 3688254.1459 | 3768052.5676 | 3847850.9893 | 3916000.3818 | 3916000.3818 | 4041000.3818 | 4041000.3818 | 4041000.3818 | 4041000.3818 | 4041000.3818 | 4041000.3818 | 4041000.3818 | 4041000.3818 | 4041000.3818 | 4041000.3818 | 4041000.3818 | 4041000.3818 | 4041000.3818 | 4041000.3818 | 4041000.3818 | 4141000.3818 | 4141000.3818 | 4141000.3818
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 36123 | 37823 | 39523 | 45280 | 48280 | 56820 | 60820 | 65320 | 73601 | 79601 | 85601 | 91601 | 100414 | 100414 | 100414 | 102914 | 106771.53 | 111771.53 | 118701.53 | 524791.53 | 498791.53 | 542467.96 | 191568.96 | 209219.7303 | 237720.0549 | 322750.3616 | 407780.6683 | 542810.9739 | 542810.9739 | 542810.9739 | 629777.8987 | 716744.8234 | 818711.7481 | 905678.6728 | 992203.5976 | 1078694.5223 | 1165185.447 | 1251676.3718 | 1338167.2965 | 1424658.2212 | 1509675.7064 | 1594693.1915 | 1829888.7589 | 1829888.7589 | 1829888.7589 | 1914522.6824 | 1999156.6059 | 2083790.5294 | 2168424.4529 | 2253058.3764 | 2337692.2999 | 2422326.2235 | 2515201.9052 | 2622912.7518 | 2730623.5984 | 2838334.445 | 2946045.2916 | 3178920.5217 | 3178920.5217 | 3178920.5217 | 3286631.3683 | 3394342.2149 | 3502053.0615 | 3609763.9081 | 3717351.8827 | 3824829.9672 | 3932308.0518 | 4031544.3781 | 4115945.5395 | 4200346.701 | 4273098.8331 | 4277701.5728 | 4407468.6961 | 4407468.6961 | 4407468.6961 | 4407468.6961 | 4407468.6961 | 4407468.6961 | 4407468.6961 | 4407468.6961 | 4407468.6961 | 4407468.6961 | 4407468.6961 | 4407468.6961 | 4407468.6961 | 4407468.6961 | 4407468.6961 | 4507468.6961 | 4507468.6961 | 4507468.6961
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 310000 | 760000 | 843333 | 931666.3333 | 1024999.6667 | 1024999.6667 | 1024999.6667 | 1224999.6667 | 1424999.6667 | 1624999.6667 | 2638105.6667 | 4442926.6667 | 6515417.8399 | 8491955.8399 | 4104133.8399 | 5638555.8399 | 6287474.8399 | 7513405.8399 | 9213549.8399 | 11034752.8399 | 11034752.8399 | 11034752.8399 | 13818062.8399 | 16528202.8399 | 19296963.8399 | 22205034.8399 | 24964695.8399 | 27919295.8399 | 30284556.8399 | 32355450.8399 | 34078980.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399 | 34797194.8399
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272060 | 623320.05 | 903444.73 | 1186473.07 | 1484598.23 | 1855176.23 | 2139765.23 | 2439873.23 | 2758370.23 | 2953338.23 | 2953338.23 | 2953338.23 | 3243797.23 | 3547950.33 | 3858229.73 | 4166987.49 | 4473829.55 | 4785420.36 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23 | 4977927.23
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 310000 | 760000 | 843333 | 931666.3333 | 1024999.6667 | 1024999.6667 | 1024999.6667 | 1224999.6667 | 1424999.6667 | 1624999.6667 | 2910165.6667 | 5066246.7167 | 7418862.5699 | 9678428.9099 | 5588732.0699 | 7493732.0699 | 8427240.0699 | 9953279.0699 | 11971920.0699 | 14113091.0699 | 14113091.0699 | 14113091.0699 | 17186860.0699 | 20201153.1699 | 23280193.5699 | 26497022.3299 | 29563525.3899 | 32829716.1999 | 35387484.0699 | 37458378.0699 | 39181908.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699 | 39900122.0699
|  |  |  | 21485 | 21485 | 21485 | 31835 | 131835 | 156835 | 156835 | 186835 | 877500 | 928646 | 971396 | 1026919 | 1124669 | 1124669 | 1124669 | 1124669 | 1124669 | 1198416 | 1347416 | 2097102.77 | 3022583.77 | 3893508.77 | 2216018.77 | 2600823.77 | 2694456.77 | 2991018.77 | 3341018.77 | 3826018.77 | 3826018.77 | 3826018.77 | 4576018.77 | 5326018.77 | 5976018.77 | 6514937.29 | 7356501.42 | 8212637.37 | 8703356.77 | 9103356.77 | 9528356.77 | 9953356.77 | 10378356.77 | 10791183.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 21485 | 21485 | 21485 | 31835 | 131835 | 156835 | 156835 | 186835 | 877500 | 928646 | 971396 | 1026919 | 1124669 | 1124669 | 1124669 | 1124669 | 1124669 | 1198416 | 1347416 | 2097102.77 | 3022583.77 | 3893508.77 | 2216018.77 | 2600823.77 | 2694456.77 | 2991018.77 | 3341018.77 | 3826018.77 | 3826018.77 | 3826018.77 | 4576018.77 | 5326018.77 | 5976018.77 | 6514937.29 | 7356501.42 | 8212637.37 | 8703356.77 | 9103356.77 | 9528356.77 | 9953356.77 | 10378356.77 | 10791183.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77 | 11627213.77
|  |  |  | 21485 | 21485 | 21485 | 31835 | 131835 | 156835 | 156835 | 286835 | 1187500 | 1688646 | 1814729 | 1958585.3333 | 2149668.6667 | 2149668.6667 | 2149668.6667 | 2349668.6667 | 2549668.6667 | 2823415.6667 | 4257581.6667 | 7163349.4867 | 10441446.3399 | 13571937.6799 | 7804750.8399 | 10094555.8399 | 11121696.8399 | 12944297.8399 | 15312938.8399 | 17939109.8399 | 17939109.8399 | 17939109.8399 | 21762878.8399 | 25527171.9399 | 29256212.3399 | 33011959.6199 | 36920026.8099 | 41042353.5699 | 44090840.8399 | 46561734.8399 | 48710264.8399 | 49853478.8399 | 50278478.8399 | 50691305.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399 | 51527335.8399
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30040000 | 36240000 | 36240000 | 36240000 | 49427407.5218 | 57436258.9301 | 67989399.1457 | 80665813.2349 | 91776780.1337 | 98400722.5444 | 108193744.5821 | 117886636.4985 | 127847728.0862 | 135620982.0044 | 144167109.4662 | 153530155.7918 | 161771389.593 | 161771389.593 | 161771389.593 | 169055533.0523 | 177147081.5899 | 183996465.5788 | 191361839.9489 | 195047095.4799 | 199314515.6718 | 204147713.6718 | 209539189.3182 | 211149462.5887 | 212937933.9972 | 214723697.9967 | 215178898.7126 | 215549605.4649 | 215549605.4649 | 215549605.4649 | 215720312.2172 | 215836241.6834 | 216175662.4766 | 216291591.9428 | 216517075.9811 | 216578228.1614 | 216584603.0556 | 216700532.5218 | 216926016.5601 | 216948350.4543 | 217477180.3234 | 217477180.3234 | 217477180.3234 | 217477180.3234 | 217477180.3234 | 217477180.3234 | 217477180.3234 | 217477180.3234 | 217477180.3234 | 217477180.3234 | 217477180.3234 | 217477180.3234 | 217477180.3234 | 217477180.3234 | 217477180.3234 | 217477180.3234 | 217477180.3234 | 217477180.3234 | 217477180.3234 | 217477180.3234
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1845637.9913 | -3172998.9511 | -4922042.0549 | -7022989.6582 | -8864485.1405 | -9962315.7915 | -11585379.3831 | -13191847.7343 | -14842766.6259 | -16131080.4246 | -17547487.7684 | -19099288.5852 | -20465163.8463 | -20465163.8463 | -20465163.8463 | -21672414.0698 | -23013480.9826 | -24148675.5868 | -25369388.7571 | -25980171.0116 | -26687439.3417 | -27074136.0518 | -27967701.6736 | -28234583.1232 | -28530998.5521 | -28826965.2639 | -28902408.7487 | -28963848.4789 | -28963848.4789 | -28963848.4789 | -29025288.2092 | -29077649.3305 | -29167051.1767 | -29219412.2979 | -29289930.6372 | -29333213.1494 | -29367417.0525 | -29419778.1738 | -29490296.5131 | -29524500.4162 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571 | -29612146.9571
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 400000 | 600000 | 800000 | 1000000 | 1200000 | 1400000 | 1600000 | 1800000 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041 | 1984041
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21387171 | -21387171 | -21387171 | -32127455 | -32127455 | -32127455 | -43616079 | -43616079 | -43616079 | -43616079 | -47775756 | -47775756 | -47775756 | -47775756 | -47775756 | -41633928 | -41633928 | -41633928 | -30947694 | -30947694 | -30947694 | -16726142 | -16726142 | -16726142 | -16726142 | -3445083 | -3445083 | -3445083 | -3445083 | -3445083 | 5063716 | 5063716 | 5063716 | 5524108 | 5524108 | 5524108 | 6942362 | 6942362 | 6942362 | 6942362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4080524 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15500000 | -15500000 | -15500000 | -15500000 | -15500000 | -15500000 | -13250000 | -13250000 | -13250000 | -11000000 | -11000000 | -11000000 | -8750000 | -8750000 | -8750000 | -6500000 | -6500000 | -6500000 | -6500000 | -6500000 | -6500000 | -4875000 | -4875000 | -4875000 | -3250000 | -3250000 | -3250000 | -1625000 | -1625000 | -1625000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7700000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 10200000 | 10200000 | 10200000 | 10200000 | 10200000 | 10200000 | 10200000 | 10200000 | 12700000 | 12700000 | 12700000 | 12700000 | 12700000 | 12802332 | 12802332 | 12802332 | 14102332 | 14102332 | 14102332 | 14102332 | 14102332 | 14102332 | 14102332 | 14102332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332 | 16502332
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113900 | 227800 | 341700 | 455600 | 569500 | 683400 | 797300 | 911200 | 1025100 | 1139000 | 1252900 | 1366800 | 1480700 | 1480700 | 1480700 | 1594600 | 1708500 | 1822400 | 1936300 | 2050200 | 2164100 | 2278000 | 2391900 | 2505800 | 2619700 | 2733600 | 2847500 | 2961400 | 2961400 | 2961400 | 3075300 | 3189200 | 3303100 | 3417000 | 3530900 | 3644800 | 3758700 | 3872600 | 3986500 | 4100400 | 4214300 | 4328200 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000 | 4442000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4080524 | 21540000 | 27740000 | 27740000 | 27740000 | 39195669.5304 | 45991059.979 | 43471886.0908 | 55061252.5767 | 64444623.9932 | 61594351.7529 | 69878210.199 | 78078533.7642 | 77263982.4603 | 85462822.5797 | 92706442.6978 | 102881588.2066 | 105711169.7468 | 105711169.7468 | 105711169.7468 | 111901962.9825 | 118766344.6074 | 134861261.992 | 141119823.1918 | 144308196.4684 | 160293482.3301 | 164853883.62 | 169568025.6446 | 186871869.4655 | 188477825.445 | 191381522.7328 | 193500179.964 | 207204405.9859 | 207204405.9859 | 207204405.9859 | 207627573.0079 | 208005041.3529 | 217077759.2999 | 219855227.6449 | 220324093.3439 | 221116255.0119 | 221402326.003 | 221779794.3481 | 223666914.047 | 223952985.0381 | 224508068.3662 | 224621968.3662 | 217793406.3662 | 217793406.3662 | 217793406.3662 | 217793406.3662 | 217793406.3662 | 217793406.3662 | 217793406.3662 | 217793406.3662 | 217793406.3662 | 217793406.3662 | 217793406.3662 | 217793406.3662 | 217793406.3662 | 217793406.3662 | 217793406.3662 | 217793406.3662 | 217793406.3662 | 217793406.3662
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000 | 42000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 25000 | 25000 | 10000 | 10000 | 12000 | 12000 | 12000 | 12000 | 22000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000 | 32000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37000 | 37000 | 51642 | 51642 | 77462 | 77462 | 77462 | 77462 | 77462 | 77462 | 92462 | 92462 | 92462 | 107462 | 107462 | 122462 | 137462 | 137462 | 152462 | 152462 | 152462 | 152462 | 152462 | 152462 | 152462 | 152462 | 152462 | 152462 | 177462 | 177462 | 202462 | 227462 | 227462 | 252462 | 277462 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 62000 | 62000 | 61642 | 61642 | 89462 | 89462 | 89462 | 89462 | 99462 | 109462 | 124462 | 124462 | 124462 | 139462 | 139462 | 154462 | 169462 | 169462 | 184462 | 226462 | 226462 | 226462 | 226462 | 226462 | 226462 | 226462 | 226462 | 226462 | 251462 | 251462 | 276462 | 301462 | 301462 | 326462 | 351462 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000 | 374000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574 | 134574
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741 | 179741
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405559 | 1112559 | 2123000 | 2692660 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685 | 2914685
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 944600 | 1354489 | 1579041 | 1579041 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394 | 2162394
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134574 | 719874 | 1426874 | 2437315 | 3056975 | 4173600 | 4583489 | 4808041 | 4808041 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394 | 5391394
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134574 | 739874 | 1488874 | 2499315 | 3118617 | 4235242 | 4672951 | 4897503 | 4897503 | 5480856 | 9571380 | 27040856 | 33255856 | 33255856 | 33255856 | 44726525.5304 | 51521915.979 | 49017742.0908 | 60622108.5767 | 70005479.9932 | 67170207.7529 | 75496066.199 | 83696389.7642 | 82881838.4603 | 91080678.5797 | 98324298.6978 | 108499444.2066 | 111329025.7468 | 111329025.7468 | 111329025.7468 | 117544818.9825 | 124409200.6074 | 140529117.992 | 146812679.1918 | 150001052.4684 | 166011338.3301 | 170596739.62 | 175333419.6446 | 192637263.4655 | 194243219.445 | 197146916.7328 | 199265573.964 | 212969799.9859 | 212969799.9859 | 212969799.9859 | 213392967.0079 | 213770435.3529 | 222843153.2999 | 225620621.6449 | 226089487.3439 | 226881649.0119 | 227167720.003 | 227545188.3481 | 229432308.047 | 229718379.0381 | 230273462.3662 | 230387362.3662 | 223558800.3662 | 223558800.3662 | 223558800.3662 | 223558800.3662 | 223558800.3662 | 223558800.3662 | 223558800.3662 | 223558800.3662 | 223558800.3662 | 223558800.3662 | 223558800.3662 | 223558800.3662 | 223558800.3662 | 223558800.3662 | 223558800.3662 | 223558800.3662 | 223558800.3662 | 223558800.3662
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4850000 | 9300000 | 9300000 | 9300000 | 12879057 | 12890724.4266 | 12902391.8531 | 12914059.2797 | 12925726.7063 | 12937394.1328 | 12949061.5594 | 12960728.986 | 12972396.386 | 22847955.186 | 22865068.186 | 22882181.186 | 23067644.586 | 23067644.586 | 23067644.586 | 23754075.086 | 24528551.086 | 25529086.286 | 27665105.786 | 29402082.186 | 31320239.686 | 33537014.586 | 36010774.286 | 38695902.586 | 40532067.586 | 42680422.686 | 44712538.586 | 46634829.486 | 46634829.486 | 46634829.486 | 48369400.186 | 49940097.786 | 51349815.686 | 52503333.986 | 53234938.186 | 55634496.986 | 55646164.386 | 55651998.086 | 55651998.086 | 55651998.086 | 55651998.086 | 55651998.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086 | 51120225.086
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4350000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -8700000 | -6525000 | -6525000 | -6525000 | -4350000 | -4350000 | -4350000 | -2175000 | -2175000 | -2175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 750000 | 850000 | 850000 | 850000 | 4429057 | 4440724.4266 | 4452391.8531 | 4464059.2797 | 4475726.7063 | 4487394.1328 | 4499061.5594 | 4510728.986 | 4522396.386 | 14397955.186 | 14415068.186 | 14432181.186 | 14617644.586 | 14617644.586 | 14617644.586 | 15304075.086 | 16078551.086 | 19254086.286 | 21390105.786 | 23127082.186 | 27220239.686 | 29437014.586 | 31910774.286 | 36770902.586 | 38607067.586 | 40755422.686 | 44962538.586 | 46884829.486 | 46884829.486 | 46884829.486 | 48619400.186 | 50190097.786 | 51599815.686 | 52753333.986 | 53484938.186 | 55884496.986 | 55896164.386 | 55901998.086 | 55901998.086 | 55901998.086 | 55901998.086 | 55901998.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086 | 51370225.086
|  |  |  | 20762.74 | 25762.74 | 30762.74 | 57499.74 | 57568.74 | 92568.74 | 105453.74 | 115453.74 | 125453.74 | 135453.74 | 145453.74 | 126397.74 | 137782.74 | 137782.74 | 137782.74 | 144237.74 | 145135.74 | 166113.74 | 169435.74 | 169435.74 | 169435.74 | 169435.74 | 169435.74 | 151591.74 | 151591.74 | 156052.74 | 160513.74 | 164974.74 | 164974.74 | 164974.74 | 167575.74 | 170176.74 | 172777.74 | 175378.74 | 177981.74 | 180582.74 | 183183.74 | 185784.74 | 188385.74 | 190986.74 | 193587.74 | 196188.74 | 198795.74 | 198795.74 | 198795.74 | 200495.74 | 202195.74 | 203895.74 | 205595.74 | 207295.74 | 208995.74 | 210695.74 | 212395.74 | 214095.74 | 215795.74 | 217495.74 | 219195.74 | 220895.74 | 220895.74 | 220895.74 | 222595.74 | 224295.74 | 225995.74 | 227695.74 | 229395.74 | 231095.74 | 232795.74 | 234495.74 | 236195.74 | 237895.74 | 239595.74 | 241295.74 | 242995.74 | 242995.74 | 242995.74 | 244695.74 | 246395.74 | 248095.74 | 249795.74 | 251495.74 | 253195.74 | 254895.74 | 256595.74 | 258295.74 | 259995.74 | 261695.74 | 263395.74 | 265615.74 | 265615.74 | 265615.74
|  |  |  | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000 | 3093000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1300000 | -1300000 | -1300000 | -1300000 | -1300000 | -1300000 | -1300000 | -1300000 | -1300000 | -1300000 | -1300000 | -1300000 | -1300000 | -1300000 | -1300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000 | 1500000 | 3313600 | 5127200 | 6940800 | 8751100 | 10513800 | 12185400 | 13586600 | 14729500 | 15791100 | 16214300 | 16620100 | 16999800 | 25074055 | 25074055 | 25074055 | 25447555 | 25836355 | 26225155 | 26626555 | 27027955 | 27429355 | 27808555 | 28186955 | 28565355 | 28873955 | 29182555 | 29491155 | 41924800 | 41924800 | 41924800 | 42233400 | 42542000 | 42850600 | 43159200 | 43434800 | 43710400 | 43986000 | 44282500 | 44579000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000 | 48974000
|  |  |  | 3113762.74 | 3118762.74 | 3123762.74 | 3150499.74 | 3150568.74 | 3185568.74 | 3198453.74 | 3208453.74 | 3218453.74 | 3228453.74 | 3238453.74 | 3219397.74 | 3230782.74 | 3230782.74 | 3230782.74 | 3237237.74 | 3238135.74 | 3259113.74 | 3262435.74 | 3262435.74 | 3262435.74 | 3262435.74 | 3262435.74 | 3244591.74 | 3244591.74 | 3249052.74 | 3253513.74 | 4757974.74 | 4757974.74 | 4757974.74 | 6574175.74 | 8390376.74 | 10206577.74 | 12019478.74 | 13784781.74 | 14158982.74 | 15562783.74 | 16708284.74 | 17772485.74 | 18198286.74 | 18606687.74 | 18988988.74 | 27065850.74 | 27065850.74 | 27065850.74 | 27441050.74 | 27831550.74 | 28222050.74 | 28625150.74 | 29028250.74 | 30731350.74 | 31112250.74 | 31492350.74 | 31872450.74 | 32182750.74 | 32493050.74 | 32803350.74 | 45238695.74 | 45238695.74 | 45238695.74 | 45548995.74 | 45859295.74 | 46169595.74 | 46479895.74 | 46757195.74 | 47034495.74 | 47311795.74 | 47609995.74 | 47908195.74 | 52304895.74 | 52306595.74 | 52308295.74 | 52309995.74 | 52309995.74 | 52309995.74 | 52311695.74 | 52313395.74 | 52315095.74 | 52316795.74 | 52318495.74 | 52320195.74 | 52321895.74 | 52323595.74 | 52325295.74 | 52326995.74 | 52328695.74 | 52330395.74 | 52332615.74 | 52332615.74 | 52332615.74
|  |  |  | 13757346.0836 | 15529413.9561 | 18054145.2174 | 20863603.9974 | 23244671.9974 | 25373041.812 | 28027166.0059 | 30652018.0059 | 33889665.0059 | 36546731.0059 | 38730962.0059 | 41890729.3393 | 44188179.6713 | 44188179.6713 | 44188179.6713 | 56996232.2853 | 59284896.5578 | 63184299.8305 | 72819089.0007 | 76595724.262 | 81388503.7328 | 87892498.8678 | 83489807.2416 | 88564084.2328 | 92100549.8103 | 99986547.8955 | 122156168.081 | 136488227.3772 | 136488227.3772 | 136488227.3772 | 160366152.5574 | 173819661.0759 | 177921940.3276 | 196140056.0934 | 212275893.6297 | 215016285.8793 | 228799285.8763 | 241630467.9716 | 245019147.8112 | 265641339.2142 | 274683008.7748 | 286981970.5962 | 300009665.0081 | 300009665.0081 | 300009665.0081 | 308091167.7342 | 316882264.1696 | 337339986.5945 | 346929077.4848 | 353024080.7918 | 375610198.8539 | 383554594.7342 | 391898684.6875 | 415220356.9719 | 419750330.7949 | 425890251.9561 | 433309774.8208 | 462281318.4998 | 462281318.4998 | 462281318.4998 | 465594685.1566 | 468724470.7864 | 480508428.3183 | 485791066.6481 | 488352811.3599 | 492982872.7507 | 494781211.0646 | 496724752.2742 | 499989724.9728 | 505788140.9636 | 506717950.2621 | 507138426.8401 | 496210832.8016 | 496210832.8016 | 496210832.8016 | 496380472.1585 | 496508226.5655 | 496635309.9725 | 496762393.3794 | 496889331.7864 | 497029628.6934 | 497158155.6003 | 497271682.5073 | 497385209.4143 | 497498736.3213 | 497612263.2282 | 497725790.1352 | 498059836.8883 | 498059836.8883 | 498059836.8883
111302.95
| 1B | TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53571.43 | 494815.67 | 498762.9 | 1047150 | 1047150 | 0 | 607932 | 191799 | 42171 | 16853 | 268347 | 0 | 0 | 0 | 0 | 0 | 261041 | 575000 | 1963143 | 3010293 | 489539 | -11373.38 | 5552.58 | 5062.87 | 46060.26 | 75474.3 | 69156.89 | 278636.7 | 562421.71 | 570106.9 | 565823.1 | 584367.4 | 567966 | 3808794.33 | 6819087.33 | 5042133.04 | 691302.6 | -3449484.1 | 2501965.8823 | 3201938.1823 | 2909024.4923 | 1037888.8223 | 3008070.1623 | 3223849.6723 | 3481141.3723 | 3074238.1423 | 3394325.6023 | 1094571.3023 | 29210965.1731 | 36030052.5031 | 6489181.6923 | 2943943.5623 | 3142536.2423 | 3163986.1671 | 3344652.6771 | 3453805.9871 | 3254358.1171 | 3137465.7371 | 3300749.4871 | 3886253.0371 | 3847310.32 | 2867163.88 | 3223520.58 | 46054927.4869 | 82084979.99 | 2892313 | 689364.35 | 84683.98 | 8611.99 | 7848.87 | 62373.64 | 127374.59 | 147379.18 | 216116.53 | 213805.07 | 265530.28 | 52973.72 | 448065.17 | 5216440.37 | 87301420.36 |  |  | 1963143 | 0 |  |  | 836041 | 5548436
|  | Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53571.43 | 548387.1 | 1047150 | 1047150 | 1047150 | 1047150 | 1655082 | 1846881 | 1889052 | 1905905 | 2174252 | 2174252 | 2174252 | 2174252 | 2174252 | 2174252 | 2435293 | 3010293 | 3010293 | 3010293 | 3499832 | 3488458.62 | 3494011.2 | 3499074.07 | 3545134.33 | 3620608.63 | 3689765.52 | 3968402.22 | 4530823.93 | 5100930.83 | 5666753.93 | 6251121.33 | 6819087.33 | 6819087.33 | 6819087.33 | 11861220.37 | 12552522.97 | 9103038.87 | 11605004.7523 | 14806942.9346 | 17715967.4269 | 18753856.2492 | 21761926.4115 | 24985776.0838 | 28466917.4562 | 31541155.5985 | 34935481.2008 | 36030052.5031 | 36030052.5031 | 36030052.5031 | 42519234.1954 | 45463177.7577 | 48605714 | 51769700.1671 | 55114352.8443 | 58568158.8314 | 61822516.9486 | 64959982.6857 | 68260732.1729 | 72146985.21 | 75994295.53 | 78861459.41 | 82084979.99 | 82084979.99 | 82084979.99 | 84977292.99 | 85666657.34 | 85751341.32 | 85759953.31 | 85767802.18 | 85830175.82 | 85957550.41 | 86104929.59 | 86321046.12 | 86534851.19 | 86800381.47 | 86853355.19 | 87301420.36 | 87301420.36 | 87301420.36
| Total | TOTAL |  | 13757346.0836 | 1772067.8726 | 2524731.2613 | 2809458.78 | 2381068 | 2128369.8145 | 2654124.194 | 2624852 | 3237647 | 2657066 | 2237802.43 | 3654583.0033 | 2796213.232 | 31477983.5878 | 45235329.6713 | 12808052.614 | 2896596.2724 | 4091202.2727 | 9676960.1702 | 3793488.2613 | 5061126.4708 | 6503995.135 | -4402691.6261 | 5074276.9912 | 3536465.5774 | 7885998.0853 | 22430661.1854 | 14907059.2963 | 94263190.7059 | 139498520.3772 | 24367464.1801 | 13442135.1385 | 4107831.8317 | 18223178.6358 | 16181897.7964 | 2815866.5496 | 13852156.887 | 13109818.7953 | 3951101.5496 | 21192298.3029 | 9607492.6606 | 12883329.2214 | 13595660.4119 | 167330231.9609 | 306828752.3381 | 13123635.7661 | 9482399.0353 | 17008238.325 | 12091056.7725 | 9296941.4893 | 25495142.5545 | 8982284.7026 | 11352160.1156 | 26545521.9567 | 8011115.1953 | 9214159.3036 | 10813848.467 | 30066114.9813 | 191482618.6647 | 498311371.0029 | 9802548.3491 | 6073729.1922 | 14926493.7741 | 8446624.497 | 5906397.3889 | 8083867.378 | 5052696.431 | 5081006.9467 | 6565722.1858 | 9684669.028 | 4777119.6185 | 3287640.458 | -7704073.4585 | 79984441.7887 | 578295812.7916 | 3061952.3569 | 817118.757 | 211767.387 | 135695.397 | 134787.277 | 202670.547 | 255901.497 | 260906.087 | 329643.437 | 327331.977 | 379057.187 | 166500.627 | 782111.9231 | 7065444.4567 | 585361257.2483 |  |  | 95016742.0055 | -753551.2996 |  |  | 45223718.567 | 367120045.5111
0
|  | Cumulative |  | 13757346.0836 | 15529413.9561 | 18054145.2174 | 20863603.9974 | 23244671.9974 | 25373041.812 | 28027166.0059 | 30652018.0059 | 33889665.0059 | 36546731.0059 | 38784533.4359 | 42439116.4393 | 45235329.6713 | 45235329.6713 | 45235329.6713 | 58043382.2853 | 60939978.5578 | 65031180.8305 | 74708141.0007 | 78501629.262 | 83562755.7328 | 90066750.8678 | 85664059.2416 | 90738336.2328 | 94274801.8103 | 102160799.8955 | 124591461.081 | 139498520.3772 | 139498520.3772 | 139498520.3772 | 163865984.5574 | 177308119.6959 | 181415951.5276 | 199639130.1634 | 215821027.9597 | 218636894.5093 | 232489051.3963 | 245598870.1916 | 249549971.7412 | 270742270.0442 | 280349762.7048 | 293233091.9262 | 306828752.3381 | 306828752.3381 | 306828752.3381 | 319952388.1042 | 329434787.1396 | 346443025.4645 | 358534082.2371 | 367831023.7264 | 393326166.2808 | 402308450.9834 | 413660611.099 | 440206133.0557 | 448217248.251 | 457431407.5546 | 468245256.0216 | 498311371.0029 | 498311371.0029 | 498311371.0029 | 508113919.352 | 514187648.5441 | 529114142.3183 | 537560766.8152 | 543467164.2042 | 551551031.5822 | 556603728.0132 | 561684734.9599 | 568250457.1456 | 577935126.1736 | 582712245.7921 | 585999886.2501 | 578295812.7916 | 578295812.7916 | 578295812.7916 | 581357765.1485 | 582174883.9055 | 582386651.2925 | 582522346.6894 | 582657133.9664 | 582859804.5134 | 583115706.0103 | 583376612.0973 | 583706255.5343 | 584033587.5113 | 584412644.6982 | 584579145.3252 | 585361257.2483 | 585361257.2483 | 585361257.2483
94263190.7059
[31 empty] | AMP | 24300000
[31 empty] | Total | 118563190.7059
Note on DE11: Stewart McGarrity: Increase in cost of depot advance works allocated against PM costs in P10
Note on DH11: Stewart McGarrity: Includes £364k increase in DLA forecast which was offset against PM costs in P9