## Sheet1
[5 empty] | Indicates Manhours content has changed |  | Indicates Date has improved |  | Indicates Date has Slipped |  | Indicates Completion in the Period | [32 empty] | Movement since Previous Issue finish date (Days) | Movement since V9 Dec 2006 agreed BASELINE issue finish date (Days) | Comments
[26 empty] | Revised Programme |  |  | Revised Programme |  |  | Revised Programme |  |  | Revised Programme |  |  | Revised Programme |  |  | Revised Programme
[5 empty] | Baseline |  |  | Forecast to 28th April (received 25/4/6) |  |  | Actual to 30th April (received 18/5/6) |  |  | Forecast to 31st May (received 26/5/6) |  |  | Forecast to 30th June (received 30/6/6) |  |  | Actual to 14th Aug (received 21/8/6) |  |  | Actual to 28th Aug (received 29/9/6) |  |  | Actual to 28th Aug (received 6/10/6) |  |  | V5 Actual to 25th Sep (received 1/11/6) |  |  | V7 Actual to 23rd Oct (received 20/11/6) |  |  | V8 Assumed Progress to 30Nov (received 1/12/6) |  |  | V9 with Amended Utility Dates Data Date 23Oct06 (received 06/12/6) **NEW BASELINE** |  |  | V10 Actual Progress to 11Dec (received 22/12/6)
[5 empty] | @19-Apr-06 Issue |  |  | @24-Apr-06 Issue |  |  | @24-Apr-06 Issue |  |  | @01-Jun-06 Issue |  |  | @01-Jul-06 Issue |  |  | @01-Aug-06 Issue |  |  | @01-Oct-06 Issue |  |  | @01-Oct-06 Issue |  |  | @01-Oct-06 Issue |  |  | @01-Nov-06 Issue |  |  | @01-Dec-06 Issue |  |  | @01-Dec-06 Issue |  |  | @01-Dec-06 Issue
Sector | Section | Intermediate Sector | Sub-Sector | Phase | Man-hours | Start | Finish | Man-hours | Start | Finish | Man-hours | Start | Finish | Man-hours | Start | Finish | Man-hours | Start | Finish | Man-hours | Start | Finish | Man-hours | Start | Finish | Man-hours | Start | Finish | Man-hours | Start | Finish | Man-hours | Start | Finish | Man-hours | Start | Finish | Man-hours | Start | Finish | Man-hours | Start | Finish
Programme Key Milestones | Project Wide
Management Project Wide Activities | Project Wide |  |  | PD | 39250 | 2005-09-29 | 2007-02-28 | 45170 | 2005-09-29 | 2007-02-28 | 39250 | 2005-09-29 | 2007-02-28 | 39250 | 2005-09-29 | 2007-02-28 | 39250 | 2005-09-29 | 2006-07-28 | 39250 | 29-Sep-05A | 2006-08-14 | 39250 | 29-Sep-05A | 2006-08-29 | 39250 | 29-Sep-05A | 2006-08-29 | 39250 | 29-Sep-05A | 28-Jul06A | 39250 | 29-Sep-05A | 28-Jul06A | 39250 | 29-Sep-05A | 28-Jul06A | 39250 | 29-Sep-05A | 28-Jul06A | 39250 | 29-Sep-05A | 2006-12-22 |  |  | Actual finish date of 28th Jul now replaced with planned finish date of 22nd Dec 2006
| Project Wide |  |  | DD | 45153.5 | 2006-06-01 | 2007-04-27 | 45153.5 | 2006-06-01 | 2007-04-27 | 45153.5 | 2006-06-01 | 2007-04-27 | 45153.5 | 2006-06-01 | 2007-04-27 | 39681.25 | 2006-06-01 | 2007-04-27 | 51331.25 | 03-Jul-06A | 2007-04-30 | 51952.75 | 03-Jul-06A | 2007-04-30 | 51952.75 | 03-Jul-06A | 2007-04-30 | 51952.75 | 03-Jul-06A | 2007-04-30 | 45947.75 | 03-Jul-06A | 2007-04-30 | 45947.75 | 03-Jul-06A | 2007-04-30 | 45947.75 | 03-Jul-06A | 2007-04-30 | 45947.75 | 03-Jul-06A | 2007-09-28 | 151 | 151
Engineering Project Wide Activities | Project Wide |  |  | PD | 13057 | 2005-09-29 | 2010-07-02 | 13057 | 2005-09-29 | 2010-07-02 | 13057 | 2005-09-29 | 2010-07-02 | 13057 | 2005-09-29 | 2010-07-02 | 12688.55 | 2005-09-29 | 2010-07-02 | 12518.55 | 29-Sep-05A | 2006-10-24 | 12623.55 | 29-Sep-05A | 2006-11-07 | 12758.55 | 29-Sep-05A | 2007-01-11 | 12758.55 | 29-Sep-05A | 2007-01-11 | 12758.55 | 29-Sep-05A | 2007-01-11 | 12758.55 | 29-Sep-05A | 2007-01-11 | 12758.55 | 29-Sep-05A | 2007-01-11 | 12822.55 | 29-Sep-05A | 2007-02-27 | 47 | 47
| Project Wide |  |  | DD | 11858 | 2006-03-20 | 2007-05-24 | 11858 | 2006-03-20 | 2007-05-24 | 11858 | 2006-04-24 | 2007-05-24 | 11858 | 2006-06-01 | 2007-05-24 | 17330.28 | 2006-06-01 | 2007-04-27 | 20183.53 | 06-Jun-06A | 2008-04-11 | 22513.08 | 06-Jun-06A | 2008-04-11 | 20133.62 | 06-Jun-06A | 2008-04-11 | 23170.79 | 06-Jun-06A | 2008-08-29 | 21654.08 | 06-Jun-06A | 2008-08-27 | 21654.08 | 06-Jun-06A | 2008-08-27 | 21654.08 | 23-Mar-06A | 2008-08-27 | 21783.58 | 23-Mar-06A | 2008-08-27 | 0 | 0
Procurement | Project Wide | [42 empty] | 0 | 0
Haymarket to Newhaven Road | Section Wide |  |  | DD | 216 | 2006-06-27 | 2006-08-07 | 216 | 2006-06-27 | 2006-08-07 | 216 | 2006-06-27 | 2006-08-07 | 216 | 2006-07-04 | 2006-08-14 | 216 | 2006-07-04 | 2006-08-30 | 216 | 17-Jul-06A | 2007-04-04 | 216 | 17-Jul-06A | 2007-04-11 | 216 | 17-Jul-06A | 2007-04-05 | 216 | 17-Jul-06A | 2007-04-05 | 216 | 17-Jul-06A | 2007-04-05 | 216 | 17-Jul-06A | 2007-04-05 | 216 | 17-Jul-06A | 2007-04-05 | 216 | 17-Jul-06A | 2007-04-17 | 12 | 12
| FOW - NER | Intermediate Section Wide |  | PD | 1624 | 2006-03-07 | 2006-06-26 | 1624 | 2006-03-07 | 2006-06-26 | 1624 | 2006-03-07 | 2006-06-26 | 1624 | 2006-03-07 | 2006-06-26 | 1624 | 07-Mar-06A | 2006-07-04 | 1624 | 07-Mar-06A | 2006-08-14 | 1624 | 07-Mar-06A | 2006-08-29 | 1624 | 07-Mar-06A | 2006-08-29 | 1624 | 07-Mar-06A | 2006-09-25 | 1624 | 07-Mar-06A | 04-Jul06A | 1400 | 07-Mar-06A | 04-Jul06A | 1624 | 07-Mar-06A | 04-Jul06A | 1624 | 07-Mar-06A | 04-Jul06A
| FOW - NER | Intermediate Section Wide |  | DD | 3774 | 2006-06-19 | 2007-03-12 | 3774 | 2006-06-19 | 2007-03-12 | 3774 | 2006-06-19 | 2007-03-12 | 3774 | 2006-06-19 | 2007-03-12 | 3774 | 2006-07-03 | 2007-03-14 | 3986.5 | 23-Jun-06A | 2007-05-31 | 3936.5 | 23-Jun-06A | 2007-08-17 | 3936.5 | 23-Jun-06A | 2007-09-03 | 3936.5 | 23-Jun-06A | 2007-09-03 | 3916.5 | 23-Jun-06A | 2007-09-03 | 3916.5 | 23-Jun-06A | 2007-09-03 | 3916.5 | 23-Jun-06A | 2007-09-03 | 3916.5 | 23-Jun-06A | 2007-10-25 | 52 | 52
| FOW - NER |  | FOW - COS | PD | 40 | 2006-05-02 | 2006-05-08 | 40 | 2006-05-02 | 2006-05-08 | 40 | 2006-05-02 | 2006-05-08 | 40 | 2006-05-22 | 2006-05-26 | 40 | 22-May-06A | 23-Jun-06A | 40 | 22-May-06A | 30-Jun-06A | 40 | 22-May-06A | 30-Jun-06A | 40 | 22-May-06A | 30-Jun-06A | 40 | 22-May-06A | 30-Jun-06A | 40 | 22-May-06A | 30-Jun-06A | 40 | 22-May-06A | 30-Jun-06A | 40 | 22-May-06A | 30-Jun-06A | 40 | 22-May-06A | 30-Jun-06A
| FOW - NER |  | FOW - COS | DD | 345 | 2006-07-24 | 2007-02-06 | 345 | 2006-07-24 | 2007-02-06 | 345 | 2006-07-24 | 2007-02-06 | 345 | 2006-07-24 | 2007-02-06 | 345 | 2006-07-26 | 2007-02-08 | 345 | 2006-11-01 | 2007-04-05 | 345 | 2006-11-15 | 2007-04-23 | 345 | 2006-11-15 | 2007-05-29 | 345 | 2006-09-07 | 2007-05-29 | 345 | 2006-09-07 | 2007-05-29 | 345 | 07-Sep-06A | 2007-05-29 | 345 | 07-Sep-06A | 2007-05-29 | 345 | 07-Sep-06A | 2007-06-29 | 31 | 31
| FOW - NER |  | COS - OCD | PD | 40 | 2006-05-03 | 2006-05-09 | 40 | 2006-05-03 | 2006-05-09 | 40 | 2006-05-03 | 2006-05-09 | 40 | 2006-05-22 | 2006-05-26 | 40 | 22-May-06A | 23-Jun-06A | 40 | 22-May-06A | 30-Jun-06A | 40 | 22-May-06A | 30-Jun-06A | 40 | 22-May-06A | 30-Jun-06A | 40 | 22-May-06A | 30-Jun-06A | 40 | 22-May-06A | 30-Jun-06A | 40 | 22-May-06A | 30-Jun-06A | 40 | 22-May-06A | 30-Jun-06A | 40 | 22-May-06A | 30-Jun-06A
| FOW - NER |  | COS - OCD | DD | 345 | 2006-07-24 | 2007-02-06 | 345 | 2006-07-24 | 2007-02-06 | 345 | 2006-07-24 | 2007-02-06 | 345 | 2006-07-24 | 2007-02-06 | 345 | 2006-07-26 | 2007-02-08 | 345 | 2006-11-01 | 2007-04-05 | 345 | 2006-11-15 | 2007-04-23 | 345 | 2006-11-15 | 2007-05-29 | 345 | 2006-11-19 | 2007-05-29 | 345 | 2006-11-19 | 2007-05-29 | 345 | 2006-12-19 | 2007-05-29 | 345 | 2006-12-19 | 2007-05-29 | 345 | 17-Nov-06A | 2007-07-02 | 34 | 34
| FOW - NER |  | OCD - OCT | PD | 330 | 2006-03-13 | 2006-08-04 | 330 | 2006-03-13 | 2006-08-18 | 330 | 2006-03-13 | 2006-08-31 | 330 | 2006-03-13 | 2006-08-31 | 330 | 13-Mar-06A | 2006-09-19 | 330 | 13-Mar-06A | 2006-10-23 | 330 | 13-Mar-06A | 2006-09-18 | 330 | 13-Mar-06A | 2006-09-18 | 330 | 13-Mar-06A | 2006-10-10 | 330 | 13-Mar-06A | 2006-11-07 | 330 | 13-Mar-06A | 2006-11-07 | 330 | 13-Mar-06A | 2006-11-07 | 330 | 13-Mar-06A | 2006-12-18 | 41 | 41
| FOW - NER |  | OCD - OCT | DD | 1770 | 2006-07-24 | 2007-03-02 | 1770 | 2006-07-24 | 2007-03-16 | 1770 | 2006-07-24 | 2007-03-23 | 1770 | 2006-07-24 | 2007-03-23 | 1770 | 2006-07-26 | 2007-03-30 | 1770 | 01-Aug-06A | 2007-07-05 | 1770 | 01-Aug-06A | 2007-07-19 | 1770 | 01-Aug-06A | 2007-08-23 | 1770 | 01-Aug-06A | 2007-08-23 | 1770 | 01-Aug-06A | 2007-08-23 | 1770 | 01-Aug-06A | 2007-08-23 | 1770 | 01-Aug-06A | 2007-08-23 | 1770 | 01-Aug-06A | 2007-10-25 | 63 | 63
| FOW - NER |  | OCT - NER | PD | 259 | 2006-02-27 | 2006-07-21 | 259 | 2006-02-27 | 2006-07-24 | 259 | 2006-02-27 | 2006-07-27 | 259 | 2006-02-27 | 2006-08-09 | 259 | 27-Feb-06A | 2006-08-03 | 259 | 27-Feb-06A | 2006-09-25 | 259 | 27-Feb-06A | 2006-09-05 | 259 | 27-Feb-06A | 2006-09-05 | 259 | 27-Feb-06A | 2006-10-02 | 259 | 27-Feb-06A | 2006-10-30 | 244 | 27-Feb-06A | 30-Oct-06A | 259 | 27-Feb-06A | 30-Oct-06A | 259 | 27-Feb-06A | 2006-12-22 |  |  | Actual finish date of 30th Oct now replaced with planned finish date of 22nd Dec 2006
| FOW - NER |  | OCT - NER | DD | 954 | 2006-06-28 | 2007-02-06 | 954 | 2006-06-28 | 2007-02-06 | 954 | 2006-06-28 | 2007-02-06 | 954 | 2006-07-20 | 2007-02-06 | 954 | 2006-07-12 | 2007-02-08 | 954 | 2006-08-14 | 2007-07-20 | 954 | 2006-08-29 | 2007-08-17 | 954 | 2006-08-29 | 2007-09-03 | 954 | 2006-09-08 | 2007-09-03 | 972 | 2006-09-08 | 2007-09-03 | 972 | 08-Sep-06A | 2007-09-03 | 972 | 08-Sep-06A | 2007-09-03 | 960 | 09-Aug-06A | 2007-09-03 | 0 | 0 | Actual start date of 8th Sep now replaced with actual date of 9th Aug 2006
| MDR-FOW | Intermediate Section Wide |  | PD | 1190 | 2006-03-06 | 2006-06-13 | 1190 | 2006-03-06 | 2006-06-13 | 1190 | 2006-03-06 | 2006-06-13 | 1190 | 2006-03-06 | 2006-06-27 | 1190 | 2006-03-06 | 2006-07-03 | 1130 | 06-Mar-06A | 30/06/2006A | 1130 | 06-Mar-06A | 30-Jun-06A | 1130 | 06-Mar-06A | 30-Jun-06A | 1130 | 06-Mar-06A | 30-Jun-06A | 1130 | 06-Mar-06A | 30-Jun-06A | 1130 | 06-Mar-06A | 30-Jun-06A | 1130 | 06-Mar-06A | 30-Jun-06A | 1130 | 06-Mar-06A | 30-Jun-06A
| MDR-FOW | Intermediate Section Wide |  | DD | 3361.5 | 2006-06-05 | 2007-04-30 | 3361.5 | 2006-06-05 | 2007-04-30 | 3361.5 | 2006-06-05 | 2007-04-30 | 3361.5 | 2006-06-20 | 2007-05-08 | 3361.5 | 22-May-06A | 2007-05-23 | 3709 | 10-May-06A | 2007-09-26 | 3775 | 10-May-06A | 2007-09-05 | 3775 | 10-May-06A | 2007-08-22 | 3775 | 10-May-06A | 2007-08-30 | 3775 | 10-May-06A | 2007-08-22 | 3775 | 10-May-06A | 2007-08-22 | 3775 | 10-May-06A | 2007-08-22 | 3775 | 10-May-06A | 2007-08-22 | 0 | 0
| MDR-FOW |  | MDR - BAS | PD | 140 | 2006-03-13 | 2006-08-04 | 140 | 2006-03-13 | 2006-08-18 | 140 | 2006-03-13 | 2006-08-25 | 140 | 2006-03-13 | 2006-08-16 | 140 | 2006-03-13 | 2006-09-04 | 120 | 13-Mar-06A | 2006-10-17 | 120 | 13-Mar-06A | 2006-09-12 | 120 | 13-Mar-06A | 2006-09-12 | 120 | 13-Mar-06A | 2006-10-09 | 120 | 13-Mar-06A | 2006-11-06 | 120 | 13-Mar-06A | 06-Nov-06A | 120 | 13-Mar-06A | 2006-11-06 | 120 | 13-Mar-06A | 12-Dec-06A
| MDR-FOW |  | MDR - BAS | DD | 495 | 2006-06-28 | 2007-01-26 | 495 | 2006-06-28 | 2007-01-26 | 495 | 2006-06-28 | 2007-01-26 | 495 | 2006-07-05 | 2007-01-26 | 495 | 2006-07-20 | 2007-02-02 | 495 | 2006-08-14 | 2007-08-08 | 495 | 2006-08-29 | 2007-07-18 | 495 | 2006-08-29 | 2007-07-31 | 495 | 25-Sep-06A | 2007-08-07 | 495 | 25-Sep-06A | 2007-07-31 | 495 | 10-Oct-06A | 2007-07-31 | 495 | 10-Oct-06A | 2007-07-31 | 495 | 09-Aug-06A | 2007-07-31 | 0 | 0 | Actual start date of 10th Oct now replaced with actual date of 9th Aug 2006
| MDR-FOW |  | BAS - FOW | PD | 104 | 2006-04-17 | 2006-06-01 | 104 | 2006-04-17 | 2006-06-08 | 104 | 2006-05-23 | 2006-07-07 | 104 | 2006-05-08 | 2006-07-17 | 104 | 2006-05-08 | 2006-07-27 | 104 | 08-May-06A | 27/07/2006A | 104 | 08-May-06A | 27-Jul-06A | 104 | 08-May-06A | 27-Jul-06A | 104 | 08-May-06A | 27-Jul-06A | 104 | 08-May-06A | 27-Jul-06A | 104 | 08-May-06A | 27-Jul-06A | 104 | 08-May-06A | 27-Jul-06A | 104 | 08-May-06A | 27-Jul-06A
| MDR-FOW |  | BAS - FOW | DD | 615 | 2006-06-01 | 2007-01-11 | 615 | 2006-06-08 | 2007-01-11 | 615 | 2006-06-28 | 2007-01-11 | 615 | 2006-07-05 | 2007-01-18 | 615 | 2006-07-20 | 2007-02-02 | 615 | 2007-03-08 | 2007-09-26 | 615 | 2007-02-15 | 2007-09-05 | 615 | 2007-02-15 | 2007-08-22 | 615 | 2007-02-09 | 2007-08-30 | 625 | 2007-02-09 | 2007-08-01 | 625 | 2007-02-02 | 2007-08-01 | 625 | 2007-02-02 | 2007-08-01 | 625 | 17-Nov-06A | 2007-08-01 | 0 | 0
| PSW - MDR | Intermediate Section Wide |  | PD | 1788 | 2006-03-06 | 2006-06-22 | 1788 | 2006-03-06 | 2006-06-22 | 1788 | 2006-03-06 | 2006-06-28 | 1788 | 2006-03-06 | 2006-07-10 | 1788 | 2006-03-06 | 30-Jun-06A | 1692 | 06-Mar-06A | 30/06/2006A | 1692 | 06-Mar-06A | 30-Jun-06A | 1692 | 06-Mar-06A | 30-Jun-06A | 1692 | 06-Mar-06A | 30-Jun-06A | 1692 | 06-Mar-06A | 30-Jun-06A | 1692 | 06-Mar-06A | 30-Jun-06A | 1692 | 06-Mar-06A | 30-Jun-06A | 1692 | 06-Mar-06A | 30-Jun-06A
| PSW - MDR | Intermediate Section Wide |  | DD | 4098 | 2006-06-15 | 2007-05-16 | 4098 | 2006-06-15 | 2007-05-16 | 4098 | 2006-06-15 | 2007-05-16 | 4098 | 2006-06-19 | 2007-05-23 | 4098 | 13-Jun-06A | 2007-06-08 | 4376.5 | 13-Jun-06A | 2007-10-29 | 4476.5 | 13-Jun-06A | 2007-11-01 | 4476.5 | 13-Jun-06A | 2007-09-04 | 4476.5 | 13-Jun-06A | 2007-09-04 | 4476.5 | 13-Jun-06A | 2007-09-04 | 4476.5 | 13-Jun-06A | 2007-09-04 | 4476.5 | 13-Jun-06A | 2007-09-04 | 4476.5 | 13-Jun-06A | 2007-09-17 | 13 | 13
| PSW - MDR |  | PSW - SAS | PD | 40 | 2006-03-31 | 2006-04-07 | 40 | 2006-03-31 | 2006-04-07 | 40 | 2006-05-08 | 2006-05-15 | 40 | 2006-06-08 | 2006-06-15 | 40 | 2006-06-07 | 23-Jun-06A | 40 | 07-Jun-06A | 30/06/2006A | 40 | 07-Jun-06A | 30-Jun-06A | 40 | 07-Jun-06A | 30-Jun-06A | 40 | 07-Jun-06A | 30-Jun-06A | 40 | 07-Jun-06A | 30-Jun-06A | 40 | 07-Jun-06A | 30-Jun-06A | 40 | 07-Jun-06A | 30-Jun-06A | 40 | 07-Jun-06A | 30-Jun-06A
| PSW - MDR |  | PSW - SAS | DD | 345 | 2006-06-23 | 2007-01-08 | 345 | 2006-06-23 | 2007-01-08 | 345 | 2006-06-23 | 2007-01-08 | 345 | 2006-06-30 | 2007-01-15 | 345 | 2006-07-17 | 2007-01-30 | 345 | 2007-03-06 | 2007-08-06 | 345 | 2007-03-09 | 2007-08-09 | 345 | 2007-03-09 | 2007-08-13 | 345 | 2007-03-13 | 2007-08-13 | 345 | 2007-03-13 | 2007-08-13 | 345 | 2007-03-13 | 2007-08-13 | 345 | 2007-03-13 | 2007-08-13 | 345 | 17-Nov-06A | 2007-08-24 | 11 | 11
| PSW - MDR |  | SAS - PIP | PD | 104 | 2006-03-31 | 2006-05-26 | 104 | 2006-03-31 | 2006-05-26 | 104 | 2006-04-24 | 2006-07-03 | 104 | 2006-04-24 | 2006-07-03 | 104 | 2006-04-24 | 2006-07-27 | 104 | 24-Apr-06A | 27/07/2006A | 104 | 24-Apr-06A | 27-Jul-06A | 104 | 24-Apr-06A | 27-Jul-06A | 104 | 24-Apr-06A | 27-Jul-06A | 104 | 24-Apr-06A | 27-Jul-06A | 104 | 24-Apr-06A | 27-Jul-06A | 104 | 24-Apr-06A | 27-Jul-06A | 104 | 24-Apr-06A | 27-Jul-06A
| PSW - MDR |  | SAS - PIP | DD | 612 | 2006-06-23 | 2007-05-16 | 612 | 2006-06-23 | 2007-05-16 | 612 | 2006-06-23 | 2007-05-16 | 612 | 2006-06-30 | 2007-05-23 | 612 | 2006-07-17 | 2007-06-08 | 621 | 2007-03-06 | 2007-10-29 | 621 | 2007-03-09 | 2007-11-01 | 621 | 2007-03-09 | 2007-08-13 | 621 | 15-Sep-06A | 2007-08-13 | 631 | 15-Sep-06A | 2007-08-13 | 631 | 15-Sep-06A | 2007-08-13 | 631 | 15-Sep-06A | 2007-08-13 | 631 | 15-Sep-06A | 2007-08-24 | 11 | 11
| PSW - MDR |  | PIP - MDR | PD | 40 | 2006-04-10 | 2006-04-18 | 40 | 2006-04-10 | 2006-04-18 | 40 | 2006-05-03 | 2006-05-09 | 40 | 2006-06-01 | 2006-06-07 | 40 | 2006-05-31 | 23-Jun-06A | 40 | 31-May-06A | 30/06/2006A | 40 | 31-May-06A | 30-Jun-06A | 40 | 31-May-06A | 30-Jun-06A | 40 | 31-May-06A | 30-Jun-06A | 40 | 31-May-06A | 30-Jun-06A | 40 | 31-May-06A | 30-Jun-06A | 40 | 31-May-06A | 30-Jun-06A | 40 | 31-May-06A | 30-Jun-06A
| PSW - MDR |  | PIP - MDR | DD | 345 | 2006-06-23 | 2007-01-08 | 345 | 2006-06-23 | 2007-01-08 | 345 | 2006-06-23 | 2007-01-08 | 345 | 2006-06-30 | 2007-01-15 | 345 | 2006-07-17 | 2007-01-30 | 345 | 2007-03-06 | 2007-08-06 | 345 | 2007-03-09 | 2007-08-09 | 345 | 2007-03-09 | 2007-08-13 | 345 | 2007-03-13 | 2007-08-13 | 362 | 2007-03-13 | 2007-08-13 | 362 | 26-Sep-06A | 2007-08-13 | 362 | 26-Sep-06A | 2007-08-13 | 362 | 26-Sep-06A | 2007-08-24 | 11 | 11
| HAY - PSW | Intermediate Section Wide |  | PD | 1117 | 2006-01-30 | 2006-06-16 | 1117 | 2006-01-30 | 2006-06-16 | 1117 | 2006-01-30 | 2006-06-16 | 1117 | 2006-01-30 | 2006-06-16 | 1117 | 2006-01-30 | 2006-07-03 | 1077 | 30-Jan-06A | 30/06/2006A | 1077 | 30-Jan-06A | 30-Jun-06A | 1077 | 30-Jan-06A | 30-Jun-06A | 1077 | 30-Jan-06A | 30-Jun-06A | 1077 | 30-Jan-06A | 30-Jun-06A | 1077 | 30-Jan-06A | 30-Jun-06A | 1077 | 30-Jan-06A | 30-Jun-06A | 1077 | 30-Jan-06A | 30-Jun-06A
| HAY - PSW | Intermediate Section Wide |  | DD | 3661.5 | 2006-06-12 | 2007-01-31 | 3661.5 | 2006-06-12 | 2007-01-31 | 3661.5 | 2006-06-12 | 2007-01-31 | 3661.5 | 2006-06-19 | 2007-02-07 | 3661.5 | 2006-07-03 | 2007-02-22 | 4009 | 04-May-06A | 2007-09-07 | 4075 | 04-May-06A | 2007-09-12 | 4075 | 04-May-06A | 2007-09-03 | 4075 | 04-May-06A | 2007-09-03 | 4075 | 04-May-06A | 2007-09-03 | 4075 | 04-May-06A | 2007-09-03 | 4075 | 04-May-06A | 2007-09-03 | 4075 | 04-May-06A | 2007-09-03 | 0 | 0
| HAY - PSW |  | HAY - SHP | PD | 40 | 2006-03-20 | 2006-03-23 | 40 | 2006-03-20 | 2006-03-23 | 40 | 2006-04-24 | 2006-04-27 | 40 | 2006-04-24 | 2006-05-30 | 40 | 2006-04-24 | 23-Jun-06A | 40 | 24-Apr-06A | 30/06/2006A | 40 | 24-Apr-06A | 30-Jun-06A | 40 | 24-Apr-06A | 30-Jun-06A | 40 | 24-Apr-06A | 30-Jun-06A | 40 | 24-Apr-06A | 30-Jun-06A | 0 | 24-Apr-06A | 30-Jun-06A | 40 | 24-Apr-06A | 30-Jun-06A | 40 | 24-Apr-06A | 30-Jun-06A
| HAY - PSW |  | HAY - SHP | DD | 345 | 2006-06-16 | 2006-12-22 | 345 | 2006-06-16 | 2006-12-22 | 345 | 2006-06-16 | 2006-12-22 | 345 | 2006-06-23 | 2007-01-08 | 345 | 2006-07-10 | 2007-01-23 | 345 | 2007-03-15 | 2007-08-15 | 345 | 2007-03-20 | 2007-08-20 | 345 | 2007-03-20 | 2007-08-16 | 345 | 2007-03-16 | 2007-08-16 | 345 | 2007-03-16 | 2007-08-16 | 345 | 26-Sep-06A | 2007-08-16 | 345 | 26-Sep-06A | 2007-08-16 | 345 | 26-Sep-06A | 2007-08-16 | 0 | 0
| HAY - PSW |  | SHP - PSW | PD | 40 | 2006-03-24 | 2006-03-30 | 40 | 2006-03-24 | 2006-03-30 | 40 | 2006-04-28 | 2006-05-05 | 40 | 2006-04-28 | 2006-06-07 | 40 | 2006-04-28 | 23-Jun-06A | 40 | 28-Apr-06A | 30/06/2006A | 40 | 28-Apr-06A | 30-Jun-06A | 40 | 28-Apr-06A | 30-Jun-06A | 40 | 28-Apr-06A | 30-Jun-06A | 40 | 28-Apr-06A | 30-Jun-06A | 0 | 28-Apr-06A | 30-Jun-06A | 40 | 28-Apr-06A | 30-Jun-06A | 40 | 28-Apr-06A | 30-Jun-06A
| HAY - PSW |  | SHP - PSW | DD | 345 | 2006-06-16 | 2006-12-22 | 345 | 2006-06-16 | 2006-12-22 | 345 | 2006-06-16 | 2006-12-22 | 345 | 2006-06-23 | 2007-01-08 | 345 | 2006-07-10 | 2007-01-23 | 345 | 2007-03-15 | 2007-08-15 | 345 | 2007-03-20 | 2007-08-20 | 345 | 2007-03-20 | 2007-08-16 | 345 | 30-Aug-06A | 2007-08-16 | 345 | 30-Aug-06A | 2007-08-16 | 345 | 30-Aug-06A | 2007-08-16 | 345 | 30-Aug-06A | 2007-08-16 | 345 | 30-Aug-06A | 2007-08-16 | 0 | 0
Haymarket Corridor | Section Wide |  |  | DD | 216 | 2006-07-10 | 2006-08-18 | 216 | 2006-07-10 | 2006-08-18 | 216 | 2006-07-10 | 2006-08-18 | 216 | 2006-07-10 | 2006-08-18 | 216 | 2006-07-17 | 2006-08-25 | 216 | 24-Jul-06A | 2006-11-21 | 216 | 24-Jul-06A | 2006-12-05 | 216 | 24-Jul-06A | 2007-01-16 | 216 | 24-Jul-06A | 2007-01-16 | 216 | 24-Jul-06A | 2007-03-01 | 216 | 24-Jul-06A | 2007-03-01 | 216 | 24-Jul-06A | 2007-03-01 | 216 | 24-Jul-06A | 2007-03-22 | 21 | 21
| ROJ - HAY | Intermediate Section Wide |  | PD | 572 | 2006-02-20 | 2006-05-30 | 572 | 2006-02-20 | 2006-05-30 | 572 | 2006-02-20 | 2006-05-30 | 572 | 2006-02-20 | 2006-06-30 | 572 | 2006-02-20 | 30-Jun-06A | 536 | 20-Feb-06A | 07/07/2006A | 536 | 20-Feb-06A | 07-Jul-06A | 536 | 20-Feb-06A | 07-Jul-06A | 536 | 20-Feb-06A | 07-Jul-06A | 536 | 20-Feb-06A | 07-Jul-06A | 536 | 20-Feb-06A | 07-Jul-06A | 536 | 20-Feb-06A | 07-Jul-06A | 536 | 20-Feb-06A | 07-Jul-06A
| ROJ - HAY | Intermediate Section Wide |  | DD | 2625.5 | 2006-05-31 | 2007-01-05 | 2625.5 | 2006-05-31 | 2007-01-05 | 2625.5 | 2006-05-31 | 2007-01-05 | 2625.5 | 2006-06-26 | 2007-01-11 | 2625.5 | 2006-07-03 | 2007-02-06 | 5544.5 | 01-Apr-06A | 2007-04-26 | 4493.64 | 01-Apr-06A | 2007-08-28 | 4493.64 | 01-Apr-06A | 2007-09-03 | 4493.64 | 01-Apr-06A | 2007-09-03 | 5565.36 | 01-Apr-06A | 2007-09-03 | 5565.36 | 03-Apr-06A | 2007-09-03 | 5565.36 | 01-Apr-06A | 2007-09-03 | 5480.36 | 01-Apr-06A | 2007-09-03 | 0 | 0
| ROJ - HAY |  | ROJ - HAY | PD | 254 | 2006-02-20 | 2006-07-28 | 254 | 2006-02-20 | 2006-08-17 | 254 | 2006-02-20 | 2006-08-09 | 254 | 2006-02-20 | 2006-08-17 | 254 | 2006-02-20 | 2006-08-24 | 483 | 20-Feb-06A | 2006-10-20 | 483 | 20-Feb-06A | 2006-09-05 | 483 | 20-Feb-06A | 2006-09-05 | 483 | 20-Feb-06A | 2006-10-02 | 483 | 20-Feb-06A | 2006-11-03 | 483 | 20-Feb-06A | 03-Nov-06A | 483 | 20-Feb-06A | 2006-11-03 | 483 | 20-Feb-06A | 2006-12-22 | 49 | 49
| ROJ - HAY |  | ROJ - HAY | DD | 2258 | 2006-05-12 | 2007-02-06 | 2258 | 2006-05-15 | 2007-02-26 | 2258 | 2006-06-19 | 2007-02-16 | 2258 | 2006-07-03 | 2007-02-26 | 2258 | 2006-07-10 | 2007-03-05 | 4226 | 12-Jul-06A | 2007-07-30 | 4226 | 12-Jul-06A | 2007-08-28 | 4226 | 12-Jul-06A | 2007-09-03 | 4226 | 12-Jul-06A | 2007-09-03 | 4368.5 | 12-Jul-06A | 2007-09-03 | 4368.5 | 12-Jul-06A | 2007-09-03 | 4368.5 | 12-Jul-06A | 2007-09-03 | 4344.5 | 12-Jul-06A | 2007-09-03 | 0 | 0
Haymarket to Granton Square | Section Wide |  |  | DD | 216 | 2006-09-01 | 2006-10-12 | 216 | 2006-09-01 | 2006-10-12 | 216 | 2006-09-01 | 2006-10-12 | 216 | 2006-09-01 | 2006-10-12 | 216 | 2006-09-08 | 2006-10-01 | 216 | 17-Jul-06A | 2007-02-12 | 216 | 17-Jul-06A | 2007-02-26 | 216 | 17-Jul-06A | 2007-04-17 | 216 | 17-Jul-06A | 2007-04-17 | 216 | 17-Jul-06A | 2007-04-17 | 216 | 17-Jul-06A | 2007-04-05 | 216 | 17-Jul-06A | 2007-04-17 | 216 | 17-Jul-06A | 2007-04-17 | 0 | 0
| ROJ - CRT | Intermediate Section Wide |  | PD | 934.5 | 2006-03-06 | 2006-06-30 | 934.5 | 2006-03-06 | 2006-06-30 | 934.5 | 2006-03-06 | 2006-06-30 | 934.5 | 2006-03-06 | 2006-06-30 | 934.5 | 2006-03-06 | 2006-07-03 | 914.5 | 06-Mar-06A | 30/06/2006A | 914.5 | 06-Mar-06A | 30-Jun-06A | 914.5 | 06-Mar-06A | 30-Jun-06A | 914.5 | 06-Mar-06A | 30-Jun-06A | 914.5 | 06-Mar-06A | 30-Jun-06A | 914.5 | 06-Mar-06A | 30-Jun-06A | 914.5 | 06-Mar-06A | 30-Jun-06A | 914.5 | 06-Mar-06A | 30-Jun-06A
| ROJ - CRT | Intermediate Section Wide |  | DD | 2088 | 2006-07-03 | 2007-02-22 | 2088 | 2006-07-03 | 2007-02-22 | 2088 | 2006-07-03 | 2007-02-22 | 2088 | 2006-07-03 | 2007-02-22 | 2088 | 2006-07-03 | 2007-03-01 | 6636.25 | 11-Apr-06A | 2007-07-05 | 6712.25 | 01-Apr-06A | 2007-08-14 | 6712.25 | 01-Apr-06A | 2007-08-28 | 6712.25 | 01-Apr-06A | 2007-08-28 | 6712.25 | 01-Apr-06A | 2007-08-28 | 6712.25 | 03-Apr-06A | 2007-08-28 | 6712.25 | 01-Apr-06A | 2007-08-28 | 6660.25 | 01-Apr-06A | 2007-09-17 | 20 | 20
| ROJ - CRT |  | ROJ - ROS | PD | 290 | 2006-02-20 | 2006-07-21 | 290 | 2006-02-20 | 2006-07-21 | 290 | 2006-02-20 | 2006-07-17 | 290 | 2006-02-20 | 2006-07-17 | 290 | 2006-02-20 | 2006-07-17 | 290 | 20-Feb-06A | 2006-08-29 | 290 | 20-Feb-06A | 2006-08-29 | 290 | 20-Feb-06A | 2006-08-29 | 290 | 20-Feb-06A | 2006-09-25 | 290 | 20-Feb-06A | 2006-10-23 | 290 | 20-Feb-06A | 23-Oct-06A | 290 | 20-Feb-06A | 2006-10-23 | 290 | 20-Feb-06A | 2006-12-11 | 49 | 49
| ROJ - CRT |  | ROJ - ROS | DD | 795 | 2006-07-24 | 2007-02-19 | 795 | 2006-07-24 | 2007-02-19 | 795 | 2006-07-17 | 2007-02-19 | 795 | 2006-07-17 | 2007-02-19 | 795 | 2006-07-18 | 2007-02-26 | 795 | 2006-08-14 | 2007-06-05 | 795 | 2006-08-14 | 2007-07-03 | 795 | 2006-08-14 | 2007-08-10 | 795 | 2006-08-14 | 2007-07-23 | 795 | 2006-08-14 | 2007-08-10 | 795 | 14-Aug-06A | 2007-08-10 | 795 | 14-Aug-06A | 2007-08-10 | 795 | 09-Aug-06A | 2007-09-10 | 31 | 31 | Actual start date of 14th Aug now replaced with actual date of 9th Aug 2006
| ROJ - CRT |  | ROS - RAD | PD | 500 | 2005-12-20 | 2006-07-21 | 500 | 2005-12-20 | 2006-07-21 | 500 | 2005-12-20 | 2006-08-09 | 500 | 2005-12-20 | 2006-08-03 | 500 | 2005-12-20 | 2006-08-03 | 500 | 20-Dec-05A | 2006-09-29 | 500 | 20-Dec-05A | 2006-10-03 | 500 | 20-Dec-05A | 2006-10-03 | 500 | 20-Dec-05A | 2006-10-30 | 500 | 20-Dec-05A | 2006-11-27 | 500 | 20-Dec-05A | 27-Nov-06A | 500 | 20-Dec-05A | 2006-11-27 | 500 | 20-Dec-05A | 2006-12-18 | 21 | 21
| ROJ - CRT |  | ROS - RAD | DD | 1508 | 2006-07-10 | 2007-02-19 | 1508 | 2006-07-10 | 2007-02-19 | 1508 | 2006-07-14 | 2007-02-19 | 1508 | 2006-07-11 | 2007-02-19 | 1508 | 2006-07-31 | 2007-02-26 | 1508 | 2006-08-14 | 2007-07-17 | 1508 | 2006-08-29 | 2007-08-14 | 1508 | 2006-08-29 | 2007-08-20 | 1508 | 29-Aug-06A | 2007-08-20 | 1508 | 29-Aug-06A | 2007-08-20 | 1508 | 29-Aug-06A | 2007-08-20 | 1508 | 29-Aug-06A | 2007-08-20 | 1508 | 29-Aug-06A | 2007-09-17 | 28 | 28
| ROJ - CRT |  | RAD - CRA | PD | 535 | 2006-01-30 | 2006-07-21 | 535 | 2006-01-30 | 2006-08-17 | 535 | 2006-01-30 | 2006-09-06 | 535 | 2006-01-30 | 2006-08-31 | 535 | 2006-01-30 | 2006-08-31 | 535 | 30-Jan-06A | 2006-10-26 | 535 | 30-Jan-06A | 2006-10-10 | 535 | 30-Jan-06A | 2006-10-10 | 535 | 30-Jan-06A | 2006-11-06 | 535 | 30-Jan-06A | 2006-12-04 | 535 | 30-Jan-06A | 2006-12-04 | 535 | 30-Jan-06A | 2006-12-04 | 535 | 30-Jan-06A | 2007-01-15 | 42 | 42
| ROJ - CRT |  | RAD - CRA | DD | 1583 | 2006-07-17 | 2007-02-19 | 1583 | 2006-07-24 | 2007-02-19 | 1583 | 2006-07-31 | 2007-02-19 | 1583 | 2006-07-31 | 2007-02-19 | 1583 | 2006-08-07 | 2007-02-26 | 1133 | 2006-08-14 | 2007-05-22 | 1133 | 14-Aug-06A | 2007-05-18 | 1133 | 14-Aug-06A | 2007-06-26 | 1133 | 14-Aug-06A | 2007-06-26 | 1133 | 14-Aug-06A | 2007-06-26 | 1133 | 14-Aug-06A | 2007-06-26 | 1133 | 14-Aug-06A | 2007-06-26 | 1133 | 14-Aug-06A | 2007-09-04 | 70 | 70
| ROJ - CRT |  | CRA - WGH | PD | 404 | 2006-01-30 | 2006-07-28 | 404 | 2006-01-30 | 2006-08-17 | 404 | 2006-01-30 | 2006-09-06 | 404 | 2006-01-30 | 2006-08-31 | 404 | 2006-01-30 | 2006-08-31 | 404 | 30-Jan-06A | 2006-10-26 | 404 | 30-Jan-06A | 2006-09-05 | 404 | 30-Jan-06A | 2006-09-05 | 404 | 30-Jan-06A | 2006-10-02 | 404 | 30-Jan-06A | 2006-10-30 | 364 | 30-Jan-06A | 30-Oct-06A | 404 | 30-Jan-06A | 2006-10-30 | 404 | 30-Jan-06A | 29-Nov-06A
| ROJ - CRT |  | CRA - WGH | DD | 1245 | 2006-07-13 | 2007-02-19 | 1245 | 2006-07-13 | 2007-02-19 | 1245 | 2006-07-13 | 2007-02-19 | 1245 | 2006-08-04 | 2007-02-19 | 1245 | 2006-07-21 | 2007-02-26 | 1254 | 03-Jul-06A | 2007-06-08 | 1254 | 03-Jul-06A | 2007-06-26 | 1254 | 03-Jul-06A | 2007-07-17 | 1254 | 03-Jul-06A | 2007-07-17 | 1282 | 03-Jul-06A | 2007-07-17 | 1282 | 03-Jul-06A | 2007-07-17 | 1282 | 03-Jul-06A | 2007-07-17 | 1282 | 03-Jul-06A | 2007-08-07 | 21 | 21
| ROJ - CRT |  | WGH - CRT | PD | 340 | 2006-02-06 | 2006-07-21 | 340 | 2006-02-06 | 2006-07-21 | 340 | 2006-02-06 | 2006-07-27 | 340 | 2006-02-06 | 2006-08-10 | 340 | 2006-02-06 | 2006-08-03 | 340 | 06-Feb-06A | 2006-09-26 | 340 | 06-Feb-06A | 2006-09-13 | 340 | 06-Feb-06A | 2006-09-13 | 340 | 06-Feb-06A | 2006-10-10 | 340 | 06-Feb-06A | 2006-11-07 | 340 | 06-Feb-06A | 07-Nov-06A | 340 | 06-Feb-06A | 2006-11-07 | 340 | 06-Feb-06A | 07-Dec-06A
| ROJ - CRT |  | WGH - CRT | DD | 1095 | 2006-08-04 | 2007-02-19 | 1095 | 2006-08-04 | 2007-02-19 | 1095 | 2006-08-04 | 2007-02-19 | 1095 | 2006-08-04 | 2007-02-19 | 1095 | 2006-08-11 | 2007-02-26 | 795 | 2006-08-14 | 2007-07-18 | 795 | 2006-08-29 | 2007-07-02 | 795 | 2006-08-29 | 2007-08-07 | 795 | 2006-09-12 | 2007-08-07 | 796 | 2006-09-12 | 2007-08-07 | 796 | 12-Sep-06A | 2007-08-07 | 796 | 12-Sep-06A | 2007-08-07 | 796 | 12-Sep-06A | 2007-08-07 | 0 | 0
| CRT - CAP | Intermediate Section Wide |  | PD | 924.5 | 2006-03-06 | 2006-06-30 | 924.5 | 2006-03-06 | 2006-06-30 | 924.5 | 2006-03-06 | 2006-06-30 | 924.5 | 2006-03-06 | 2006-06-30 | 924.5 | 2006-03-06 | 30-Jun-06A | 888.5 | 06-Mar-06A | 30/06/2006A | 888.5 | 06-Mar-06A | 30-Jun-06A | 888.5 | 06-Mar-06A | 30-Jun-06A | 888.5 | 06-Mar-06A | 30-Jun-06A | 888.5 | 06-Mar-06A | 30-Jun-06A | 888.5 | 06-Mar-06A | 30-Jun-06A | 888.5 | 06-Mar-06A | 30-Jun-06A | 888.5 | 06-Mar-06A | 30-Jun-06A
| CRT - CAP | Intermediate Section Wide |  | DD | 2489 | 2006-07-03 | 2007-04-05 | 2489 | 2006-07-03 | 2007-04-05 | 2489 | 2006-07-03 | 2007-04-05 | 2489 | 2006-07-03 | 2007-04-05 | 2489.25 | 2006-07-03 | 2007-04-16 | 3093.75 | 02-May-06A | 2007-06-29 | 3173.75 | 02-May-06A | 2007-07-23 | 3173.75 | 02-May-06A | 2007-08-31 | 3173.75 | 02-May-06A | 2007-08-31 | 3153.75 | 02-May-06A | 2007-08-31 | 3153.75 | 02-May-06A | 2007-08-31 | 3153.75 | 02-May-06A | 2007-08-31 | 3109.75 | 02-May-06A | 2007-09-14 | 14 | 14
| CRT - CAP |  | CRT - WGA | PD | 210 | 2006-02-06 | 2006-07-14 | 210 | 2006-02-06 | 2006-08-03 | 210 | 2006-02-06 | 2006-08-22 | 210 | 2006-02-06 | 2006-08-30 | 210 | 2006-02-06 | 2006-08-30 | 210 | 06-Feb-06A | 2006-10-16 | 210 | 06-Feb-06A | 2006-09-05 | 210 | 06-Feb-06A | 2006-09-05 | 210 | 06-Feb-06A | 2006-10-02 | 210 | 06-Feb-06A | 2006-10-30 | 170 | 06-Feb-06A | 30-Oct-06A | 210 | 06-Feb-06A | 2006-10-30 | 210 | 06-Feb-06A | 2006-12-18 | 49 | 49
| CRT - CAP |  | CRT - WGA | DD | 1395 | 2006-07-24 | 2007-02-22 | 1395 | 2006-08-04 | 2007-02-22 | 1395 | 2006-08-09 | 2007-02-27 | 1395 | 2006-08-09 | 2007-03-06 | 1395 | 2006-08-16 | 2007-03-06 | 1395 | 2006-08-14 | 2007-06-25 | 1395 | 2006-08-29 | 2007-07-23 | 1395 | 2006-08-29 | 2007-08-31 | 1395 | 25-Sep-06A | 2007-08-31 | 1395 | 25-Sep-06A | 2007-08-31 | 1395 | 12-Oct-06A | 2007-08-31 | 1395 | 12-Oct-06A | 2007-08-31 | 1395 | 12-Oct-06A | 2007-09-14 | 14 | 14
| CRT - CAP |  | WGA - CAP | PD | 40 | 2006-06-13 | 2006-06-16 | 40 | 2006-06-13 | 2006-06-16 | 40 | 2006-06-13 | 2006-06-16 | 40 | 2006-06-13 | 2006-06-16 | 40 | 2006-06-13 | 23-Jun-06A | 104 | 17-Apr-06A | 20-Jul-06A | 104 | 17-Apr-06A | 20-Jul-06A | 104 | 17-Apr-06A | 20-Jul-06A | 104 | 17-Apr-06A | 20-Jul-06A | 104 | 17-Apr-06A | 20-Jul-06A | 64 | 17-Apr-06A | 20-Jul-06A | 104 | 17-Apr-06A | 20-Jul-06A | 104 | 17-Apr-06A | 20-Jul-06A
| CRT - CAP |  | WGA - CAP | DD | 345 | 2006-08-09 | 2007-02-22 | 345 | 2006-08-09 | 2007-02-22 | 345 | 2006-08-09 | 2007-02-22 | 345 | 2006-08-09 | 2007-02-22 | 345 | 2006-08-16 | 2007-03-01 | 579 | 2006-08-14 | 2007-06-25 | 579 | 2006-09-18 | 2007-07-09 | 579 | 2006-09-18 | 2007-08-21 | 579 | 2007-03-08 | 2007-08-21 | 579 | 2007-03-08 | 2007-08-31 | 579 | 06-Oct-06A | 2007-07-31 | 579 | 16-Oct-06A | 2007-07-31 | 579 | 16-Oct-06A | 2007-07-31 | 0 | 0
| CAP - GRS | Intermediate Section Wide |  | PD | 1004.5 | 2006-03-06 | 2006-06-30 | 1004.5 | 2006-03-06 | 2006-06-30 | 1004.5 | 2006-03-06 | 2006-06-30 | 1004.5 | 2006-03-06 | 2006-06-30 | 1004.5 | 2006-03-06 | 2006-07-03 | 984.5 | 06-Mar-06A | 03/07/2006A | 984.5 | 06-Mar-06A | 03-Jul-06A | 984.5 | 06-Mar-06A | 03-Jul-06A | 984.5 | 06-Mar-06A | 03-Jul-06A | 984.5 | 06-Mar-06A | 03-Jul-06A | 984.5 | 06-Mar-06A | 03-Jul-06A | 984.5 | 06-Mar-06A | 03-Jul-06A | 984.5 | 06-Mar-06A | 03-Jul-06A
| CAP - GRS | Intermediate Section Wide |  | DD | 2967 | 2006-07-03 | 2007-06-07 | 2967 | 2006-07-03 | 2007-06-07 | 2967 | 2006-07-03 | 2007-06-07 | 2967 | 2006-07-03 | 2007-06-07 | 2958 | 2006-07-03 | 2007-06-14 | 3562.5 | 01-Apr-06A | 2007-07-03 | 3628.5 | 01-Apr-06A | 2007-07-17 | 3628.5 | 01-Apr-06A | 2007-09-05 | 3628.5 | 01-Apr-06A | 2007-09-04 | 3628.5 | 01-Apr-06A | 2007-09-04 | 3628.5 | 03-Apr-06A | 2007-08-24 | 3628.5 | 01-Apr-06A | 2007-09-04 | 3578.5 | 01-Apr-06A | 2007-09-04 | 0 | 0
| CAP - GRS |  | CAP - GRW | PD | 104 | 2006-05-08 | 2006-06-21 | 104 | 2006-05-16 | 2006-06-30 | 104 | 2006-04-17 | 2006-07-26 | 104 | 2006-04-17 | 2006-07-31 | 104 | 17-Apr-06A | 2006-07-27 | 40 | 05-Jun-06A | 27/07/2006A | 40 | 05-Jun-06A | 27-Jul-06A | 40 | 05-Jun-06A | 27-Jul-06A | 40 | 05-Jun-06A | 27-Jul-06A | 40 | 05-Jun-06A | 27-Jul-06A | 0 | 05-Jun-06A | 27-Jul-06A | 40 | 05-Jun-06A | 27-Jul-06A | 40 | 05-Jun-06A | 27-Jul-06A
| CAP - GRS |  | CAP - GRW | DD | 570 | 2006-06-21 | 2007-02-27 | 570 | 2006-06-30 | 2007-02-27 | 570 | 2006-07-27 | 2007-02-27 | 570 | 2006-08-01 | 2007-02-27 | 579 | 2006-07-28 | 2007-03-06 | 579 | 2006-08-14 | 2007-06-25 | 579 | 2006-09-18 | 2007-07-09 | 579 | 2006-09-18 | 2007-09-05 | 579 | 2006-11-25 | 2007-09-04 | 586 | 2006-11-25 | 2007-08-24 | 586 | 13-Oct-06A | 2007-08-16 | 586 | 13-Oct-06A | 2007-08-24 | 586 | 13-Oct-06A | 2007-08-24 | 0 | 0
| CAP - GRS |  | GRW - GRS | PD | 40 | 2006-06-12 | 2006-06-16 | 40 | 2006-06-12 | 2006-06-16 | 40 | 2006-06-12 | 2006-06-16 | 40 | 2006-06-12 | 2006-06-16 | 40 | 2006-06-12 | 23-Jun-06A | 40 | 12-Jun-06A | 30/06/2006A | 40 | 12-Jun-06A | 30-Jun-06A | 40 | 12-Jun-06A | 30-Jun-06A | 40 | 12-Jun-06A | 30-Jun-06A | 40 | 12-Jun-06A | 30-Jun-06A | 0 | 12-Jun-06A | 30-Jun-06A | 40 | 12-Jun-06A | 30-Jun-06A | 40 | 12-Jun-06A | 30-Jun-06A
| CAP - GRS |  | GRW - GRS | DD | 345 | 2006-08-14 | 2007-02-27 | 345 | 2006-08-14 | 2007-02-27 | 345 | 2006-08-14 | 2007-02-27 | 345 | 2006-08-14 | 2007-02-27 | 345 | 2006-08-21 | 2007-03-06 | 345 | 2007-01-23 | 2007-06-25 | 345 | 2007-02-06 | 2007-07-09 | 345 | 2007-02-06 | 2007-08-24 | 345 | 2007-06-01 | 2007-08-24 | 345 | 2007-06-01 | 2007-08-24 | 345 | 2007-03-15 | 2007-08-16 | 345 | 2007-03-26 | 2007-08-24 | 345 | 2007-03-26 | 2007-08-24 | 0 | 0
Granton Square to Newhaven Road | Section Wide |  |  | DD | 216 | 2006-08-18 | 2006-09-29 | 216 | 2006-08-18 | 2006-09-29 | 216 | 2006-08-18 | 2006-09-29 | 216 | 2006-08-18 | 2006-09-29 | 216 | 2006-08-18 | 2006-09-29 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
| GRS - LGR | Intermediate Section Wide |  | PD | 803.5 | 2006-03-06 | 2006-06-30 | 803.5 | 2006-03-06 | 2006-06-30 | 803.5 | 2006-03-06 | 2006-07-07 | 803.5 | 2006-03-06 | 2006-07-07 | 803.5 | 2006-03-06 | 2006-08-10 | 315.5 | 06-Mar-06A | 30/06/2006A | 315.5 | 06-Mar-06A | 30-Jun-06A | 315.5 | 06-Mar-06A | 30-Jun-06A | 315.5 | 06-Mar-06A | 30-Jun-06A | 315.5 | 06-Mar-06A | 30-Jun-06A | 315.5 | 06-Mar-06A | 30-Jun-06A | 315.5 | 06-Mar-06A | 30-Jun-06A | 315.5 | 06-Mar-06A | 30-Jun-06A
| GRS - LGR | Intermediate Section Wide |  | DD | 2527.5 | 2006-07-03 | 2007-02-22 | 2527.5 | 2006-07-03 | 2007-02-22 | 2527.5 | 2006-07-10 | 2007-02-22 | 2527.5 | 2006-07-10 | 2007-02-22 | 2527.5 | 2006-08-03 | 2007-02-22 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
| GRS - LGR |  | GRS - LGR | PD | 104 | 2006-04-03 | 2006-06-28 | 104 | 2006-04-03 | 2006-07-06 | 104 | 2006-04-17 | 2006-08-01 | 104 | 2006-04-17 | 2006-08-04 | 104 | 2006-04-17 | 2006-08-11 | 104 | 17-Apr-06A | 23/06/2006A | 104 | 17-Apr-06A | 23-Jun--06A | 104 | 17-Apr-06A | 23-Jun-06A | 104 | 17-Apr-06A | 23-Jun-06A | 104 | 17-Apr-06A | 23-Jun-06A | 104 | 17-Apr-06A | 23-Jun-06A | 104 | 17-Apr-06A | 23-Jun-06A | 104 | 17-Apr-06A | 23-Jun-06A
| GRS - LGR |  | GRS - LGR | DD | 793.5 | 2006-06-28 | 2007-02-22 | 793.5 | 2006-07-07 | 2007-02-22 | 793.5 | 2006-08-01 | 2007-02-22 | 793.5 | 2006-08-04 | 2007-02-22 | 793.5 | 2006-08-09 | 2007-02-22 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
| LGR - NER | Intermediate Section Wide |  | PD | 751.5 | 2006-05-05 | 2006-06-30 | 751.5 | 2006-05-05 | 2006-06-30 | 751.5 | 2006-05-25 | 2006-07-06 | 751.5 | 2006-06-02 | 2006-07-06 | 751.5 | 2006-06-02 | 2006-07-19 | 315.5 | 02-Jun-06A | 16/06/2006A | 315.5 | 02-Jun-06A | 16-Jun-06A | 315.5 | 02-Jun-06A | 16-Jun-06A | 315.5 | 02-Jun-06A | 16-Jun-06A | 315.5 | 02-Jun-06A | 16-Jun-06A | 315.5 | 02-Jun-06A | 16-Jun-06A | 315.5 | 02-Jun-06A | 16-Jun-06A | 315.5 | 02-Jun-06A | 16-Jun-06A
| LGR - NER | Intermediate Section Wide |  | DD | 3419 | 2006-07-03 | 2007-05-10 | 3419 | 2006-07-03 | 2007-05-10 | 3419 | 2006-07-03 | 2007-05-10 | 3419 | 2006-07-03 | 2007-05-10 | 3418.75 | 2006-07-10 | 2007-05-10 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
Haymarket to Gogar | Section Wide |  |  | DD | 216 | 2006-06-08 | 2006-07-19 | 216 | 2006-06-08 | 2006-07-19 | 216 | 2006-06-08 | 2006-07-19 | 216 | 2006-06-12 | 2006-07-21 | 216 | 2006-07-12 | 2006-08-22 | 216 | 17-Jul-06A | 2007-01-08 | 216 | 17-Jul-06A | 2007-01-22 | 216 | 17-Jul-06A | 2007-02-19 | 216 | 17-Jul-06A | 2007-02-19 | 216 | 17-Jul-06A | 2007-03-01 | 216 | 17-Jul-06A | 2007-03-01 | 216 | 17-Jul-06A | 2007-03-01 | 216 | 17-Jul-06A | 2007-03-22 | 21 | 21
| HAY - BAR | Intermediate Section Wide |  | PD | 954 | 2006-02-20 | 2006-05-23 | 954 | 2006-02-20 | 2006-05-23 | 954 | 2006-02-20 | 2006-06-09 | 954 | 2006-02-20 | 2006-06-30 | 954 | 2006-02-20 | 30-Jun-06A | 934 | 20-Feb-06A | 30/06/2006A | 934 | 20-Feb-06A | 30-Jun-06A | 934 | 20-Feb-06A | 30-Jun-06A | 934 | 20-Feb-06A | 30-Jun-06A | 934 | 20-Feb-06A | 30-Jun-06A | 934 | 20-Feb-06A | 30-Jun-06A | 934 | 20-Feb-06A | 30-Jun-06A | 934 | 20-Feb-06A | 30-Jun-06A
| HAY - BAR | Intermediate Section Wide |  | DD | 1913 | 2007-05-24 | 2007-01-02 | 1913 | 2007-05-24 | 2007-01-02 | 1913 | 2006-05-30 | 2007-01-02 | 1913 | 2006-05-30 | 2007-01-24 | 1913 | 2006-07-03 | 2007-01-29 | 2612.5 | 01-Apr-06A | 2007-06-12 | 2207.26 | 01-Apr-06A | 2007-08-14 | 2207.26 | 01-Apr-06A | 2007-09-04 | 2207.26 | 01-Apr-06A | 2007-09-04 | 2207.26 | 01-Apr-06A | 2007-09-04 | 2207.26 | 03-Apr-06A | 2007-09-04 | 2207.26 | 01-Apr-06A | 2007-09-04 | 2207.26 | 01-Apr-06A | 2007-11-08 | 65 | 65
| HAY - BAR |  | HAY - MUR | PD | 1244 | 2005-12-20 | 2006-07-28 | 1244 | 2005-12-20 | 2006-08-17 | 1244 | 2005-12-20 | 2006-08-31 | 1244 | 2005-12-20 | 2006-08-31 | 1244 | 2005-12-20 | 2006-08-31 | 430 | 20-Dec-05A | 2006-10-23 | 430 | 20-Dec-05A | 2006-09-05 | 430 | 20-Dec-05A | 2006-09-05 | 430 | 20-Dec-05A | 2006-10-02 | 430 | 20-Dec-05A | 2006-10-30 | 430 | 20-Dec-05A | 30-Oct-06A | 430 | 20-Dec-05A | 2006-10-30 | 430 | 20-Dec-05A | 30-Nov-06A
| HAY - BAR |  | HAY - MUR | DD | 4170 | 2006-06-05 | 2007-02-06 | 4170 | 2006-06-05 | 2007-02-06 | 4170 | 2006-06-05 | 2007-03-09 | 4170 | 2006-06-05 | 2007-03-09 | 4170 | 2006-07-07 | 2007-03-06 | 3217.5 | 02-Aug-06A | 2007-06-26 | 2392.5 | 02-Aug-06A | 2007-07-16 | 2392.5 | 02-Aug-06A | 2007-08-06 | 2392.5 | 02-Aug-06A | 2007-08-06 | 3220 | 02-Aug-06A | 2007-08-20 | 3220 | 02-Aug-06A | 2007-08-20 | 3220 | 02-Aug-06A | 2007-08-20 | 3220 | 02-Aug-06A | 2007-11-08 | 80 | 80
| HAY - BAR |  | MUR - BAR | PD | 2524 | 2006-03-30 | 2006-09-11 | 40 | 2006-03-30 | 2006-09-11 | 2524 | 2006-03-30 | 2006-09-11 | 2524 | 2006-03-30 | 2006-09-14 | 2524 | 2006-03-30 | 2006-09-18 | 2479.5 | 30-Mar-06A | 2006-10-31 | 2479.5 | 30-Mar-06A | 2006-11-14 | 2479.5 | 30-Mar-06A | 2006-11-14 | 2479.5 | 30-Mar-06A | 2006-12-11 | 2419.5 | 30-Mar-06A | 2007-01-16 | 2419.5 | 30-Mar-06A | 2007-01-16 | 2419.5 | 30-Mar-06A | 2007-01-16 | 2419.5 | 30-Mar-06A | 2007-01-16 | 0 | 0
| HAY - BAR |  | MUR - BAR | DD | 8957.5 | 2006-06-05 | 2007-03-30 | 8957.5 | 2006-06-05 | 2007-03-30 | 8957.5 | 2006-06-05 | 2007-03-30 | 8957.5 | 2006-06-23 | 2007-03-30 | 8957.5 | 2006-07-03 | 2007-04-10 | 8067.5 | 03-Jul-06A | 2007-08-02 | 8067.5 | 03-Jul-06A | 2007-08-14 | 8067.5 | 03-Jul-06A | 2007-09-04 | 8067.5 | 03-Jul-06A | 2007-09-04 | 7867.5 | 03-Jul-06A | 2007-09-04 | 7867.5 | 31-Jul-06A | 2007-09-04 | 7867.5 | 31-Jul-06A | 2007-09-04 | 8108.5 | 31-Jul-06A | 2007-10-22 | 48 | 48
| BAR - EDP | Intermediate Section Wide |  | PD | 531 | 2006-03-07 | 2006-05-12 | 531 | 2006-03-07 | 2006-05-12 | 531 | 2006-03-07 | 2006-05-31 | 531 | 2006-03-07 | 2006-06-30 | 531 | 2006-03-07 | 2006-07-03 | 511 | 07-Mar-06A | 30/06/2006A | 511 | 07-Mar-06A | 30-Jun-06A | 511 | 07-Mar-06A | 30-Jun-06A | 511 | 07-Mar-06A | 30-Jun-06A | 511 | 07-Mar-06A | 30-Jun-06A | 511 | 07-Mar-06A | 30-Jun-06A | 511 | 07-Mar-06A | 30-Jun-06A | 511 | 07-Mar-06A | 30-Jun-06A
| BAR - EDP | Intermediate Section Wide |  | DD | 1941 | 2006-05-11 | 2007-01-31 | 1941 | 2006-05-11 | 2007-01-31 | 1941 | 2006-05-30 | 2007-01-31 | 1941 | 2006-06-06 | 2007-02-07 | 1914 | 2006-07-03 | 2007-02-22 | 2492.5 | 01-Apr-06A | 2007-07-17 | 2018.74 | 01-Apr-06A | 2007-10-01 | 2018.74 | 01-Apr-06A | 2007-09-03 | 2018.74 | 01-Apr-06A | 2007-09-03 | 2018.74 | 01-Apr-06A | 2007-09-03 | 2018.74 | 03-Apr-06A | 2007-09-03 | 2018.74 | 01-Apr-06A | 2007-09-03 | 2018.74 | 01-Apr-06A | 2007-10-12 | 39 | 39
| BAR - EDP |  | BAR - SRN | PD | 394 | 2006-01-23 | 2006-06-30 | 394 | 2006-01-23 | 2006-06-30 | 394 | 2006-01-23 | 2006-07-14 | 394 | 2006-01-23 | 2006-07-19 | 394 | 2006-01-23 | 2006-07-27 | 434 | 23-Jan-06A | 2006-08-21 | 434 | 23-Jan-06A | 2006-09-05 | 434 | 23-Jan-06A | 2006-09-05 | 434 | 23-Jan-06A | 2006-10-02 | 434 | 23-Jan-06A | 2006-10-30 | 434 | 23-Jan-06A | 30-Oct-06A | 434 | 23-Jan-06A | 2006-10-30 | 434 | 23-Jan-06A | 2007-01-08 | 70 | 70
| BAR - EDP |  | BAR - SRN | DD | 2445 | 2006-06-08 | 2007-01-29 | 2445 | 2006-06-08 | 2007-01-29 | 2445 | 2006-06-08 | 2007-01-29 | 2445 | 2006-06-12 | 2007-01-29 | 2454 | 2006-07-07 | 2007-01-29 | 2799 | 2006-08-14 | 2007-07-17 | 2799 | 2006-08-14 | 2007-07-31 | 2799 | 2006-08-14 | 2007-09-03 | 2799 | 2006-08-14 | 2007-09-03 | 2809 | 2006-08-14 | 2007-09-03 | 2809 | 14-Aug-06A | 2007-09-03 | 2809 | 14-Aug-06A | 2007-09-03 | 2809 | 14-Aug-06A | 2007-09-19 | 16 | 16
| BAR - EDP |  | SRN - SGA | PD | 755 | 2006-02-27 | 2006-09-11 | 194 | 2006-02-27 | 2006-09-11 | 755 | 2006-02-27 | 2006-09-11 | 755 | 2006-02-27 | 2006-09-11 | 755 | 2006-02-27 | 2006-09-15 | 755 | 27-Feb-06A | 2006-09-14 | 755 | 27-Feb-06A | 2006-09-14 | 755 | 27-Feb-06A | 2006-09-14 | 755 | 27-Feb-06A | 2006-10-27 | 735 | 27-Feb-06A | 2006-11-16 | 735 | 27-Feb-06A | 16-Nov-06A | 735 | 27-Feb-06A | 2006-11-16 | 735 | 27-Feb-06A | 16-Nov-06A
| BAR - EDP |  | SRN - SGA | DD | 2005 | 2006-06-08 | 2007-01-22 | 2005 | 2006-06-08 | 2007-01-22 | 2005 | 2006-06-08 | 2007-01-22 | 2005 | 2006-06-12 | 2007-01-31 | 2014 | 2006-07-03 | 2007-01-29 | 2696.5 | 06-Jul-06A | 2007-07-17 | 2696.5 | 06-Jul-06A | 2007-07-17 | 2696.5 | 06-Jul-06A | 2007-09-03 | 2696.5 | 06-Jul-06A | 2007-09-03 | 2703.5 | 06-Jul-06A | 2007-08-10 | 2703.5 | 10-Jul-06A | 2007-08-10 | 2703.5 | 10-Jul-06A | 2007-08-10 | 2703.5 | 10-Jul-06A | 2007-08-10 | 0 | 0
| BAR - EDP |  | SGA - EPS | PD | 240 | 2006-01-23 | 2006-06-30 | 240 | 2006-01-23 | 2006-06-30 | 240 | 2006-01-23 | 2006-07-17 | 240 | 2006-01-23 | 2006-07-31 | 240 | 2006-01-23 | 2006-07-10 | 240 | 23-Jan-06A | 2006-08-21 | 240 | 23-Jan-06A | 21-Aug-06A | 240 | 23-Jan-06A | 21-Aug-06A | 240 | 23-Jan-06A | 21-Aug-06A | 240 | 23-Jan-06A | 21-Aug-06A | 240 | 23-Jan-06A | 21-Aug-06A | 240 | 23-Jan-06A | 21-Aug-06A | 240 | 23-Jan-06A | 21-Aug-06A
| BAR - EDP |  | SGA - EPS | DD | 2370 | 2006-06-08 | 2007-01-23 | 2370 | 2006-06-08 | 2007-01-23 | 2370 | 2006-06-08 | 2007-02-07 | 2370 | 2006-06-12 | 2007-02-21 | 2370 | 2006-07-11 | 2007-01-31 | 2370 | 2006-08-14 | 2007-08-14 | 2370 | 2006-08-14 | 2007-10-08 | 2370 | 2006-08-14 | 2007-08-28 | 2370 | 2006-08-14 | 2007-09-04 | 2370 | 2006-08-14 | 2007-09-04 | 2370 | 14-Aug-06A | 2007-09-04 | 2370 | 14-Aug-06A | 2007-09-04 | 2370 | 14-Aug-06A | 2007-10-15 | 41 | 41
| BAR - EDP |  | EPS - EDP | PD | 104 | 2006-04-04 | 2006-05-19 | 104 | 2006-04-04 | 2006-05-19 | 104 | 2006-04-24 | 2006-06-26 | 104 | 2006-04-24 | 2006-07-17 | 104 | 2006-04-24 | 2006-08-04 | 104 | 24-Apr-06A | 27/07/2006A | 104 | 24-Apr-06A | 27-Jul-06A | 104 | 24-Apr-06A | 27-Jul-06A | 104 | 24-Apr-06A | 27-Jul-06A | 104 | 24-Apr-06A | 27-Jul-06A | 104 | 24-Apr-06A | 27-Jul-06A | 104 | 24-Apr-06A | 27-Jul-06A | 104 | 24-Apr-06A | 27-Jul-06A
| BAR - EDP |  | EPS - EDP | DD | 570 | 2006-06-08 | 2007-01-31 | 570 | 2006-06-08 | 2007-01-31 | 570 | 2006-06-08 | 2007-01-31 | 570 | 2006-06-12 | 2007-02-07 | 579 | 2006-07-12 | 2007-02-22 | 345 | 2006-12-20 | 2007-05-30 | 345 | 2006-12-20 | 2007-05-30 | 345 | 2006-12-20 | 2007-07-18 | 345 | 2006-12-20 | 2007-07-18 | 345 | 2006-12-20 | 2007-07-26 | 345 | 22-Sep-06A | 2007-07-26 | 345 | 22-Sep-06A | 2007-07-26 | 345 | 22-Sep-06A | 2007-07-26 | 0 | 0
| EDP - GOG | Intermediate Section Wide |  | PD | 571 | 2006-03-06 | 2006-06-23 | 571 | 2006-03-06 | 2006-06-23 | 571 | 2006-03-06 | 2006-06-23 | 571 | 2006-03-06 | 2006-06-30 | 571 | 2006-03-06 | 30-Jun-06A | 571 | 06-Mar-06A | 30/06/2006A | 571 | 06-Mar-06A | 30-Jun-06A | 571 | 06-Mar-06A | 30-Jun-06A | 571 | 06-Mar-06A | 30-Jun-06A | 571 | 06-Mar-06A | 30-Jun-06A | 571 | 06-Mar-06A | 30-Jun-06A | 571 | 06-Mar-06A | 30-Jun-06A | 571 | 06-Mar-06A | 30-Jun-06A
| EDP - GOG | Intermediate Section Wide |  | DD | 2508.5 | 2006-05-31 | 2007-01-15 | 2508.5 | 2006-05-31 | 2007-01-15 | 2508.5 | 2006-05-31 | 2007-01-15 | 2508.5 | 2006-05-31 | 2007-01-15 | 2508.5 | 2006-07-03 | 2007-02-16 | 3857 | 05-May-06A | 2007-05-14 | 2848.22 | 05-May-06A | 2008-01-30 | 2848.22 | 05-May-06A | 2007-09-04 | 2848.22 | 05-May-06A | 2007-09-04 | 2848.22 | 05-May-06A | 2007-08-29 | 2848.22 | 05-May-06A | 2007-08-29 | 2848.22 | 05-May-06A | 2007-08-29 | 2754.47 | 05-May-06A | 2007-08-29 | 0 | 0
| EDP - GOG |  | EDP - GYL | PD | 40 | 2006-05-16 | 2006-05-22 | 40 | 2006-05-16 | 2006-05-22 | 40 | 2006-05-31 | 2006-06-06 | 40 | 2006-05-15 | 2006-06-05 | 40 | 2006-05-15 | 19-Jun-06A | 40 | 15-May-06A | 30/06/2006A | 40 | 15-May-06A | 30-Jun-06A | 40 | 15-May-06A | 30-Jun-06A | 40 | 15-May-06A | 30-Jun-06A | 40 | 15-May-06A | 30-Jun-06A | 40 | 15-May-06A | 30-Jun-06A | 40 | 15-May-06A | 30-Jun-06A | 40 | 15-May-06A | 30-Jun-06A
| EDP - GOG |  | EDP - GYL | DD | 345 | 2006-06-06 | 2006-12-12 | 345 | 2006-06-06 | 2006-12-12 | 345 | 2006-06-06 | 2006-12-12 | 345 | 2006-06-06 | 2006-12-12 | 345 | 2006-07-07 | 2007-01-22 | 345 | 2006-11-29 | 2007-05-08 | 1083 | 11-Aug-06A | 2007-07-10 | 1083 | 11-Aug-06A | 2007-07-10 | 1083 | 11-Aug-06A | 2007-07-10 | 1671 | 11-Aug-06A | 2007-07-10 | 1671 | 11-Aug-06A | 2007-07-10 | 1671 | 11-Aug-06A | 2007-07-10 | 1671 | 11-Aug-06A | 2007-07-10 | 0 | 0
| EDP - GOG |  | GYL - DEH | PD | 1650 | 2006-03-30 | 2006-09-11 | 0 | 2006-03-30 | 2006-09-11 | 1650 | 2006-03-30 | 2006-09-11 | 1650 | 2006-03-30 | 2006-09-11 | 1650 | 2006-03-30 | 2006-09-15 | 1400 | 30-Mar-06A | 2007-01-12 | 1400 | 30-Mar-06A | 2007-01-26 | 1400 | 30-Mar-06A | 2006-11-06 | 1400 | 30-Mar-06A | 2006-12-01 | 1272 | 30-Mar-06A | 21-Sep-06A | 1272 | 30-Mar-06A | 21-Sep-06A | 1272 | 30-Mar-06A | 21-Sep-06A | 1272 | 30-Mar-06A | 21-Sep-06A
| EDP - GOG |  | GYL - DEH | DD | 5947.5 | 2006-06-06 | 2007-04-17 | 5947.5 | 2006-06-06 | 2007-04-17 | 5947.5 | 2006-06-06 | 2007-04-17 | 5947.5 | 2006-06-06 | 2007-04-17 | 5947.5 | 2006-07-03 | 2007-04-24 | 6100 | 07-Jul-06A | 2007-11-07 | 6067.5 | 07-Jul-06A | 2008-01-30 | 4230 | 07-Jul-06A | 2007-09-04 | 4230 | 07-Jul-06A | 2007-09-04 | 3567.5 | 07-Jul-06A | 2007-07-05 | 3567.5 | 20-Oct-06A | 2007-07-05 | 3567.5 | 20-Oct-06A | 2007-07-05 | 3567.5 | 20-Oct-06A | 2007-07-05 | 0 | 0
| EDP - GOG |  | DEH - GOG | PD | 40 | 2006-05-15 | 2006-05-19 | 40 | 2006-05-15 | 2006-05-19 | 40 | 2006-05-15 | 2006-05-19 | 40 | 2006-05-15 | 2006-06-05 | 40 | 2006-05-15 | 23-Jun-06A | 40 | 15-May-06A | 30/06/2006A | 40 | 15-May-06A | 30-Jun-06A | 40 | 15-May-06A | 2006-06-30 | 40 | 15-May-06A | 2007-01-29 | 40 | 15-May-06A | 29-Sep-06A | 40 | 15-May-06A | 29-Sep-06A | 40 | 15-May-06A | 29-Sep-06A | 40 | 15-May-06A | 29-Sep-06A |  |  | Previously complete 30-Jun-06A then realigned for Jan'07, now completed Sep'06
| EDP - GOG |  | DEH - GOG | DD | 345 | 2006-06-06 | 2006-12-12 | 345 | 2006-06-06 | 2006-12-12 | 345 | 2006-06-06 | 2006-12-12 | 345 | 2006-06-06 | 2006-12-12 | 345 | 2006-07-07 | 2007-01-22 | 345 | 2006-11-29 | 2007-05-08 | 345 | 2006-11-29 | 2007-05-08 | 2182.5 | 2006-11-29 | 2007-08-29 | 2182.5 | 2006-11-29 | 2007-08-29 | 1137.5 | 2006-11-29 | 2007-08-29 | 1137.5 | 20-Oct-06A | 2007-08-29 | 1137.5 | 20-Oct-06A | 2007-08-29 | 1137.5 | 20-Oct-06A | 2007-08-29 | 0 | 0
Gogar Depot | GDE | Intermediate Section Wide | GDE | PD | 6019.5 | 2006-02-01 | 2006-09-04 | 5620 | 2006-02-01 | 2006-09-04 | 6019.5 | 2006-02-01 | 2006-09-04 | 6019.5 | 2006-02-01 | 2006-09-04 | 5955 | 2006-02-01 | 2006-09-15 | 6205 | 01-Feb-06A | 2006-11-09 | 6205 | 01-Feb-06A | 2006-11-23 | 6205 | 01-Feb-06A | 2006-11-23 | 6205 | 01-Feb-06A | 2006-12-20 | 6161 | 01-Feb-06A | 2006-11-23 | 6161 | 01-Feb-06A | 23-Nov-06A | 6161 | 01-Feb-06A | 2006-11-23 | 6161 | 01-Feb-06A | 2007-03-09 | 106 | 106
| GDE | Intermediate Section Wide | GDE | DD | 13606.5 | 2006-03-20 | 2007-04-25 | 13606.5 | 2006-03-20 | 2007-04-25 | 13606.5 | 2006-04-24 | 2007-04-25 | 13606.5 | 2006-06-01 | 2007-05-02 | 13606.33 | 2006-07-03 | 2007-06-05 | 15349.83 | 03-Jul-06A | 2007-07-07 | 13953.51 | 03-Jul-06A | 2007-07-31 | 13953.51 | 03-Jul-06A | 2007-08-23 | 13953.51 | 03-Jul-06A | 2007-08-28 | 13620.02 | 03-Jul-06A | 2007-09-04 | 13620.02 | 03-Jul-06A | 2007-09-04 | 13620.02 | 03-Jul-06A | 2007-09-04 | 13620.02 | 03-Jul-06A | 2007-10-02 | 28 | 28
Gogar to Edinburgh Airport | Section Wide | [42 empty] | 0 | 0
| Section Wide |  |  | DD | 216 | 2006-08-25 | 2006-10-06 | 216 | 2006-08-25 | 2006-10-06 | 216 | 2006-08-25 | 2006-10-06 | 216 | 2006-08-30 | 2006-10-10 | 216 | 2006-09-29 | 2006-11-09 | 216 | 2006-09-05 | 2006-11-22 | 216 | 2006-09-19 | 2006-12-06 | 216 | 2006-09-19 | 2007-02-28 | 216 | 2006-09-19 | 2007-02-28 | 216 | 2006-09-19 | 2007-02-28 | 216 | 29-Aug-06A | 2007-02-28 | 216 | 29-Aug-06A | 2007-02-28 | 216 | 29-Aug-06A | 2007-03-22 | 22 | 22
| GOG - AIR | Intermediate Section Wide |  | PD | 650.5 | 2006-03-06 | 2006-06-30 | 650.5 | 2006-03-06 | 2006-06-30 | 650.5 | 2006-03-06 | 2006-06-30 | 650.5 | 2006-03-06 | 2006-06-30 | 650.5 | 2006-03-06 | 30-Jun-06A | 650.55 | 06-Mar-06A | 30/06/2006A | 650.55 | 06-Mar-06A | 30-Jun-06A | 650.55 | 06-Mar-06A | 30-Jun-06A | 650.55 | 06-Mar-06A | 30-Jun-06A | 650.55 | 06-Mar-06A | 30-Jun-06A | 650.55 | 06-Mar-06A | 30-Jun-06A | 650.55 | 06-Mar-06A | 30-Jun-06A | 650.55 | 06-Mar-06A | 30-Jun-06A
| GOG - AIR | Intermediate Section Wide |  | DD | 2618 | 2006-06-16 | 2007-02-16 | 2618 | 2006-06-16 | 2007-02-16 | 2618 | 2006-06-16 | 2007-02-16 | 2618 | 2006-06-16 | 2007-02-20 | 2609 | 2006-07-03 | 2007-03-22 | 3931.25 | 11-Jul-06A | 2007-04-27 | 2907.9 | 03-Jul-06A | 2007-08-06 | 2907.9 | 03-Jul-06A | 2007-08-24 | 2907.9 | 03-Jul-06A | 2007-08-24 | 2907.9 | 03-Jul-06A | 2007-08-28 | 2907.9 | 03-Jul-06A | 2007-08-28 | 2907.9 | 03-Jul-06A | 2007-08-28 | 2907.9 | 03-Jul-06A | 2007-08-28 | 0 | 0
| GOG - AIR |  | GOG - IPR | PD | 614 | 2006-03-06 | 2006-09-11 | 184 | 2006-03-06 | 2006-09-11 | 614 | 2006-03-06 | 2006-09-04 | 614 | 2006-03-06 | 2006-09-07 | 614 | 2006-03-06 | 2006-09-05 | 614 | 06-Mar-06A | 2006-10-27 | 614 | 06-Mar-06A | 2006-09-07 | 614 | 06-Mar-06A | 2006-09-07 | 614 | 06-Mar-06A | 2006-10-20 | 614 | 06-Mar-06A | 2006-10-30 | 614 | 06-Mar-06A | 30-Oct-06A | 614 | 06-Mar-06A | 2006-10-30 | 614 | 06-Mar-06A | 2006-12-18 | 49 | 49
| GOG - AIR |  | GOG - IPR | DD | 2290 | 2006-06-15 | 2007-01-05 | 2290 | 2006-06-22 | 2007-01-05 | 2290 | 2006-06-22 | 2007-01-23 | 2290 | 2006-06-22 | 2007-01-26 | 2299 | 2006-07-03 | 2007-01-29 | 3349 | 10-Jul-06A | 2007-07-23 | 3349 | 10-Jul-06A | 2007-08-06 | 5029 | 10-Jul-06A | 2007-08-28 | 5029 | 10-Jul-06A | 2007-08-28 | 5424 | 10-Jul-06A | 2007-08-24 | 5424 | 24-Jul-06A | 2007-08-24 | 5424 | 24-Jul-06A | 2007-08-24 | 5424 | 24-Jul-06A | 2007-08-24 | 0 | 0
| GOG - AIR |  | IPR - AIR | PD | 510 | 2006-02-20 | 2006-08-04 | 120 | 2006-02-20 | 2006-08-04 | 510 | 2006-02-20 | 2006-08-23 | 510 | 2006-02-20 | 2006-08-30 | 510 | 2006-02-20 | 2006-08-31 | 510 | 20-Feb-06A | 2006-10-20 | 510 | 20-Feb-06A | 2006-09-05 | 510 | 20-Feb-06A | 2006-09-05 | 510 | 20-Feb-06A | 2006-10-02 | 510 | 20-Feb-06A | 2006-10-30 | 510 | 20-Feb-06A | 30-Oct-06A | 510 | 20-Feb-06A | 2006-10-30 | 472 | 20-Feb-06A | 2006-12-18 | 49 | 49
| GOG - AIR |  | IPR - AIR | DD | 2472.5 | 2006-06-22 | 2007-05-10 | 2472.5 | 2006-06-22 | 2007-05-10 | 2472.5 | 2006-06-22 | 2007-05-10 | 2472.5 | 2006-06-22 | 2007-05-10 | 2472.5 | 2006-07-07 | 2007-05-10 | 2245 | 10-Jul-06A | 2007-03-20 | 2245 | 10-Jul-06A | 2007-05-18 | 565 | 10-Jul-06A | 2007-08-06 | 565 | 10-Jul-06A | 2007-08-21 | 565 | 10-Jul-06A | 2007-08-29 | 565 | 14-Aug-06A | 2007-08-29 | 565 | 14-Aug-06A | 2007-08-29 | 565 | 14-Aug-06A | 2007-08-29 | 0 | 0
|  |  |  | PD | 83855.5 |  |  | 83861 |  |  | 83855.5 |  |  | 83855.5 |  |  | 83422.55 |  |  | 81371.1 |  |  | 81476.1 |  |  | 81611.1 |  |  | 81611.1 |  |  | 81359.1 |  |  | 80840.1 |  |  | 81359.1 |  | PD | 81385.1
|  |  |  | DD | 162271.5 |  |  | 162271.5 |  |  | 162271.5 |  |  | 162271.5 |  |  | 162271.36 |  |  | 186769.36 |  |  | 184646.6 |  |  | 182267.14 |  |  | 185304.31 |  |  | 178634.33 |  |  | 178634.33 |  |  | 178634.33 |  | DD | 178644.08
|  |  |  | TOT | 246127 |  |  | 246132.5 |  |  | 246127 |  |  | 246127 |  |  | 245693.91 |  |  | 268140.46 |  |  | 266122.7 |  |  | 263878.24 |  |  | 266915.41 |  |  | 259993.43 |  |  | 259474.43 |  |  | 259993.43 |  | TOT | 260029.18