## Original
|  | Anticipated Final Account | Gross Cert. at Novation | Balance
1 | Contract Sum | 21882529 | 18970081 | 2912448
2 | Variations -agreed | 776172 | 776172 | 0
| Agreed | 1726171 | 1226060 | 500111
| Settlement of all outstanding Change Requests |  | 0 | 0
| and Variations at Novation | 800000 | 800000 | 0
3 | Additional Services agreement | 2500000 | 2500000 | 0
| Further Additional Services agreement | 450000 | 450000 | 0
| Novation and completion costs | 300000 | 300000 | 0
4 | ER's Alignment agreement | 900000 | 900000 | 0
5 | Sub Total (i) | 29334872 | 25922313 | 3412559
6 | Construction Support (Provisional Sum) | 1000000 |  | 1000000
7 | Consents Support (Provisional Sum) | 675000 |  | 675000
8 | Sub Total (ii) | 31009872 | 25922313 | 5087559
9 | Incentivisation (Non Infraco) | 1000000 |  | 1000000
10 | MUDFA | -103744 |  | -103744
11 | Overall Total | 31906128 | 25922313 | 5983815

## Detail
Edinburgh Tram Network SDS Contract |  |  | Totals
|  |  | Value | Certified
Contract Value
Original Contract Value
|  | Lump Sum Mobilisation | 228000 | 228000
|  | Management Fee - RD, PD and DD Phase | 4484864 | 4484864
|  | Management Fee - CS | 1054023 | 0
|  | Modelling | 151400 | 151400
|  | Mile and Sub-Milestones | 0 | 0
|  | Requirements Definition | 1074157 | 1074157
|  | Preliminary Design | 3478515 | 3478515
|  | Detailed Design | 9362063 | 7735119.13
|  | Surveys | 1750000 | 1700000
|  | Planning Approvals | 300000 | 118519
|  | Adjustment | -493 | -493
Sub Total |  | Original Contract Value | 21882529 | 18970081.13
Changes
TEL/CEC
CRT012/CNB001 | 2006-10-19 | Interchange design and cost benefit | 108576 | 108576
CRT018/CNB007/COB007 | 2006-10-19 | Tramstop locations | 67596 | 67596
CRT022,024-028/CNB008 COB010 - 015 | 2006-10-19 | Charettes (CNB008,010A, 011, 012, 013, 014, 015) | 600000 | 600000
Sub Total |  | All TEL /CEC Changes | 776172 | 776172
tie with Change Orders
CRT001/COS001 | 2006-10-19 | ETN Phasing | -800000 | -800000
CRT002/COS008 |  | Citypoint Rental Contribution | -119910 | -119910
CRT028/CNS010/COS010 | 2006-12-19 | Earl Tram Depot and Stabling | 108376 | 108376
CRT029/CNS011/COS029 | 2006-12-19 | Earl Bridge Structure S33 | 116996 | 116996
CRT030/COS013 | 2006-09-05 | Earl GI | 5992 | 5992
CRT074/COS014 |  | Updated Utilities Capex | 38006 | 38006
CRT009/COS016 |  | tie procurement | 59483 | 59483
CRT045/COS017 | 2006-10-17 | Ocean Terminal Revised Layout | 9660 | 9660
CR072/ CNS018/ COS018 |  | Eastfield Avenue Realignment | 18924 | 18924
CRT049/CNS019/COS019 | 2006-11-14 | Additional GI Scope Granton to Newhaven | 20274 | 20274
CRT076/CNS020/COS020 |  | Gogar Depot BAA Runway Extension | 14009 | 14009
CRT102/CNS030/COS030 |  | Employers Requirements | 17000 | 17000
CRT010/CRS004/005/ COS038 |  | Modelling | 240000 | 240000
CRT190/CNS040/COS040 |  | Crew Relief facilities - Haymarket Tramstop Structure | 11669 | 11669
CRT212/CNS042/COS042 | 2007-06-06 | Co-ordination and sequencing works - St Andrew Square | 29000 | 29000
CRT050/COS021 | 2006-10-19 | Gogarburn Partnership Report | 1425 | 1425
CRT140/COS057 |  | St Andrews Square OLE | 5556 | 5556
CRT143/ COS099 | 2007-02-20 | St Andrews Square Island Platform | 78101 | 78101
CRT144/ COS100 | 2007-02-21 | Shandwick Place Charette | 24508 | 24508
CRT145/ COS101 | 2007-02-22 | Princess St Realignment | 48331 | 48331
CRT146/ COS102 | 2007-02-23 | Picardy Place Concept Revision | 69919 | 69919
CRT147/ COS060 | 2007-02-24 | Bottom of Leith Walk | 31400 | 31400
CRT148/ COS103 | 2007-06-20 | Bus Provision Foot of Leith Walk and Constitution Street | 22593 | 22593
CRT163/COS056 |  | SRU Cross Sections | 6989 | 6989
CRT176/COS058 | 2007-02-19 | Catherdral Substation Revisions | 8256 | 8256
CRT177/ COS026 | 2007-02-28 | Additional Infraco Information | 24083 | 24083
CRT180/COS059 |  | Lothian Road Junction | 5480 | 5480
CRT182/ COS025 |  | Casino Sq Trial Area | 11484 | 11484
CRT193/ COS106 |  | Carricknowe Bridge Widening | 38294 | 38294
CRT194/COS035 |  | Ocean Terminal Stop Functional Design Forth Ports Concepts | 41000 | 41000
CRT208/COS068 | 2007-06-27 | South Gyle Tramstop | 8290 | 8290
CRT215/ COS090 | 2008-01-10 | Changing Tramstop Names | 16160 | 16160
CRT216/ COS094 | 2007-06-27 | Coltbridge Viaduct Additional Preliminary Design Work | 16928 | 16928
CRT219/COS043 |  | Utilities MUDFA Reprogramming | 20000 | 20000
CRT222/ COS095 | 2007-06-06 | Edinburgh Park Bus Stop | 11775 | 11775
CRT228/COS045 |  | Local to OS Grid | 3500 | 3500
CRT231/ COS104 | 2007-11-29 | Balgreen Road Option 3 | 85268 | 51161
CRT232/ COS096 | 2007-06-27 | Ground Investigation Gogar Additional Costs Due to UXO | 11966 | 11966
CRT241/COS049 |  | Segregation of Phase 1a and 1b | 47000 | 47000
CRT243/COS066 | 2007-11-15 | EARL - Tram Changes 3 | 113599 | 85199
CRT244/COS065 | 2007-08-02 | Gogar Depot Adjustments due tO EARL | 27435 | 27435
CRT245/ COS110 | 2007-08-09 | Wide Area Modelling | 360050 | 180025
CRT251/ COB007 | 2007-11-15 | RBS Gogarburn tramstop design and approvals | 24117 | 12059
CRT252/ COB006 | 2007-11-16 | Ocean Terminal Area Redesign | 85533 | 37590
CRT253/ COB004 | 2007-11-16 | Lindsay Road Detailed Design | 131600 | 105280
CRT254/ COS071 rev 1 | 2007-11-16 | Casino Sq | 15645 | 15645
CRT257 /COS079 | 2007-11-15 | Alignment from Tower Place to Casino Square 1a | 56003 | 44802
CRT258/ COS085 | 2007-12-06 | Torphichen Street Two way Conversion 1D | 22269 | 22269
CRT259/ COS089 | 2007-11-16 | Bernard Street Baltic Street Road Works | 23659 | 23659
CRT262/COS082 | 2007-11-20 | Review of Actual Tram Vehicle Load against Assumed Vehicle Load | 17975 | 8988
CRT274/ COB005 | 2007-11-22 | Additional Work Lindsay Road Functional Design | 11458 | 11458
CRT276/ COB003 | 2007-11-21 | 3A Realignment of Telford Road Bridge stepped access | 21468 | 2146.8
CRT281 /COS087 | 2007-11-29 | Meeting Room Re-charges | 22433 | 22433
CRT284/ COS078 | 2007-12-03 | St Andrew Square Advance Tram TRO | 5960 | 5960
CRT287/COS034 |  | Tram Alignment on BAA Services Drawing | 380 | 380
CRT288/COS033 |  | Tram Length Report | 14075 | 14075
CRT289/ COS092 | 2007-12-07 | Utilities SGN IFC Drawings | 1208 | 1208
CRT290/ COS098 | 2007-12-07 | Scottish Gas Networks Plates 27 to 31 | 5642 | 5642
CRT293/ COS084 | 2007-12-21 | Design of Car Parking at Haymarket Depot | 14260 | 14260
CRT294/ COB013 | 2007-12-21 | West Pilton Way West Granton Access Junction Re Design | 70384 | 35192
CRT295/ COS093 | 2007-12-12 | Re-submission of Roseburn Corridor - Maintenance and Access Strategy | 416 | 416
CRT300/ COS105 | 2008-01-08 | Utilities Diversion on Constitution Street | 11242 | 11242
CRT301 /COS117 | 2008-01-08 | Full Planning Permission | 22421 | 0
CRT304/ COS097 | 2008-01-09 | MUDFA Plate 1 to 12 Section 1A | 9772 | 4886
CRT305/ COS080 | 2008-01-09 | Edinburgh Park Private Utilities Relocation | 5770 | 4616
CRT306/ COS091 | 2008-01-15 | Traffic Modelling Changes to Road Design - Frederick Street & Mound | 11760 | 11760
CRT307 /COS127 | 2008-01-23 | Frederick Street Opening | 53027 | 26514
CRT312 /COS121 | 2008-02-01 | Ocean Terminal Optioneering and Additional Detailed Design | 43873 | 43873
CRT313 /COS123 | 2008-02-27 | Police Box Coffee Bar Relocation | 7364 | 0
CRT317 /COS112 | 2008-02-27 | Tram Stop Changes | 24996 | 18747
CRT324 /COS119 | 2008-03-04 | Building Warrants for Cathedral Lane substation, Leith Walk substation, Murrayfield Accommodation and Haymarket Crew Facilities | 25570 | 3836
CRT326 /COS111 | 2008-02-29 | Forth Port Drawings | 2400 | 2400
CRT327 /COS120 | 2008-03-13 | Coltbridge Viaduct Security Barrier | 6234 | 0
CRT328 /CNS114 /COS114 | 2008-03-13 | Employer's Requirements v3.5a Review | 39748 | 39748
CRT330 /CNS113 | 2008-03-19 | Railway Access Points | 392 | 392
CRT331 /CNS115 /COS115 | 2008-03-17 | Review of Infraco Civils Proposals | 8248 | 8248
|  | Adjustment - Delta on Change Order COB001 | 0 | 0
|  | Balancing adjustment | 0 | -1.93
Sub Total |  | All tie Changes | 1726171 | 1226059.87
Settled at Novation
CRT308 | 2008-01-22 | Utilities A8 Underpass | 800000 | 800000
CRT318 |  | Leith Walk Footpath Finishes
CRT319 | 2008-02-29 | Roseburn Street Bridge Redesign Feasibility Study
CRT321 | 2008-02-27 | SGN Constitution Street Iterations
CRT322 | 2008-04-30 | Edinburgh Airport Tramstop Kiosk
CRT334 | 2008-03-25 | Additional visualisations at Dublin St
CRT336 | 2008-04-04 | York Place Crossover
CRT338 | 2008-04-04 | Haymarket Station Access Road
CRT341 | 2008-04-04 | Picardy Place Abortive Work
CRT342 | 2008-04-04 | Additional Scope to CR253 Lindsay Road Detailed Design
CRT344 | 2008-04-16 | Victoria Swing Bridge Scheduled Ancient Monument
CRT345 | 2008-04-16 | Advanced directional signage
CRT347 | 2008-04-16 | Drainage survey review
CRT348 |  | Relocation of civil monuments
CRT349 | 2008-04-16 | AMIS manhole survey
CRT350 | 2008-04-16 | Leith Wlak bus priority redesign
CRT351 | 2008-04-16 | Building warrant Police Box Picardy Place
CRT352 | 2008-04-16 | Ocean Terminal detail design optioneering
CRT353 | 2008-04-16 | Craigleith Tramstop access
CRT355 | 2008-04-30 | CEC Changes to Shandwick Place
CRT356 | 2008-04-30 | CEC Changes to Haymarket Parapets and Spans
CRT357 |  | Additional Topographical Survey at Balgreen Rd Access Bridge
CRT358 | 2008-04-24 | Separation of Phase 1a and 1b Roseburn Junction
CRT359 |  | Additional Management Services
CRT360 |  | N.I.L. Future Proofing for Roads and Stops
CRT361 | 2008-04-25 | Building Fixings Owners Approvals
CRT362 |  | Employers Requirements Alignment Review
CRT363 |  | Additional Optioneering at Balgreen Road Structures
CRT364 | 2008-04-30 | Disruption to IDC Process due to Critical Issues
CRT365 | 2008-04-25 | Section 1A Split into sub sections
CRT366 | 2008-04-30 | Request for Various Drawings and Supporting Information
CRT367 | 2008-04-25 | Section 1C Split into sub sections
CRT368 | 2008-04-28 | Gogarburn RBS stop New Prior Approval Batch
CRT374 | 2008-05-08 | Omission of Stanby Generator | 900000 | 900000
CRT375 | 2008-05-08 | Tram Vehicle Tecghnical Info
CRT376 | 2008-05-08 | Picardy Place
CRT377 | 2008-05-08 | Tramstop equipment
CRT378 | 2008-05-08 | Systems Branding
CRT379 | 2008-05-08 | EAL Tramstop Kiosk
CRT380 | 2008-05-08 | Workshop attendance
CRT381 | 2008-05-08 | Ingliston Park & Ride
Sub Total |  | All settled at Novation | 1700000 | 1700000
SDS Claims Approved
2007-06-01 |  | Additional Management & Supervision Services | 2500000 | 2500000
2008-01-01 |  | Additional Management & Supervision Services | 450000 | 450000
2008-05-01 |  | Additional Management & Supervision Services | 300000 | 300000
Sub Total |  | All SDS Approved Claims | 3250000 | 3250000
MUDFA Reduction
|  | tie retained scope | -103744 | 0
Sub Total |  | MUDFA Reduction | -103744 | 0
Total |  | Total Fixed Contract Value | 29231128 | 25922313
Provisional Sums
|  | Siemens Support | 675000
|  | Construction Support | 1000000
Sub Total |  | All Provisional Sums | 1675000 | 0
Grand Total |  | Total Novated Contract Value | 30906128 | 25922313