## Risk Allocation
EDINBURGH TRAM PROJECT | [123 empty] | 2026-07-29
Risk Allocation Report
Current Period End | 2007-09-15 | [59 empty] | Total Allocation |  |  |  |  | 0
[56 empty] | Risk Mean Sum |  |  |  |  | Phase 1A | Phase 1B
Sim Run P90 1A+1B | 48376.0547 | £k | [50 empty] | k |  |  | 36015.0481 | £k |  |  |  | 41882.0193 | 9497.4611 | £k
WBS Item | Allocated Risks |  |  |  | Impact Assessment 3 July 2007 |  |  |  | Exposure Period | [45 empty] | No of Periods | Sim Run Risk Mean | P90 Risk Allocation |  | Proportion allocated to 1A | Parameter used to Split 1A/1B | P90 Risk Allocation 1A | P90 Risk Allocation 1B | P90 Value Per Period | total P90 | 80:20 Sum | 80:20 %age | [46 empty] | Utilised for Risk Treatment | Utilised for Risk Exposure
| Risk ID | Cause | Risk Event | Effect | Prob | Current Impact Assessment £k |  |  | Start | End | [43 empty] | Construction End | [10 empty] | Cumulative | Cumulative | [9 empty] | 2008/09 | [12 empty] | 2009/10 | [12 empty] | 2010/11 | [8 empty] | Construction Programme End |  |  |  | QUANTITATIVE RISK CALCULATIONS
[5 empty] | % | Min | Most Likely | Max |  |  | 2007-09-15 | 2007-10-13 | 2007-11-10 | 2007-12-08 | 2008-01-05 | 2008-02-02 | 2008-03-01 | 2008-03-31 | 2008-04-26 | 2008-05-24 | 2008-06-21 | 2008-07-19 | 2008-08-16 | 2008-09-13 | 2008-10-11 | 2008-11-08 | 2008-12-06 | 2009-01-03 | 2009-01-31 | 2009-02-28 | 2009-03-31 | 2009-04-25 | 2009-05-23 | 2009-06-20 | 2009-07-18 | 2009-08-15 | 2009-09-12 | 2009-10-10 | 2009-11-07 | 2009-12-05 | 2010-01-02 | 2010-01-30 | 2010-02-27 | 2010-03-31 | 2010-05-01 | 2010-05-29 | 2010-06-26 | 2010-07-24 | 2010-08-21 | 2010-09-18 | 2010-10-16 | 2010-11-13 | 2010-12-11 | 2011-01-08 |  | £k | £k | [5 empty] | £k |  | £k (P90) | % (P90) | 2007-08-18 | 2007-09-15 | 2007-10-13 | 2007-11-10 | 2007-12-08 | 2008-01-05 | 2008-02-02 | 2008-03-01 | 2008-03-31 | 2008-04-26 | 2008-05-24 | 2008-06-21 | 2008-07-19 | 2008-08-16 | 2008-09-13 | 2008-10-11 | 2008-11-08 | 2008-12-06 | 2009-01-03 | 2009-01-31 | 2009-02-28 | 2009-03-31 | 2009-04-25 | 2009-05-23 | 2009-06-20 | 2009-07-18 | 2009-08-15 | 2009-09-12 | 2009-10-10 | 2009-11-07 | 2009-12-05 | 2010-01-02 | 2010-01-30 | 2010-02-27 | 2010-03-31 | 2010-05-01 | 2010-05-29 | 2010-06-26 | 2010-07-24 | 2010-08-21 | 2010-09-18 | 2010-10-16 | 2010-11-13 | 2010-12-11 | 2011-01-08 |  | £k | £k | Risk Distribution | Sim Run Risk Mean | Probability | Reverse Probability | Most Likely | No Impact | Cost @Risk | No Impact | Overall Contingency
1.1 Land & Property | 6 | CEC fails to manage existing assets or changes | tie required to assume asset management role during and following construction | Increased legal and management costs to deal with change. Delay to construction programme. | 20 | 50 | 100 | 200 | 2007-04-11 | 2010-12-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 43 | 23.157 | 31.1049 | 1A + 1B | 0.81 | Surface Area Affected (from Highways element of Infraco estimate) | 25.195 | 5.9099 | 0.72337 | 31.1049 | 31.1049 | 0.0643% | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0.72337 | 0 | 31.8283 |  |  | TRIANG | #NAME? | 0.2 | 0.8 | 100 | 0 | #NAME? | 0 | #NAME?
1.1 Land & Property | 9 | Reclassification of land | Land reclassification changes value | Reclassification of land increases value/ cost of land. | 10 | 1000 |  | 1000 | 2007-03-20 | 2012-03-20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 44 | 100 | 134.3218 | 1A + 1B | 0.82 | MUDFA + Infraco + Tramco Estimate | 110.1439 | 24.1779 | 3.0528 | 134.3218 | 165.4267 | 0.342% | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 3.0528 | 137.3746 |  |  | UNIFORM | #NAME? | 0.1 | 0.9 | 0 | 0 | #NAME? | 0 | #NAME?
1.1 Land & Property | 10 | Costs of obtaining access rights are unknown | Cost associated with obtaining wayleaves | Increased legal costs relating to obtaining wayleaves | 40 | 50 | 200 | 500 | 2007-04-02 | 2007-10-25 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 99.6484 | 133.8495 | 1A + 1B | 0.85 | Land and Property Estimate | 113.7721 | 20.0774 | 66.9247 | 133.8495 | 299.2762 | 0.6186% | 66.9247 | 66.9247 | 66.9247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.7742 |  |  | TRIANG | #NAME? | 0.4 | 0.6 | 200 | 0 | #NAME? | 0 | #NAME?
7.2 MUDFA/Utilities | 21 | Design constraints e.g. presence of other utilities, proximity of LoD boundary, diversion technical requirements etc. | Design requires that Utilities are diverted outside of LoD | Additional design; additional land purchase required and consequent contact with landowners; design may result in increased work quantities due to extent of diversions; potential increased duration of works. | 80 | 100 | 250 | 500 | 2007-03-08 | 2008-10-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 226.4112 | 304.1196 | 1A + 1B | 0.78 | Infraco Prelims | 237.2133 | 66.9063 | 20.2746 | 304.1196 | 603.3957 | 1.247% | 20.2746 | 20.2746 | 20.2746 | 20.2746 | 20.2746 | 20.2746 | 20.2746 | 20.2746 | 20.2746 | 20.2746 | 20.2746 | 20.2746 | 20.2746 | 20.2746 | 20.2746 | 20.2746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 324.3942 |  |  | TRIANG | #NAME? | 0.8 | 0.2 | 250 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 22 | Base estimate does not account for presence of hazardous materials on land | Hazardous materials encountered during construction | Additional treatment costs and protective measures | 50 | 100 | 400 | 2000 | 2008-01-01 | 2010-09-30 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 36 | 416.0072 | 558.7883 | 1A + 1B | 0.94 | MUDFA Price | 525.261 | 33.5273 | 15.5219 | 558.7883 | 1162.184 | 2.402% | 0 | 0 | 0 | 0 | 0 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 15.5219 | 0 | 0 | 0 | 0 | 558.7883 |  |  | TRIANG | #NAME? | 0.5 | 0.5 | 400 | 0 | #NAME? | 0 | #NAME?
1.1 Land & Property | 26 | Protracted negotiation, additional claims, late acquisitions or late claims in relation to land and property | Use of legal advisors required beyond current budget | Legal/ advisor budget may be exceeded | 25 | 100 |  | 100 | 2007-03-20 | 2012-03-21 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 44 | 25 | 33.5804 | 1A + 1B | 0.81 | Highways Element of Infraco Estimate | 27.2002 | 6.3803 | 0.76319 | 33.5804 | 1195.7645 | 2.472% | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 0.76319 | 34.3436 |  |  | UNIFORM | #NAME? | 0.25 | 0.75 | 0 | 0 | #NAME? | 0 | #NAME?
2 PROCUREMENT CONSULTANT | 44 | SDS contractor does not deliver the required prior approval consents before novation | Late prior aproval consents | Delay to programme with additional resource costs and delay to infraco. procurement. Impact upon risk balance. | 50 | 900 | 1800 | 2700 | 2006-06-30 | 2007-09-28 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 898.9515 | 1207.4877 | 1A + 1B | 1 | Geographic - items in risk generally apply to 1A therefore 100% allocation | 1207.4877 | 0 | 1207.4877 | 1207.4877 | 2403.2521 | 4.968% | 1207.4877 | 1207.4877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2414.9753 |  |  | TRIANG | #NAME? | 0.5 | 0.5 | 1800 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 47 | Poor design and review processes; cumbersome approvals process; reiterative design/approvals process. | Completion of MUDFA works is delayed (due to late design/approvals) - late utility diversions in advance of Infraco works. | Increase in price and time delay in the Infraco contract; Infraco could end up delay to commencement or with utility diversion and would have to price for or have to carry out unplanned re-sequencing; Claims from MUDFA as a result of being unable to proce | 50 | 400 | 2400 | 4800 | 2007-10-01 | 2009-06-30 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 1267.5105 | 1702.5427 | 1A + 1B | 1 | Costs applicable whether or not 1B is done | 1702.5427 | 1702.5427 | 74.0236 | 1702.5427 | 4105.7948 | 8.487% | 0 | 0 | 74.0236 | 74.0236 | 74.0236 | 74.0236 | 74.0236 | 74.0236 | 74.0236 | 74.0236 | 74.0236 | 74.0236 | 74.0236 | 74.0236 | 74.0236 | 74.0236 | 74.0236 | 74.0236 | 74.0236 | 74.0236 | 74.0236 | 74.0236 | 74.0236 | 74.0236 | 74.0236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1702.5427 |  |  | TRIANG | #NAME? | 0.5 | 0.5 | 2400 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 54 | Contractor default e.g. insolvency. | Construction bond not available in the event of Infraco default | Increase in cost and progeamme due to appointment of replacement contractor | 1 | 0 | 3300 | 6300 | 2007-01-12 | 2011-01-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 43 | 32.8172 | 44.0807 | 1A + 1B | 0.78 | Infraco Estimate | 34.3829 | 9.6978 | 1.0251 | 44.0807 | 4149.8755 | 8.578% | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 1.0251 | 0 | 45.1058 |  |  | TRIANG | #NAME? | 0.01 | 0.99 | 3300 | 0 | #NAME? | 0 | #NAME?
2.1 tie Resources | 58 | Poor performance (quality) by Infraco during construction; poor materials; latent defects | Infraco fails to deliver construction quality; latent defects occur during or after Infraco maintenance period | Rework, stakeholder criticism, negative PR, programme delay if quality issue occurs during construction, operations affected by rework, project management costs to deal with issues | 10 | 25 |  | 100 | 2010-12-31 | 2016-12-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 6.2179 | 8.352 | 1A + 1B | 0.78 | Infraco Estimate | 6.5145 | 1.8374 | 8.352 | 8.352 | 4158.2275 | 8.596% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.352 | 8.352 |  |  | UNIFORM | #NAME? | 0.1 | 0.9 | 0 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 66 | Infraco and Tram systems not compatible and/or contracts not aligned. | Inadequate system integration | Time delay and interface problems between specialist contractors / sub systems. | 50 | 0 | 1000 | 3000 | 2007-01-12 | 2011-01-03 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 43 | 668.9332 | 898.523 | 1A + 1B | 0.78 | Infraco Estimate | 700.848 | 197.6751 | 20.8959 | 898.523 | 5056.7505 | 10.45% | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 20.8959 | 0 | 919.4189 |  |  | TRIANG | #NAME? | 0.5 | 0.5 | 1000 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 67 | Interface with CEC as roads authority | Roads maintenance is not carried out | CEC is in breach of its statutory duties | 20 | 100 | 250 | 500 | 2008-01-01 | 2010-09-30 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 36 | 56.4086 | 75.7691 | 1A + 1B | 1 | Geographic | 75.7691 | 0 | 2.1047 | 75.7691 | 5132.5196 | 10.61% | 0 | 0 | 0 | 0 | 0 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 2.1047 | 0 | 0 | 0 | 0 | 75.7691 |  |  | TRIANG | #NAME? | 0.2 | 0.8 | 250 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 68 | Interface with Transdev | Supply of commissioning services from Transdev to Infraco. | Delay and costs incurred by Infraco. | 1 | 0 | 1000 | 3000 | 2009-09-30 | 2010-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 16 | 13.8126 | 18.5534 | 1A + 1B | 1 | Geographic | 18.5534 | 0 | 1.1596 | 18.5534 | 5151.073 | 10.65% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1596 | 1.1596 | 1.1596 | 1.1596 | 1.1596 | 1.1596 | 1.1596 | 1.1596 | 1.1596 | 1.1596 | 1.1596 | 1.1596 | 1.1596 | 1.1596 | 1.1596 | 1.1596 | 0 | 18.5534 |  |  | TRIANG | #NAME? | 0.01 | 0.99 | 1000 | 0 | #NAME? | 0 | #NAME?
2 PROCUREMENT CONSULTANT | 76 | Introduction of TEL as client | Change of client during works | Delay and cost during re-negotiation of DPOF contract and additional approvals process | 50 | 12.5 |  | 12.5 | 2006-07-03 | 2007-09-24 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6.25 | 8.3951 | 1A + 1B | 0.73 | Track Estimate | 6.1284 | 2.2667 | 8.3951 | 8.3951 | 5159.4681 | 10.67% | 8.3951 | 8.3951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.7902 |  |  | UNIFORM | #NAME? | 0.5 | 0.5 | 0 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 78 | Inadequate scope of surveys and site investigations - SDS does not scope surveys and investigations adequately | Contractor claims that ground information is not sufficient or encounters unforeseen ground conditions. | Delay and cost due to scope increase, design, rework etc during construction or pricing of additional surveys by Bidders. | 80 | 200 | 500 | 1000 | 2007-10-01 | 2010-12-31 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 42 | 454.4869 | 610.4749 | 1A + 1B | 1 | Geographic | 610.4749 | 0 | 14.5351 | 610.4749 | 5769.943 | 11.93% | 0 | 0 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 14.5351 | 0 | 610.4749 |  |  | TRIANG | #NAME? | 0.8 | 0.2 | 500 | 0 | #NAME? | 0 | #NAME?
7.4 Tramco | 97 | Problems with tram supplier (industrial relations, financial problems etc) | Delay in supply of vehicles - 1A | Time delay to operations, costs relating procurement of replacement manufacturer | 25 | 0 | 260 | 450 | 2007-07-19 | 2009-10-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 59.5075 | 79.9315 | 1A | 0.87 | Transdev Estimate | 69.5404 | 10.3911 | 2.9604 | 79.9315 | 5849.8745 | 12.09% | 2.9604 | 2.9604 | 2.9604 | 2.9604 | 2.9604 | 2.9604 | 2.9604 | 2.9604 | 2.9604 | 2.9604 | 2.9604 | 2.9604 | 2.9604 | 2.9604 | 2.9604 | 2.9604 | 2.9604 | 2.9604 | 2.9604 | 2.9604 | 2.9604 | 2.9604 | 2.9604 | 2.9604 | 2.9604 | 2.9604 | 2.9604 | 2.9604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82.8919 |  |  | TRIANG | #NAME? | 0.25 | 0.75 | 260 | 0 | #NAME? | 0 | #NAME?
7.4 Tramco | 98 | Problems with tram supplier (industrial relations, financial problems etc) | Delay in supply of vehicles - 1B | Time delay to operations, costs relating procurement of replacement manufacturer | 25 | 0 | 240 | 400 | 2007-07-19 | 2009-10-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 53.4959 | 71.8566 | 1B | 0.87 | No of Trams | 62.5152 | 9.3414 | 2.6614 | 71.8566 | 5921.7311 | 12.24% | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.5179 |  |  | TRIANG | #NAME? | 0.25 | 0.75 | 240 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 100 | 3rd party agreements impact on works not accounted for in estimate/ become apparent during construction | Increase in fencing, walls, screen requirements | Additional construction costs | 30 | 60 | 120 | 240 | 2006-07-03 | 2007-09-24 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 41.7474 | 56.0759 | 1B | 1 | Geographic | 56.0759 | 0 | 56.0759 | 56.0759 | 5977.807 | 12.36% | 56.0759 | 56.0759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112.1518 |  |  | TRIANG | #NAME? | 0.3 | 0.7 | 120 | 0 | #NAME? | 0 | #NAME?
3 DESIGN | 102 | Change in Design Kinematic Envelope requirements | Detail design leads to kinematic envelope impact on vertical and horizontal alignment | Realignment of track to accommodate an increased 3 dimensional safe zone around the preferred route | 50 | 0 | 500 | 3250 | 2006-01-01 | 2007-07-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 623.6043 | 837.6364 | 1A | 1 | Geographic | 837.6364 | 0 | 0 | 0 | 6815.4434 | 14.09% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | TRIANG | #NAME? | 0.5 | 0.5 | 500 | 0 | #NAME? | 0 | #NAME?
3 DESIGN | 104 | Delay in design information release from specialist tram manufacturer | Delay in detailing of stops, trackway, OLE etc for Phase 1B | Time delay and consequent costs | 30 | 0 | 25 | 83 | 2007-01-01 | 2007-09-30 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 10.837 | 14.5565 | 1B | 1 | Geographic | 14.5565 | 0 | 14.5565 | 14.5565 | 6829.9999 | 14.12% | 14.5565 | 14.5565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.113 |  |  | TRIANG | #NAME? | 0.3 | 0.7 | 25 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 105 | Encountering archaeological finds/burials/munitions during construction | Exhumation of archaeological finds/burials | Delay in construction programme | 85 | 0 | 150 | 500 | 2007-09-28 | 2009-12-30 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 184.5958 | 247.9524 | 1A | 0.81 | Highways Element of Infraco Estimate | 200.8415 | 47.111 | 8.5501 | 247.9524 | 7077.9523 | 14.63% | 0 | 0 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 8.5501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247.9524 |  |  | TRIANG | #NAME? | 0.85 | 0.15 | 150 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 115 | Network Rail cancels planned possessions | Planned work at interface with Network Rail is delayed | Time delay and resulting cost increase | 10 | 350 | 750 | 2000 | 2007-10-01 | 2010-12-31 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 42 | 104.6722 | 140.5975 | 1A | 1 | Geographic | 140.5975 | 0 | 3.3476 | 140.5975 | 7218.5498 | 14.92% | 0 | 0 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 3.3476 | 0 | 140.5975 |  |  | TRIANG | #NAME? | 0.1 | 0.9 | 750 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 132 | Realignment of existing road geometry required | Increase in off-route junction improvements, certain junctions requiring realignment of kerbs etc | Increase in design costs. | 80 | 0 | 250 | 500 | 2006-07-03 | 2009-01-26 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 199.9409 | 268.5642 | 1A | 0 | Geographic | 0 | 268.5642 | 14.9202 | 268.5642 | 7487.1141 | 15.48% | 14.9202 | 14.9202 | 14.9202 | 14.9202 | 14.9202 | 14.9202 | 14.9202 | 14.9202 | 14.9202 | 14.9202 | 14.9202 | 14.9202 | 14.9202 | 14.9202 | 14.9202 | 14.9202 | 14.9202 | 14.9202 | 14.9202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283.4845 |  |  | TRIANG | #NAME? | 0.8 | 0.2 | 250 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 134 | Network Rail possessions over and above that estimate are required | Compensation paid to Train Operating Companies | Increased compensation paid to Train Operating Companies | 5 | 500 | 2000 | 4000 | 2007-10-01 | 2010-12-31 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 42 | 107.3361 | 144.1758 | 1A | 0.73 | Track Estimate | 105.2483 | 38.9275 | 3.4328 | 144.1758 | 7631.2898 | 15.77% | 0 | 0 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 3.4328 | 0 | 144.1758 |  |  | TRIANG | #NAME? | 0.05 | 0.95 | 2000 | 0 | #NAME? | 0 | #NAME?
7.2 MUDFA/Utilities | 139 | Utilities diversion outline specification only from plans | Uncertainty of Utilities location and consequently required diversion work/ unforeseen utility services within LoD | Increase in MUDFA costs or delays as a result of carrying out more diversions than estimated | 90 | 0 |  | 4000 | 2007-04-02 | 2008-05-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1802.6185 | 2421.3093 | 1A + 1B | 0.87 | No of Trams | 2106.5391 | 314.7702 | 242.1309 | 2421.3093 | 10052.5991 | 20.78% | 242.1309 | 242.1309 | 242.1309 | 242.1309 | 242.1309 | 242.1309 | 242.1309 | 242.1309 | 242.1309 | 242.1309 | 242.1309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2663.4403 |  |  | UNIFORM | #NAME? | 0.9 | 0.1 | 0 | 0 | #NAME? | 0 | #NAME?
7.4 Tramco | 142 | Base estimate allows only for minimum on-board supervisory and comms equipment. | Specification for on-board and supervisory equipment has not been established for Trams on Phase 1A. | A high specification is required for on-board supervisory and comms equipment. | 50 | 0 | 75 | 675 | 2007-07-19 | 2009-10-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 124.153 | 166.7645 | 1A | 1 | Geographic | 166.7645 | 0 | 6.1765 | 166.7645 | 10219.3636 | 21.12% | 6.1765 | 6.1765 | 6.1765 | 6.1765 | 6.1765 | 6.1765 | 6.1765 | 6.1765 | 6.1765 | 6.1765 | 6.1765 | 6.1765 | 6.1765 | 6.1765 | 6.1765 | 6.1765 | 6.1765 | 6.1765 | 6.1765 | 6.1765 | 6.1765 | 6.1765 | 6.1765 | 6.1765 | 6.1765 | 6.1765 | 6.1765 | 6.1765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172.941 |  |  | TRIANG | #NAME? | 0.5 | 0.5 | 75 | 0 | #NAME? | 0 | #NAME?
7.4 Tramco | 143 | Base estimate allows only for minimum on-board supervisory and comms equipment. | Specification for on-board and supervisory equipment has not been established for Trams on Phase 1B. | A high specification is required for on-board supervisory and comms equipment. | 50 | 0 | 25 | 100 | 2007-07-19 | 2009-10-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 20.7293 | 27.844 | 1B | 0.68 | CEC Owned Land Value | 18.9339 | 8.9101 | 1.0313 | 27.844 | 10247.2076 | 21.18% | 1.0313 | 1.0313 | 1.0313 | 1.0313 | 1.0313 | 1.0313 | 1.0313 | 1.0313 | 1.0313 | 1.0313 | 1.0313 | 1.0313 | 1.0313 | 1.0313 | 1.0313 | 1.0313 | 1.0313 | 1.0313 | 1.0313 | 1.0313 | 1.0313 | 1.0313 | 1.0313 | 1.0313 | 1.0313 | 1.0313 | 1.0313 | 1.0313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.8753 |  |  | TRIANG | #NAME? | 0.5 | 0.5 | 25 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 150 | Blackspots for radio/mobile communications | Geographic areas where radio/mobile communications cannot obtain signal | Additional remedial equipment required e.g. repeater masts, booster packs etc | 50 | 0 |  | 10 | 2009-09-30 | 2010-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 16 | 2.4982 | 3.3557 | 1A | 0.95 | Utilities Estimate | 3.1879 | 0.16778 | 0.20973 | 3.3557 | 10250.5633 | 21.19% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.20973 | 0.20973 | 0.20973 | 0.20973 | 0.20973 | 0.20973 | 0.20973 | 0.20973 | 0.20973 | 0.20973 | 0.20973 | 0.20973 | 0.20973 | 0.20973 | 0.20973 | 0.20973 | 0 | 3.3557 |  |  | UNIFORM | #NAME? | 0.5 | 0.5 | 0 | 0 | #NAME? | 0 | #NAME?
7.4 Tramco | 155 | Increase in specification over and above assumptions in base estimate regarding equipment and quality specification for tram vehicles | Business case runtime and CEC requirements (change in equipment and quality specification) | Increased cost of tramsets | 20 | 160 | 270 | 600 | 2007-07-19 | 2009-10-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 69.1174 | 92.8397 | 1B | 0.81 | Highways Element of Infraco Estimate | 75.2002 | 17.6395 | 3.4385 | 92.8397 | 10343.403 | 21.38% | 3.4385 | 3.4385 | 3.4385 | 3.4385 | 3.4385 | 3.4385 | 3.4385 | 3.4385 | 3.4385 | 3.4385 | 3.4385 | 3.4385 | 3.4385 | 3.4385 | 3.4385 | 3.4385 | 3.4385 | 3.4385 | 3.4385 | 3.4385 | 3.4385 | 3.4385 | 3.4385 | 3.4385 | 3.4385 | 3.4385 | 3.4385 | 3.4385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96.2782 |  |  | TRIANG | #NAME? | 0.2 | 0.8 | 270 | 0 | #NAME? | 0 | #NAME?
3 DESIGN | 162 | Land is not acquired yet | Gaining access to land prior to purchase for advanced works | Increased management costs and delays to design | 10 | 0 |  | 30 | 2007-04-02 | 2007-09-28 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.572 | 2.1115 | 1A + 1B | 1 | Business Claims Compensation Estimate | 2.1115 | 0 | 2.1115 | 2.1115 | 10345.5145 | 21.39% | 2.1115 | 2.1115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.223 |  |  | UNIFORM | #NAME? | 0.1 | 0.9 | 0 | 0 | #NAME? | 0 | #NAME?
7.2 MUDFA/Utilities | 164 | Utilities assets uncovered during construction that were not previously accounted for; unidentified abandoned utilities assets; asbestos found in excavation for utilities diversion; unknown cellars and basements intrude into works area; other physical obs | Unknown or abandoned assets or unforeseen/contaminated ground conditions affect scope of MUDFA work. | Re-design and delay as investigation takes place and solution implemented; Increase in Capex cost as a result of additional works. | 95 | 2000 | 5000 | 8500 | 2007-04-02 | 2008-09-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 4902.9626 | 6585.7468 | 1A + 1B | 1 | Geographic | 6585.7468 | 0 | 470.4105 | 6585.7468 | 16931.2613 | 35% | 470.4105 | 470.4105 | 470.4105 | 470.4105 | 470.4105 | 470.4105 | 470.4105 | 470.4105 | 470.4105 | 470.4105 | 470.4105 | 470.4105 | 470.4105 | 470.4105 | 470.4105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7056.1573 |  |  | TRIANG | #NAME? | 0.95 | 0.05 | 5000 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 167 | Long/ inaccurate lead times on various materials especially steel and copper. | Contractor specialist materials procurement problems | Programme delay and assumed output not possible | 50 | 0 |  | 200 | 2007-10-01 | 2009-11-23 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 49.9803 | 67.1344 | 1A + 1B | 0.9 | PM Cost Estimate | 60.421 | 6.7134 | 2.3977 | 67.1344 | 16998.3957 | 35.14% | 0 | 0 | 2.3977 | 2.3977 | 2.3977 | 2.3977 | 2.3977 | 2.3977 | 2.3977 | 2.3977 | 2.3977 | 2.3977 | 2.3977 | 2.3977 | 2.3977 | 2.3977 | 2.3977 | 2.3977 | 2.3977 | 2.3977 | 2.3977 | 2.3977 | 2.3977 | 2.3977 | 2.3977 | 2.3977 | 2.3977 | 2.3977 | 2.3977 | 2.3977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67.1344 |  |  | UNIFORM | #NAME? | 0.5 | 0.5 | 0 | 0 | #NAME? | 0 | #NAME?
1 GENERAL/OVERALL | 169 | Concurrent major projects in Edinburgh | Other major projects in Edinburgh interface with Tram | Delay in sequence in certain areas, Additional interface project management costs. | 50 | 0 |  | 100 | 2007-03-01 | 2010-12-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 43 | 24.9475 | 33.5099 | 1A + 1B | 1 | Geographic | 33.5099 | 0 | 0.7793 | 33.5099 | 17031.9056 | 35.21% | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0.7793 | 0 | 34.2892 |  |  | UNIFORM | #NAME? | 0.5 | 0.5 | 0 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 172 | Area of possible contamination and unstable ground (unlicensed tip) has been highlighted during desk study immediately to east of Gogar Burn - investigation for CERT project indicates that this consists of building rubble and domestic waste. | Tramway runs through area of possible contamination and special foundation is required to cope with unstable ground | Increase in costs to provide special foundation solution | 90 | 1000 | 1500 | 2000 | 2008-01-01 | 2010-09-30 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 36 | 1350.6289 | 1814.1889 | 1A | 0.87 | No of Trams | 1578.3443 | 235.8446 | 50.3941 | 1814.1889 | 18846.0945 | 38.96% | 0 | 0 | 0 | 0 | 0 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 50.3941 | 0 | 0 | 0 | 0 | 1814.1889 |  |  | TRIANG | #NAME? | 0.9 | 0.1 | 1500 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 173 | Area of possible contamination (unlicensed tip) has been highlighted during desk study immediately to west of Gogar Burn - investigation for CERT project indicates that this consists of building rubble and domestic waste. However, there is a risk that so | Tramway runs through area of possible contamination and material requires to be removed and replaced (dig and dump). | Increase in costs to remove material to special and other tip. | 2.5 | 1368 |  | 8208 | 2006-09-29 | 2007-09-28 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 124.3056 | 166.9695 | 1A | 1 | Geographic | 166.9695 | 0 | 166.9695 | 166.9695 | 19013.064 | 39.3% | 166.9695 | 166.9695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333.939 |  |  | UNIFORM | #NAME? | 0.025 | 0.975 | 0 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 177 | Unforeseen external events impact on Construction | InfraCo seeks compensation as a result of external events having an impact on Construction | Legal costs and compensation costs for events not agreed in contract | 30 | 0 | 25 | 50 | 2008-01-01 | 2011-12-31 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 40 | 7.497 | 10.0702 | 1A | 1 | Costs applicable whether or not 1B is done | 10.0702 | 10.0702 | 0.25175 | 10.0702 | 19023.1342 | 39.32% | 0 | 0 | 0 | 0 | 0 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 0.25175 | 10.0702 |  |  | TRIANG | #NAME? | 0.3 | 0.7 | 25 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 178 | Procurement Strategy novates SDS to InfraCo after Detailed Design; Limited input on buidability from Infraco. | Infraco due diligence process reveals that design rework will be required after novation of SDS. | Bids will be higher than envisaged in base estimate as Infraco will price for re-work. | 75 |  | 500 |  | 2006-10-02 | 2007-12-31 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 375 | 503.7067 | 1A + 1B | 1 | Geographic | 503.7067 | 0 | 125.9267 | 503.7067 | 19526.8409 | 40.36% | 125.9267 | 125.9267 | 125.9267 | 125.9267 | 125.9267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629.6334 |  |  | DISCRETE | #NAME? | 0.75 | 0.25 | 500 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 179 | Construction impacts cause distress to surrounding buildings. | Construction causes structural damage to 3rd party property resulting in a claim | Costs of repair or claim; unaccounted for legal costs. | 10 | 0 | 500 | 1000 | 2007-10-01 | 2010-12-31 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 42 | 49.9367 | 67.0759 | 1A + 1B | 0.95 | Utilities Estimate | 63.7221 | 3.3538 | 1.597 | 67.0759 | 19593.9168 | 40.5% | 0 | 0 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 1.597 | 0 | 67.0759 |  |  | TRIANG | #NAME? | 0.1 | 0.9 | 500 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 182 | Unusually adverse weather conditions | Delay in Infraco construction programme as a result of exceptional weather conditions | Contractor claims for delay in construction programme | 50 | 500 |  | 1000 | 2007-10-01 | 2010-12-31 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 42 | 374.8627 | 503.5223 | 1A + 1B | 1 | Geographic | 503.5223 | 0 | 11.9886 | 503.5223 | 20097.4391 | 41.54% | 0 | 0 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 11.9886 | 0 | 503.5223 |  |  | UNIFORM | #NAME? | 0.5 | 0.5 | 0 | 0 | #NAME? | 0 | #NAME?
7.2 MUDFA/Utilities | 183 | Unusually adverse weather conditions | Delay in Utilities Diversion programme as a result of exceptional weather conditions | Contractor claims for delay in construction programme | 15 | 100 |  | 500 | 2007-04-02 | 2008-09-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 44.9449 | 60.3707 | 1A + 1B | 0.78 | Infraco Estimate | 47.0892 | 13.2816 | 4.3122 | 60.3707 | 20157.8098 | 41.67% | 4.3122 | 4.3122 | 4.3122 | 4.3122 | 4.3122 | 4.3122 | 4.3122 | 4.3122 | 4.3122 | 4.3122 | 4.3122 | 4.3122 | 4.3122 | 4.3122 | 4.3122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64.6829 |  |  | UNIFORM | #NAME? | 0.15 | 0.85 | 0 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 192 | OLE pole location requirements | OLE pole location requirments result in special foundation requirements | Foundation requirements cause increase in construction costs | 10 | 0 |  | 250 | 2007-10-01 | 2010-09-30 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 39 | 12.5655 | 16.8781 | 1A + 1B | 1 | Geographic | 16.8781 | 0 | 0.43277 | 16.8781 | 20174.688 | 41.7% | 0 | 0 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0.43277 | 0 | 0 | 0 | 0 | 16.8781 |  |  | UNIFORM | #NAME? | 0.1 | 0.9 | 0 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 303 | Proximity in time and space to other works within Edinburgh | Third party works in Edinburgh impact on Tram infrastructure construction | CEC may limit the number of workfronts allowed; programme re-sequencing; slower overall construction rate; effective increase in preliminaries; overall programme delay | 40 | 100 |  | 500 | 2007-09-30 | 2010-12-31 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 42 | 119.5512 | 160.5833 | 1A + 1B | 1 | Geographic | 160.5833 | 0 | 3.8234 | 160.5833 | 20335.2713 | 42.04% | 0 | 0 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 3.8234 | 0 | 160.5833 |  |  | UNIFORM | #NAME? | 0.4 | 0.6 | 0 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 304 | Infrastructure design development e.g. building fixing approvals not achieved as designed | Utilities (diverted by MUDFA or left in place) are found to be in the path of infrastructure works at time of construction | Additional utilities diversions are required to be undertaken by Infraco with additional cost and programme impacts | 20 | 0 |  | 25 | 2007-10-01 | 2010-12-31 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 42 | 2.4777 | 3.328 | 1A + 1B | 1 | CEC Approvals | 3.328 | 0 | 0.079239 | 3.328 | 20338.5993 | 42.04% | 0 | 0 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0.079239 | 0 | 3.328 |  |  | UNIFORM | #NAME? | 0.2 | 0.8 | 0 | 0 | #NAME? | 0 | #NAME?
7.2 MUDFA/Utilities | 313 | BT requirement for 10 year warranty is unusual | BT 10 year warranty on jointing chambers and ducts is not provided | Warranty requirements not met, additional costs to provide required quality, possible additional costs to repair during warranty period | 5 | 0 |  | 150 | 2008-09-30 | 2018-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 30 | 3.7441 | 5.0291 | 1A + 1B | 1 | Geographic | 5.0291 | 0 | 0.16764 | 5.0291 | 20343.6285 | 42.05% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 0.16764 | 5.0291 |  |  | UNIFORM | #NAME? | 0.05 | 0.95 | 0 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 318 | Failure to make arrangements with Utilities for the phasing of necessary connections; Utility Company operational constraints | Utility connections cannot proceed as planned | Potential delay to start of Infraco works in certain sections | 50 | 100 |  | 500 | 2007-04-04 | 2008-10-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 149.561 | 200.893 | 1A + 1B | 0.78 | Infraco Estimate | 156.6966 | 44.1965 | 13.3929 | 200.893 | 20544.5215 | 42.47% | 13.3929 | 13.3929 | 13.3929 | 13.3929 | 13.3929 | 13.3929 | 13.3929 | 13.3929 | 13.3929 | 13.3929 | 13.3929 | 13.3929 | 13.3929 | 13.3929 | 13.3929 | 13.3929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214.2859 |  |  | UNIFORM | #NAME? | 0.5 | 0.5 | 0 | 0 | #NAME? | 0 | #NAME?
7.4 Tramco | 319 | Trams are not compatiable and interoperable with each other and other parts of the system | Trams found to be incompatible during commisisoning | Delay to commissioning, costs to deal with issue | 10 | 0 |  | 50 | 2009-10-01 | 2010-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 16 | 2.498 | 3.3554 | 1A + 1B | 1 | Geographic | 3.3554 | 0 | 0.20971 | 3.3554 | 20547.8769 | 42.48% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.20971 | 0.20971 | 0.20971 | 0.20971 | 0.20971 | 0.20971 | 0.20971 | 0.20971 | 0.20971 | 0.20971 | 0.20971 | 0.20971 | 0.20971 | 0.20971 | 0.20971 | 0.20971 | 0 | 3.3554 |  |  | UNIFORM | #NAME? | 0.1 | 0.9 | 0 | 0 | #NAME? | 0 | #NAME?
2 PROCUREMENT CONSULTANT | 337 | Unsuccessful tenderer challenges procurement process (Tramco or Infraco) | OJEU procurement process is challenged | Possible retender; Delays; Legals costs to deal with challenge | 20 | 0 |  | 100 | 2007-01-12 | 2008-04-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 10.3014 | 13.8371 | 1A + 1B | 1 | Geographic | 13.8371 | 0 | 1.5375 | 13.8371 | 20561.7139 | 42.5% | 1.5375 | 1.5375 | 1.5375 | 1.5375 | 1.5375 | 1.5375 | 1.5375 | 1.5375 | 1.5375 | 1.5375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.3745 |  |  | UNIFORM | #NAME? | 0.2 | 0.8 | 0 | 0 | #NAME? | 0 | #NAME?
7.2 MUDFA/Utilities | 342 | Tram alignment at A8 crossing at Gogar co-incides BT data nests/cable (main coms link between Glasgow and Edinburgh) | A8 crossing tunnel requires special design or BT data nest/cables require to be moved | Capex cost to cover BT data nest/cable move; additional design costs; delay while works to undertake move are carried out; additional tunnelling costs. | 50 | 1000 |  | 1500 | 2007-04-04 | 2008-09-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 624.9807 | 839.4853 | 1A | 0.85 | Land and Property Estimate | 713.5625 | 125.9228 | 59.9632 | 839.4853 | 21401.1992 | 44.24% | 59.9632 | 59.9632 | 59.9632 | 59.9632 | 59.9632 | 59.9632 | 59.9632 | 59.9632 | 59.9632 | 59.9632 | 59.9632 | 59.9632 | 59.9632 | 59.9632 | 59.9632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 899.4485 |  |  | UNIFORM | #NAME? | 0.5 | 0.5 | 0 | 0 | #NAME? | 0 | #NAME?
1.7 Miscellaneous | 343 | General delay to programme with various causes e.g. failure to obtain approvals on time; parliamentary processes, delays due to lack of prioritisation of BAA agreement with new owners | Delay to completion of project | Inflation at 5% causes increased out-turn cost due to delay plus revenue loss | 20 | 5900 | 15200 | 22600 | 2010-12-31 | 2011-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2920.9005 | 3923.4056 | 1A + 1B | 0.85 | Land and Property Estimate | 3334.8948 | 588.5108 | 3923.4056 | 3923.4056 | 25324.6048 | 52.35% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3923.4056 | 3923.4056 |  |  | TRIANG | #NAME? | 0.2 | 0.8 | 15200 | 0 | #NAME? | 0 | #NAME?
7.4 Tramco | 351 | Depot not completed on time | Trams are manufacturered but Depot unavailable to take delivery | Trams need to be stored resulting in storage costs | 50 | 100 | 300 | 600 | 2007-03-01 | 2007-07-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167.0673 | 224.4077 | 1A + 1B | 1 | Geographic | 224.4077 | 0 | 0 | 0 | 25549.0125 | 52.81% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | TRIANG | #NAME? | 0.5 | 0.5 | 300 | 0 | #NAME? | 0 | #NAME?
1.1 Land & Property | 352 | Increase in land values | Higher land compensation claims than anticipated | Additional uplift on compensation claims | 70 | 0 |  | 5750 | 2007-03-05 | 2010-12-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 43 | 2032.6719 | 2730.3211 | 1A + 1B | 1 | Geographic | 2730.3211 | 0 | 63.4958 | 2730.3211 | 28279.3336 | 58.46% | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 63.4958 | 0 | 2793.8169 |  |  | UNIFORM | #NAME? | 0.7 | 0.3 | 0 | 0 | #NAME? | 0 | #NAME?
1.1 Land & Property | 354 | Land and property values experience a net reduction in value as a result of the introduction of the Tram | Part 1 Claims for land and property - (Noise and Vibration) | Possible successful claims resulting in increased costs to project with impact after construction | 50 | 0 |  | 3300 | 2011-12-30 | 2015-12-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 823.6864 | 1106.3902 | 1A + 1B | 1 | Geographic | 1106.3902 | 0 | 1106.3902 | 1106.3902 | 29385.7239 | 60.74% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1106.3902 | 1106.3902 |  |  | UNIFORM | #NAME? | 0.5 | 0.5 | 0 | 0 | #NAME? | 0 | #NAME?
1.1 Land & Property | 357 | Landowner disagrees with District Valuer s Assessment of land value and submits a Certificate of Appropriate Alternative Development - Plot 322 | Submission of CAAD Claim for Plot 322 | Increase in land value for plot | 10 |  | 375 |  | 2006-04-03 | 2015-12-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 44 | 37.5 | 50.3707 | 1A | 0.87 | No of Trams | 43.8225 | 6.5482 | 1.1448 | 50.3707 | 29436.0945 | 60.85% | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 51.5155 |  |  | DISCRETE | #NAME? | 0.1 | 0.9 | 375 | 0 | #NAME? | 0 | #NAME?
1.1 Land & Property | 358 | Landowner disagrees with District Valuer s Assessment of land value and submits a Certificate of Appropriate Alternative Development - Plot 327 | Submission of CAAD Claim for plot 327 | Increase in land value for plot | 10 |  | 375 |  | 2006-04-03 | 2015-12-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 44 | 37.5 | 50.3707 | 1A | 1 | Costs applicable whether or not 1B is done | 50.3707 | 50.3707 | 1.1448 | 50.3707 | 29486.4652 | 60.95% | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 1.1448 | 51.5155 |  |  | DISCRETE | #NAME? | 0.1 | 0.9 | 375 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 205 | Network Rail issue new Group and Company Standards during construction. Design and construction is aligned to current Network Rail Group and Company Standards. | Network Rail emerging Group and Company Standards are different at time of construction | New standards require to be adopted resulting in re-design, delay and increased construction cost. | 20 | 0 |  | 150 | 2007-10-01 | 2010-08-31 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 38 | 15.5456 | 20.8811 | 1A + 1B | 1 | Geographic | 20.8811 | 0 | 0.5495 | 20.8811 | 29507.3463 | 61% | 0 | 0 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0.5495 | 0 | 0 | 0 | 0 | 0 | 20.8811 |  |  | UNIFORM | #NAME? | 0.2 | 0.8 | 0 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 244 | Inadequate provision for people with disabilities | People with disabilities are unable to access Tram Service | Breach of DDA legislation, costs to rectify and negative PR | 17.5 | 0 |  | 25 | 2010-01-03 | 2010-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 12 | 2.1761 | 2.9229 | 1A + 1B | 0.87 | No of Trams | 2.543 | 0.37998 | 0.24358 | 2.9229 | 29510.2693 | 61% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24358 | 0.24358 | 0.24358 | 0.24358 | 0.24358 | 0.24358 | 0.24358 | 0.24358 | 0.24358 | 0.24358 | 0.24358 | 0.24358 | 0 | 2.9229 |  |  | UNIFORM | #NAME? | 0.175 | 0.825 | 0 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 279 |  | Third party consents including Network Rail, CEC Planning, CEC Roads Department, Historic Scotland, Building Fixing Owner consent is denied or delayed | Delay to programme; Risk transfer response by bidders is to return risk to tie; Increased out-turn cost if transferred an also as a result of any delay due to inflation. | 94.5 |  | 1250 |  | 2006-07-03 | 2007-09-24 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1181.25 | 1586.6761 | 1A + 1B | 0.87 | No of Trams | 1380.4082 | 206.2679 | 1586.6761 | 1586.6761 | 31096.9453 | 64.28% | 1586.6761 | 1586.6761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3173.3521 |  |  | DISCRETE | #NAME? | 0.945 | 0.055 | 1250 | 0 | #NAME? | 0 | #NAME?
4.3 Business Case | 294 | Traffic model identifies areas where design is not compatible with efficient transport network operations. | Final Design impacts negatively on Final Business Case | Could be negative implications on Tram final business case. Potential to negatively impact BCR | 20 | 100 |  | 500 | 2007-03-31 | 2007-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59.7969 | 80.3203 | 1A + 1B | 0.81 | Highways Element of Infraco Estimate | 65.0595 | 15.2609 | 0 | 0 | 31177.2656 | 64.45% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | UNIFORM | #NAME? | 0.2 | 0.8 | 0 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 952 | Scope of works relating to Wide Area Modelling (WAM) have not been agreed with SDS because they consider this to be out with the scope of their contract. | Uncertainty about extent of construction works required on road network relating to Wide Area Modelling issues. | Potential claim from SDS to deal with additional design work; Potential construction costs to deal with WAM issues (difficult to quantify without design) over and above those already included. | 95 | 0 |  | 2500 | 2006-07-03 | 2007-09-24 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1185.5386 | 1592.4366 | 1A + 1B | 1 | Geographic | 1592.4366 | 0 | 1592.4366 | 1592.4366 | 32769.7023 | 67.74% | 1592.4366 | 1592.4366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3184.8732 |  |  | UNIFORM | #NAME? | 0.95 | 0.05 | 0 | 0 | #NAME? | 0 | #NAME?
5 PALIAMENTARY PROCESS/ APPROVALS | 271 | Inadequate quality of submission of approval. Partial submission of package. Programme compression. Lack of CEC resources. | Failure to process prior approvals applications within 8 weeks | Delay and disruption to Infraco programme | 80 | 750 | 750 | 1000 | 2006-01-03 | 2008-08-29 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 666.8827 | 895.7687 | 1A + 1B | 0.87 | No of Trams | 779.3188 | 116.4499 | 68.9053 | 895.7687 | 33665.471 | 69.59% | 68.9053 | 68.9053 | 68.9053 | 68.9053 | 68.9053 | 68.9053 | 68.9053 | 68.9053 | 68.9053 | 68.9053 | 68.9053 | 68.9053 | 68.9053 | 68.9053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 964.674 |  |  | TRIANG | #NAME? | 0.8 | 0.2 | 750 | 0 | #NAME? | 0 | #NAME?
4.0 Detailed Design | 861 | Lack of capacity in existing surface water outfalls | Drainage proposals cannot be provided cost efficiently | New surface water drainage required outwith existing land or potential to prevent project from going ahead | 2.5 |  | 5 |  | 2007-01-01 | 2007-09-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.125 | 0.1679 | 1A | 1 | Depot | 0.1679 | 0 | 0 | 0 | 33665.6389 | 69.59% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DISCRETE | #NAME? | 0.025 | 0.975 | 5 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 865 | Buildings contain asbestos that was not uncovered during surveys | Asbestos found during demolition works and excavations for construction | Cost and delay during investigation and removal | 90 | 60 |  | 150 | 2008-01-01 | 2009-03-31 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 94.5213 | 126.9626 | 1A | 1 | Costs applicable whether or not 1B is done | 126.9626 | 126.9626 | 7.4684 | 126.9626 | 33792.6015 | 69.85% | 0 | 0 | 0 | 0 | 0 | 7.4684 | 7.4684 | 7.4684 | 7.4684 | 7.4684 | 7.4684 | 7.4684 | 7.4684 | 7.4684 | 7.4684 | 7.4684 | 7.4684 | 7.4684 | 7.4684 | 7.4684 | 7.4684 | 7.4684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126.9626 |  |  | UNIFORM | #NAME? | 0.9 | 0.1 | 0 | 0 | #NAME? | 0 | #NAME?
7.1.1 Invasive Species | 869 | Surveying team unable to obtain access to Network Rail, BAA and other privately owned land because they were not cleared to access this land (including PTS). | Extent of Invasive Species Area Exceeds Estimate from Survey | Underestimating the extent of works; leads to an increase in cost | 17.5 |  | 20 |  | 2007-04-17 | 2009-04-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 3.5 | 4.7013 | 1A | 1 | Costs applicable whether or not 1B is done | 4.7013 | 4.7013 | 0.22387 | 4.7013 | 33797.3028 | 69.86% | 0.22387 | 0.22387 | 0.22387 | 0.22387 | 0.22387 | 0.22387 | 0.22387 | 0.22387 | 0.22387 | 0.22387 | 0.22387 | 0.22387 | 0.22387 | 0.22387 | 0.22387 | 0.22387 | 0.22387 | 0.22387 | 0.22387 | 0.22387 | 0.22387 | 0.22387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9251 |  |  | DISCRETE | #NAME? | 0.175 | 0.825 | 20 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 870 | SDS Designs are late and do not provide detail Infraco requires | Infraco does not have detail to achieve contract close | Delay to due diligence and start on site and need to appoint aditional design consultants | 94.5 |  | 3000 |  | 2007-01-31 | 2007-04-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2835 | 3808.0225 | 1A + 1B | 0.78 | Infraco Estimate | 2970.2576 | 837.765 | 0 | 0 | 37605.3253 | 77.74% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DISCRETE | #NAME? | 0.945 | 0.055 | 3000 | 0 | #NAME? | 0 | #NAME?
7.1.3 Depot | 876 | Agreement with SEPA fo use Gravity Drain Proposal | Gravity Drain Proposal | Cost & time saving | 79.5 |  | 12.5 |  | 2008-03-19 | 2008-07-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9.9375 | 13.3482 | 1A | 1 | Geographic | 13.3482 | 0 | 3.3371 | 13.3482 | 37618.6736 | 77.76% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3371 | 3.3371 | 3.3371 | 3.3371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.3482 |  |  | DISCRETE | #NAME? | 0.795 | 0.205 | 12.5 | 0 | #NAME? | 0 | #NAME?
7.1.2 Badger Relocation | 883 | Ineffective/Inappropriate Proposals; new setts must be built before old ones can be closed and licenses will not be issued until nearer time of closure; animals must have settled in new home before closure of old one can take place | Gogarburn Badger/Otter Proposals for closure of old setts not approved by SNH/SEERAD | Delay in accessing land to construct Tram works and hence in Programme | 17.5 | 0 |  | 25 | 2007-10-01 | 2007-11-30 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2.2029 | 2.959 | 1A | 1 | Geographic | 2.959 | 0 | 1.4795 | 2.959 | 37621.6325 | 77.77% | 0 | 0 | 1.4795 | 1.4795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.959 |  |  | UNIFORM | #NAME? | 0.175 | 0.825 | 0 | 0 | #NAME? | 0 | #NAME?
2.2 Transdev | 887 | Transdev do not resource up sufficiently in Edinburgh or key rsources are lost | Resource to operate Tram is insufficent with DPOFA obligations not achieved in time or to sufficient quality | Delay to tram service commencement. Delay costs for Infraco as Testing and Commissioning cannot commence. Overall project management costs as a result of delays. | 1 | 3000 |  | 6000 | 2009-06-01 | 2010-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 20 | 44.6482 | 59.9723 | 1A + 1B | 1 | Geographic | 59.9723 | 0 | 2.9986 | 59.9723 | 37681.6048 | 77.89% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9986 | 2.9986 | 2.9986 | 2.9986 | 2.9986 | 2.9986 | 2.9986 | 2.9986 | 2.9986 | 2.9986 | 2.9986 | 2.9986 | 2.9986 | 2.9986 | 2.9986 | 2.9986 | 2.9986 | 2.9986 | 2.9986 | 2.9986 | 0 | 59.9723 |  |  | UNIFORM | #NAME? | 0.01 | 0.99 | 0 | 0 | #NAME? | 0 | #NAME?
2.2 Transdev | 888 | Design, construction and/or testing does not meet Transdev requirements or gain approval from the ROGS Competent Person | Transdev refuse to operate system on safety ground or apply overly restrictive procedures that are not directly the responsibility of Infraco | Delay to comencement of service, additional cost both for delay and rectification of the issue | 5 | 3000 |  | 6000 | 2009-06-30 | 2010-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 19 | 224.0802 | 300.9885 | 1A + 1B | 0.78 | Infraco Estimate | 234.771 | 66.2175 | 15.8415 | 300.9885 | 37982.5934 | 78.52% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.8415 | 15.8415 | 15.8415 | 15.8415 | 15.8415 | 15.8415 | 15.8415 | 15.8415 | 15.8415 | 15.8415 | 15.8415 | 15.8415 | 15.8415 | 15.8415 | 15.8415 | 15.8415 | 15.8415 | 15.8415 | 15.8415 | 0 | 300.9885 |  |  | UNIFORM | #NAME? | 0.05 | 0.95 | 0 | 0 | #NAME? | 0 | #NAME?
2.9 TEL | 889 | Unsuccessful negotiation. TEL believes costs inflated too much. | Target operating costs for Phase D are not agreed. | TEL Business Case becomes undeliverable. Potential to undertake Dispute Resolution to gain agreement. | 5 |  | 300 |  | 2010-01-04 | 2019-01-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 15 | 20.1483 | 1A + 1B | 1 | Phase D is on 1B | 20.1483 | 0 | 1.5499 | 20.1483 | 38002.7416 | 78.56% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5499 | 1.5499 | 1.5499 | 1.5499 | 1.5499 | 1.5499 | 1.5499 | 1.5499 | 1.5499 | 1.5499 | 1.5499 | 1.5499 | 1.5499 | 20.1483 |  |  | DISCRETE | #NAME? | 0.05 | 0.95 | 300 | 0 | #NAME? | 0 | #NAME?
2.2 Transdev | 890 | DPOFA amendment is not fully negotiated | Key performance indicators for DPOFA are not agreed | In absence of KPIs, would have to refer to Dispute Resolution to resolve issues. | 2.5 |  | 300 |  | 2007-01-23 | 2007-10-31 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7.5 | 10.0741 | 1A + 1B | 0.74 | Track Estimate | 7.4549 | 2.6193 | 5.0371 | 10.0741 | 38012.8158 | 78.58% | 5.0371 | 5.0371 | 5.0371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.1112 |  |  | DISCRETE | #NAME? | 0.025 | 0.975 | 300 | 0 | #NAME? | 0 | #NAME?
2.9 TEL | 893 | VE process concentrates on reducing Capex to the detriment of Opex | VE Process makes TEL Business Case undeliverable | TEL Business Case becomes undeliverable | 20 |  | 300 |  | 2010-10-31 | 2015-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 60 | 80.5931 | 1A + 1B | 1 |  | 80.5931 | 0 | 26.8644 | 80.5931 | 38093.4088 | 78.74% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.8644 | 26.8644 | 26.8644 | 80.5931 |  |  | DISCRETE | #NAME? | 0.2 | 0.8 | 300 | 0 | #NAME? | 0 | #NAME?
7.1.2 Badger Relocation | 894 | Ineffective/Inappropriate Proposals; new setts must be built before old ones can be closed and licenses will not be issued until nearer time of closure; animals must have settled in new home before closure of old one can take place | Roseburn Badger Proposals for closure of old setts not approved by SNH | Delay in accessing land to construct Tram works and hence in Programme | 17.5 | 0 |  | 25 | 2008-10-01 | 2008-11-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2.1567 | 2.8969 | 1B | 0 | Geographic | 0 | 2.8969 | 1.4484 | 2.8969 | 38096.3057 | 78.75% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4484 | 1.4484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8969 |  |  | UNIFORM | #NAME? | 0.175 | 0.825 | 0 | 0 | #NAME? | 0 | #NAME?
7.4 Tramco | 899 | Stakeholder indecision/unclarified role | Inability to determine and sign off aeshetic requirements for Tram | Programme delay in finalising design; potential cost impacts | 20 | 0 | 250 | 500 | 2007-07-19 | 2008-07-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 50.3695 | 67.6573 | 1A | 1 | Costs applicable whether or not 1B is done | 67.6573 | 67.6573 | 5.6381 | 67.6573 | 38163.963 | 78.89% | 5.6381 | 5.6381 | 5.6381 | 5.6381 | 5.6381 | 5.6381 | 5.6381 | 5.6381 | 5.6381 | 5.6381 | 5.6381 | 5.6381 | 5.6381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73.2954 |  |  | TRIANG | #NAME? | 0.2 | 0.8 | 250 | 0 | #NAME? | 0 | #NAME?
7.4 Tramco | 905 | Not controlled by Project | Tramco Insolvency without bale-out or acquisition | Trams are not delivered;legal costs;delay | 1 |  | 25000 |  | 2007-03-01 | 2009-10-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 250 | 335.8045 | 1A + 1B | 0.85 | Land and Property Estimate | 285.4338 | 50.3707 | 12.4372 | 335.8045 | 38499.7674 | 79.58% | 12.4372 | 12.4372 | 12.4372 | 12.4372 | 12.4372 | 12.4372 | 12.4372 | 12.4372 | 12.4372 | 12.4372 | 12.4372 | 12.4372 | 12.4372 | 12.4372 | 12.4372 | 12.4372 | 12.4372 | 12.4372 | 12.4372 | 12.4372 | 12.4372 | 12.4372 | 12.4372 | 12.4372 | 12.4372 | 12.4372 | 12.4372 | 12.4372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348.2417 |  |  | DISCRETE | #NAME? | 0.01 | 0.99 | 25000 | 0 | #NAME? | 0 | #NAME?
7.2 MUDFA/Utilities | 911 | Scottish Power own and maintain a cable tunnel in the vicinity of Leith Walk that may or may not interfere with Tram construction and operation; exact location and depth of tunnel is unknown; condition of tunnel is unknown. | Presence of Scottish Power tunnel in Leith Walk requires radical solution | Tunnel may have to be decommissioned and re-laid in a more suitable location; tram alignment may require to be adjusted; special foundation soluiton e.g. cantilever may be required; increased capex; potential for tunnel collapse during operation and conse | 80 | 400 | 500 | 600 | 2007-04-02 | 2008-10-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 400.1173 | 537.4447 | 1A | 1 | Costs applicable whether or not 1B is done | 537.4447 | 537.4447 | 35.8296 | 537.4447 | 39037.2121 | 80.7% | 35.8296 | 35.8296 | 35.8296 | 35.8296 | 35.8296 | 35.8296 | 35.8296 | 35.8296 | 35.8296 | 35.8296 | 35.8296 | 35.8296 | 35.8296 | 35.8296 | 35.8296 | 35.8296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573.2744 |  |  | TRIANG | #NAME? | 0.8 | 0.2 | 500 | 0 | #NAME? | 0 | #NAME?
7.3 Infraco | 931 | Utilities assets uncovered during construction that were not previously accounted for; unidentified abandoned utilities assets; known redudant utilities; unknown live utilities; unknown redundant utilities. | Unknown or abandoned assets impacts scope of Infraco work | Re-design and delay as investigation takes place and solution implemented; Increase in Capex cost as a result of additional works. | 50 | 500 |  | 1000 | 2007-10-01 | 2010-12-31 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 42 | 374.9774 | 503.6764 | 1A + 1B | 1 | Costs applicable whether or not 1B is done | 503.6764 | 503.6764 | 11.9923 | 503.6764 | 39540.8885 | 81.74% | 0 | 0 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 11.9923 | 0 | 503.6764 |  |  | UNIFORM | #NAME? | 0.5 | 0.5 | 0 | 0 | #NAME? | 0 | #NAME?
1.3.1 NR Immunisation Project | 932 | Information handed over in draft format as part of continual design development; Downstream Tram design change that impacts on requirements; Zone of interference not defined adequately. | SDS gives wrong or insufficient infromation to Network Rail | Network Rail design their works inappropriately for final Tram requirements; Network Rail are unable to complete their design in time to meet programme; Cost to change design; Delay during redesign; Final works are not suitable and consequently Tram canno | 5 | 100 |  | 500 | 2007-04-02 | 2009-10-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 15.0129 | 20.1656 | 1A | 1 | Geographic | 20.1656 | 0 | 0.7202 | 20.1656 | 39561.054 | 81.78% | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0.7202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.8858 |  |  | UNIFORM | #NAME? | 0.05 | 0.95 | 0 | 0 | #NAME? | 0 | #NAME?
1.3.1 NR Immunisation Project | 935 | Immunisation project not prioritised by Network Rail; Network Rail resources diverted to other projects or emergencies; Multiple iterations of design development; Tram requirements change as a result of Tram design development; Network Rail standards chan | Network Rail do not deliver the immunisation works before the drop dead date of October 2009. | Tram cannot be commissioned to programme; Critical delay. | 80 | 100 |  | 500 | 2009-04-30 | 2010-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 21 | 240.1881 | 322.6249 | 1A + 1B | 0.81 | Highways Element of Infraco Estimate | 261.3262 | 61.2987 | 15.3631 | 322.6249 | 39883.6789 | 82.45% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.3631 | 15.3631 | 15.3631 | 15.3631 | 15.3631 | 15.3631 | 15.3631 | 15.3631 | 15.3631 | 15.3631 | 15.3631 | 15.3631 | 15.3631 | 15.3631 | 15.3631 | 15.3631 | 15.3631 | 15.3631 | 15.3631 | 15.3631 | 15.3631 | 0 | 322.6249 |  |  | UNIFORM | #NAME? | 0.8 | 0.2 | 0 | 0 | #NAME? | 0 | #NAME?
1.3.1 NR Immunisation Project | 936 | Information not accurately and/or timeously passed between tie and Network Rail for Immunisation Works. Communication protocol not set up or is unclear; Nature of contract between Transport Scotland and Network Rail restricts direct communication; tie/Ne | Network Rail do not deliver the immunisation works before October 2009 | Incorrect or lack of information received by Network Rail/tie; Development of poor relationships; Cumbersome resolution; Delay with works being delayed beyond October 2009; Project Management costs of dispute resolution; Increased cost of work; tie not ad | 50 | 500 |  | 1000 | 2007-04-02 | 2009-10-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 375.6017 | 504.5149 | 1A + 1B | 1 |  | 504.5149 | 0 | 18.0184 | 504.5149 | 40388.1938 | 83.49% | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 18.0184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522.5333 |  |  | UNIFORM | #NAME? | 0.5 | 0.5 | 0 | 0 | #NAME? | 0 | #NAME?
1.3.1 NR Immunisation Project | 938 | Project objectives and requirements not made clear to Network Rail | ties overall interface with Network Rail, including consents, approvals and involvement in projects prevents project success. | Drop dead date of October 2009 not achieved; Costs increase beyond budget. | 80 | 0 |  | 0 | 2007-04-02 | 2009-10-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 1A + 1B | 0.78 | Infraco Estimate | 0 | 0 | 0 | 0 | 40388.1938 | 83.49% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | UNIFORM | #NAME? | 0.8 | 0.2 | 0 | 0 | #NAME? | 0 | #NAME?
1.3.1 NR Immunisation Project | 940 | SDS not novated to Infraco; SDS requirements in relation to Immunisation Works after novation not clearly defined; tie/Infraco and Infraco/SDS contracts not aligned or integrated. | Infraco not competent to provide design requirements/challenge design of Immunisation Works | Immunisation Works requirements not adequately specified; Issues arise during Tram commissioning. | 50 | 0 |  | 0 | 2007-10-01 | 2009-03-31 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 1B | 0 | Geographic | 0 | 0 | 0 | 0 | 40388.1938 | 83.49% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | UNIFORM | #NAME? | 0.5 | 0.5 | 0 | 0 | #NAME? | 0 | #NAME?
1.3.1 NR Immunisation Project | 942 | Decision making process, relating to funding and works, not undertaken during purdah period | Network Rail do not commence works at required time | Acceleration of works required to reduce duration; Additional costs; Works not completed by drop dead date of October 2009 | 50 | 500 |  | 1000 | 2007-03-30 | 2009-10-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 374.2872 | 502.7492 | 1A | 1 | Geographic | 502.7492 | 0 | 17.9553 | 502.7492 | 40890.943 | 84.53% | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 17.9553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520.7045 |  |  | UNIFORM | #NAME? | 0.5 | 0.5 | 0 | 0 | #NAME? | 0 | #NAME?
7.1.3 Depot | 948 | Requirement for 35k cubic m Spoil by Ingliston P/Ride | Ingliston P/Ride opportunity of using spoil from Depot | Reduction in costs for disposal | 50 | 1250 | 1250 | 1250 | 2007-08-27 | 2007-09-28 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 625 | 839.5111 | 1A + 1B | 0.85 | Land and Property Estimate | 713.5845 | 125.9267 | 839.5111 | 839.5111 | 41730.4542 | 86.26% | 0 | 839.5111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 839.5111 |  |  | TRIANG | #NAME? | 0.5 | 0.5 | 1250 | 0 | #NAME? | 0 | #NAME?
7.2 MUDFA/Utilities | 955 | Combined Storm Overflow at Caroline Park impinges on works. | Caroline Park Combined Storm Overflow require new roof slab. | Increase capex due to cost of solution construction. | 60 | 50 | 75 | 100 | 2007-06-07 | 2007-12-31 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 44.9241 | 60.3428 | 1A | 1 |  | 60.3428 | 0 | 15.0857 | 60.3428 | 41790.797 | 86.39% | 15.0857 | 15.0857 | 15.0857 | 15.0857 | 15.0857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.4285 |  |  | TRIANG | #NAME? | 0.6 | 0.4 | 75 | 0 | #NAME? | 0 | #NAME?
11.1 Construction | 964 | Prevarication over scope of project | Delay to start of work thereby jeopardising funding | Funding cannot be realised from SEStran and CEC to complete project | 10 | 0 | 600 | 1200 | 2008-04-01 | 2008-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 58.9437 | 79.1742 | 1A | 0 | Geographic | 0 | 79.1742 | 26.3914 | 79.1742 | 41869.9711 | 86.55% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.3914 | 26.3914 | 26.3914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79.1742 |  |  | TRIANG | #NAME? | 0.1 | 0.9 | 600 | 0 | #NAME? | 0 | #NAME?
7.1.3 Depot | 974 | Innacurate Topo Survey results | Increase in levels of Spoil Excavation | Increased Cost & Programme extension | 25 | 100 | 300 | 500 | 2007-05-14 | 2007-08-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.8391 | 100.5251 | 1A | 1 | Geographic | 100.5251 | 0 | 0 | 0 | 41970.4963 | 86.76% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | TRIANG | #NAME? | 0.25 | 0.75 | 300 | 0 | #NAME? | 0 | #NAME?
5 PALIAMENTARY PROCESS/ APPROVALS | 977 | Absence of signed-off final design. Legal challenge. Extension of statutory consultation process. Large number of objections. TRO process is subject to a public hearing process. | Delay in achievement of permanent TROs causing delay to project | Requirement to start construction using TTROs | 70 |  | 3000 |  | 2007-06-18 | 2009-12-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 2100 | 2820.7574 | 1B | 0 | Geographic | 0 | 2820.7574 | 94.0252 | 2820.7574 | 44791.2537 | 92.59% | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 94.0252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2914.7827 |  |  | DISCRETE | #NAME? | 0.7 | 0.3 | 3000 | 0 | #NAME? | 0 | #NAME?
5 PALIAMENTARY PROCESS/ APPROVALS | 980 | Transport Minister unsympathetic to case put forward for change / SNP hostility towards project. Legal challenge of proposal. | Proposed Scottish Exec amendment of Traffic Regs for Tram core measures is unsuccessful thereby triggering public hearings | Delay to date by which TROs can be made increasing difficulty of managing the gap period between Infraco commemcement and the date of the TROs being made. Impact (yet to be assessed) on project costs. | 50 |  | 1500 |  | 2007-05-01 | 2008-07-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 750 | 1007.4134 | 1A | 1 | Geographic | 1007.4134 | 0 | 83.9511 | 1007.4134 | 45798.6671 | 94.67% | 83.9511 | 83.9511 | 83.9511 | 83.9511 | 83.9511 | 83.9511 | 83.9511 | 83.9511 | 83.9511 | 83.9511 | 83.9511 | 83.9511 | 83.9511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1091.3645 |  |  | DISCRETE | #NAME? | 0.5 | 0.5 | 1500 | 0 | #NAME? | 0 | #NAME?
7.1.3 Depot | 981 | Existing Spoil Site Unable to accept future spoil | Increase in the Lothian Valuation Joint Board rateable value of the spoil site | New Landfill site will have to be found and agreements reached. Possibility of increased costs | 80 | 0 | 25 | 50 | 2007-07-19 | 2008-03-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 19.9692 | 26.823 | 1A | 1 | Geographic | 26.823 | 0 | 3.3529 | 26.823 | 45825.4901 | 94.73% | 3.3529 | 3.3529 | 3.3529 | 3.3529 | 3.3529 | 3.3529 | 3.3529 | 3.3529 | 3.3529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.1759 |  |  | TRIANG | #NAME? | 0.8 | 0.2 | 25 | 0 | #NAME? | 0 | #NAME?
4.3 Business Case | 983 |  | All five TROs are subject to public hearings | Additional cost of up to £1m | 50 | 750 | 750 | 750 | 2007-07-02 | 2010-01-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 375 | 503.7067 | 1A + 1B | 1 | Geographic | 503.7067 | 0 | 15.7408 | 503.7067 | 46329.1968 | 95.77% | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 15.7408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 519.4475 |  |  | TRIANG | #NAME? | 0.5 | 0.5 | 750 | 0 | #NAME? | 0 | #NAME?
5 PALIAMENTARY PROCESS/ APPROVALS | 986 | Inadequate information supplied by tie. | CEC failure to sign legal agreement - legal oficer level | Delay to commencement of contract | 17.5 | 2000 | 2500 | 3000 | 2008-01-28 | 2008-01-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 438.9766 | 589.6413 | 1A + 1B | 1 | Geographic | 589.6413 | 0 | 0 | 0 | 46918.8381 | 96.99% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | TRIANG | #NAME? | 0.175 | 0.825 | 2500 | 0 | #NAME? | 0 | #NAME?
Ingliston Park and Ride | 988 | CEC want existing EARL side agreemenent amended to allow for future carpark and land | CEC do not approve award of P&R contract | Existing funding which must be spent before 31/03/08 could be lost due to delay in awarding contract | 50 | 0 | 400 | 1600 | 2007-08-09 | 2007-09-28 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 334.3426 | 449.0949 | 1A | 1 |  | 449.0949 | 0 | 449.0949 | 449.0949 | 47367.933 | 97.92% | 449.0949 | 449.0949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 898.1898 |  |  | TRIANG | #NAME? | 0.5 | 0.5 | 400 | 0 | #NAME? | 0 | #NAME?
5 PALIAMENTARY PROCESS/ APPROVALS | 989 | tie fail to provide CEC with all relevant and necessary information in a timeous manner. tie fail to follow agreed protocols. | CEC lack the opportunity for informed decision making | Delay to project. Increased financial liability. Impact on quality. | 50 | 500 | 750 | 1000 | 2007-08-13 | 2010-12-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 43 | 375.4679 | 504.3352 | 1A + 1B | 1 |  | 504.3352 | 0 | 11.7287 | 504.3352 | 47872.2681 | 98.96% | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 11.7287 | 0 | 516.0639 |  |  | TRIANG | #NAME? | 0.5 | 0.5 | 750 | 0 | #NAME? | 0 | #NAME?
5 PALIAMENTARY PROCESS/ APPROVALS | 990 | SDS are behind programme with design review certificates and tie have decided not to extend programme period to account for this. | CEC carry financial impact of uncertified designs provided to Infraco | Modifications required to the designs post-contract award resulting in additional costs | 50 | 500 | 750 | 1000 | 2007-08-13 | 2008-01-31 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 375.0595 | 503.7866 | 1A + 1B | 1 |  | 503.7866 | 0 | 100.7573 | 503.7866 | 48376.0547 | 100% | 100.7573 | 100.7573 | 100.7573 | 100.7573 | 100.7573 | 100.7573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604.5439 |  |  | TRIANG | #NAME? | 0.5 | 0.5 | 750 | 0 | #NAME? | 0 | #NAME?
[55 empty] | p50= | 36015.0481 | [58 empty] | TOTALS | #NAME? | [6 empty] | #NAME?
[6 empty] | 30435.5 | 83227.5 | 131358.5 | [46 empty] | p90= | 48376.0547 | 48376.0547 | [6 empty] | 42735.3334 | [47 empty] | 49437.6306
[64 empty] | 2333.38 |  |  | 6702.2972 | 7541.8083 | 1756.7226 | 1684.7608 | 1683.2813 | 1618.0098 | 1517.2525 | 1517.2525 | 1520.5895 | 1543.6281 | 1542.0906 | 1299.9597 | 1270.2312 | 1180.642 | 1111.7367 | 578.6669 | 509.1697 | 507.7213 | 507.7213 | 492.801 | 492.801 | 492.801 | 485.1088 | 500.4719 | 503.4705 | 445.2884 | 445.2884 | 445.2884 | 418.1622 | 381.4683 | 379.0706 | 276.4953 | 278.2887 | 262.5479 | 262.5479 | 262.5479 | 262.5479 | 262.5479 | 262.5479 | 262.5479 | 261.9984 | 193.5449 | 220.4093 | 220.4093 | 5073.087 | 98875.2612
45068.7134
Note on DI122: Colin Clements: this is an error compared to b5: check period calculations of nina's

## QRA Output DX121
Simulation Results for
QRA Output / DX121
Summary Information
| Workbook Name |  | 07.09.10 Period 6 QRA - (Risks Removed as per BD).xls
| Number of Simulations |  | 1
| Number of Iterations |  | 10000
| Number of Inputs |  | 376
| Number of Outputs |  | 1
| Sampling Type |  | Latin Hypercube
| Simulation Start Time |  | 2007-09-10 10:49
| Simulation Stop Time |  | 2007-09-10 10:51
| Simulation Duration |  | 0:02
| Random Seed |  | 1778982004
Summary Statistics
| Statistic | Value | %tile | Value
| Minimum | 14317.832 | 5% | 25476.2812
| Maximum | 82570.9766 | 10% | 27263.2871
| Mean | 36015.0481 | 15% | 28481.1309
| Std Dev | 8159.1449 | 20% | 29539.1641
| Variance | 66571644.9222 | 25% | 30371.7812
| Skewness | 0.97284 | 30% | 31270.4492
| Kurtosis | 4.0855 | 35% | 32056.6953
| Median | 34359.9883 | 40% | 32802.2188
| Mode | 31639.92 | 45% | 33576.2539
| Left X | 25476.2812 | 50% | 34359.9883
| Left P | 5% | 55% | 35208.8203
| Right X | 52319.75 | 60% | 36130.4062
| Right P | 95% | 65% | 37113.9922
| Diff X | 26843.4688 | 70% | 38252.7734
| Diff P | 90% | 75% | 39818.5352
| #Errors | 0 | 80% | 41994.8281
| Filter Min |  | 85% | 44893.9609
| Filter Max |  | 90% | 48376.0547
| #Filtered | 0 | 95% | 52319.75
Sensitivity
| Rank | Name | Regr | Corr
| #1 | Delay to completion of project / $DX$59 | 0.74209 | 0.64613
| #2 | Tramco Insolvency without bale-out or acquisition / $DV$84 | 0.30296 | 0.16596
| #3 | Higher land compensation claims than anticipated / $DX$61 | 0.23532 | 0.26438
| #4 | Unknown or abandoned assets or unforeseen/contaminated ground conditions affect scope of MUDFA work. / $DX$41 | 0.20913 | 0.2313
| #5 | Completion of MUDFA works is delayed (due to late design/approvals) - late utility diversions in advance of Infraco works. / $DX$18 | 0.17275 | 0.20844
| #6 | Delay in achievement of permanent TROs causing delay to project / $DV$97 | 0.17073 | 0.21507
| #7 | Uncertainty of Utilities location and consequently required diversion work/ unforeseen utility services within LoD / $DX$35 | 0.15439 | 0.1721
| #8 | Part 1 Claims for land and property - (Noise and Vibration) / $DX$62 | 0.12994 | 0.12291
| #9 | Transdev refuse to operate system on safety ground or apply overly restrictive procedures that are not directly the responsibility of Infraco / $DX$78 | 0.1237 | 0.14608
| #10 | Late prior aproval consents / $DX$17 | 0.11607 | 0.15533
| #11 | CEC failure to sign legal agreement - legal oficer level / $DX$101 | 0.11378 | 0.13575
| #12 | Tramway runs through area of possible contamination and material requires to be removed and replaced (dig and dump). / $DX$45 | 0.10466 | 0.098019
| #13 | Detail design leads to kinematic envelope impact on vertical and horizontal alignment / $DX$29 | 0.099831 | 0.091593
| #14 | Inadequate system integration / $DX$21 | 0.09933 | 0.10506
| #15 | Uncertainty about extent of construction works required on road network relating to Wide Area Modelling issues. / $DX$69 | 0.094696 | 0.11154
| #16 | Proposed Scottish Exec amendment of Traffic Regs for Tram core measures is unsuccessful thereby triggering public hearings / $DV$98 | 0.090671 | 0.093205