## Sheet1
Printed On: 11 Jan 2008
ETN Risk Register
Risk Description
ARM Risk ID | Cause | Event | Effect | Risk Owner | Prob | Significance | Black Flag | Treatment Strategy |  | P90 Risk Allocation | CEC Comments
187 | Poor relationships with stakeholders including political, Network Rail and other major organisations, businesses, frontages, special interest groups (including Spokes, SNH etc) Equalities Transport (DDA), media, community councils and residents associations | Project loses political and public support during construction. | Loss of funding support | M Crosse | 18% |  | Project | Continue with Hearts and Minds Campaign |  | Not included in Cost QRA | Loss of funding would clearly mean the project could not progress. It is understood by CEC that this eventuallity is not covered within the QRA. However CEC wants to know the financial effect of withdrawal from the project at 6 monthly intervals between programmed financial close to the transfer to operational stage. Costs of withdrawal v's costs of completion to be estimated. Given a probability has been calculated costs must be known.
Develop strategies to counteract and negative comments
Regular involvement with stakeholders to keep them informed and to better understand their concenrs
Seek support from pro-tram lobby groups to promote positive views
286 | Infraco lack of confidence in SDS designs or delivery programme | Infraco refuses to accept or fully engage in novation of SDS. | Possible delay to award; Damage to reputation; Possible extra costs or risk transfered back to tie. | B Dawson | 20% |  | Project | Complete designs and allow due dilligence to be undertaken by bidders |  | Not included in Cost QRA | A value of delay to contract award must be known within a certain time window. CEC requires the costs of delay of signing per month. In addition how much would it cost for Infraco to take the design risk, is this worth buying out?
Consult with legal on options relating to due diligence to be carried out on design and availability of consents
Introduce and engage Infraco bidders to SDS as early as possible
915 | Policy or operational decision | Transport Scotland and CEC do not provide indemnities on payment | Bidders will not commit to contract without this assurance; Delay in bid process; Possible bidder withdrawal from negotiations and bid process. | G Gilbert | 0% |  | Project | Ensure Transport Scotland understand implication of not resolving the funding agreement and obtain buy-in from them |  | Not included in Cost QRA | Funding agreement has been signed by CEC/TS
1001 |  | Termination due to failure to satisfy a CP within 3 months of Effective Date which tie does not waive | Potential project suspension/cancellation | S Clark | 10% |  | Project | Costs will be recovered from Infraco up to the cap under Clause 77. tie contract management team will obtain CP document on contract award. |  | Not included in Cost QRA | What is the CP reference?
1002 |  | Termination due to failure to satisfy a CP within 6 months of the Effective Date which tie does not waive | Potential project suspension/cancellation | S Clark | 10% |  | Project | Costs recovered from Infraco up to the cap under Clause 77. tie contract management will obtain CP document at contract award. |  | Not included in Cost QRA | What is the CP reference?
1004 |  | Failure to pay the Infraco resulting in the title in all materials, goods and equipment not transferring to CEC | Project cancellation | G Gilbert | 5% |  | Project | Project financial reporting will provide CEC with advance notice of payment drawdown requirement. CEC to effect treasury management to support the payment requirements |  | Not included in Cost QRA | This would be a call on the CEC guarantee, not nessesarily project cancellation.
1005 |  | Failure of tie to issue the Certificate of Tram Commissioning (due to tie default or due to tests not having been passed) | Project delay or potentially cancellation | S Clark | 1% |  | Project | Tie project management will ensure that ties actions are discharged timeously so as not to disrupt tram testing and commissioning. |  | Not included in Cost QRA
#N/A
#N/A
987 | Unnacceptable financial cost and/or risk | CEC do not agree to final negotiated contract | Potential cancellation of project | D Fraser | 0% |  | Project | Ongoing member engagement |  | Not included in Cost QRA | See CEC comments in relation to Risk ID 187
#N/A
#N/A
916 | CEC do not achieve capability to deliver | CEC do not honour funding obligations | Potential showstopper to project if contribution not reached; Line 1B may depend on incremental funding from CEC | S McGarrity | 0% |  | Project | CEC has formed a multi discipline Tram Contributions Group to monitor identified sources of £45m contribution including critically developers contributions. tie are invited to that group. (see add info) |  | Not included in Cost QRA | This is not a Black Flag. The £45m risk is applicable to CEC. CEC have already borrowed elements of the £45m.
CEC to deliver necessary contributions for 1a
Tram Project Board to monitor progress towards gaining contributions
#N/A
995 |  | Short term funding beyond the existing arrangements of £60m plus 2006-07 rollover of £10.6m cannot be agreed. | Future of project placed in jeapordy | G Bissett | 0% |  | Project | Identify extent and timing of potential shortfall including allowance for cost overrun and short term programme slippage and seek agreement with CEC/TS of funding for the shortfall in the context of the New Award Letter anticiapted from TS. |  | Not included in Cost QRA | This has been overtaken by the new Grant Award Letter.
If short term funding is resisted, assess scope to reduce short term expenditure and the implications for programme and cost. Tram Project Board to determine appropriate action
996 | CEC and TS cannot agree on any of the following: Scope of project, quantum of funding, rate of release of funding, contribution percentages, governance arrangements | Funding agreement between CEC and TS not concluded and financial close cannot be achieved | Project unable to proceed | G Bissett | 50% |  | Project | Seek to negotiate mutually acceptable terms between CEC and TS in the context of the New Award Letter |  | Not included in Cost QRA | CEC/TS funding agreement has been signed. Probability is showing at 50%. Should be 0%.
See CEC response to Risk ID 996 above.
997 |  | Components of the funding package cannot be delivered in the necessary timescale | Significant delay which threatens project continuation | G Bissett | 50% |  | Project | Seek agreement that scope of project follows Phase 1a committment |  | Not included in Cost QRA
998 |  | Funding arrangements cannot be concluded because a material tax exposure emerges which cannot be resolved | Failure to achieve financial close | G Bissett | 5% |  | Project | Seek advice from PWC timeously to avoid creating funding arrangements, corporate structure or other aspects which create such a tax exposure. |  | Not included in Cost QRA | Tax letter from HMRC has been signed off. No issues here as far as the funding agreement is concerned.
999 |  | Extent of concessionary fare support committment from TS provides inadequate comfort to CEC | CEC wihdraw support for FBC and project fails | G Bissett | 50% |  | Project | Negotiate the terms of Government committment to concessionary fare support to level which is satisfactory to CEC |  | Not included in Cost QRA | Sensitivity analysis should be undertaken to demonstrate the potential financial impact on TEL operations. Current assumption in business plan is that the status quo will be applied
1000 |  | OGC Gateway 3 Review does not take plece timeously or identifies material weaknesses | Delay and potential withdrawal of support from CEC and/or TS. | S Clark | 20% |  | Project | Timeous arrangements with qualified team to prepare for review. Internal reveiw to assess compliance ahead of formal review. |  | Not included in Cost QRA | The OGC gateway review 3 was undertaken and reported on the 9th October. Therefore why is there still a 20% probability on risks associated.
268 | Final Business Case is not approved or is approved subject to the gaining of additional funding | Funding not secured/agreements not finalised for total aggregate funding from TS and CEC including grant/indexation at FBC; risk sharing between parties; cashflow profile; financial covenant; public sector risk allocation. | Possible showstopper; Delays and increase in out-turn cost may affect affordability. Event: also decision on line 1B. | S McGarrity | 0% |  | Project | Acquire confidence in contingency figures |  | Not included in Cost QRA | As above - funding agreement in place with CEC/TS
tie are facilitating interaction between TS ANd CEC in the delivery of a funding agreement which will cover all funding matters including decision making on Phase 1b. This process requires each party to facilitate decision making within. Target resoluti Tram Project Board to monitor progress towards conclusion of agreement.
1015 |  | · [Definition of tie Default] ties failure to make payment due under Interim Certificates exceeding, in aggregate, 5% of the Contract Price | Project suspension or cancellation | G Gilbert | 1% |  | Project | Provide forecasts, updated on a four weekly period basis. CEC to manage treasury function to ensure funds are available |  | Not included in Cost QRA
1016 |  | · [Definition or tie Default] ties breach of obligation under the Agreement which materially and adversely affects the carrying out/completion of the Infraco Works[31] |  | S Clark | 1% |  | Project | Apply effective project management. CEC to support tie with quick and effective decision making. |  | Not included in Cost QRA
1017 |  | Tax fluctuations where tie is informed of such increase within 3 month | Increase in costs | G Gilbert | 10% |  | Project | Residual Risk - CEC to back this off to TS under funding agreement |  | Not included in Cost QRA | Explanation required of this risk and treatment of it.
1008 |  | Failure of tie to create the novation agreement – risk is pre-award in that Infraco refuses to accept the novation of SDS. |  | G Gilbert | 5% |  | Project | tie have developed the Facilitated Negotiations activity prior to contract award to deal with impediments to resolution. Under the Preferred Bidder Agreement award is conditional on Infraco accepting both SDS and Tramco novation. |  | Not included in Cost QRA | Risk of consents issues to be quantified. As commented on at Risk ID 286, how much would it cost for buy out this risk by getting Infraco to accept?
#N/A
1014 |  | Termination on tie Default, tie pays value of work done, prelims, supplies goods committed to, demobilisation (and materials removal), 15% as profit loss on all payments | Project cancellation | S Clark | 1% |  | Project | Apply effective project management to avoid creating basis for termination |  | Not included in Cost QRA | As in Risk ID 187 what would be the cost of termination
#N/A
#N/A
870 | SDS Designs are late and do not provide detail Infraco requires | Infraco does not have detail to achieve a fixed price without provisional designs | Delay to due diligence and start on site and need to appoint aditional design consultants | T Glazebrook | 95% | High - 25.00 |  | Monitor design progress and quality |  | 3789.8892
Obtain Design Progress Dashboard from SDS
Review AIPs for Structural Information
139 | Utilities diversion outline specification only from plans | Uncertainty of Utilities location and consequently required diversion work/ unforeseen utility services within LoD | Increase in MUDFA costs or delays as a result of carrying out more diversions than estimated | G Barclay | 90% | High - 25.00 |  | Carry out GPR Adien survey |  | 2280.4994
Identify increase in services diversions. MUDFA to resource/re-programme to meet required timescales.
In conjunction with MUDFA, undertake trial excavations to confirm locations of Utilities and inform designer
164 | Utilities assets uncovered during construction that were not previously accounted for; unidentified abandoned utilities assets; asbestos found in excavation for utilities diversion; unknown cellars and basements intrude into works area; other physical obstructions; other contaminated land | Unknown or abandoned assets or unforeseen/contaminated ground conditions affect scope of MUDFA work. | Re-design and delay as investigation takes place and solution implemented; Increase in Capex cost as a result of additional works. | I Clark | 95% | High - 25.00 |  | Carry out GPR Adien survey |  | 6233.5717
Identify increase in services diversions. MUDFA to resource/re-programme to meet required timescales.
In conjunction with MUDFA, undertake trial excavations to confirm locations of Utilities and inform designer
952 | Scope of works relating to Wide Area Modelling (WAM) have not been agreed with SDS because they consider this to be out with the scope of their contract. | Uncertainty about extent of construction works required on road network relating to Wide Area Modelling issues. | Potential claim from SDS to deal with additional design work; Potential construction costs to deal with WAM issues (difficult to quantify without design) over and above those already included. | K Rimmer | 95% | High - 25.00 |  | Agree design requirements relating to WAM with SDS |  | 1906.5412
Employ further traffic management expertise
Finalise boundaries of Tram responsibility for WAM requirements
Obtain design and quantify construction cost for inclusion in base estimate
Provision of £500k in Draft Final Business Case estimate to deal with WAM requirements
342 | Tram alignment at A8 crossing at Gogar co-incides BT data nests/cable (main coms link between Glasgow and Edinburgh) | A8 crossing tunnel requires special design or BT data nest/cables require to be moved | Capex cost to cover BT data nest/cable move; additional design costs; delay while works to undertake move are carried out; additional tunnelling costs. | I Clark | 80% | High - 24.00 |  | Confirmation of BT requirements to tie |  | 1336.4412
911 | Scottish Power own and maintain a cable tunnel in the vicinity of Leith Walk that may or may not interfere with Tram construction and operation; exact location and depth of tunnel is unknown; condition of tunnel is unknown. | Presence of Scottish Power tunnel in Leith Walk requires radical solution | Tunnel may have to be decommissioned and re-laid in a more suitable location; tram alignment may require to be adjusted; special foundation soluiton e.g. cantilever may be required; increased capex; potential for tunnel collapse during operation and consequent disruption for tram. | M Blake | 80% | High - 24.00 |  | Scottish Power to establish exact location of tunnel |  | 534.6961
SDS to try and ensure tram alignment footprint is outwith Scottish Power alignment - confirmation via thumbnails due 16th November
tie to undertake engineering feasibility study
935 | Immunisation project not prioritised by Network Rail; Network Rail resources diverted to other projects or emergencies; Multiple iterations of design development; Tram requirements change as a result of Tram design development; Network Rail standards changes; Tram programme not able to be achieved in the first place. | Network Rail do not deliver the immunisation works before the drop dead date of October 2009. | Tram cannot be commissioned to programme; Critical delay. | S Bell | 80% | High - 24.00 |  | Confirm and review importance of works with regular Transport Scotland meetings regarding Network Rail |  | 320.6821
Ensure Immunisation Works programme allows for design development.
Establish baseline, change control and constraints
Monitor and challenge tie and Network Rail programme development, agree milestones.
Review current applicable signalling standards and options for design solutions
Review draft Immunisation Design Contract and Works Contract
tie to agree Immunisation Design Contract with NR
tie to agree Immunisation Works Contract with NR
980 | Government/Parliament not persuaded of case for amendmnet to Traffic Order Regulations. Requirement for a mandatory publi hearing for TROs remains adding approximately 1 year to time required to confirm Orders. | Proposed Scottish Executive amendment of the Traffic Order Regulations fails thereby triggering public hearing | Public hearing required with additional cost (£1m) plus delay to making of TRO(s). Public hearing leads to greater risk of variation to promoted street and regulatory features. Increased difficulty of managing gap period - some constructed Infraco street features may require to be removed or altered to accord with made TRO. | K Rimmer | 50% | High - 23.00 |  | Encourage and assist SE as much as possible in order to promote change to regulations |  | 2005.2324
47 | Poor design and review processes; cumbersome approvals process; reiterative design/approvals process. | Completion of MUDFA works is delayed (due to late design/approvals) - late utility diversions in advance of Infraco works. | Increase in price and time delay in the Infraco contract; Infraco could end up delay to commencement or with utility diversion and would have to price for or have to carry out unplanned re-sequencing; Claims from MUDFA as a result of being unable to proceed with works. | G Barclay | 50% | High - 23.00 |  | Incentivisation oF SDS |  | 1356.5124
Micro management of design
Review design timscales
Review tie design review
Revise design process
48 | Two stage tender pricing does not achieve price certainty for works at first stage. | Price certainty is not achieved | Price creep post tender (during pre-construction period). Tender evaluation period exceeds 2 months currently planned. Bidder may attempt to price low at first stage. | B Dawson | 50% | High - 23.00 |  | Close principal contract conditions prior to preferred bidder selection |  | 5344.3561
Infraco to undertake due diligence on SDS design
Minimize Infraco qualifications to price and assumptions
Principles or formulae for adjusting prices on certain items following due diligence and value engineering
352 | Increase in land values | Higher land compensation claims than anticipated | Additional uplift on compensation claims | A Sim | 70% | High - 23.00 |  | Close out |  | 2694.4608
Initiate early negotiations between DV and landowners
Liaise with CEC Planning
354 | Land and property values experience a net reduction in value as a result of the introduction of the Tram | Part 1 Claims for land and property - (Noise and Vibration) | Possible successful claims resulting in increased costs to project with impact after construction | A Sim | 50% | High - 23.00 |  | Close out - inform base estimate |  | 1105.1132
Reduce noise & light at track-side/stops - eg noise barriers, light shields
Reduce noise at source - wheel/rail interface design
Reduce noise/light at receptor through design mitigation measures
44 | SDS contractor does not deliver the required prior approval consents before novation | Late prior aproval consents | Delay to programme with additional resource costs and delay to infraco. Impact upon risk balance. | T Glazebrook | 50% | High - 23.00 |  | Evaluation of prior approval programme |  | 1080.9213
Hold fortnightly Roads Design Group
Hold weekly CEC/SDS liaison meetings
Informal consultation prior to statutory consultation
Integrate CEC into tie organisation/accomodation (office move)
Tram Design Working Group
279 |  | Third party consents including Network Rail consent are denied or delayed | Delay to programme; Risk transfer response by bidders is to return risk to tie; Increased out-turn cost if transferred and also as a result of any delay due to inflation. | T Glazebrook | 50% | High - 23.00 |  | Additional EMC modelling to give better info to NR |  | 751.9621
CEC Planning - mock application by SDS
Draft depot and station change proposals to NR
Engagement with third parties to discussed and obtain prior approvals to plans
Identify fallback options
Obtain critical consents prior to financial close
70 | SDS does not provide its defined deliverables (technical specs) in accordance with the SDS contract. Infraco Proposals not fully considered. | Poor definition of design and Employers Requirements in Infraco tender documents | Creates impact on the Infraco ability to develop its tender - pricing and supply chain. Increase in time for BAFO and increase in costs. Increase in bidder queries. | B Dawson | 50% | High - 23.00 |  | Finalise Employers Requirements for Infraco tenders |  | 1203.6934
Monitor commercial impact of bidder queries
receive bidder queries and transmit to sds pm
SDS PM transmits queries and monitors response to ensure timeliness
SDS to provide information to programme
52 | Political and/or Stakeholder objectives change or require design developments that constitute a change of scope; Planning Department requires scope over and above baseline scope in order to give approval (may be as a result of lack of agreement over interpretation of planning legal requirements). | Amendments to design scope from current baseline and functional specification. | Programme delay as a result of re-work; Programme delay due late receipt of change requirements and lack of resolution; Scope/cost creep (dealt with through change process); Project ultimately could become unaffordable. | T Glazebrook | 20% | High - 22.00 |  | Close working relationship with CEC and stakeholders |  | #N/A
Weekly critical issues meeting
986 | Inadequate information supplied by tie. | CEC failure to sign legal agreement - legal oficer level | Delay to commencement of contract | D Fraser | 18% | High - 22.00 |  | Tranparency of and value of risks to CEC from bespoke contract |  | 585.8197
343 | General delay to programme with various causes e.g. failure to obtain approvals on time; parliamentary processes, delays due to lack of prioritisation of BAA agreement with new owners | Delay to completion of project | Inflation at 5% causes increased out-turn cost due to delay plus revenue loss | M Crosse | 20% | High - 22.00 |  |  |  | 3104.6813
893 | VE process concentrates on reducing Capex to the detriment of Opex | VE Process makes TEL Business Case undeliverable | TEL Business Case becomes les undeliverable | A Richards | 20% | High - 22.00 |  | Make Tram Project Board aware of implications of VE proposals |  | 64.1674
TEL/Transdev involvemen in VE Workshop process to ensur balance Capex/Opex
903 | Successful challenge from unsuccessful tram bidder | Procurement challenge by Tram bidders | prgramme risk -worst case is to start again | D Powell | 1% | High - 21.00 |  | Ensure process meets all aspects of EU procurement law |  | #N/A
905 | Not controlled by Project | Tramco Insolvency | Trams are not delivered;legal costs;delay | D Powell | 1% | High - 21.00 |  | Annual helth Check on Tramco post contract Award |  | 267.3643
Pre contract Award health check
906 | Currency fluctation Euro/Sterling | Tramco pricing risk between now and awarding contract | price may go up/down | D Powell | 5% | High - 21.00 |  | Ensure long bid validities quoted in sterling until novation completed |  | 104.6104
Preferred TRAMCO to hedge currency risk on appointment of preferred bidder
888 | Design, construction and/or testing does not meet Transdev requirements and gain approval from the ROGS Competent Person | Transdev refuse to operate system on safety ground or apply overly restrictive procedures that are not directly the responsibility of Infraco (ROGS Competent Person agrees with this) | Delay to comencement of service, additional cost both for delay and rectification of the issue | A Richards | 5% | High - 21.00 |  | Ensure Infraco Agreement requires Operator to be consulted on appropriate issues |  | 239.2036
Involve Transdev fully in design, construction and testing/review process.
54 | Contractor default e.g. insolvency. | Construction bond not available in the event of Infraco default | Increase in cost and progeamme due to appointment of replacement contractor | B Dawson | 1% | High - 21.00 |  | Joint and several liability of consortium members + parent company guarantees prior to award |  | 33.215
134 | Network Rail possessions over and above that estimate are required | Compensation paid to Train Operating Companies | Increased compensation paid to Train Operating Companies | S Clark | 5% | High - 21.00 |  | Ensure NR Possession risk is backed off to Infraco |  | 144.38
Review Infraco programme to ensure it is robust with respect to NR Possessions
173 | Uncertainty over extent of contaminated land on route | Tramway runs through area of previously unidentified contamination and material requires to be removed and replaced (dig and dump). | Increase in costs to remove material to special and other tip. | T Glazebrook | 3% | High - 21.00 |  | Issue containation and gi report to Infraco bidders |  | 127.9257
tie to obtain ground investigation and contamination reports from SDS
924 | Tram crosses high voltage transmission cables in 4 areas (2x Leith Walk - 275kV; 2 times bridge abutment - 132kV); Design found to be inadequate; Infraco do not follow design requirements; Cable not shut down to Scottish Power requirements. | Very high voltage underground electricity transmission cables are encountered and damaged during Infraco Works | Potential to cause damage and consequent accident during work; Scottish Power delay works if cable shut down notice periods not adhered to; Significant injury (potential for multiple deaths) caused to workforce; Delay in project section. | S Clark | 3% | High - 21.00 |  | Ensure Infraco follow relevant safety procedures during construction |  | #N/A
Ensure Infraco understand and agree with design requirements near to cables.
Ensure method statements refer to and deal with very high voltage cables adequately
Ensure notice periods for cable shut down are understood by Infraco and incorporated into programme
928 | Major single safety incident (including a dangerous occurrence) during construction | Safety incident during construction | Delay (potentially critical) due to HSE investigation and rework. PR risk to tie and stakeholders. | S Clark | 5% | High - 21.00 |  | All Site Staff to get CSCS or equivalent |  | #N/A
Develop and Implement Incident Management Processes
HSQE Audits, site inspections and Management Safety Tours to be carried out
Safety Induction to be carried out for all site staff
Site Supervisors to be appointed by tie
1013 |  | Indirect Losses sustained in by Third Parties claiming against tie or Infraco or because of third party agreements or land consents | Additional cost | S Clark | 1% | High - 21.00 |  | Agree programme and methodologies with significant Third Parties |  | 24.0628
1010 |  | Occurrence of termination or omission of Infraco Works if permission to resume not granted by tie within 6 months | Project suspension or cancellation | S Clark | 1% | High - 21.00 |  | Suspensions are generally due to Infraco default. If tie responsibility - unlikely to apply to whole of works and partial suspension could be deployed for affected area. |  | 109.0633
931 | Utilities assets uncovered during construction that were not previously accounted for; unidentified abandoned utilities assets; known redudant utilities; unknown live utilities; unknown redundant utilities. | Unknown or abandoned assets impacts scope of Infraco work | Re-design and delay as investigation takes place and solution implemented; Increase in Capex cost as a result of additional works. | T Glazebrook | 90% | High - 20.00 |  | GPR surveys in areas where there are likey to be services |  | 722.1827
MUDFA trial holes to verify GPR surveys
977 | Legal challenge. Extension of statutory consultation process. Large number of objections. TRO process is subject to a public hearing process. | Delay in achievement of TRO(s) due to a large number of public objections and/or a legal challenge to using a TTRO to construct Infraco. | Requirement to start construction using TTROs | K Rimmer | 90% | High - 20.00 |  | Use of TTROs to undertake construction of permanent works in advance of permanent TROs being approved. |  | 1203.1394
914 | Required approval/acceptance turnaround time does not reflect SUC standard practice; SUCs do not have enough resource or process capability to achieve 20 day turnaround | Statutory Utility Companies unable to meet design approval/acceptance turnaround time to meet programme | Additional period required for design approval/acceptance turnaround | T Glazebrook | 95% | High - 20.00 |  | SDS to obtain consent for design in accordance with programme requirements - Scottish Water and all Telecoms |  | 1061.7037
SDS to obtain consent for design in accordance with programme requirements - SGN and Scottisk Power
105 | Encountering archaeological finds/burials/munitions during construction | Exhumation of archaeological finds/burials | Delay in construction programme | S Clark | 85% | High - 19.00 |  | Agree protocol |  | 220.861
AMIS to re-programme works accounting for hot-spots
Assess Infraco programme to determine if float contained within the high risk areas
Check to ensure that AMIS programme has adequate float
Identify hotspots
Meet Archaeologist
Review Infraco programme regarding archaeological hotspots and ensure adequate programme float
938 | Failure to reach agreement on roles and requirements | ties overall interface with Network Rail, including consents, approvals and involvement in projects prevents project success. | Drop dead date of October 2009 not achieved; Costs increase beyond budget. | S Bell | 80% | High - 19.00 |  | Employ dedicated, competent Project Manager to oversee development, programme and implementation |  | #N/A
Establish critical path and importance with Network Rail Senior Management Team
Facilitate the development of a shared viewed on requirements
SDS to prepare requirements specification and necessary technical reports
Support legal agreements/approval process with Network Rail
271 | Inadequate quality of submission of approval. Partial submission of package. Programme compression. Lack of CEC resources. | Failure to process prior approvals applications within 8 weeks | Delay and disruption to Infraco programme | T Glazebrook | 80% | High - 19.00 |  | Agree approvals submission arrangements with CEC to align with SDS design programme and procurement programme. |  | 891.3541
Assure the quality and timing of submissions
Final agreement to be approved by Roads Authority, CEC Promoter, CEC in-house legal and tie
Finalise alignments and gain agreement from CEC
Where appropriate increase case officer resource to cope with programme compression
940 | SDS not novated to Infraco; SDS requirements in relation to Immunisation Works after novation not clearly defined; tie/Infraco and Infraco/SDS contracts not aligned or integrated. | Infraco not competent to provide design requirements/challenge design of Immunisation Works | Immunisation Works requirements not adequately specified; Issues arise during Tram commissioning. | S Bell | 50% | High - 18.00 |  | Clarify that bidders understand issues relating to design requirements for Immunisation Works (post Consolidated Proposals) |  | #N/A
Clarify with SDS that they understand all of the issues
Review emerging risk allocation and budget provision for Infraco
Review proposed novation and Infraco contract regarding Network Rail interface works and in particular Immunisation Works within that
59 | Poor performance (time) by Infraco during construction | Infraco fails to deliver to programme within Liquidated Damages cap | Stakeholder criticism, negative PR, extended programme delay to system. | S Clark | 70% | High - 18.00 |  | Agree optimum programme wih preferred Infraco bidder |  | #N/A
Detailed evaluation of Infraco programme to ensure it is robust
Ensure contractual controls are in place
Robust programme monitoring to be established to detect slippage
926 | Complexity of traffic management proposals require additional approvals (relating mainly to city centre) | Approvals for traffic management proposals are not approved or take so long to approve that work cannot commence in line with the programme | Delay to project. | G Barclay | 50% | High - 18.00 |  | Review traffic management requirements for rev 6 programme and the alignment of these requirements with programme start dates |  | #N/A
989 | tie fail to provide CEC with all relevant and necessary information in a timeous manner. tie fail to follow agreed protocols. | CEC lack the opportunity for informed decision making | Delay to project. Increased financial liability. Impact on quality. | M Crosse | 50% | High - 18.00 |  |  |  | 451.2199
990 | SDS are behind programme with design review certificates and tie have decided not to extend programme period to account for this. | CEC carry financial impact of uncertified designs provided to Infraco | Modifications required to the designs post-contract award resulting in additional costs | D Fraser | 50% | High - 18.00 |  |  |  | 400.9357
1011 |  | Occurrence of any delay caused by Utilities Works, MUDFA Works, breach of Third Party Agreements, Unplanned City Events, New Utilities and/or any other event referred to as a Compensation Event | Delay and additional cost | S Clark | 40% | High - 18.00 |  | Construction programme has been sequenced and interleaved with that of Infraco’s. Infraco programme to be shared with CEC and significant third parties and monitored on a period by period bais to avoid programme clashes. |  | 507.9922
172 | Area of possible contamination and unstable ground (unlicensed tip) has been highlighted during desk study immediately to east of Gogar Burn - investigation for CERT project indicates that this consists of building rubble and domestic waste. | Tramway runs through area of possible contamination and special foundation is required to cope with unstable ground | Increase in costs to provide special foundation solution | T Glazebrook | 95% | High - 17.00 |  | Include SI Report and Information in next issue of information to Infraco. |  | 253.9969
Monitor design progress and include costs in base estimate.
Obtain ground investigation information.
865 | Buildings contain asbestos that was not uncovered during surveys | Asbestos found during demolition works and excavations for construction | Cost and delay during investigation and removal | T Condie | 90% | High - 17.00 |  |  |  | 101.1165
178 | Procurement Strategy novates SDS to InfraCo after Detailed Design; Limited input on buidability from Infraco. | Infraco due diligence process reveals that design rework will be required after novation of SDS. | Bids will be higher than envisaged in base estimate as Infraco will price for re-work. | G Gilbert | 75% | High - 16.00 |  | Undertake bidder due diligence on designs and apply value engineering within the bid process to capture bidder buildability input |  | 401.0465
132 | Realignment of existing road geometry required | Increase in off-route junction improvements, certain junctions requiring realignment of kerbs etc | Increase in design costs. | T Glazebrook | 80% | High - 16.00 |  | Increase in off-route junction improvements, certain junctions requiring realignment of kerbs etc |  | 213.7108
[9 empty] | Sum of Black Flag and Key Risks | 43178.3255
[9 empty] | Sum of remaining risks identified as "Amber" or "Green" | 3858.5634
47036.8889