## Sheet1
Critical Contractual Decisions to enable Chief Executive to
to use delegated powers to approve tie to sign the contract with BBS
[7 empty] | approval | approval | approval
Item | Issue | CEC Status | tie status |  | Description | tie Final Deal Countdown List Item Dated 14 Jan 2008 | Finance | Legal | CDD | tie action | Document or report where evidence of this can be found | tie Deliverer |  | Notes
[12 empty] | Document | Report
1 | Contract |  |  | 1.1 | Novation agreement ready to be signed off - CAF | 1.4 |  |  | DF |  | Agreements concluded & reference in close report | AF/GG | GB
[5 empty] | SDS | 1.3 |  |  | DF |  | Agreements concluded & reference in close report | AF/GG | GB
|  |  |  | 1.2 | CEC Guarantee agreed with BBS and ready to sign off | 2.1 |  | CM |  |  | Agreements concluded & reference in close report | AF | GB
|  |  |  | 1.3 | Due Diligence on approvals for Infraco & Tramco | 8.4 |  |  | DF |  | Report from DLA & mention in close report | AF | GB
|  |  |  | 1.4 | Operating Agreement - tie | 4.1 |  | NS |  |  | Agreement signed and mention in close report | GB | GB
[5 empty] | Operating Agreement - TEL | 4.2 |  | NS |  |  | Agreement signed and mention in close report | GB | GB
|  |  |  | 1.5 | Mudfa - risks related to Infraco? | 5.5 |  |  | DF |  | Close report | G Barclay | GB
|  |  |  | 1.6 | DLA supportive letter with risk matrices | 5.2 |  | GL | DF |  | All available and mention in close report | AF | SMcG | explanation of risk profile
|  |  |  | 1.7 | OCIP exclusions | 9.4 |  |  | DF | CEC request this item is moved from 9.4 into Section 4 Governance and Corporate and request detail on caps or non insured aspects. | Report available, summary of poliicy arrangements & reference in close report | TK | GB
|  |  |  | 1.8 | tie to provide a list of what is not included within the BBS contract ( i.e. the items which BBS have specifically excluded ) with a financial value against each item. | 5.3 |  |  | DF |  | Pricing spreadsheet & Close report | SMcG | GB | OCIP caps, scope of works etc
2 | Programme |  |  | 2.1 | Confirm dates for 1a and 1b | 5.7 |  |  | DF |  | Close report | TH | GB
|  |  |  | 2.2 | Agreement of On-street Construction Methodology | 1.11 |  |  | DF |  | Sign off sheet | TH | GB | closure periods v cost implications
3 | Employers Requirements |  |  | 3.1 | Summary to CEC of Employers' Requirements, including detailed scope of the Tram Works with endorsement from DLA. The ER is a key part of the overall contract which sets compliance standards of the tram works. BBS have been given version 2.4 to price. BBS have responded to this with variations, this may be a lowering of standards to keep the price level below the net £498m e.g CCTV specification. tie to produce a list of variations that they are minded to accept from version 2.4, with a justification for the variation with TELs comments, and also to give assurances that what is proposed to accept as a variation is in all cases "fit for purpose" both in term of price and quality. | 1.5/5.6 |  |  | DF |  | Close report | MC | GB | to assure CEC liabilities are explicit
4 | Due Diligence |  |  | 4.1 | Statement from the Preferred Bidder that they accept the performance run-time model and "law of physics" results and confirmation of acceptance of the emerging quality of design. | 8.2 |  |  | DF |  | Letters from bidders and Close report | MC | GB | potential for additional design costs
5 | Risk |  |  | 5.1 | Full transparency of QRA | 5.3 |  | RA |  | All issues on CEC Item 5 require to be in corporated in 5.3 of tie's list. | Risk report & close report | MH | SMcG
|  |  |  | 5.2 | (a) Black flag risks: Provide a list of these items and what is the likelihood of any of these risks occurring ? What is tie's strategy to avoid said risks materialising ? What is the cost of exiting from a Black Flag item ? | 5.3 |  | RA |  |  | Risk report & close report |  |  | be explicit even if outwith budget avoidance strategy
[5 empty] | (b) Details of the risk management strategy for the key risks through delivery. | 5.3 |  | RA |  |  | Risk report & close report |  |  | highlighted by OGC report
[5 empty] | (c) Detailed analysis of programme risk. Confirmation of the risk allowance for programme delay. Detail of items on critical path and what is being done to ensure they do not cause (further) delay. | 5.3 |  | RA |  |  | Risk report & close report |  |  | emphasis on liability to CEC
|  |  |  | 5.3 | Tie written statement to CEC on risks as at 25 October 2007 compared to immediately post contract award. | 5.3 |  | RA |  |  | Risk report & close report
6 | Value Engineering |  |  | 6.1 | VE summary included in the final deal and highlighting other potential savings with a probability value | 5.8 |  |  | DF | Item 5.8 on tie list to include probabilities of VE items | VE report & Close report | JM | GB
7 | Pricing & Funding |  |  | 7.1 | The Council requires a detailed analysis of prices, costs and risks allowance. tie required to explain how prices for maintenance,etc. impact on operating cost assumptions | 1.9/5.8 |  | RA |  | Detail of CEC Item 7 requires expansion of tie list items 1.9/5.8 | Spreadsheets, commentary & Close report | SMcG | GB | including for both construction and operation e.g. design timescale not accepted
|  |  |  | 7.2 | Cross refer to item 1 above re exclusions from contract by BBS. | 1.9/5.8 |  | RA |  |  | As above | SMcG | GB
|  |  |  | 7.3 | Statement on % of costs fixed and % outstanding as provisional sums with programme for moving these to fixed costs | 1.9/5.8 |  | RA |  |  | As above | SMcG | GB
8 | NR Insurance |  |  | 8.1 | Full statement from tie on current status of every proposed agreement between CEC and NR, including Depot and Station Change Procedures. Full risk analysis in respect of each agreement explaining consequences for CEC in terms of time and cost relative to any delays in concluding agreements. This analysis to cross refer to BBS programme | Section 6 |  |  | SS | All items relating to NR in section 6 of tie list should be moved to Section 3 (Third Party Agreements) these are not seen as subsidiary items from CEC perspective. | Paper & Close report | AS | GB
|  |  |  | 8.2 | NR is contracting with third parties re other works at the Depot. Risk analysis to be provided regarding impact on BBS contract ( time and cost) arising from late completion of NR works. | Section 6 |  |  | SS |  | Paper & Close report | AS | GB
|  |  |  | 8.3 | Plan B to take account of any delays in achieving agreement with NR on all matters, including Caley Ale House, Lift and Shift and Immunisation. This to be included in QRA report. | Section 6 |  |  | SS |  | Paper & Close report | AS | GB
|  |  |  | 8.4 | Minimum requirements of the APA agreement | Section 6 |  |  | SS |  | Paper & Close report | AS | GB
|  |  |  | 8.5 | Written confirmation from First Scotrail ( and from other TOCs in respect of Station Change ) that they are not objecting to Depot and Station Change. | Section 6 |  |  | SS |  | Letters and close report | AS | GB
9 | SDS Assurances |  |  | 9.1 | Full written explanation of SDS Novation to be provided by tie, including risks of failing to deliver design | 1.4 |  |  | DF/ACon |  | Paper & Close report | DS | GB | including risks of failing to deliver in terms of quality and in time to meet BBS programme
|  |  |  | 9.2 | Full details are required from tie on status and degree of completion of SDS design work as at 14 January 2008, including prior and technical approvals. If approvals risk is not being transferred to BBS the Council needs to know the impact and likelihood of the risks and a strategy for managing the risks. | 1.4 |  |  | DF/ACon |  | Paper & Close report | DS | GB
also show how this will be managed by tie with CEC
|  |  |  | 9.3 | Confirmation that the public sector (tie & CEC) are not liable for delays for Planning or Road Approvals | 1.4 |  |  | DF/ACon |  | Paper & Close report | DS | GB | assumes CEC act reasonably
|  |  |  | 9.4 | tie to provide written report on previous claim settlement with SDS identifying details, cause of claim and costs of settlement. Are any further claims expected from SDS ? Are any further claims from SDS competent | 1.4 |  |  | DF/ACon |  | Paper & Close report | DS | GB | showing justification and causes and lessons learned
10 | Funding Letter |  |  | 10.1 | Terms to be agreed with CEC and TS | 2.2 |  | RA |  |  | Letter & close report | SMcG | GB | letter from CEC required to say the "best endevours" reference in the tie operating agreement will not expose TS or Scottish Ministers
11 | Third Party Agreements |  |  | 11.1 | Status report on third party agreements | 5.9 |  |  | DF | Items in Section 11of CEC list require to be added to item 5.9 of tie list | Report Close report | AS | GB
|  |  |  | 11.2 | Disclosure list and acceptance of these by BBS | 5.9 |  |  | DF |  | List & Close report | AS | GB | check for exclusions
|  |  |  | 11.3 | Status of Telewest and SP agreement and when req. | 5.9 |  |  | DF |  | Agreements & Close report | AS | GB
|  |  |  | 11.4 | Forth Ports agreement and risk of not having this in place | 5.9 |  |  | DF |  | Letter of comfort & Close report | AS | GB
12 | Lease between CEC and tie |  |  | 12.1 | To be concluded before financial close | 3.3 |  |  | SS |  | Agreement & close report | AS | GB
13 | Land Acquisition |  |  | 13.1 | Statement of land acquisitions | 5.10 |  |  | SS | Items in Section 13 of CEC list require to be added to 5.10 of tie list. | Statement & Close report | AS | GB
|  |  |  | 13.2 | Confirmation that GVD completed | 5.10 |  |  | SS |  | Statement & Close report | AS | GB | any outstanding matters
|  |  |  | 13.3 | Confirmation of match between what land has been acquired by CEC matching BBS requirements | 5.10 |  |  | SS |  | Statement & Close report | AS | GB | check programme/cost or time implications
Other Issues
Issue re protection re advance purchase of steel to be added to 1.6 in tie list.
7.1 – 7.5 inclusive in tie’s list to be moved to Section 3.
Street traders issue to be added to Section 3.
SRU issue in 3.4 in the tie list to be expanded upon and explained further.