## Summary of Options
Financial Comparison of Core Possible Outcomes
| COWD | Continue as is w/Silver Bullet |  | Carlisle |  | Terminate & Reprocure Now |  |  | Terminate & Postpone
| to P7 9 Oct 10 | w/Silver Bullet | BSC Obstinacy | Carlisle tie price | Carlisle BSC price | Win litigation | Lose litigation | Settle out of court | Reprocure after winning Litigation | Cancel after losing litigation
(P'fork 3C)
| A | B | C | D | E | F | G | H | J | K
Infrastructure ready to operate:
Airport to Haymarket |  | 2012-10-01 | 2013-12-01 | 2012-10-01 | 2013-06-01 | 2012-12-01 | 2012-12-01 | 2012-12-01 | 2014-12-01 | n/a
Haymarket to St A Sq |  | 2012-10-01 | 2015-12-01 | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2015-12-01 | n/a
St A Sq to FOW |  | 2012-10-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2017-12-01 | n/a
FOW to Newhaven |  | 2012-10-01 | 2015-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2019-12-01 | n/a
BB+S
Constn Works Price (BB+S) | 65.2 | 233.5 | 233.5 | 169 | 333.9 | 65.2 | 65.2 | 65.2 | 65.2 | 65.2
Existing Change - Princes St | 9.5 | 9 | 9 | 9 |  | 9.5 | 9.5 | 9.5 | 9.5 | 9.5
Existing Change - Other | 11.8 | 35.5 | 45.3 | 43.8 |  | 11.8 | 11.8 | 11.8 | 11.8 | 11.8
Existing Prolongation |  | 21 | 21 | 3.5
Further on-street change and disruption |  | 21.1 | 21.1
Further allowance for risks and delay |  | 20.4 | 150 | 16.5 | 40
Entitlement for work done (BB+S) | 86.5 | 340.5 | 479.9 | 241.8 | 373.9 | 86.5 | 86.5 | 86.5 | 86.5 | 86.5
Certified in advance of work done (BB+S) | 31.9 |  |  |  |  | 31.9 | 31.9 | 31.9 | 31.9 | 31.9
Certified to Date (BB+S) | 118.4 | 340.5 | 479.9 | 241.8 | 373.9 | 118.4 | 118.4 | 118.4 | 118.4 | 118.4
Net Accounting accruals/prepayments | -8.4
Bond call (BB+S) | [5 empty] | -25 | -25 | -25 | -25 | -25
Settlement Premium | [7 empty] | 35
Infrastructure (BB+S) | 110 | 340.5 | 479.9 | 241.8 | 373.9 | 93.4 | 93.4 | 128.4 | 93.4 | 93.4
Vehicles (CAF) | 46.4 | 58.5 | 58.5 | 58.5 | 60.8 | 58.5 | 58.5 | 58.5 | 58.5 | 58.5
Design Post Novation (SDS) | 5 | 5 | 14 | 14 | 15.9 | 5 | 5 | 5 | 5 | 5
Total BSC | 161.4 | 404 | 552.4 | 314.3 | 450.6 | 156.9 | 156.9 | 191.9 | 156.9 | 156.9
Interim Works & Reinstatement
Interim Works during Reprocure | [5 empty] | 20 | 20 | 20
Reinstate/remedials during Reprocure | [5 empty] | 3 | 3 | 3 | 10 | 10
Reinstatement following cancellation | [9 empty] | 40
Total | 0 | 0 | 0 | 0 | 0 | 23 | 23 | 23 | 10 | 50
New Procurement Costs
Infrastructure - to SAS |  |  |  | 13.9 | 22.9 | 255 | 255 | 255 | 317
Infrastructure - to FOW |  |  |  | 40 | 40
Infrastructure - to NHN |  |  |  | 20 | 20
Vehicles - Lease / Sale recoveries | [5 empty] | -10.5 | -10.5 | -10.5 | -13.5 | -46.8
Re-Design | [5 empty] | 15 | 15 | 15 | 15
Direct Reprocurement Costs
Risk allowance on new procurement |  |  |  | 20 | 30 | 25 | 25 | 25 | 29
Total New Procurement | 0 | 0 | 0 | 93.9 | 112.9 | 284.5 | 284.5 | 284.5 | 347.5 | -46.8
Total Infrastructure & vehicles | 161.4 | 404 | 552.4 | 408.2 | 563.5 | 464.4 | 464.4 | 499.4 | 514.4 | 160.1
Termination Costs
Securing sites | [5 empty] | 2 | 2 | 2 | 2 | 2
Our litigation & professional costs | [5 empty] | 30 | 30 |  | 30 | 30
Third party costs | [5 empty] | 10 | 10 | 10 | 10 | 20
BSC Loss of profits | [6 empty] | 35 |  |  | 35
BSC Litigation Costs | [6 empty] | 30 |  |  | 30
Total Termination Costs | 0 | 0 | 0 | 0 | 0 | 42 | 107 | 12 | 42 | 117
Other Costs
Ph1b Payment to BSC | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2
Design Pre Nov incl Ph1b and Utilities | 32.3 | 28.7 | 32.3 | 32.3 | 32.3 | 32.3 | 32.3 | 32.3 | 32.2 | 32.3
Utilties and Other Infrastructure | 87.6 | 78.7 | 89.9 | 89.9 | 89.9 | 89.9 | 89.9 | 89.9 | 89.9 | 88.7
Project Costs | 70.2 | 91.5 | 109.5 | 95.2 | 95.2 | 72.7 | 72.7 | 72.7 | 72.7 | 72.7
Project Costs - Post Termination | [5 empty] | 21.5 | 21.5 | 21.5 | 26.5 | 8.6
Other Costs - Incl Land | 32.5 | 33.8 | 33.8 | 33.8 | 33.8 | 32.3 | 32.3 | 32.3 | 32.3 | 32.3
Other Costs | 225.8 | 235.9 | 268.7 | 254.4 | 254.4 | 251.9 | 251.9 | 251.9 | 256.8 | 237.8
Gross Outturn Costs | 387.2 | 639.9 | 821.1 | 662.6 | 817.9 | 758.3 | 823.3 | 763.3 | 813.2 | 514.9
Recovery 75% of Costs from BSC | [5 empty] | -88.8 |  |  | -88.8
Net Outturn Costs | 387.2 | 639.9 | 821.1 | 662.6 | 817.9 | 669.5 | 823.3 | 763.3 | 724.4 | 514.9
758.3
639.9
118.4
88.8
Note on B19: SMcGarrity: As estimated by DM at end P6 Cert - see tab included.
Note on B21: SMcGarrity: As certified end P6 - see tab included
Note on B25: SMcGarrity: T19.01 £132.6m T19.04 £(14.3)m Less Ph1b Payment £3.2m (see below) Less Post Novation design £5m (see below)
Note on D13: SMcGarrity: CWP £238.6m Less: Prov Sums 3rd party funded £3.1m Less: Target savings on Prov Sums (Picardy) £3.0m Add: Contingency for non VE delivery £1.2m
Note on D15: SMcGarrity: Design Development £14.1m Ground Conditions £9.9m Cleint & Other changes £11.5m NB All based on QS view of change register as it stood back in March 2010 at time of Pitchfork 1
Note on D16: SMcGarrity: Per DM workings attached to 16/3/ email - includes EOT1 agreed
Note on D17: SMcGarrity: On-street scope changes £9.9m On-street dealy and dusruption £8.2m Risk re OSSA credit £3m Assumes no premium costs which would be associated with doing remaining on-street under an OSSA similar to PSSA See DM email to SMcG of 6/3 and SMcG powerpoint analysis of option 3c
Note on D18: SMcGarrity: 4mth Delay to start on street £4m (see DM workings attached to 16/3 email) Further Delay allowance £12.1m (as above) VE Deliverability £4.3m
Note on D19: SMcGarrity: Pitchfork was based upon the Change Register(s) and QS view extant back in March 2010. I dont think it would move around by more than a few £m +/_ but we need to keep an eye on reconciliation to the current reported QS view!
Note on D59: SMcGarrity: See seprate tab which reconciles what was included in P'fork 3C (£78.7m) compared to whats getting reported as AFC now (£89.9m) - needs watching as MUDFA final account settled.
Note on D60: SMcGarrity: See Project Costs tab - forecast to Feb 12 = £87.5m plus £0.5m per month for prolongation to Oct 2012 = £91.5m.
Note on D69: SMcGarrity: Nothing changes in this column to preserve total for Pitchfork 3c - if we were doing again the answer might be a bit different.
Note on E18: SMcGarrity: Not capable of being estimated with any certainty but included an additional 3 years prelims for BSC = £80m plus estimate for on street premium costs £40m plus movement to top end of on-street design = £30m.
Note on E27: SMcGarrity: Assumes we'd end up haing to pay them the £14m design costs as per Carlisle 'Explantory Note'
Note on E60: SMcGarrity: Not capable of being estimated with any certainty but included an additional 3 years at £500k per month on top of the Sillver Bullet scenario. Big factor would be the Commercial/DRP costs associated with toughing it out issue by issue.
Note on G19: SMcGarrity: Recon to tie Carlisle offer for 'Part A' as per my email 'HANDOVER - Cost Estimates - Carlisle tie Price' of 7/11.
Note on G43: SMcGarrity: Allowance for market uncertainties in procurement and subsequent retained risk - final amount would be an output from a formal QRA.
Note on G44: SMcGarrity: Recon to Carlisle "Explanatory Note" per my email 'HANDOVER - Cost Estimates - Carlisle tie Price' of 7/11.
Note on G60: SMcGarrity: Aggregate Project Costs assumed materially the same as the term & reprocurement option in aggregate.
Note on H13: SMcGarrity: From BSC revised proposal dated 12/9/10 - BB £215.3m plus Siemens £118.8m to Haymarket only.
Note on H18: SMcGarrity: Draft terms from BSC fall well short of a genuine GMP. Also would need to pick up the pieces on Princes st defects and figure out who is taking responsibility for Princes St. Final amount would be an output from a formal QRA.
Note on H26: SMcGarrity: CAF price including storage costs from BSC revised proposal dated 12/9/10.
Note on H27: SMcGarrity: SDS price from BSC revised proposal dated 12/9/10.
Note on H37: SMcGarrity: Added in the £9m Systems cost from Haymarket to Wav Bridge not included in BSC offer.
Note on J19: SMcGarrity: As estimated by DM at end P6 Cert - see tab included. Will need to be updated to date of termination but on the basis they stopped work in Oct and we're not paying prelims it should not move a lot?
Note on J26: SMcGarrity: Assumed CAF are novated back and we become proud owners of 27 trams.
Note on J31: SMcGarrity: Placemaker - assuming its legal, honest and decent to engage with existing subbies, and CEC are happy with exposure (ie we are not going to canx) - we assume there will be works which it will be good VfM to do works (especially at Depot and other bits off-street) between termination and new procurement.
Note on J37: SMcGarrity: Range of reprocurement costs range up to £300m. Depends of course on final design, packaging, public sector risk, phasing/programme and market conditions. This figure calulated as: Carlisle tie price £241.8m + Carlisle new procurement £93.9m - Value of work done by BSC to date £86.5m - Assumed value of work done between term and new procurement £20m Value of work done by BSC not value to new contractors £25m (c 25%)
Note on J40: SMcGarrity: Assumes best option is we take CAF contract back then lease surplus vehicles (with maintenance) we dont need for Apt to SAS (10 of) for 10 yrs at a yield of 7.5% pa ie £150k per tram per year for 7 years. Take the trams back after 7 years to operate to Newhaven. Pricing subject to proper professional advice and negotiation. Option to sell also a possibility. Both need TS endorsement.
Note on J43: SMcGarrity: Allowance for market uncertainties in procurement and subsequent retained risk. Would also be very sensitive to VE of final design. Final figure would be an output from a formal QRA.
Note on J59: SMcGarrity: See tab for Utilities and other infrastructure.
Note on J60: SMcGarrity: See tab for Project Costs
Note on J61: SMcGarrity: See tab for Project Costs
Note on J67: SMcGarrity: Difference between gross outturn costs under this option and the gross outturn costs under the Pitchfork 3 option @ 75% assumed recoery rate. This estimate to be reviewed by those with a knowledge and experience of litigation outcomes.
Note on L24: SMcGarrity: Highly uncertain what BSC would walk away for - assume here they'd want the bond call back plus something for their trouble. Very hard to prove VfM except against what it avoids (uncertain litigation, protracted uncertainty as to financial outcome)
Note on N32: SMcGarrity: Assumes that if we are doing nothing till litigation is over the cost of required interim reinstatement will be considerably higher.
Note on N37: SMcGarrity: Assume no interim works and that costs go up 7.5% compound over the 2 years.
Note on N40: SMcGarrity: Additional 2 year lease income - this assumes 17 trams doing nothing for a considerable preiod of time.
Note on N61: SMcGarrity: Additional 2 yrs prolongation and escalation - say £5m
Note on N67: SMcGarrity: Assuming our decision to postpone and cost consequences thereof are not help BSCs responsibility???
Note on O33: SMcGarrity: Very uncertain - placemarker only.
Note on O40: SMcGarrity: Assumes 80% recovery on cost
Note on O59: SMcGarrity: Wouldnt do the utilities at Baltic street if you're Canx

## Profile - F
Profile for Termination and Reprocurement
Design and reprocurement
Continuing works/off street
On street to SAS
SAS to Newhaven
[5 empty] | End Litig |  | OFRS to SAS
| to P7 9 Oct 10 | 2011-06-01 | 2011-12-01 | 2012-06-01 | 2012-12-01 | 2013-06-01 | 2013-12-01 | 2014-06-01 | 2014-12-01 | 2015-06-01 | 2015-12-01 | 2016-06-01 | 2016-12-01 | 2017-06-01 | 2017-12-01 | Win litigation | Check
BB+S
Constn Works Price (BB+S) | 65.2 | [14 empty] | 65.2 | 65.2
Existing Change - Princes St | 9.5 | [14 empty] | 9.5 | 9.5
Existing Change - Other | 11.8 | [14 empty] | 11.8 | 11.8
Existing Prolongation | [15 empty] | 0 | 0
Further on-street change and disruption | [15 empty] | 0 | 0
Further allowance for risks and delay | [15 empty] | 0 | 0
Entitlement for work done (BB+S) | 86.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86.5 | 86.5
Certified in advance of work done (BB+S) | 31.9 | [14 empty] | 31.9 | 31.9
Certified to Date (BB+S) | 118.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118.4 | 118.4
Net Accounting accruals/prepayments | -8.4 | 2011-06-01: 8.4 | 0 | 0
Bond call (BB+S) |  | 2011-06-01: -25 | -25 | -25
Settlement Premium | [15 empty] | 0 | 0
Infrastructure (BB+S) | 110 | -16.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93.4 | 93.4
Vehicles (CAF) | 46.4 | 2011-06-01: 12.1 | 58.5 | 58.5
Design Post Novation (SDS) | 5 | [14 empty] | 5 | 5
Total BSC | 161.4 | -4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156.9 | 156.9
Interim Works & Reinstatement
Interim Works during Reprocure |  | 2011-06-01: 20 | 20 | 20
Reinstate/remedials during Reprocure |  | 2011-06-01: 3 | 3 | 3
Reinstatement following cancellation | [16 empty] | 0
Total | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 23
New Procurement Costs
Infrastructure - to SAS |  | 2012-06-01: 20; 2012-12-01: 50; 2013-06-01: 75; 2013-12-01: 50 | 195 | 255
Infrastructure - to FOW |  | 2014-12-01: 10; 2015-06-01: 20; 2015-12-01: 10 | 40 | 0
Infrastructure - to NHN |  | 2016-12-01: 5; 2017-06-01: 10; 2017-12-01: 5 | 20 | 0
Vehicles - Lease / Sale recoveries |  | -0.75 | -0.75 | -0.75 | -0.75 | -0.75 | -0.75 | -0.75 | -0.75 | -0.75 | -0.75 | -0.75 | -0.75 | -0.75 | -0.75 | -10.5 | -10.5
Design |  | 2011-06-01: 10; 2011-12-01: 5 | 15 | 15
Direct Reprocurement Costs | [15 empty] | 0 | 0
Risk allowance on new procurement |  | 2013-12-01: 10; 2015-12-01: 10; 2017-12-01: 5 | 25 | 25
Total New Procurement | 0 | 9.25 | 4.25 | 19.25 | 49.25 | 74.25 | 59.25 | -0.75 | 9.25 | 19.25 | 19.25 | -0.75 | 4.25 | 9.25 | 9.25 | 284.5 | 284.5
Total Infrastructure & vehicles | 161.4 | 27.75 | 4.25 | 19.25 | 49.25 | 74.25 | 59.25 | -0.75 | 9.25 | 19.25 | 19.25 | -0.75 | 4.25 | 9.25 | 9.25 | 464.4 | 464.4
Termination Costs | [16 empty] | 0
Securing sites |  | 2011-06-01: 2 | 2 | 2
Our litigation costs |  | 2011-06-01: 7.5; 2011-12-01: 7.5; 2012-06-01: 7.5; 2012-12-01: 7.5 | 30 | 30
Third party costs |  | 2011-06-01: 5; 2011-12-01: 5 | 10 | 10
BSC Loss of profits | [15 empty] | 0 | 0
BSC Litigation Costs | [15 empty] | 0 | 0
Total Termination Costs | 0 | 14.5 | 12.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 42
Other Costs
Ph1b Payment to BSC | 3.2 | [14 empty] | 3.2 | 3.2
Design Pre Nov incl Ph1b and Utilities | 32.3 | [14 empty] | 32.3 | 32.3
Utilties and Other Infrastructure | 87.6 | 2011-06-01: 1.1; 2014-06-01: 1.2 | 89.9 | 89.9
Project Costs | 70.2 | 2011-06-01: 2.5 | 72.7 | 72.7
Project Costs - Post Termination |  | 2.5071 | 2.6707 | 1.7161 | 1.7161 | 3.3661 | 3.3661 | 0.52596 | 0.52596 | 1.026 | 1.026 | 0.52596 | 0.52596 | 1.026 | 1.026 | 21.5498 | 21.5
Other Costs - Incl Land | 32.5 | 2011-06-01: -0.2 | 32.3 | 32.3
Other Costs | 225.8 | 5.9071 | 2.6707 | 1.7161 | 1.7161 | 3.3661 | 3.3661 | 1.726 | 0.52596 | 1.026 | 1.026 | 0.52596 | 0.52596 | 1.026 | 1.026 | 251.9498 | 251.9
Gross Outturn Costs | 387.2 | 48.1571 | 19.4207 | 28.4661 | 58.4661 | 77.6161 | 62.6161 | 0.97596 | 9.776 | 20.276 | 20.276 | -0.22404 | 4.776 | 10.276 | 10.276 | 758.3498 | 758.3
Recovery 75% of Costs from BSC |  | 2012-12-01: -88.8 | -88.8 | -88.8
Net Outturn Costs | 387.2 | 48.1571 | 19.4207 | 28.4661 | -30.3339 | 77.6161 | 62.6161 | 0.97596 | 9.776 | 20.276 | 20.276 | -0.22404 | 4.776 | 10.276 | 10.276 | 669.5498 | 669.5
Cumulative Funding Req | 387.2 | 435.3571 | 454.7778 | 483.2439 | 452.91 | 530.5261 | 593.1422 | 594.1182 | 603.8941 | 624.1701 | 644.446 | 644.222 | 648.9979 | 659.2739 | 669.5498
Note on I56: SMcGarrity: Baltic St

## Liability P6
[7 empty] | Milestone Payment Certification |  |  | Milestone Payment Difference
| Edinburgh Tram Network | [8 empty] | Certified v Application
Infraco Contract
[6 empty] | Date : | #REF! |  | Date : | #REF!
Milestone Analysis
[6 empty] | Certification Nr : | #REF! |  | Certification Nr : | #REF!
23 September 2010
[6 empty] | Period End : | #REF! |  | Period End : | #REF!
[5 empty] | CERTIFIED |  |  | DIFFERENCE |  |  |  | ACTUAL EARNED VALUE
[5 empty] | Current Cumulative | Previous Cumulative | Period | Current Application | Current Certified | Difference |  | Milestones | Incomplete Milestones | Preliminaries | Change | Total
Preliminaries
00 Mobilisation and Preliminaries
00A Mobilisation
|  | BBUK |  |  | 22600000 | 22600000 | 0 | #REF! | 22600000 | #REF! |  | 0 | 0 | 0 | 0 | 0
|  | Siemens |  |  | 22600000 | 22600000 | 0 | #REF! | 22600000 | #REF! |  | 0 | 0 | 0 | 0 | 0
|  | 00A Preliminaries - BBUK |  |  | 21741298.2356 | 21741298.2356 | 0 | #REF! | 21741298.2356 | #REF! |  | 0 | 0 | 28242666 | 0 | 28242666
|  | 00C Preliminaries - Siemens |  |  | 9348999.5237 | 9348999.5237 | 0 | #REF! | 9348999.5237 | #REF! |  | 0 | 0 | 10841000 | 0 | 10841000
|  | 00D Network Rail Immunisation |  |  | 379421.42 | 379421.42 |  | #REF! | 379421.42 | #REF! |  | 0 | 0 | 379421.42 | 0 | 379421.42
|  | 00E SDS Interface |  |  | 3800000 | 3800000 | 0 | #REF! | 3800000 | #REF! |  | 0 | 0 | 1900000 | 0 | 1900000
|  | 00F Incentivisation |  |  | 0 | 0 | 0 | #REF! | 0 | #REF! |  | 0 | 0 | 0 | 0 | 0
Construction Milestones
01 Newhaven Road to Haymarket
01A Newhaven Road (inc.) to Foot of the Walk (exc.)
|  | BBUK |  |  | 498692.22 | 174346.11 | 324346.11 | #REF! | 498692.22 | #REF! | 1651204 | 498692.22 | 1152511.78 | 0 | 0 | 1651204
|  | Siemens |  |  | 0 | 0 | 0 | #REF! | 0 | #REF!
01B Foot of the Walk (inc.) to McDonald Road (exc.)
|  | BBUK |  |  | 89898.6503 | 89898.6503 | 0 | #REF! | 89898.6503 | #REF! | 315849 | 89898.6503 | 225950.3497 | 0 | 0 | 315849
|  | Siemens |  |  | 0 | 0 | 0 | #REF! | 0 | #REF!
01C McDonald Road (inc.) to Princess Street West (exc.)
|  | BBUK |  |  | 150908.67 | 150908.67 | 0 | #REF! | 150908.67 | #REF! | 76217 | 150908.67 | -74691.67 | 0 | 0 | 76217
|  | Siemens |  |  | 0 | 0 | 0 | #REF! | 0 | #REF!
01D Princes Street (inc.) to Haymarket (exc.)
|  | BBUK |  |  | 1324475.7871 | 1324475.7871 | 0 | #REF! | 1324475.7871 | #REF! | 2409450 | 2175743.8971 | 233706.1029 | 0 | 0 | 2409450
|  | Siemens |  |  | 851268.11 | 851268.11 | 0 | #REF! | 851268.11 | #REF!
02 Haymarket Corridor
|  | BBUK |  |  | 728410.951 | 728410.951 | 0 | #REF! | 728410.951 | #REF! | 979171 | 728410.951 | 250760.049 | 0 | 0 | 979171
|  | Siemens |  |  | 0 | 0 | 0 | #REF! | 0 | #REF!
05 Roseburn Junction to Gogar
05A Roseburn Junction (exc.) to Balgreen Road (inc.)
|  | BBUK |  |  | 209533.53 | 209533.53 | 0 | #REF! | 209533.53 | #REF! | 635036 | 209533.53 | 425502.47 | 0 | 0 | 635036
|  | Siemens |  |  | 0 | 0 | 0 | #REF! | 0 | #REF!
05B Balgreen Road (exc.) to Edinburgh Park (inc.)
|  | BBUK |  |  | 2782537.1738 | 2782537.1738 | 0 | #REF! | 2782537.1738 | #REF! | 6617732 | 5028467.6038 | 1589264.3962 | 0 | 0 | 6617732
|  | Siemens |  |  | 2245930.43 | 2245930.43 | 0 | #REF! | 2245930.43 | #REF!
05C Edinburgh Park (exc.) to Gogarburn (inc.)
|  | BBUK |  |  | 484331.56 | 484331.56 | 0 | #REF! | 484331.56 | #REF! | 1371637 | 484331.56 | 887305.44 | 0 | 0 | 1371637
|  | Siemens |  |  | 0 | 0 | 0 | #REF! | 0 | #REF!
06 Gogar Depot
|  | BBUK |  |  | 5819249.75 | 5633873.42 | 185376.33 | #REF! | 5819249.75 | #REF! | 7818988 | 5819249.75 | 1999738.25 | 0 | 0 | 7818988
|  | Siemens |  |  | 0 | 0 | 0 | #REF! | 0 | #REF!
07 Gogar to Edinburgh Airport
|  | BBUK |  |  | 1129672.68 | 972310.68 | 157362 | #REF! | 1129672.68 | #REF! | 1660972 | 1129672.68 | 531299.32 | 0 | 0 | 1660972
|  | Siemens |  |  | 0 | 0 | 0 | #REF! | 0 | #REF!
CAF
| 08A Tram Supply Contract |  |  |  | 46005858.3982 | 45675608.6482 | 330249.75 | #REF! | 46005858.3982 | #REF! |  | 46005858.3982 | 0 | 0 | 0 | 46005858.3982
Maintenance
Infraco Maintenance Mobilisation
|  | BBUK |  |  | 13000 | 13000 | 0 | #REF! | 13000 | #REF! |  | 267343.8 | 0 | 0 | 0 | 267343.8
|  | Siemens |  |  | 254343.8 | 254343.8 | 0 | #REF! | 254343.8 | #REF!
Tram Maintenance Mobilisation
CAF
Infraco Spare Parts
Infraco
|  |  | Subtotal |  | 143057830.8897 | 142060496.6997 | 997334.19 | #REF! | 143057830.8897 | #REF! | 23536256 | 62588111.7104 | 7221346.4878 | 41363087.42 | 0 | 111172545.6182
Additional Works
| 01 | SDS Application for payment excl Change identified in (2) |  |  | 5438490 | 5325819 | 112671 | #REF! | 5438490 | #REF! |  | 0 | 0 | 0 | 5438490 | 5438490
| 02 | Change Application | [7 empty] | 0
|  | SDS |  |  | 2265678.5 | 2242285.87 | 23392.63 | #REF! | 2265678.5 | #REF! |  | 0 | 0 | 0 | 2265678.5 | 2265678.5
|  | BBUK |  |  | 19489343.17 | 18174763.57 | 1314579.6 | #REF! | 19489343.17 | #REF! |  | 0 | 0 | 0 | 19489343.17 | 19489343.17
|  | Siemens |  |  | 1768309.32 | 1659309.32 | 109000 | #REF! | 1768309.32 | #REF! |  | 0 | 0 | 0 | 1768309.32 | 1768309.32
|  | CAF |  |  | 328471.26 | 328471.26 | 0 | #REF! | 328471.26 | #REF! |  | 0 | 0 | 0 | 328471.26 | 328471.26
| 02 | Value Engineering Not Achieved | [5 empty] | #REF! | 0 | #REF!
|  | Clause 22/65 Changes |  |  | 114177.34 |  | 114177.34 |  |  |  |  | 0 | 0 | 0 | 114177.34 | 114177.34
|  |  | Total |  | 172462300.4797 | 169791145.7197 | 2671154.76 | #REF! | 172348123.1397 | #REF! | 118423802.3215 | 62588111.7104 | 7221346.4878 | 41363087.42 | 29404469.59 | 140577015.2082 | 86538517.05
Summary Information
Preliminaries
|  | BBUK | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Siemens | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Maintenance
|  | BBUK | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Siemens | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | CAF | 3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Construction Milestones
|  | BBUK | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Siemens | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Tram Supply Agreement
|  | CAF | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Change | [16 empty] | 262522
|  | BBUK | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Siemens | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | CAF | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Value Engineering
|  | BBUK | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Design
|  | SDS Application | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | SDS Change | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Totals |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
By Company
|  | BBUK (incl SDS) | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Siemens | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [8 empty] | 125706.49
|  | CAF | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Totals |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
45000
95000
17023
121847
750000
5366
20000
-260973.48
6665
34460
22000
83029
34059
18750
12991
9006972
50000
1565
250000
3931
9000
35000
10000
15000
6500
37036.01
16870.93
15000
25000
2000
1500

## Util & Other Infa
Utilities and other Infrastructure |  | Period 7 1011 Consolidation |  |  |  | Pitchfork 3C Based on P12 0910 AFC
|  | PCB | Approved changes | CAB | P7 AFC | Included in Pitchfork 3c | P12 AFC Excluded | Other Changes | Why exclude reported P12 AFC?
T18 | Total MUDFA / Utilities | 48556163.8399 | 5554917 | 54111080.8399 | 58190955 | 59320000 |  | -1129045
T19.01.26 | Maintenance mobilisation and spare parts | 2795381 | 0 | 2795381 | 2795382 | 2795000
T19.01.34 | Power for comissioning | 1030000 | 0 | 1030000 | 1030000.4444 | 1030000
T19.02.02 | Relocate historic monuments | 42000 | -42000 | 0 | 0
T19.02.03 | Environ. impacts - badgers | 32000 | -2088 | 29912 | 26576.05 | 27000
T19.02.04 | Invasive species | 299917 | -31000 | 268917 | 268277 | 268000
T19.03.01 | Unallocated | 134574 | 0 | 134574 | 111574 |  |  | 111574
T19.03.02 | Set up / mobilisation | 179741 | 0 | 179741 | 179741 |  |  | 179741
T19.03 | Subtotal depot advance works | 5438987 | 0 | 5438987 | 5415378 | 5438000 |  | -22622
T19.06.61 | VE - Marerial recovery / reprocessing - MUDFA | -120000 | 0 | -120000 | -120000 | -120000
T19.06.62 | VE - Reduction in extent of road reinstatement | -116000 | 0 | -116000 | -116000 | -116000
T19.06.63 | VE - Deferred Leasing | -2961000 | 0 | -2961000 | -2961000 | -2961000
T19.06.64 | VE - Network Reinforcement | -1363000 | 0 | -1363000 | -1363000 | -1363000
T19.07.04 | Power - Network reinforcement | 1579674 | 0 | 1579674 | 1579674 | 1580000
T19.07.05 | Ticket machines | 750000 | 0 | 750000 | 750000 | 750000
T19.07.06 | IPR2 contingency | 300000 | 0 | 300000 | 300000 | 300000
T19.07.07 | Traffic signal and UTC | 0 | -38372 | -38372 | 0
T19.07.08 | Murrayfield modifications | 940010 | 223014 | 1163024 | 1104356 | 999000 |  | 105356
T19.07.16 | 0 |  | 0 | 0 | 0
T19.07.10 | Office land rental |  | 209601.37 | 209601.37 | 313499.88 | 313000
T19.07.11 | Leith goods yard |  | 56000.08 | 56000.08 | 79541.0223 | 80000
T19.07.12 | Traffic management design |  | 400000 | 400000 | 400000 | 400000
T19.07.17 | Burnside Road - Construction Costs |  | 1611394 | 1611394 | 1564042.99 | 1564042.99
T19.07.18 | Burnside Road - BAA Costs |  | 349142 | 349142 | 414643.46 | 414643.46
T19.07.19 | Burnside Road - Consultancy Costs |  | 215000 | 215000 | 200097.76 | 200097.76
T19.07.20 | Burnside Road - Other Costs |  | 330000 | 330000 | 246813.08 | 246813.08
T19.07.21 | BAA MUDFA - Construction Costs |  | 445081 | 445081 | 439643.44 |  | 440000 |  | Included in MUDFA AFC
T19.07.22 | BAA MUDFA - BAA Costs |  | 119119 | 119119 | 144119.07 |  | 144000 |  | Included in MUDFA AFC
T19.07.23 | BAA MUDFA - Consultancy Costs |  | 75000 | 75000 | 116793.71 |  | 117000 |  | Included in MUDFA AFC
T19.07.24 | BAA MUDFA - Other Costs |  | 0 | 0 | 0
T19.07.25 | Forth Ports Section 1a |  | 0 | 0 | 0
T19.07.26 | SW Global Resourcing |  | 0 | 0 | 792000 | 560000 |  | 232000
T19.07.27 | Stray Current Monitoring |  | 89596 | 89596 | 156223 | 156000
T19.07.28 | Manhole at Balbirnie Place (Frontline cost) |  | 0 | 0 | 219000 | 45000 |  | 174000
T19.07.29 | SGN Gas main haymarket |  | 0 | 0 | 47687 | 48000
T19.07.30 | Crash Gate 10 |  | 0 | 0 | 175000 | 175000
T19.07.31 | Constitution Street – Mock-up |  | 0 | 0 | 46037.4033 | 46000
T19.07.32 | SGN Gas diversion |  | 302000 | 302000 | 592000 |  | 552000 | 40000 | Included in MUDFA AFC
T19.07.33 | MUDFA scoped side entry manholes |  | 0 | 0 | 616043 |  | 616000 |  | Included in MUDFA AFC
T19.07.34 | Power network Reinforcement |  | 0 | 0 | 0
T19.07.35 | Section 1a Utilities |  | 3099374 | 3099374 | 3399337.0585 | 3350000 |  | 49337.0585
T19.07.36 | Clancy Docwra Utilities Works |  | 1454000 | 1454000 | 4882963 |  | 2122000 | 2760963 | Included in MUDFA AFC
T19.07.37 | Section 5C Edinburgh Park Clancy |  | 54284 | 54284 | 256957 |  |  | 256957
T19.07.38 | Mass Barier Costs |  | 200000 | 200000 | 401000 | 200000 |  | 201000
T19.07.39 | Baltic Street |  | 12739 | 12739 | 1200000 |  |  | 1200000
T19.07.40 | South Gyle - Sewer Diversion |  | 892027 | 892027 | 892207 |  |  | 892207
T19.07.41 | Visirail / Rubber Kerbs |  | 678282 | 678282 | 773600 |  |  | 773600
T19.07.42 | SUC Costs - from MUDFA |  | 782500 | 782500 | 650000 |  |  | 650000
T19.07.43 | SUC Betterment - from MUDFA |  | -458309 | -458309 | -380400 |  |  | -380400
T19.07.44 | Grontmij design novation section 7 BAA |  | 80000 | 80000 | 0
T19.07.45 | Trial Holes S. Gyle |  | 0 | 0 | 70000 |  |  | 70000
T19.07.46 | Bus Tracker Work |  | 0 | 0 | 45000 |  |  | 45000
T19.07.47 | POL HA Temp Retention Works |  | 0 | 0 | 100000 |  |  | 100000
T19.07.09 | Fastlink alternative |  | 529477 | 529477 | 549000 |  | 549000 |  | Utilised Infraco Prov sum - avoid double count
T19.07.13 | Ancient monuments |  | 95700 | 95700 | 174500 |  | 175000 |  | Utilised Infraco Prov sum - avoid double count
T19.07.14 | TMi cycle integration study |  | 17700 | 17700 | 19657 |  | 20000 |  | Utilised Infraco Prov sum - avoid double count
T19.07.15 | Siemens out of hours monitoring |  | 100000 | 100000 | 100000 |  | 100000 |  | Utilised Infraco Prov sum - avoid double count
T19 | Total Infraco | 8962284 | 11849261.45 | 20811545.45 | 28697964.3685 | 16425597.29 | 4835000 | 7438713.0585
T999 | Total | 57518447.8399 | 17404178.45 | 74922626.2899 | 86888919.3685 | 75745597.29 | 4835000 | 6309668.0585
|  | W/Off tax VE item |  |  | 2961000 | 2961000
[5 empty] | 89849919.3685 | 78706597.29

## Project Costs
Pitchfork 2 - Project Costs
Design and re-procurement
Continuing works/off street
On street to SAS
On street remaining
|  |  | Extract from P7 Consolidation | [7 empty] | To term at end Dec |  | Post termination in the Terminate & Reprocure Option
|  |  | Cum COWD | P7 COWD | PCB | App'd changes | CAB | P7 AFC | Option 3C AFC |  | F'cast to P10 31/12 | Cum to terminate | 6m to Jun 11 | 6m to Dec 11 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | Post terminate
T01.01 | Project management Staff Costs |  | 28242944 | 420884.8065 | 26697669.9218 | 523193.5343 | 27220863.4561 | 35244468.8207 | 36795388 |  | 1262654.4195 | 29505598.4195 | 1003500 | 1170750 | 2174250 | 2174250 | 681460 | 681460 | 681460 | 681460 | 9248590
T01.02 | Recruitment Fees |  | 430135 | 0 | 466202.6166 | -0.02 | 466202.5966 | 466204.3333 | 466202.9 |  |  | 430135 | [8 empty] | 0
T01.03 | Travel & Subsistence / Conference |  | 328001.94 | 2886.94 | 356214.2 | -0.44462 | 356213.7554 | 366158.94 | 366158 |  | 8660.82 | 336662.76 | [8 empty] | 0
T01.04 | Central Overheads |  | 4946800 | 55957 | 5580828.4493 | 0.38 | 5580828.8293 | 5595423 | 5595422.222 |  | 167871 | 5114671 | 167871 | 195849.5 | 363720.5 | 363720.5 | 72744.1 | 72744.1 | 72744.1 | 72744.1 | 1382137.9
T01.05 | IT & Software Costs / fitout |  | 3004237 | 33988 | 3109074.5062 | 0.27308 | 3109074.7792 | 4241492 | 3635042.8767 |  | 101964 | 3106201 | 101964 | 118958 | 220922 | 220922 | 44184.4 | 44184.4 | 44184.4 | 44184.4 | 839503.6
T01.06 | Citypoint - rent,rates,s/c |  | 2554822.766 | 48838.766 | 2171872.6414 | -0.1759 | 2171872.4655 | 3465481.5003 | 3481507.5914 |  | 146516.298 | 2701339.064 | 293032.596 | 170935.681 | 317451.979 | 317451.979 | 158725.9895 | 158725.9895 | 158725.9895 | 158725.9895 | 1733776.1928
T01.08 | Short Term Contractors |  | 196804 | 0 | 196804 | 0 | 196804 | 196804 | 196804 |  |  | 196804 | [8 empty] | 0
T01.09 | City Point Overheads |  | 25271.09 | 0 | 25270.8462 | 0 | 25270.8462 | 25271.09 | 25270.8262 |  |  | 25271.09 | [8 empty] | 0
T01.10 | Active Risk Manager |  | 83666 | 0 | 83665 | 0 | 83665 | 83666 | 83665 |  |  | 83666 | [8 empty] | 0
T01.11 | Archaeological supervisor - Gogar works |  | 153992.9103 | 0 | 267879 | -82646.11 | 185232.89 | 247730.9103 | 251487.9103 |  |  | 153992.9103 | [8 empty] | 0
T01.13 | Archaeology - Non Gogar |  | 334183 | 0 | 0 | 642742.2423 | 642742.2423 | 580469 | 552454.2838 |  |  | 334183 | [8 empty] | 0
T01.14 | DRP Costs |  | 3541491.43 | 198679.43 | 0 | 2985327 | 2985327 | 3999809.43 | 2132505.93 |  | 458318 | 3999809.43 | [8 empty] | 0
T01.15 | Tax Planning / Governance Costs (Non DLA) |  | 21960 | 0 | 0 | 0 | 0 | 301816 | 301816 |  |  | 21960 |  |  |  | 300000 |  |  |  |  | 300000
T01 | Total tie PM costs |  | 43864309.1362 | 761234.9425 | 38955481.1814 | 4068616.6792 | 43024097.8606 | 54814795.0246 | 53883725.5403 |  | 2145984.5375 | 46010293.6737 | 1566367.596 | 1656493.181 | 3076344.479 | 3376344.479 | 957114.4895 | 957114.4895 | 957114.4895 | 957114.4895 | 13504007.6928
T02 | Total DPOF |  | 2563732.16 | 16911.16 | 7631160.25 | 0 | 7631160.25 | 7631160.2488 | 7631159.7988 |  | 50733.48 | 2614465.64 | 101466.96 | 118378.12 |  | 3000000 |  | 1000000 |  | 1000000 | 5219845.08
T03.01-19 | DLA |  | 3443014.95 | 10900.5 | 2862498.72 | 392235.1 | 3254733.82 | 3554224.95 | 3544591.19 |  | 32701.5 | 3475716.45
T03.20-35 | Subtotal D&W |  | 2808403 | 2436 | 2922353.677 | -110751 | 2811602.677 | 2852731 | 2730832 |  | 7308 | 2815711
T03 | Total LEGALS |  | 6251417.95 | 13336.5 | 5784852.397 | 281484.1 | 6066336.497 | 6406955.95 | 6275423.19 |  | 40009.5 | 6291427.45 | 500000 | 500000 | [6 empty] | 1000000
T06.01-03 | Subtotal TSS |  | 10321631 | 31251 | 9507939.4403 | 1008900.35 | 10516839.7903 | 11021365.08 | 10652287 |  | 93753 | 10415384
T06.03a | Subtotal CEC |  | 2016008 | 41669 | 1168277 | 1011312.49 | 2179589.49 | 2266022 | 2184381.93 |  | 125007 | 2141015
T06 | Total TSS and CEC |  | 12337639 | 72920 | 10676216.4403 | 2020212.84 | 12696429.2803 | 13287387.08 | 12836668.93 |  | 218760 | 12556399 | 218760 | 255220 | 94796 | 94796 | 94796 | 94796 | 94796 | 94796 | 1042756
T12.01-12,23-40 | Subtotal Communications |  | 2026355.67 | 19146 | 1901845.7 | 272968.3077 | 2174814.0077 | 2424819.67 | 2410730.67 |  | 57438 | 2083793.67
T12.13-22 | Subtotal Stakeholder |  | 690193.3 | 937 | 624370 | 112662 | 737032 | 741507.3 | 723505.54 |  | 2811 | 693004.3
T12 | Total COMMS / MARKETING |  | 2716548.97 | 20083 | 2526215.7 | 385630.3077 | 2911846.0077 | 3166326.97 | 3134236.21 |  | 60249 | 2776797.97 | 120498 | 140581 | 261079 | 261079 |  |  |  |  | 783237
T13 | Total TEL |  | 2433101 | 10274 | 2723133 | 74100 | 2797233 | 3046117.6429 | 3720365 |  | 30822 | 2463923 | [8 empty] | 0
T999 | Total |  | 70166748.2163 | 894759.6025 | 68297058.9687 | 6830043.9269 | 75127102.8956 | 88352742.9163 | 87481578.6692 |  | 2546558.5175 | 72713306.7337 | 2507092.556 | 2670672.301 | 3432219.479 | 6732219.479 | 1051910.4895 | 2051910.4895 | 1051910.4895 | 2051910.4895 | 21549845.7728
|  | Staff Costs | Count
Payroll:
|  | Finance/ICT | 10 | 44000 | [8 empty] | 33000 | 33000 | 33000 | 33000 | 14520 | 14520 | 14520 | 14520 | ) | Simple modelling based on % of current costs. Assumes comms/stakeholder costs all part of operating costs from OFRS to SAS from which further step-down in resources allocated to Capex. Implicitly assumes no salary increments or bonus throughout.
|  | Comms/Stakeholder | 12 | 47000 | [8 empty] | 23500 | 23500 | 23500 | 23500 |  |  |  |  | )
|  | Exec/Secretarial/Admin | 8 | 36000 | [8 empty] | 36000 | 36000 | 36000 | 36000 | 9000 | 9000 | 9000 | 9000 | )
|  | Project | 46 | 236000 | [8 empty] | 59000 | 59000 | 59000 | 59000 | 23600 | 23600 | 23600 | 23600 | )
|  |  | 76 | 363000 | [8 empty] | 151500 | 151500 | 151500 | 151500 | 47120 | 47120 | 47120 | 47120
"Contractors":
|  | Comms/Stakeholder | 1 | 5000 | [8 empty] | 2500 | 2500 | 2500 | 2500
|  | Project | 10 | 53000 | [8 empty] | 13250 | 13250 | 13250 | 13250 | 5300 | 5300 | 5300 | 5300
|  |  | 11 | 58000 | [8 empty] | 15750 | 15750 | 15750 | 15750 | 5300 | 5300 | 5300 | 5300
|  | Per 4wk period | 87 | 421000 | [8 empty] | 167250 | 167250 | 167250 | 167250 | 52420 | 52420 | 52420 | 52420
Note on L34: Forecasts are to Feb 12. Included in Pitchfork 3C = £87.5m plus £0.5m per month for prolongation to Oct 2012 = £91.5m.
Note on O20: Assumed we burn all AFC for this prior to Dec. Professional fees related to post termination BSC matters included in the provision for Assumed we burn all AFC for this prior to Dec. Professional fees related to post termination BSC matters included in the provision for litigiation costs £30m
Note on T4: OFRS on section from Airport to SAS at end of 2013.
Note on Y9: Preliminary view of the post termination staff profile below - much smaller project team. it will be wrong. Needs to be based on a considered manpower plan which reflects inter-alia: -PM philosophy -Site supervision appropriate to contracting method -Proper integration/efficiencies with CEC and Operational Readiness budgets No allowance for any redundancy costs!
Note on Y12: Proportional to staff costs (kind of)
Note on Y13: Proportional to staff costs (kind-of). At some stage the joined up ICT strategy as between tie, LB and Tram operations needs to swim into focus.
Note on Y14: Assumes we all fit onto CP2 from July 2011 (and therefore that lease on CP1 extended till then) following which we occupy CP2 or equivalent space till OFRS to SAS in Dec 13. Thereafter occupancy costs half again for the smaller project team but they could be zero depending on overall accomodation needs of tie/TEL/LB/CEC
Note on Y21: Depends entirely on bus/tram business integration happening.
Note on Y23: Assumes phased spending of the existing operational readiness budget with bulk in 20134 for a OFRS Apt to SAS in 2013.
Note on Y26: This is the cost of professional services (mostly lawyers) to put the new procurements in place.
Note on Y29: CEC costs to be part of joined up manpower planning.
Note on Y32: Becomes part of operating costs from OFRS to SAS
Note on Y33: Mostly LB recharges - assumes A Richards is in our costs going forward. Cant justify any other recharges of LB management time myself.