## Summary
Utilities - Total Final Cost Reconciliation
As at the end of Period 13 2009/10 - £k |  |  |  |  | Analysis at end P12 |  |  | Analysis end P13
(A) Category Relating to Original MUDFA contract | COWD | PCB | Budget Change | Budget Transfers | CAB P12 | P12 AFC |  | CAB P13 | P13 AFC
MUDFA Contract | 58624.5 | 42226.5 | 16731.24 | -6025.238 | 52932.502 | 59925.5 |  | 51410.5 | 58464.5
Less: Depot Excavation (T19.03) - CUS element only | 5311.5 | 5311.5 | 0 |  | 5311.5 | 5311.5 | -1 | 5311.5 | 5311.5
MUDFA (incl in T18) | 53313 | 36915 | 16731.24 | -6025.238 | 47621.002 | 54614 |  | 46099 | 53153 | -8515
Other T18 (incl betterment) | 9381 | 11627 | -3135 |  | 8492 | 4678 |  | 8023 | 4508
MUDFA PM Cost line | 28 | 13 | 0 |  | 13 | 28 |  | 13 | 28
T18 Total | 62722 | 48555 | 13596.24 | -6025.238 | 56126.002 | 59320 |  | 54135 | 57689
(B) Utilities Delivered By BSC | COWD | PCB | Budget Change | Budget Transfers | CAB | P12 AFC |  | CAB P13 | P13 AFC
Sewer at South Gyle Access Bridge (INTC17) | 162.528 | 0 |  | 433.158 | 433.158 | 1012.528 |  | 433.158 | 1012.528
MUDFA section 1A Utilities Diversions (INTC86) | 0 | 0 |  | 750 | 750 | 750 |  | 750 | 750
Manhole Construction MUDFA works | 252 | 0 |  | 616.43 | 616.43 | 616.43 |  | 616.43 | 616.43
SGN Gas Diversion | 123 | 0 |  | 0 | 0 | 552 |  | 0 | 552
Other | 441 | 0 |  | 683 | 683 | 1259.667 | -4 | 694.922 | 1251.495
(B) Sub-total Utilities Delivered By BSC | 978.528 | 0 | 0 | 2482.588 | 2482.588 | 4190.625 | -4 | 2494.51 | 4182.453
(C) Utilities Delivered By Others (managed through Infraco team) | COWD | PCB | Budget Change | Budget Transfers | CAB P12 | P12 AFC |  | CAB P13 | P13 AFC
MUDFA works section 1A (Farrans) - T19.07.35 | 703 | 0 | 0 | 2539 | 2539 | 3200 |  | 2539 | 3200
MUDFA works section 1A (C4/Betterment) - T19.07.35 | 0 | 0 | 0 |  | 0 | 150 |  | 0 | 150
Burnside Road Utilities (Farrans) - T19.07.21-24 | 701 | 0 | 64.2 | 575 | 639.2 | 701 | -2 | 639 | 701
Clancy Docwra Utilities - T19.07.36 | 1099 | 0 | -100 |  | -100 | 2122 | -3 | 1354 | 2578
Additional cost of Baltic Street (excluding Clancy budget) | [6 empty] | -6 | 0 | 1200
MUDFA works Mass Barrier - T19.07.38 | 50 | 0 | 0 |  | 0 | 200 |  | 200 | 300
Other MUDFA costs (various SUC transferred/ Grontmij) - T19.07.44 | 0 | 0 | 0 | 80 | 80 | 80 |  | 80 | 0
SUC costs and betterment transferred MUDFA > Infraco (T19.07.42/43) | [7 empty] | 347.5 | 270
'Other' Budget Transfers MUDFA | 348.811 | 0 |  | 348.811 | 348.811 | 348.811 | -5 | 348.811 | 348.811
(C) Sub-total Utilities Delivered By Others | 2901.811 | 0 | -35.8 | 3542.811 | 3507.011 | 6801.811 |  | 5508.311 | 8747.811
Total Final Cost for Utilities (A+B+C) | 66602.339 | 48555 | 13560.44 | 0.161 | 62115.601 | 70312.436 |  | 62137.821 | 70619.264
note:
(1): T19.03 Depot excavation costs are cost and budget £5,438k. The CUS Certificate element of this is £5,311.5k
(2): Burnside Road Construction savings forecast, offsetting overspend on Utilities
(3) erroneous journal posted for Clancy Utilities of -£100k to POLHA +£100k.
(4) 'Other' value £1,260k AFC is the P12 QS view for MUDFA classifications from 'Other backup' tab. COWD from change schedule P12
(5) 'Other' Non BSC transfers relate to utilities costs incurred already - mainly through insurance (see Non BSC Other tab)
(6) Baltic Street £1592k taken to change panel as 'additional costs'. Some budget already in Clancy works. Initial view of QS was £1.2m increment

## Change backup
Approved Changes - MUDFA Costs
Period | Description | Change Number | Account Code | Account Desc | AFC | Culm CAB | Change Category | Dr/(Cr) Code | Value
Period end | [5 empty] | 48556163.8399 | PCB
08/09 - 07 | MUDFA - A8 Sewer diversion at Gogar | COP030 | T18.01.16 | Section 6 | 1370000 | 49926163.8399 | Drawdown
08/09 - 11 | MUDFA prelim risk drawdown | COP050 | T18.01.02 | Contract prelims | 1069000 | 50995163.8399 | Drawdown
08/09 - 11 | Risk Drawdown for MUDFA scope claim | COP053 | T18.01.19 | Variations | 1700000 | 52695163.8399 | Drawdown
08/09 - 11 | Budget transfer MUDFA related insurance claims paid to date | COP055 | T18.01.18 | Unallocated to section | -52821 | 52642342.8399 | Transfer - Insurance
08/09 - 11 | Communications tram advisor funding | COP056 | T18.01.18 | Unallocated to section | -80000 | 52562342.8399 | Transfer - PM Costs
08/09 - 11 | Souters completion of MUDFA scope | COP060 | T18.01.18 | Unallocated to section | -58726 | 52503616.8399 | Transfer - Non Infraco
08/09 - 12 | Scope transfer from MUDFA to Infraco | COP057 | T18.01.18 | Unallocated to section | -1698592 | 50805024.8399 | Transfer - Infraco
08/09 - 12 | MUDFA / SDS £50k transfer for design of 800mm watermain | COP061 | T18.01.18 | Unallocated to section | -50000 | 50755024.8399 | Transfer - SDS
08/09 - 13 | Track monitoring of NR infrastructure at Gogar depot | COP076 | T18.01.18 | Unallocated to section | -4673 | 50750351.8399 | Transfer - Network Rail
08/09 - 13 | MUDFA Risk Drawdown 1084/1085 | COP074 | T18.01.02 | Contract prelims | 2194677 | 52945028.8399 | Drawdown
08/09 - 13 | MUDFA Risk Drawdown 1084/1085 | COP074 | T18.01.03 | Section 1a | -807547 | 52137481.8399 | Drawdown
08/09 - 13 | MUDFA Risk Drawdown 1084/1085 | COP074 | T18.01.04 | Section 1b | 100560 | 52238041.8399 | Drawdown
08/09 - 13 | MUDFA Risk Drawdown 1084/1085 | COP074 | T18.01.05 | Section 1c | 780495 | 53018536.8399 | Drawdown
08/09 - 13 | MUDFA Risk Drawdown 1084/1085 | COP074 | T18.01.06 | Section 1d | -290451 | 52728085.8399 | Drawdown
08/09 - 13 | MUDFA Risk Drawdown 1084/1085 | COP074 | T18.01.07 | Section 2 | -1209032 | 51519053.8399 | Drawdown
08/09 - 13 | MUDFA Risk Drawdown 1084/1085 | COP074 | T18.01.14 | Section 5b | 601934 | 52120987.8399 | Drawdown
08/09 - 13 | MUDFA Risk Drawdown 1084/1085 | COP074 | T18.01.16 | Section 6 | 360466 | 52481453.8399 | Drawdown
08/09 - 13 | MUDFA Risk Drawdown 1084/1085 | COP074 | T18.01.17 | Section 7 | -1800647 | 50680806.8399 | Drawdown
08/09 - 13 | MUDFA Risk Drawdown 1084/1085 | COP074 | T18.01.18 | Unallocated to section | 2021584 | 52702390.8399 | Drawdown
08/09 - 13 | MUDFA Risk Drawdown 1084/1085 | COP074 | T18.01.19 | Variations | 959716 | 53662106.8399 | Drawdown
08/09 - 13 | MUDFA Risk Drawdown 1084/1085 | COP074 | T18.01.22 | Transfer to / from Infraco | -125000 | 53537106.8399 | Drawdown
08/09 - 13 | MUDFA Risk Drawdown 1084/1085 | COP074 | T18.02.18 | Unallocated to section | -1753755 | 51783351.8399 | Drawdown
08/09 - 13 | Budget transfer MUDFA related insurance claims paid to date | COP080 | T18.01.18 | Unallocated to section | -31502 | 51751849.8399 | Transfer - Insurance
09/10 - 01 | MUDFA risk drawdown | COP087 | T18.01.18 | Unallocated to section | 1643346 | 53395195.8399 | Drawdown
09/10 - 02 | Transfer from MUDFA to Infraco | COP078 | T18.01.18 | Unallocated to section | -57850 | 53337345.8399 | Transfer - Infraco
09/10 - 05 | Mudfa Risk Drawdown - ID 139 and 343 | COP114 | T18.01.18 | Unallocated to section | 6761000 | 60098345.8399 | Drawdown
09/10 - 07 | Burnside Road - Farrans | COP162 | T18.02.22 | Transfer to infraco | -575000 | 59523345.8399 | Transfer - Non Infraco | T19.07.21 | 639200 | Non-Inf works | £64,200 from contingency
09/10 - 07 | Mudfa scope/budget transfer | COP178 | T18.02.18 | Unallocated to section | -725989 | 58797356.8399 | Transfer - Infraco | T19.01.27 | 725989 | Infraco Variations
09/10 - 08 | Mudfa transfter section 1A | COP180 | T18.01.03 | Section 1a | -2539000 | 56258356.8399 | Transfer - Non Infraco | T19.07.35 | 2539000 | Non-Inf changes
09/10 - 08 | Mudfa claims transfer | COP181 | T18.01.18 | Unallocated to section | -45845 | 56212511.8399 | Transfer - Insurance | T17.05 | 45845 | Claims Recoverable
09/10 - 09 | Design - MUDFA Phase2 800mm Water Main at Depot (Budget Reconciliation) | COP214 | T18.01.01 | Pre-construction Services | 3278 | 56215789.8399 | Transfer - Internal
09/10 - 09 | Design - MUDFA Phase2 800mm Water Main at Depot (Budget Reconciliation) | COP214 | T18.01.18 | Unallocated to section | -3278 | 56212511.8399 | Transfer - Internal
09/10 - 11 | Mudfa Claims Transfer | COP231 | T18.01.18 | Unallocated to section | -25244 | 56187267.8399 | Transfer - Insurance | T17.05 | 25244 | Claims Recoverable
09/10 - 11 | Existing Services (CW/Th) A8 Underpass | COP234 | T18.01.15 | Section 5c | 20324 | 56207591.8399 | Drawdown | T44.02 | -20324 | Contingency
09/10 - 12 | Grontmij design novation section 7 BAA | COP249 | T18.02.18 | Unallocated to section | -80000 | 56127591.8399 | Transfer - Non Infraco | T19.07.44 | 80000 | Infraco Variations
7571428
[6 empty] | 13596670 | Drawdown
[6 empty] | -2482431 | Transfer - Infraco
[6 empty] | -155412 | Transfer - Insurance
[6 empty] | 0 | Transfer - Internal
[6 empty] | -4673 | Transfer - Network Rail
[6 empty] | -3252726 | Transfer - Non Infraco
[6 empty] | -80000 | Transfer - PM Costs
[6 empty] | -50000 | Transfer - SDS
[6 empty] | 7571428 | Total

## BSC delivered AFC
Client/ Other Risk Analysis
INTC No | Description | Description | Further Reason | Await Estimate | Estimated Final Cost | Disputed value (quantum) | Disputed Value (principle) | External Funding | Tramco | MUDFA | Prov sums | book versus risk item | Contingency/other | Total | Risk Reference | P3 09/10 QS View | P9 09/10 QS View | P12 09/10 QS View | Risk Drawn Down | COP Reference | Comments | COWD at P12 |  |  |  |  | Change order reference
| Utility Diversions (Outwith MUDFA Scope) | Other | Additional Utility Diversions | [13 empty] | 2500000 | 2500000 |  |  | Further anticipated Utility diversions over and above MUDFA trf scope (Leith Walk)? |  | 2 |  | Hilton Hotel Car Park
17 | Sewer at South Gyle Access Bridge | MUDFA | S Gyle Access Bridge | [12 empty] | 150000 | 1000000 | 850000 | 350000 |  | Internal scope transfer from MUDFA to Infraco |  | 17 |  | Sewer at South Gyle Access Bridge | 83158 | COP116a & COP057
17 | Sewer at South Gyle Access Bridge | MUDFA | S Gyle Access Bridge | [12 empty] | 162528 | 162528 | 162528 | 83158 |  | Internal scope transfer from MUDFA to Infraco |  | 86 |  | MUDFA Transfer of Utilities Diversions Section 1A, 1B, 1C, 1D | 750000 | COP057
86 | MUDFA Transfer of Utilities Diversions Section 1A, 1B, 1C, 1D | MUDFA | Other MUDFA | [12 empty] | 750000 | 750000 | 750000 | 750000 |  | Internal scope transfer from MUDFA to Infraco |  | 44 |  | Amendements to Ocean Terminal
| Manhole Construction (MUDFA Works) | MUDFA | Manholes | [13 empty] | 616043 | 616043 | 616043 |  | Internal scope transfer from MUDFA to Infraco |  | 42 | 42 | SDS Delay to ravelston Tramstop | 2409 | COP106
269 | Instructions arising from Trackform Development Workshop | Other | Development Workshop | [12 empty] | 371058 | 371058 | 371058 | 371058 |  | SDS Trackform development workshop attendance |  | 197 |  | Cyclepath near gyle tramstop | 11700 | COP142
| SGN Gas Diversion - A8 Underpass | MUDFA | SGN Diversion | [12 empty] | 302000 | 302000 | 302000 |  |  | Change in Piling works location on drawing amended SGN Gas Diversion at Gogar |  | 144 |  | Land Drain encountered in pastured areas
| SGN Gas Diversion - Culvert | MUDFA | SGN Diversion | [12 empty] | 250000 | 250000 | 250000 |  |  | Change in Piling works location on drawing amended SGN Gas Diversion at Gogar |  | 347 |  | Section 1D - Traffic Flow and Remodel at Lothian Road Junction
242 | TRO Presentations by SDS at Public Meetings | Other | Traffic Management | [12 empty] | 20000 | 23480 | 234380 |  |  | Traffic management - out by a factor of 10??? |  | 244 |  | Building Fixing Owner Agreements
78 | Alterations to design of Edinburgh Airport | Client | Airport | [12 empty] | 200000 | 200000 | 200000 |  |  | BAA driven costs increase - change in design |  | 268 |  | Scottish Power Diversion - Gogar Roundabout | 14617 | COP057 & COP178
78 | Alterations to design of Edinburgh Airport | Client | Airport | [12 empty] | 48620 | 48174 | 48174 | 48174 |  | BAA driven costs increases |  |  |  | OLE Development Workshop
79 | Haymarket Junction Re-Design | Client | CEC Planning | [12 empty] | 200000 | 200000 | 200000 |  |  | CEC planning changes to Haymarket junction due to H&S requirements??? |  | 171 | 73 | Contract with Faber Maunsell for Transyt & Linsig Modelling Assessments
79 | Haymarket Junction Re-Design | Client | CEC Planning | [12 empty] | 53856 | 51722 | 51722 | 51722 |  |  |  | 451 |  | Stage E Landscape Drawings
197 | Cyclepath near gyle tramstop | Client | CEC Planning | [12 empty] | 200000 | 200000 | 200000 |  |  | CEC planning changes to cycleways due to change in LOD |  | 81 |  | CEC requested using 42 watt pit lamp (Bat Lighting)
197 | Cyclepath near gyle tramstop | Client | CEC Planning | [12 empty] | 12146 | 11700 | 11700 | 11700 |  |  |  | 372 |  | Utility Diversion 5A/SP/D/08 | 25000 | COP178
342 | Section 5C - Edinburgh Park Private Utilities | MUDFA | Other MUDFA | [12 empty] | 15000 | 247263 | 185000 | 161022 |  | Change in design scope to account for EP private utilities |  | 21 | 2 | Asbestos work at CAH | 5268 | COP062
138 | Design the piled foundations to the Water of Leith Bridge to avoid the existing 950 x 1200mm egg shaped combined sewer | Client | CEC Planning | [12 empty] | 50000 | 150000 | 150000 |  |  | Change to Piling location of design |  | 364 | MUDFA | Manhole at Balbirnie Place (Frontline cost) | 45000 | COP178
138 | Redesign Water of Leith Bridge Foundations | Client | CEC Planning | [12 empty] | 33567 | 32068 | 32068 | 32068 |  |  |  | 60 |  | Gogar Bridge Sewer Diversion
208 | Christmas Embargo Leith Walk | Client | CEC Planning | [12 empty] | 125000 | 150000 | 150000 |  |  | Additional costs anticipated due to CEC Embargo enforecement |  | 369 |  | Existing Services A8 Underpass Phase 1
277 | Airport Canopy tie in options | Client | Airport | [13 empty] | 150000 | 150000 |  |  | BAA driven costs increases |  | 329 |  | Section 1B - Breakout Foamed Concrete Backfill
277 | Airport Canopy tie in options | Client | Airport | [12 empty] | 50428 | 49982 | 49982 | 49982 |  | BAA driven costs increases |  | 122 |  | Delay in receipt of CEC prior approval Sections 1A1 & 1A2
336 | Consortium Office (see INTC 18) | Other | Various | [14 empty] | 150000 |  |  | Office costs for Consortium - Edinburgh Park |  | 275 |  | EAL Tramstop - BAA Interface
| Removal of Phone Boxes / Utility Diversions | MUDFA | Other MUDFA | [12 empty] | 150000 | 150000 | 150000 |  |  |  |  | 365 |  | Wider Area Fly P&R Survey
198 | Gogar Roundabout Lighting | Client | CEC Planning | [12 empty] | 145000 | 145000 | 145000 |  |  | CEC lighting requirements at Gogar |  | 310 |  | Gogar Landfill Scottish Water Utility Diversion
198 | Gogar Roundabout Lighting | Client | CEC Planning | [12 empty] | 4985 | 4539 | 4539 | 4539 |  |  |  | 419 |  | Replace MASS Barrier at St Andrews Square | 22897 | COP130
67 | Provide second access stair, Murrayfield Tramstop | Client | CEC Planning | [12 empty] | 125000 | 125000 | 125000 |  |  | CEC developement requirement for second staircase |  | 52 | 7 | Utility Diversions - Section 5B | 75694 | COP057
67 | Provide second access stair, Murrayfield Tramstop | Client | CEC Planning | [12 empty] | 32648 | 32648 | 32202 |  |  |  |  | 383 |  | Princes Street Rhino Barrier
267 | Scottish Water Diversion - Gogar Roundabout | MUDFA | Gogar Roundabout | [12 empty] | 116553 | 116553 | 116553 | 116553 |  | Internal scope transfer from MUDFA to Infraco |  | 172
53 | Utility Diversions - Section 5C (Provisional Sum - Watermain Diversion) | MUDFA | Other MUDFA | [12 empty] | 110000 | 110000 | 110000 | 110000 |  | Internal scope transfer from MUDFA to Infraco |  | 336 |  | Consortium Office (see INTC 18)
53 | Utility Diversions - Section 5C | MUDFA | Other MUDFA | [12 empty] | 33723 | 33723 | 39218 | 33723 |  | Internal scope transfer from MUDFA to Infraco |  |  |  | Removal of Phone Boxes / Utility Diversions
89 | Balfour Street Crossing | Client | Other | [12 empty] | 100000 | 100000 | 100000 |  |  | CEC change in Pedestrian crossing design at Balfour Street |  | 143
52 | Utility Diversions - Section 5B | MUDFA | Other MUDFA | [12 empty] | 75694 | 75694 | 88027 | 75694 |  | Internal scope transfer from MUDFA to Infraco |  | 208 |  | Christmas Embargo Leith Walk
52 | Allow - Provisional Sums | MUDFA | Other MUDFA | [12 empty] | 25000 | 44141 | 44141 | 44141 |  | Internal scope transfer from MUDFA to Infraco |  | 277 |  | Airport Canopy tie in options
383 | Princes Street Rhino Barrier | Client | Traffic Management | [12 empty] | 80000 | 80000 | 80000 |  |  | Costs potentially included in PSSA ??? |  | 381 |  | Charlotte Square West End - On Parking
51 | Utility Diversions - Section 5A | MUDFA | Other MUDFA | [12 empty] | 64192 | 64192 | 75489 | 64192 |  | Internal scope transfer from MUDFA to Infraco |  | 342 |  | Section 5C - Edinburgh Park Private Utilities
51 | Allow - Provisional Sums | MUDFA | Other MUDFA | [12 empty] | 25000 | 44140 | 44140 | 44140 |  | Internal scope transfer from MUDFA to Infraco |  | 138
281 | Revised Proposals for Cathedral Lane Substation | Client | CEC Planning | [12 empty] | 75000 | 75000 | 75000 |  |  |  |  | 284 |  | Russell Road Retaining Wall - Options Report
310 | Gogar Landfill Scottish Water Utility Diversion | MUDFA | Other MUDFA | [13 empty] | 75000 | 75000 |  |  |  |  | 89 |  | Balfour Street Crossing | 8796 | COP122a
310 | Gogar Landfill Scottish Water Utility Diversion | MUDFA | Other MUDFA | [12 empty] | 35000 | 23195 | 23195 |  |  |  |  | 436 |  | Pedestrian disruptiuon on Lothian Road
268 | Scottish Power Diversion - Gogar Roundabout | MUDFA | Gogar Roundabout | [12 empty] | 14617 | 14617 | 70163 | 14617 |  | Internal scope transfer from MUDFA to Infraco |  | 360 | 54 | Alteration of Design at Forth Ports Road 8
| OLE Development Workshop | Other | Development Workshop | [12 empty] | 70000 | 70000 | 70000 |  |  |  |  | 416 |  | Side Entry Manhole Princes Street 1C2/D/MH/6901 (Incl PSSA cost) | 45000 | COP178
171 | Contract with Faber Maunsell for Transyt & Linsig Modelling Assessments | Other | Various | [12 empty] | 64809 | 64809 | 64809 |  |  |  |  | 439 |  | Office Move
451 | Stage E Landscape Drawings | Other | Various | [13 empty] | 55721 | 55721 |  |  |  |  | 385 | 62 | Additional MASS barriers on Great Stuart Street
123 | Forth Ports Agreement & Design Completion | Client | Forth Ports | [12 empty] | 55842 | 55396 | 55396 | 55396 |  |  |  | 277 |  | Airport Canopy tie in options | 49982 | COP144
123 |  | Client | Forth Ports | [12 empty] | 50000 | 50000 | 50000 |  |  |  |  | 78 |  | Alterations to design of Edinburgh Airport | 48174 | COP119a
490 | Testing Carriageway Leith Walk | Other | [15 empty] | 54198 |  |  |  |  | 384 |  | Saturn Studs at George Street and Frederick Street
259 | IFC Drawing - Section 5B Cycleway at Edinburgh Park Station | Client | CEC Planning | [12 empty] | 52095 | 52095 | 52095 |  |  |  |  | 386 |  | Additional Traffic Management Princes Street
44 | Amendements to Ocean Terminal | Client | Ocean Terminal | [12 empty] | 75000 | 75000 | 50932 |  |  |  |  | 78 |  | Alterations to design of Edinburgh Airport
143 |  | Client | CEC Planning | [12 empty] | 50000 | 50000 | 50000 |  |  |  |  | 51 |  | Allow - Provisional Sums | 44140 | COP057
143 | CEC's intent to adopt private roads between Lochside Crescent & Lochside Ave | Client | CEC Planning | [12 empty] | 20000 | 40071 | 40071 | 40071 |  |  |  | 172 |  | Traffic Modelling - Pedestrian Crossing Timing Standards
243 | Forth Ports Substation | Other | Various | [13 empty] | 50000 | 50000 |  |  |  |  | 75 | 27 | Install temporary ramp - Depot
243 | Forth Ports Substation | Other | Various | [12 empty] | 8270 | 7824 | 7824 |  |  |  |  | 295 | 30 | Carry out works to protect existing SGN gas main at Culvert No, 2 | 26080 | COP078 & COP057 & COP178
244 |  | Other | Various | [12 empty] | 50000 | 50000 | 50000 |  |  |  |  | 472 |  | Developed Kinematic Envelopment (DKE) Check
244 | Building Fixing Owner Agreements | Other | Various | [12 empty] | 17750 | 16747 | 16747 |  |  |  |  | 238 |  | Temporary Traffic Lights opposite Manderson Street (Incomplete MUDFA)
| Provision, Actual Cost - Milestone (Leith Walk) | Other | Various | [12 empty] | 50000 | 50000 | 50000 |  |  |  |  | 83 |  | Roseburn Street Temporary Traffic Lights
364 | Manhole at Balbirnie Place (Frontline cost) | MUDFA | Manholes | [12 empty] | 45000 | 45000 | 45000 | 45000 |  | Internal scope transfer from MUDFA to Infraco |  | 437 |  | Section 5B - Carrickknowe Works outwith the LOD | 4324 | COP175
368 | Demolish all Structures on Plots 97 & 102 near Roseburn Street | Other | Various | [12 empty] | 45000 | 45000 | 45000 |  |  |  |  | 48 | 15 | Additional TRO drgs | 3550 | COP067
60 | Gogar Bridge Sewer Diversion | MUDFA | Other MUDFA | [12 empty] | 35000 | 44661 | 44661 |  |  |  |  | 67 |  | Provide second access stair, Murrayfield Tramstop
172 | Traffic Modelling - Pedestrian Crossing Timing Standards | Other | Traffic Management | [12 empty] | 43290 | 43290 | 42844 |  |  |  |  | 448 |  | Street lighting Haymarket Terrace
172 |  | Other | Traffic Management | [12 empty] | 120000 | 120000 | 12000 |  |  |  |  | 320 |  | Proposed CEC Changes to demarcation requirements
18 | Consortium Office | Other | Various | [12 empty] | 36732 | 36732 | 36732 | [5 empty] | MUDFA | Manhole Construction (MUDFA Works) | 616043 | COP178
61 | Re-location of Archeological Arisings | Other | Archeological | [12 empty] | 35000 | 35000 | 35000 |  |  |  |  | 267 |  | Scottish Water Diversion - Gogar Roundabout | 116553 | COP057 & COP178
250 | Closure / Additional Works Leith Walk | Other | Various | [12 empty] | 35000 | 35000 | 35000 |  |  |  |  | 163
275 | EAL Tramstop - BAA Interface | Client | Airport | [13 empty] | 34000 | 34000 |  |  |  |  | 81 |  | CEC requested using 42 watt pit lamp (Bat Lighting)
275 | EAL Tramstop - BAA Interface | Client | Airport | [12 empty] | 6824 | 6377 | 6377 |  |  |  |  | 169 |  | Remove and re-locate Palozzi's stones
482 | Section 6 Turning Head | Other | off | [13 empty] | 0 | 30812 |  |  |  |  | 87 | 4 & 13 | Duct Installation to Leith Walk | 300 | COP057
50 | Traffic Signal Works | MUDFA | Traffic Management | [12 empty] | 30550 | 30550 | 30550 | 30550 |  | Internal scope transfer from MUDFA to Infraco |  | 197 |  | Cyclepath near gyle tramstop
65 | Murrayfield - Patterned Finish | Client | Murrayfield | [12 empty] | 30000 | 30000 | 30000 | 32202 |  |  |  | 53 |  | Utility Diversions - Section 5C (Provisional Sum - Watermain Diversion) | 110000 | COP057
65 | Murrayfield - Patterned Finish | Client | Murrayfield | [12 empty] | 4166 | 4166 | 2797 | 2797 |  |  |  | 89 |  | Balfour Street Crossing
59 | Removal of Asbestos to buildings to be demolished | Other | Various | [12 empty] | 26048 | 26048 | 29948 | 26048 |  |  |  | 198 |  | Gogar Roundabout Lighting
439 | Office Move | Other | Various | [13 empty] | 28000 | 28000 |  |  |  |  | 260 | 36 | Relocate existing control box
448 | Street lighting Haymarket Terrace | Other | [15 empty] | 27499 |  |  |  |  | 207 | 30 | Trial Investigations Culvert No.2 (SGN Main Protection) | -11957 | COP078 & COP057 & COP178
320 | Proposed CEC Changes to demarcation requirements | Client | CEC Planning | [12 empty] | 26881 | 26435 | 26435 |  |  |  |  | 243 | 69 | Forth Ports Substation
163 | Haymarket Taxi Stance | Client | Operations | [12 empty] | 26662 | 26215 | 26215 |  |  |  |  | 275 |  | EAL Tramstop - BAA Interface
163 |  | Client | Operations | [12 empty] | 15000 | 15000 | 15000 |  |  |  |  | 67 |  | Provide second access stair, Murrayfield Tramstop
74 | Additional works - Revised drg / expolratory works being undertaken | MUDFA | Other MUDFA | [12 empty] | 25000 | 25000 | 25000 | 25000 |  | Internal scope transfer from MUDFA to Infraco |  | 51 | 6 | Utility Diversions - Section 5A | 64192 | COP057
74 | Divert existing 300mm diam sewer - gogar landfill | MUDFA | Other MUDFA | [12 empty] | 1434 | 1434 | 1434 | 2868 |  | Abortive Estimates design costs |  | 281 |  | Revised Proposals for Cathedral Lane Substation
81 | CEC requested using 42 watt pit lamp (Bat Lighting) | Client | CEC Planning | [12 empty] | 25000 | 25000 | 25000 |  |  |  |  | 490 |  | Testing Carriageway Leith Walk
81 | CEC requested using 42 watt pit lamp (Bat Lighting) | Client | CEC Planning | [12 empty] | 11010 | 10564 | 10564 |  |  |  |  | 259 | 72 | IFC Drawing - Section 5B Cycleway at Edinburgh Park Station
372 | Utility Diversion 5A/SP/D/08 | MUDFA | Other MUDFA | [12 empty] | 25000 | 25000 | 25000 | 25000 |  | Internal scope transfer from MUDFA to Infraco |  | 382 |  | Bus Gate at Shandwick Place
419 | Replace MASS Barrier at St Andrews Square | Other | Traffic Management | [13 empty] | 22897 | 22897 | 22897 |  |  |  | 357 |  | Section 1C / 1D - Trial Holes at Princes Street
431 | Section 5C - A8 Underpass Existing BT Services | MUDFA | Other MUDFA | [13 empty] | 22847 | 22847 | 22847 |  |  |  | 434 |  | Emergency Road Closure of George Street
369 | Existing Services A8 Underpass Phase 1 | Other | [13 empty] | 0 |  | 20325 |  |  |  |  | 157 | 50 | Survey of Existing Drainage (Gogar Landfill) | 4334 | COP078 & COP057 & COP178
166 | Demolition of Garage Building - Ocean Drive | Other | Various | [12 empty] | 17023 | 17023 | 19561 | 17023 |  |  |  | 138 |  | Redesign Water of Leith Bridge Foundations | 32068 | COP138
145 | Additional work arising from CEC's additional comments on Section 5C technical approvals | Other | Various | [12 empty] | 0 |  | 18246 |  |  |  |  | 53 | 3 | Utility Diversions - Section 5C | 33723 | COP057
75 | Install temporary ramp - Depot | Other | Various | [12 empty] | 14189 | 14189 | 16304 |  |  |  |  | 310 |  | Gogar Landfill Scottish Water Utility Diversion
295 | Carry out works to protect existing SGN gas main at Culvert No, 2 | MUDFA | Other MUDFA | [12 empty] | 13040 | 13040 | 15347 | 26080 |  | Internal scope transfer from MUDFA to Infraco |  | 412 |  | Depot Floor - Pit for manual bogie turntable | 8914 | COP219a
472 | Developed Kinematic Envelopment (DKE) Check | Other | Various | [13 empty] | 15118 | 15118 |  |  |  |  | 349 | 61 | Section 1C / 1D - TM Contingency for Emergency Utility Works
238 | Temporary Traffic Lights opposite Manderson Street (Incomplete MUDFA) | Other | Traffic Management | [12 empty] | 14078 | 15085 | 15085 |  |  |  |  | 145 |  | Additional work arising from CEC's additional comments on Section 5C technical approvals
319 |  | Other | Traffic Management | [12 empty] | 15000 | 15000 | 15000 |  |  |  |  | 450 |  | BAA New Burnside Road Alignment
319 | Shandwick Place TRO Signage | Other | Traffic Management | [12 empty] | 8386 | 7940 | 7940 |  |  |  |  | 319 |  | Shandwick Place TRO Signage
386 | Additional Traffic Management Princes Street | Client | Traffic Management | [12 empty] | 15000 | 15000 | 15000 |  |  |  |  | 170 |  | Demolition of Cathedral Lane Toilet Block
462 | Network Rail Turning Head Lighting | Other | [15 empty] | 13819 |  |  |  |  | 449 |  | Reinstatement of Bus Gate at Edinburgh Park Station
363 | Provide Wider Area Signage to Princes Street | Other | Traffic Management | [12 empty] | 0 | 12948 | 12948 |  |  |  |  | 430 |  | Additional White lining at Haymarket Car Park
360 | Alteration of Design at Forth Ports Road 8 | Other | Various | [12 empty] | 11933 | 11933 | 11933 |  |  |  |  | 80 |  | CEC requesting change to finish of Gogarburn Retaining wall | 4553 | COP121a
433 | Traffic Management at Verity House Access Road | Other | Traffic Management | [13 empty] | 10842 | 10842 |  |  |  |  | 364 | 70 | Manhole at Balbirnie Place | 2996 | COP106 & COP178
169 | Demolition of Police Box Coffee Bar - Picardy Place | Other | Various | [12 empty] | 9329 | 9329 | 10616 |  |  |  |  | 50 | 22 | Traffic Signal Works | 30550 | COP078 & COP057 & COP178
169 | Remove and re-locate Palozzi's stones | Other | Various | [12 empty] | 10323 | 10323 | 10323 |  |  |  |  | 65 |  | Murrayfield - Patterned Finish | 32202 | COP118a
329 | Section 1B - Breakout Foamed Concrete Backfill | Other | Various | [12 empty] | 10106 | 10106 | 10106 |  |  |  |  | 361 | 55 | SP _Diversion Murrayfield Underpass
122 | Delay in receipt of CEC prior approval Sections 1A1 & 1A2 | Client | CEC Planning | [12 empty] | 10000 | 10000 | 10000 | [6 empty] | Provision, Actual Cost - Milestone (Leith Walk)
284 | Russell Road Retaining Wall - Options Report | Other | Various | [12 empty] | 0 | 10000 | 10000 |  |  |  |  | 420 |  | Leith Walk Gyratory
420 | Leith Walk Gyratory | Other | [15 empty] | 10000 |  |  |  |  | 454 |  | Section 1C - Lothian Junction
294 | Reinstate access ramp at Gogar Depot | MUDFA | Other MUDFA | [12 empty] | 8507 | 8507 | 9880 | 8507 |  | Internal scope transfer from MUDFA to Infraco |  | 287 |  | Forth Ports Traffic Signal - Section 1A4 - Widened Crossing Required
350 | Protected Species Mitigation Measures | Other | Traffic Management | [12 empty] | 9262 | 9262 | 9262 | 9262 |  |  |  | 270 |  | RBS Tramstop - Provide Estimate for the diversion of LV Power and Water Supplies crossing the Tram Track
287 | Forth Ports Traffic Signal - Section 1A4 - Widened Crossing Required | Other | Various | [12 empty] | 9577 | 9131 | 9131 |  |  |  |  | 294 | 38 | Reinstate access ramp at Gogar Depot | 8507 | COP078
412 | Depot Floor - Pit for manual bogie turntable | Other | Various | [12 empty] | 15000 | 8914 | 8914 | 8914 |  |  |  | 23 | 12 | Demolish Access steps at CAH | 2020 | COP067
412 | Depot Floor - Pit for manual bogie turntable | Other | Various | [13 empty] | 6086 | 6086 |  |  |  |  | 352 | 69 | Off peak taxi rank at George Street
89 | Balfour Street Crossing | Client | Other | [12 empty] | 9242 | 8796 | 8796 | 8796 |  |  |  | 243 | 69 | Forth Ports Substation
436 | Pedestrian disruptiuon on Lothian Road | Other | Traffic Management | [14 empty] | 8640 |  |  |  |  | 328 | 42 | Section 1B - Reinstate slabbed footway after MUDFA works | 1 | COP078 & COP178
450 | BAA New Burnside Road Alignment | Other | Various | [13 empty] | 8004 | 8004 |  |  |  |  | 237 | 10 | Move Site Boundary at Haymarket Station to Accomodate Rugby Supporters on 8th & 15th November | 849 | COP067
176 | Various Works to Section 5c - Gogar Church & Gogar Castle | Other | Various | [12 empty] | 6643 | 6643 | 7725 | 6643 |  |  |  | 74 |  | Additional works - Revised drg / expolratory works being undertaken | 25000 | COP057
400 | Bicyle Provision at haymarket Steps | Other | Various | [12 empty] | 8043 | 7597 | 7597 |  |  |  |  | 356 |  | Section 1C / 1D - Replace MASS Barriers at George St., Hanover St & Frederick St.
274 | Princes St Construction Works - Closure to Traffic during Construction Works | Other | Various | [12 empty] | 6547 | 6547 | 7522 |  |  |  |  | 169 | 48 | Demolition of Police Box Coffee Bar - Picardy Place
361 | SP _Diversion Murrayfield Underpass | MUDFA | Other MUDFA | [12 empty] | 7473 | 7473 | 7473 |  |  |  |  | 198 |  | Gogar Roundabout Lighting | 4539 | COP112
474 | Section 5B - Additional Manhole | Other | Various | [13 empty] | 8848 | 7086 |  |  |  |  | 338 | 57 | Section 1B - Removal of Ornamental Iron Balls from Groathill Depot
168 | Demolition of Building 33 Ocean Drive | Other | Various | [12 empty] | 5858 | 5858 | 6745 | 5858 |  |  |  | 482 |  | Section 6 Turning Head
21 | Asbestos work at CAH | Other | Various | [12 empty] | 5268 | 5268 | 6054 | 5268 | [5 empty] | SGN Gas Diversion - A8 Underpass
19 | Archeological Works CAH | Other | Archeological | [12 empty] | 5201 | 5201 | 5977 | 5201 |  |  |  | 269 | 20 | Instructions arising from Trackform Development Workshop | 372540 | COP073
334 | Access at New Ingilston | Other | Various | [12 empty] | 3000 | 5828 | 5828 | 5828 |  |  |  | 168 | 16 | Demolition of Building 33 Ocean Drive | 5858 | COP067
173 | Discovery of underground petrol tank at NCR site | Other | Various | [12 empty] | 4813 | 4813 | 5531 |  |  |  |  | 163 |  | Haymarket Taxi Stance | 26215 | COP139
266 | Track Monitoring at Gogar Depot | Other | Various | [12 empty] | 4673 | 4673 | 5369 | 4673 |  |  |  | 363 |  | Provide Wider Area Signage to Princes Street
270 | RBS Tramstop - Provide Estimate for the diversion of LV Power and Water Supplies crossing the Tram Track | Other | Various | [12 empty] | 5000 | 5625 | 5265 |  |  |  |  | 433 |  | Traffic Management at Verity House Access Road
353 | Section 1C / 1D - Additional Measures at George Street | Other | Traffic Management | [12 empty] | 0 | 5241 | 5241 |  |  |  |  | 326 |  | Expose existing gully connections at CH272 - 328 RHS
326 | Expose existing gully connections at CH272 - 328 RHS | Other | Various | [12 empty] | 5111 | 5111 | 5111 |  |  |  |  | 176 | 9 | Various Works to Section 5c - Gogar Church & Gogar Castle | 6643 | COP067
139 | Revised Location of OLE poles in section 1A at the request of CEC | Client | CEC Planning | [12 empty] | 0 | 5000 | 5000 |  |  |  |  | 52 |  | Allow - Provisional Sums | 44141 | COP057
388 | VMS Signs on Princes St Contingency Route | Client | Traffic Management | [12 empty] | 5000 | 5000 | 5000 |  |  |  |  | 65 |  | Murrayfield - Patterned Finish | 2797 | COP117a
389 | Production of As-Built Drawings for Princes Street | Client | CEC Planning | [12 empty] | 5000 | 5000 | 5000 |  |  |  |  | 413 |  | Expose & Protect existing private drain - Section 7
465 | CCRC Walkway Interface | Other | [15 empty] | 5000 |  |  |  |  | 327 | 41 | Section 1B - Carry out dye test
80 | CEC requesting change to finish of Gogarburn Retaining wall | Client | CEC Planning | [12 empty] | 4998 | 4553 | 4553 | 4553 |  |  |  | 123 |  | Forth Ports Agreement & Design Completion | 55396 | COP136
430 | Additional White lining at Haymarket Car Park | Other | Traffic Management | [13 empty] | 7500 | 4394 |  |  |  |  | 257 | 44 | Forth Ports access to ADM Milling
437 | Section 5B - Carrickknowe Works outwith the LOD | Other | Various | [13 empty] | 4324 | 4324 | 4324 |  |  |  | 293 | 37 | Gogar Castle Road tree felling | 1162 | COP125
159 | Provisional Sum - Relocation of Ancient Monuments | Other | Various | [12 empty] | 3993 | 3993 | 3993 |  |  |  |  | 250 |  | Closure / Additional Works Leith Walk
452 | Depot turnout | Other | [15 empty] | 3986 |  |  |  |  | 7 | 17 | Hardstanding at Haymarket Yards | 881 | COP067
464 | Gogarburn Retaining Walls W14 and W15 | Other | [15 empty] | 3986 |  |  |  |  | 84 | 18 | Burnside Road Diversion | 963 | COP067
48 | Additional TRO drgs | Other | Traffic Management | [12 empty] | 3550 | 3550 | 3550 | 3550 |  |  |  | 79 |  | Haymarket Junction Re-Design
157 | Survey of Existing Drainage (Gogar Landfill) | MUDFA | Other MUDFA | [12 empty] | 4334 | 4334 | 3463 | 4334 |  | Internal scope transfer from MUDFA to Infraco |  | 61 |  | Re-location of Archeological Arisings
486 | TRO Changes September 2009 | Other | Traffic Management | [13 empty] | 3430 | 3430 |  |  |  |  | 348 |  | Section 1D - Additional signs on Queen Street
382 | Bus Gate at Shandwick Place | Other | Various | [12 empty] | 0 | 3398 | 3398 |  |  |  |  | 355 |  | Section 1C / 1D - Additional Signage at George Street / St Andrews Square
354 | Section 1C / 1D - Provide Corex Signs and Double Yellow Lines on George Street | Other | Traffic Management | [12 empty] | 0 | 3332 | 3332 |  |  |  |  | 139 |  | Revised Location of OLE poles in section 1A at the request of CEC
373 | Utility Diversion 5C/TE/D/05 | MUDFA | Other MUDFA | [12 empty] | 3269 | 3269 | 3269 | 3269 |  | Internal scope transfer from MUDFA to Infraco |  | 354 |  | Section 1C / 1D - Provide Corex Signs and Double Yellow Lines on George Street
355 | Section 1C / 1D - Additional Signage at George Street / St Andrews Square | Other | Traffic Management | [12 empty] | 0 | 3215 | 3215 |  |  |  |  | 388 |  | VMS Signs on Princes St Contingency Route
381 | Charlotte Square West End - On Parking | Other | Various | [12 empty] | 0 | 2954 | 2954 |  |  |  |  | 373 | 74 | Utility Diversion 5C/TE/D/05 | 3269 | COP178
409 | Forth Ports New Construction at Ocean Drive - Design Only | Other | Various | [12 empty] | 2817.6 | 2818 | 2818 |  |  |  |  | 97 |  | Balgreen Road Bridge Technical Design | 2448 | COP125a
367 | Haymarket Rail Station - Network Rail Access Door | Other | Various | [12 empty] | 15000 | 15000 | 2814 |  |  |  |  | 464 |  | Gogarburn Retaining Walls W14 and W15
170 | Demolition of Cathedral Lane Toilet Block | Other | Various | [12 empty] | 20000 | 20000 | 2802 |  |  |  |  | 59 | 5 | Removal of Asbestos to buildings to be demolished | 26048 | COP062
413 | Expose & Protect existing private drain - Section 7 | Other | Various | [12 empty] | 2696 | 2696 | 2696 |  |  |  |  | 330 | 49 | Section 1B - Install additional gully CH250 RHS
356 | Section 1C / 1D - Replace MASS Barriers at George St., Hanover St & Frederick St. | Other | Traffic Management | [12 empty] | 0 | 2536 | 2536 |  |  |  |  | 389 |  | Production of As-Built Drawings for Princes Street
97 | Balgreen Road Bridge Technical Design | Other | Various | [12 empty] | 2988 | 2448 | 2448 | 2448 |  |  |  | 244
23 | Demolish Access steps at CAH | Other | Various | [12 empty] | 2020 | 2020 | 2361 | 2020 | [5 empty] | SGN Gas Diversion - Culvert
352 | Off peak taxi rank at George Street | Other | Traffic Management | [12 empty] | 2213 | 2213 | 2213 |  |  |  |  | 353 |  | Section 1C / 1D - Additional Measures at George Street
330 | Section 1B - Install additional gully CH250 RHS | Other | Various | [12 empty] | 3060 | 3060 | 2170 |  |  |  |  | 474 |  | Section 5B - Additional Manhole
343 | Section 6A - Street Lighting | Client | CEC Planning | [12 empty] | 2494.75 | 2049 | 2049 |  |  |  |  | 19 | 1 | Archeological Works CAH | 5201 | COP064
357 | Section 1C / 1D - Trial Holes at Princes Street | Other | Various | [12 empty] | 2000 | 2000 | 2000 |  |  |  |  | 465 |  | CCRC Walkway Interface
454 | Section 1C - Lothian Junction | Other | Various | [13 empty] | 1742 | 1742 |  |  |  |  | 371 | 75 | Utility Diversion 5C/BT/D/05 | 856 | COP178
257 | Forth Ports access to ADM Milling | Client | Forth Ports | [12 empty] | 2071 | 1625 | 1625 |  |  |  |  | 319
434 | Emergency Road Closure of George Street | Other | Traffic Management | [13 empty] | 1516 | 1516 |  |  |  |  | 74 | 63 | Divert existing 300mm diam sewer - gogar landfill | 2868 | COP106 & COP057 & COP178
364 | Manhole at Balbirnie Place | MUDFA | Manholes | [12 empty] | 1498 | 1498 | 1498 | 2996 |  | Abortive Estimates design costs |  | 159 | 23 | Provisional Sum - Relocation of Ancient Monuments
328 | Section 1B - Reinstate slabbed footway after MUDFA works | Other | Various | [12 empty] | 1206 | 1206 | 1387 | 1 |  | Internal scope transfer from MUDFA to Infraco |  | 274 | 21 | Princes St Construction Works - Closure to Traffic during Construction Works
293 | Gogar Castle Road tree felling | Other | Various | [12 empty] | 1162 | 1162 | 1339 | 1162 |  |  |  | 350 | 64 | Protected Species Mitigation Measures | 9262 | COP101
260 | Relocate existing control box | Client | Other | [12 empty] | 1109 | 1109 | 1109 |  |  |  |  | 462 |  | Network Rail Turning Head Lighting
207 | Trial Investigations Culvert No.2 (SGN Main Protection) | MUDFA | Other MUDFA | [12 empty] | 1083 | 1083 | 1083 | -11957 |  | Internal scope transfer from MUDFA to Infraco (detail of drawdowns to be assessed) |  | 431 |  | Section 5C - A8 Underpass Existing BT Services | 22847 | COP208
151 | Excavate and replace existing BO material within existing utility trenches | MUDFA | Other MUDFA | [12 empty] | 47456 | 1066 | 1066 | 47456 |  | Internal scope transfer from MUDFA to Infraco (detail of drawdowns to be assessed) |  | 18 |  | Consortium Office
237 | Move Site Boundary at Haymarket Station to Accomodate Rugby Supporters on 8th & 15th November | Other | Various | [12 empty] | 849 | 849 | 988 | 849 |  |  |  | 166 | 8 | Demolition of Garage Building - Ocean Drive | 17023 | COP067
385 | Additional MASS barriers on Great Stuart Street | Client | Traffic Management | [12 empty] | 915 | 915 | 915 |  |  |  |  | 367 |  | Haymarket Rail Station - Network Rail Access Door
7 | Hardstanding at Haymarket Yards | Other | Various | [12 empty] | 881 | 881 | 881 | 881 |  |  |  | 17 |  | Sewer at South Gyle Access Bridge | 350000 | COP057
371 | Utility Diversion 5C/BT/D/05 | MUDFA | Other MUDFA | [12 empty] | 856 | 856 | 856 | 856 |  | Internal scope transfer from MUDFA to Infraco |  | 486 |  | TRO Changes September 2009
449 | Reinstatement of Bus Gate at Edinburgh Park Station | Other | Various | [13 empty] | 803 | 803 |  |  |  |  | 151 |  | Excavate and replace existing BO material within existing utility trenches | 47456 | COP057
84 | Burnside Road Diversion | Other | Traffic Management | [12 empty] | 963 | 963 | 720 | 963 |  |  |  | 79 |  | Haymarket Junction Re-Design | 51722 | COP120a
327 | Section 1B - Carry out dye test | Other | Various | [12 empty] | 619 | 619 | 712 |  |  |  |  | 400 |  | Bicyle Provision at haymarket Steps
349 | Section 1C / 1D - TM Contingency for Emergency Utility Works | Other | Traffic Management | [12 empty] | 405 | 405 | 405 |  |  |  |  | 266 |  | Track Monitoring at Gogar Depot | 4673 | COP076
338 | Section 1B - Removal of Ornamental Iron Balls from Groathill Depot | Other | Various | [12 empty] | 354 | 354 | 354 |  |  |  |  | 412 |  | Depot Floor - Pit for manual bogie turntable
87 | Duct Installation to Leith Walk | MUDFA | Other MUDFA | [12 empty] | 300 | 300 | 344 | 300 |  | Internal scope transfer from MUDFA to Infraco |  | 123
348 | Section 1D - Additional signs on Queen Street | Other | Traffic Management | [12 empty] | 289 | 289 | 289 |  |  |  |  | 173 |  | Discovery of underground petrol tank at NCR site
384 | Saturn Studs at George Street and Frederick Street | Other | Various | [12 empty] | 0 | 80 | 80 |  |  |  |  | 409 | 70a | Forth Ports New Construction at Ocean Drive - Design Only
2 | Hilton Hotel Car Park | Other | Various | [12 empty] | 0 | 5000 | 0 | [6 empty] | Utility Diversions (Outwith MUDFA Scope)
42 | SDS Delay to ravelston Tramstop | Other | Various | [12 empty] | 2409 | 2409 | 0 | 2409 |  | Abortive Estimates design costs |  | 242 |  | TRO Presentations by SDS at Public Meetings
144 | Land Drain encountered in pastured areas | Other | Various | [12 empty] | 0 | 3000 | 0 |  |  |  |  | 143 |  | CEC's intent to adopt private roads between Lochside Crescent & Lochside Ave | 40071 | COP215a
347 | Section 1D - Traffic Flow and Remodel at Lothian Road Junction | Other | Traffic Management | [12 empty] | 5000 | 0 | 0 |  |  |  |  | 334 |  | Access at New Ingilston | 5818 | COP135
365 | Wider Area Fly P&R Survey | Other | Various | [12 empty] | 5000 | 5000 | 0 |  |  |  |  | 452 |  | Depot turnout
416 | Side Entry Manhole Princes Street 1C2/D/MH/6901 (Incl PSSA cost) | MUDFA | Manholes | [12 empty] | 45000 | 0 | 0 | 45000 |  | Internal scope transfer from MUDFA to Infraco |  | 343 |  | Section 6A - Street Lighting
127 | Split packages for Prior Approvals; Ocean Terminal to Port of Leith | Other | Various | [12 empty] | 5734 | 0 | [5 empty] | 368 |  | Demolish all Structures on Plots 97 & 102 near Roseburn Street
| A8 Underpass - BT Supervision | Other | [16 empty] | 7959 |  |  |  |  | Other | A8 Underpass BT Supervision | 7959 | COP191
| SDS Relocation to Edinburgh Park | [17 empty] | 28000
| EAL Tramstop - BAA Interface | Client | Airport | [12 empty] | 33176 | [6 empty] | 119 |  | IFC Drawing change Leith Walk Sub Station
Other Budget Transfers out (originally Infraco Scope / PS)
| TPI Cycle Study | [17 empty] | -17700
| Ancient monument PS Drawdown | [17 empty] | -53700
| Enhanced Response Management for unplanned traffic delays | [17 empty] | -100000
| Fastlink PS transfer out | [17 empty] | -491105
| Burnside Road works transferred to Raynesway | [17 empty] | -1000000
| Ground |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5930371.35 | 10727063 | 10990943 | 1964123 | 0 |  |  | 124 |  | Requirement of Principal Contractors License for Network Rail related works
[18 empty] | Check | 1966750
[18 empty] | diff COP MUDFA trf's | -2627
[18 empty] | increment: | 9026820 |  |  |  | 127 |  | Split packages for Prior Approvals; Ocean Terminal to Port of Leith
[23 empty] | 137 |  | Sections 1A1 & 1A2 - CEC's proposed amendments to tree build outs adjacent to Constitution St.
[23 empty] | 150 |  | IFC Drawings - Roseburn Street Viaduct
[23 empty] | 177 |  | Harbour Trackwork
[23 empty] | 181 |  | CEC requested additional Temp Traffic Light
[23 empty] | 186 |  | Specification Requirements to additional bus shelters at George St
[23 empty] | 228 |  | Relocation of Busstop outwith LOD
[23 empty] | 280 |  | Change to demarcation requirements
[23 empty] | 288 |  | Deviation Road Rail Vehicle Payload
[23 empty] | 299 |  | IFC Drawing Changes - Edinburgh Park Bridge (Piers, Bearings)
[23 empty] | 305 |  | Crawley Tunnel - Insufficient ground cover (Incl PSSA costs)
[23 empty] | 325 |  | Advertising Consents
[23 empty] | 325 |  | Advertising Consents
343
[23 empty] | 366 |  | Water Ingress Gogarburn East Abutment
EAL Tramstop - BAA Interface
Addiitional office rental cost (SDS)
4190268

## BSC COWD (4)
Period 12 change register - reconciled to AFC and in-turn COWD
|  |  |  | AFC | COWD
INTC No | TNC No | Change Order | Description | MUDFA | COWD to P12 2009/10 | COWD to P113 2009/10
17 |  |  | Sewer at South Gyle Access Bridge | 162528 | 162528
17 |  |  |  | 850000 | 0
50 |  | 22 | Traffic Signal Works | 30550 | 30550
51 | 2 | 6 | Utility Diversions - Section 5A | 75489 | 15000
51 |  |  | Allow - Provisional Sums | 44140 | 0
52 | 3 | 7 | Utility Diversions - Section 5B | 88027 | 0
52 |  |  | Allow - Provisional Sums | 44141 | 0
53 | 4 | 3 | Utility Diversions - Section 5C | 39218 | 25000
53 |  |  | Utility Diversions - Section 5C (Provisional Sum - Watermain Diversion) | 110000 | 0
60 |  |  | Gogar Bridge Sewer Diversion | 9595 | 9595
60 |  |  | Gogar Bridge Sewer Diversion | 35066 | 35066
74 |  | 63 | Divert existing 300mm diam sewer - gogar landfill | 1434 | 1434
74 |  |  | Additional works - Revised drg / expolratory works being undertaken | 25000 | 25000
86 | 10 |  | MUDFA Transfer of Utilities Diversions Section 1A, 1B, 1C, 1D | 750000 | 0
87 | 11 | 4 & 13 | Duct Installation to Leith Walk | 344 | 344
151 | 17 | 133 | Excavate and replace existing BO material within existing utility trenches | 1066 | 1066
157 |  | 50 | Survey of Existing Drainage (Gogar Landfill) | 3463 | 3463
207 | 21 | 30 | Trial Investigations Culvert No.2 (SGN Main Protection) | 1083 | 1083
267 |  |  | Scottish Water Diversion - Gogar Roundabout | 116553 | 116553
268 |  | 133 | Scottish Power Diversion - Gogar Roundabout | 70163 | 14617
270 |  |  | RBS Tramstop - Provide Estimate for the diversion of LV Power and Water Supplies crossing the Tram Track | 5625 | 5625
294 |  | 38 | Reinstate access ramp at Gogar Depot | 9880 | 9880
295 |  | 30 | Carry out works to protect existing SGN gas main at Culvert No, 2 | 15347 | 15347
310 | 38 |  | Gogar Landfill Scottish Water Utility Diversion | 23195 | 23195
|  |  |  | 75000 | 25000
342 | 40 |  | Section 5C - Edinburgh Park Private Utilities | 185000 | 0
361 |  | 55 | SP _Diversion Murrayfield Underpass | 7473 | 7473
364 |  | 70 | Manhole at Balbirnie Place | 1498 | 1498
369 |  | 126 | Existing Services A8 Underpass Phase 1 | 20325 | 0
371 | 43 | 75 | Utility Diversion 5C/BT/D/05 | 856 | 856
372 | 44 |  | Utility Diversion 5A/SP/D/08 | 25000 | 25000
373 | 45 | 74 | Utility Diversion 5C/TE/D/05 | 3269 | 3269
|  |  | Per Change Register - MUDFA Period 12 | 2830328 | 558442 | 2819410 | per change register
Adjustments from Change register to match QS view provided for March Board
|  |  | SGN - Gas Diversion (non infraco per PD report and Change) | 552000 | 252000 | 552000
|  |  | Manhole Construction - Transferred from MUDFA (non infraco per PD) | 616043 | 123209 | 616043
|  |  | Balbirnie Manhole | 45000 | 45000 | 45000
|  |  | Phone box removal (included on change register but as Provisional sum) | 150000 | 0 | 150000
|  |  | sub-total adjustments to change register | 1363043 | 420209 | 1363043
|  |  | Total AFC and COWD (see BSC delivered - squared to +/- £3k) | 4193371 | 978651 | 4182453

## Non BSC Other (5)
Breakdown of Non-BSC items transferred from MUDFA
manual input
Period | Description | Change Number | Account Code | Account Desc | AFC | COWD | Change Category | Dr/(Cr) Code | Value
Period end | [6 empty] | PCB
08/09 - 11 | Budget transfer MUDFA related insurance claims paid to date | COP055 | T18.01.18 | Unallocated to section | -52821 | 52821 | Transfer - Insurance
08/09 - 11 | Communications tram advisor funding | COP056 | T18.01.18 | Unallocated to section | -80000 | 80000 | Transfer - PM Costs
08/09 - 11 | Souters completion of MUDFA scope | COP060 | T18.01.18 | Unallocated to section | -58726 | 58726 | Transfer - Non Infraco
08/09 - 12 | MUDFA / SDS £50k transfer for design of 800mm watermain | COP061 | T18.01.18 | Unallocated to section | -50000 | 50000 | Transfer - SDS
08/09 - 13 | Track monitoring of NR infrastructure at Gogar depot | COP076 | T18.01.18 | Unallocated to section | -4673 | 4673 | Transfer - Network Rail
08/09 - 13 | Budget transfer MUDFA related insurance claims paid to date | COP080 | T18.01.18 | Unallocated to section | -31502 | 31502 | Transfer - Insurance
09/10 - 07 | Burnside Road - Farrans | COP162 | T18.02.22 | Transfer to infraco | -575000 |  | Transfer - Non Infraco | T19.07.21 | 639200 | Non-Inf works | £64,200 from contingency
09/10 - 08 | Mudfa transfter section 1A | COP180 | T18.01.03 | Section 1a | -2539000 |  | Transfer - Non Infraco | T19.07.35 | 2539000 | Non-Inf changes
09/10 - 08 | Mudfa claims transfer | COP181 | T18.01.18 | Unallocated to section | -45845 | 45845 | Transfer - Insurance | T17.05 | 45845 | Claims Recoverable
09/10 - 09 | Design - MUDFA Phase2 800mm Water Main at Depot (Budget Reconciliation) | COP214 | T18.01.01 | Pre-construction Services | 3278 |  | Transfer - Internal
09/10 - 09 | Design - MUDFA Phase2 800mm Water Main at Depot (Budget Reconciliation) | COP214 | T18.01.18 | Unallocated to section | -3278 |  | Transfer - Internal
09/10 - 11 | Mudfa Claims Transfer | COP231 | T18.01.18 | Unallocated to section | -25244 | 25244 | Transfer - Insurance | T17.05 | 25244 | Claims Recoverable
09/10 - 12 | Grontmij design novation section 7 BAA | COP249 | T18.02.18 | Unallocated to section | -80000 |  | Transfer - Non Infraco | T19.07.44 | 80000 | Infraco Variations
[5 empty] | -3542811 | 348811
[5 empty] | 3194000 |  | Exclude green items on front sheet
[5 empty] | -348811 | 348811 | Balance of Non BSC transfers