## Present
June 09 Range Review
£m | Spent | App'd Budget | Delta | Mar 09 Rev | Delta | April 09 Rev | Delta | QS View | Delta | Mid | Delta | Worst | Notes Ref
tie PM |  | 39.0489 |  | 39.0489 | 5 | 44.0489 |  | 44.0489 |  | 44.0489 |  | 44.0489 | 1
Other Resources |  | 27.3624 |  | 27.3624 |  | 27.3624 | 2.3311 | 29.6934 |  | 29.6934 |  | 29.6934 | 2
SDS |  | 26.9525 |  | 26.9525 |  | 26.9525 |  | 26.9525 |  | 26.9525 |  | 26.9525
Infraco (BB & S) |  | 251.6801 |  | 251.6801 |  | 251.6801 |  | 251.6801 |  | 251.6801 |  | 251.6801 | 3
Tramco |  | 58.1519 |  | 58.1519 |  | 58.1519 |  | 58.1519 |  | 58.1519 |  | 58.1519
MUDFA |  | 53.3239 |  | 53.3236 |  | 53.3236 |  | 53.3236 |  | 53.3236 |  | 53.3236
All else (incl land) |  | 35.7537 |  | 35.7537 |  | 35.7537 | 0.39333 | 36.147 |  | 36.147 |  | 36.147
Base Costs |  | 492.2734 | 0 | 492.2731 | 5 | 497.2731 | 2.7244 | 499.9975 | 0 | 499.9975 | 0 | 499.9975
Risk Allowance (undrawn) |  | 19.7436 | 15.0822 | 34.8258 | 21.5 | 56.3258 | 22.099 | 78.4248 | 13.6507 | 92.0755 | 20.2632 | 112.3387
Total |  | 512.017 | 15.0822 | 527.0989 | 26.5 | 553.5989 | 24.8234 | 578.4223 |  | 592.073 |  | 612.3362
Risk Allowance Make Up:
Delay - EOT1 |  |  |  |  | 2.5 | 2.5 |  | 2.5 | 0.5 | 3 | 0.5 | 3.5 | 4
Delay - EOT2 and future |  | 5 | 5 | 10 | 1.7 | 11.7 | 3.3 | 15 | 5 | 20 | 5 | 25 | 5
Design (Incl BDDI to IFC) |  | 0 | 6.1 | 6.1 | 6.3 | 12.4 | 8.4271 | 20.8271 | 6.428 | 27.2551 | 11.5931 | 38.8482 | 6
Ground Related |  | 2 | 1 | 3 | 6.1 | 9.1 | -2.5175 | 6.5825 | 0.43236 | 7.0149 | 1.2371 | 8.252 | 7
Road Reconstruction |  | 1 | 2.3 | 3.3 | 0.3 | 3.6 | 3.13 | 6.73 | 0.3 | 7.03 | 0 | 7.03 | 8
Client inst / other changes |  |  |  |  | 2 | 2 | 4.2108 | 6.2108 | 0.99035 | 7.2012 | 1.933 | 9.1342 | 9
Burnside Road |  |  |  |  | 1.8 | 1.8 |  | 1.8 |  | 1.8 |  | 1.8 | 10
Deliverability of VE |  | 2 | 2.3 | 4.3 |  | 4.3 |  | 4.3 |  | 4.3 |  | 4.3 | 11
Land & Property |  | 2.5 | -2.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 12
MUDFA |  |  |  |  | 3.2 | 3.2 | 2.7 | 5.9 |  | 5.9 |  | 5.9 | 13
SDS & Approvals |  | 3.9 | -1.2 | 2.7 | -1.2 | 1.5 | 2.9 | 4.4 |  | 4.4 |  | 4.4 | 14
Other risks/contingency |  | 3.3436 | 2.0822 | 5.4258 | -1.2 | 4.2258 | -0.051496 | 4.1743 |  | 4.1743 |  | 4.1743 | 15
|  | 19.7436 | 15.0822 | 34.8258 | 21.5 | 56.3258 | 22.099 | 78.4248 | 13.6507 | 92.0755 | 20.2632 | 112.3387
June 09 Range Review - core assumptions and exclusions
Open for revenue service in Feb 2012
Total cost only allows for TNC / INTC's raised to date.
Where Estimates have not been submitted tie have taken a view of likely final costs.
No Provision for any INTC's to be raised by BSC (which are not known)
No Provision allowed for an further TNC's to be raised by tie (which are not known)
No Provision - Further SDS Design Change (which is not known about)
No Provision - Siemens Design Change (BDDI - IFC), no visibility
No Provision - INTC 397 (Revised Earthworks Specification)
No Provision - INTC 398 (Revised Concrete Specification)
No Provision - Further On-Street Supplemental Agreements.
Provision allowed for additional capping below full depth road make up (allow additional 300mm to all roads)
Provision allowed for additional cost associated with the depot (REfer INTC 203)

## Summary
EDINBURGH TRAM
| PROJECT NAME: |  | Edinburgh Tram
ADVISOR NAME
| PERIOD: |  | 09/10 - 03
tie REPRESENTATIVE:
ADVISOR CONTACT:
1 |  |  | 07/08 | 08/09 | TS "Budget" YTD | Actual YTD | Variance YTD | Remainder year | 09/10 | 10/11 | 11/12 | 12/13 | 13/14 | AFC | CAB | Variance | PCB Fin Close | Cum Approved Change | CAB P3 0910 | Unapproved Change | Reported P3 0910 | Restate Approved Base Costs | Update Risk & PM Costs Apr 09 | April 09 Update | Update June 09 | June 09 Update (QS view plus SMcG adj) | P3 PD Reports AFC
2
3 | T01.01 | Project management Staff Costs | 11440070.2586 | 7131218.4764 | 1640681.8945 | 1093502.1752 | -547179.7193 | 4559824.0891 | 5653326.2643 | 3717602.88 | 1690345 | 0 | 0 | 29632562.8793 | 26777669.4561 | 2854893.4232 | 26697669.4561 | 80000 | 26777669.4561 | 2854893.4232 | 29632562.8793 |  | 868135 | 30500697.8793 |  | 30500697.8793 | 29632562.8793
4 | T01.02 | Recruitment Fees | 274911.4166 | 111731 | 8650.38 | 19453.0833 | 10802.7033 | 18032 | 37485.0833 | 39359 | 2716 | 0 | 0 | 466202.4999 | 466202.5966 | -0.096667 | 466202.5966 | 0 | 466202.5966 | -0.096667 | 466202.4999 |  |  | 466202.4999 |  | 466202.4999 | 466202.4999
5 | T01.03 | Travel & Subsistence / Conference | 137742.7 | 101100.4615 | 15646.8462 | 8450 | -7196.8462 | 42250 | 50700 | 46680 | 19935 | 0 | 0 | 356158.1615 | 356213.7554 | -55.5938 | 356213.7554 | 0 | 356213.7554 | -55.5938 | 356158.1615 |  |  | 356158.1615 |  | 356158.1615 | 356158.1615
6 | T01.04 | Allocations from central O/H | 3774814.834 | 484868 | 110940.6923 | 69077.5 | -41863.1923 | 372851.25 | 441928.75 | 531713 | 286366 | 0 | 0 | 5519690.584 | 5580828.8293 | -61138.2454 | 5580828.8293 | 0 | 5580828.8293 | -61138.2454 | 5519690.584 |  |  | 5519690.584 |  | 5519690.584 | 5519690.584
7 | T01.05 | IT & Software Costs / fitout | 1508074.5062 | 587347 | 151938.4685 | 83222.3333 | -68716.1351 | 495078.6667 | 578301 | 434902 | 371899.6667 | 0 | 0 | 3480524.1728 | 3109074.7792 | 371449.3936 | 3109074.7792 | 0 | 3109074.7792 | 371449.3936 | 3480524.1728 |  |  | 3480524.1728 |  | 3480524.1728 | 3480524.1728
8 | T01.06 | Citypoint - rent,rates,s/c | 824675 | 753460.4615 | 144449.5377 | 162552 | 18102.4623 | 541840 | 704392 | 373490 | 196209 | 0 | 0 | 2852226.4615 | 2171872.4655 | 680353.9961 | 2171872.4655 | 0 | 2171872.4655 | 680353.9961 | 2852226.4615 |  |  | 2852226.4615 |  | 2852226.4615 | 2852226.4615
9 | T01.07 | Recovered from SDS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
10 | T01.08 | Short Term Contractors | 196804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196804 | 196804 | 0 | 196804 | 0 | 196804 | 0 | 196804 |  |  | 196804 |  | 196804 | 196804
11 | T01.09 | City Point Overheads | 25270.8462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25270.8462 | 25270.8462 | 0 | 25270.8462 | 0 | 25270.8462 | 0 | 25270.8462 |  |  | 25270.8462 |  | 25270.8462 | 25270.8462
12 | T01.10 | Active Risk Manager | 83665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83665 | 83665 | 0 | 83665 | 0 | 83665 | 0 | 83665 |  |  | 83665 |  | 83665 | 83665
13 | T01.11 | Archaeological supervisor - Gogar works | 24000 | 126234.9103 | 35000 | 109981 | 74981 | 278382 | 388363 | 0 | 0 | 0 | 0 | 538597.9103 | 185234.89 | 353363.0203 | 267878.89 | -82644 | 185234.89 | 353363.0203 | 538597.9103 |  |  | 538597.9103 |  | 538597.9103 | 538597.9103
14 | T01.12 | MUDFA Site Overheads | 9958 | 8907 | -8907 | 7007 | 15914 | 0 | 7007 | 0 | 0 | 0 | 0 | 25872 | 13458 | 12414 | 13458 | 0 | 13458 | 12414 | 25872 |  |  | 25872 |  | 25872 | 25872
15 | T01.13 | Archaeology - Non Gogar | 0 | 3230.1538 | 30125.0023 | 0 | -30125.0023 | 0 | 0 | 0 | 0 | 0 | 0 | 3230.1538 | 82644.2423 | -79414.0885 | 0.24231 | 82644 | 82644.2423 | -79414.0885 | 3230.1538 |  |  | 3230.1538 |  | 3230.1538 | 3230.1538
16 | T01.14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
17 | T01.15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
18 | T01.16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
19 | T01.17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
20 | T01.18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
21 | T01.19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
22 | T01.20 | Period Adjustments | 0 | 0 | 0 | 0 | 0 | 299122.02 | 299122.02 | -1863832.7231 | -2567470.6667 | 0 | 0 | -4132181.3697 | 0 | -4132181.3697 | 0 | 0 | 0 | -4132181.3697 | -4132181.3697 | 316 | 4131865 | -0.36974 |  | -0.36974 | 0
23 | T01 | Total tie PM costs | 18299986.5615 | 9308097.4636 | 2128525.8214 | 1553245.0919 | -575280.7295 | 6607380.0257 | 8160625.1176 | 3279914.1569 | 0 | 0 | 0 | 39048623.2997 | 39048938.8606 | -315.5609 | 38968938.8606 | 80000 | 39048938.8606 | -315.5609 | 39048623.2997 | 316 | 5000000 | 44048939.2997 | 0 | 44048939.2997 | 43180804.6694
24
25 | T02.01 | Core Team | 1238194.57 | 536612.47 | 140286 | 147786 | 7500 | 473852 | 621638 | 2497356 | 2725009.21 | 0 | 0 | 7618810.25 | 7631160.25 | -12350 | 7631160.25 | 0 | 7631160.25 | -12350 | 7618810.25 |  |  | 7618810.25 |  | 7618810.25 | 7618810.25
26 | T02.02 | Retention | 0 | 12350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12350 | 0 | 12350 | 0 | 0 | 0 | 12350 | 12350 |  |  | 12350 |  | 12350 | 12350
27 | T02.03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
28 | T02.04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
29 | T02.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
30 | T02 | Total DPOF | 1238194.57 | 548962.47 | 140286 | 147786 | 7500 | 473852 | 621638 | 2497356 | 2725009.21 | 0 | 0 | 7631160.25 | 7631160.25 | 0 | 7631160.25 | 0 | 7631160.25 | 0 | 7631160.25 | 0 | 0 | 7631160.25 | 0 | 7631160.25 | 7631160.25
31
32 | T03.01 | DLA-SDS | 132226.89 | 8397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140623.89 | 140623.89 | 0 | 140728.89 | -105 | 140623.89 | 0 | 140623.89 |  |  | 140623.89 |  | 140623.89 | 140623.89
33 | T03.02 | DLA-TSS | 31999.37 | 0 | 0 | -1 | -1 | 0 | -1 | 0 | 0 | 0 | 0 | 31998.37 | 31999.37 | -1 | 31999.37 | 0 | 31999.37 | -1 | 31998.37 |  |  | 31998.37 |  | 31998.37 | 31998.37
34 | T03.03 | DLA- Site Investigation | 1116.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1116.25 | 1116.25 | 0 | 1116.25 | 0 | 1116.25 | 0 | 1116.25 |  |  | 1116.25 |  | 1116.25 | 1116.25
35 | T03.04 | DLA-MUDFA | 674194.34 | 42421 | 0 | 21328 | 21328 | 17548 | 38876 | 0 | 0 | 0 | 0 | 755491.34 | 728896.34 | 26595 | 696475.34 | 32421 | 728896.34 | 26595 | 755491.34 |  |  | 755491.34 |  | 755491.34 | 755491.34
36 | T03.05 | DLA-Network Rail / Scotrail | 115347.45 | -788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114559.45 | 114559.45 | 0 | 119986.15 | -5426.7 | 114559.45 | 0 | 114559.45 |  |  | 114559.45 |  | 114559.45 | 114559.45
37 | T03.06 | DLA-JRC | 27382.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27382.82 | 27382.82 | 0 | 27382.82 | 0 | 27382.82 | 0 | 27382.82 |  |  | 27382.82 |  | 27382.82 | 27382.82
38 | T03.07 | DLA-Infraco | 1063439.92 | 302825 | 88462.5385 | 41222.7692 | -47239.7692 | 307396 | 348618.7692 | 0 | 0 | 0 | 0 | 1714883.6892 | 1491646.02 | 223237.6692 | 1151176.7123 | 340469.3077 | 1491646.02 | 223237.6692 | 1714883.6892 |  |  | 1714883.6892 |  | 1714883.6892 | 1714883.6892
39 | T03.08 | DLA-Vehicles & Driver supply contract | 461014.65 | 10214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 471228.65 | 471228.65 | 0 | 461014.65 | 10214 | 471228.65 | 0 | 471228.65 |  |  | 471228.65 |  | 471228.65 | 471228.65
40 | T03.09 | DLA-BAA | 22199.82 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24212.82 | 24212.82 | 0 | 22199.82 | 2013 | 24212.82 | 0 | 24212.82 |  |  | 24212.82 |  | 24212.82 | 24212.82
41 | T03.10 | DLA-Land & Property (3rd parties) | 25946.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25946.24 | 25946.24 | 0 | 25946.24 | 0 | 25946.24 | 0 | 25946.24 |  |  | 25946.24 |  | 25946.24 | 25946.24
42 | T03.11 | DLA-Ticketing Agreements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
43 | T03.12 | DLA-DPOF | 85711.01 | -732 | 0 | 1370 | 1370 | 0 | 1370 | 0 | 0 | 0 | 0 | 86349.01 | 84979.01 | 1370 | 85711.01 | -732 | 84979.01 | 1370 | 86349.01 |  |  | 86349.01 |  | 86349.01 | 86349.01
44 | T03.13 | DLA-Tram Netwk/Roads Interface | 22149.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22149.45 | 22149.45 | 0 | 22149.45 | 0 | 22149.45 | 0 | 22149.45 |  |  | 22149.45 |  | 22149.45 | 22149.45
45 | T03.14 | DLA-EARL interface | 39217.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39217.39 | 39217.39 | 0 | 39217.39 | 0 | 39217.39 | 0 | 39217.39 |  |  | 39217.39 |  | 39217.39 | 39217.39
46 | T03.15 | DLA-Commissioning Svcs Agmt | 6892.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6892.48 | 6892.48 | 0 | 6892.48 | 0 | 6892.48 | 0 | 6892.48 |  |  | 6892.48 |  | 6892.48 | 6892.48
47 | T03.16 | OCIP | 24280.06 | 2806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27086.06 | 27086.06 | 0 | 24280.06 | 2806 | 27086.06 | 0 | 27086.06 |  |  | 27086.06 |  | 27086.06 | 27086.06
48 | T03.17 | Infraco Enabling | 3950.63 | 432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4382.63 | 4382.63 | 0 | 3950.63 | 432 | 4382.63 | 0 | 4382.63 |  |  | 4382.63 |  | 4382.63 | 4382.63
49 | T03.18 | HR Issues | -0.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.31 | -0.31 | 0 | -0.31 | 0 | -0.31 | 0 | -0.31 |  |  | -0.31 |  | -0.31 | -0.31
50 | T03.19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
51 | T03.19.01 | Ingliston Park & Ride | -0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.5 | -0.5 | 0 | -0.5 | 0 | -0.5 | 0 | -0.5 |  |  | -0.5 |  | -0.5 | -0.5
52 | T03.19.02 | Mass Earthworks | 1136.06 | -1136 | 0 | 1136 | 1136 | 0 | 1136 | 0 | 0 | 0 | 0 | 1136.06 | 1136.06 | 0 | 2272.06 | -1136 | 1136.06 | 0 | 1136.06 |  |  | 1136.06 |  | 1136.06 | 1136.06
53 | T03.19.03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
54 | T03.19.04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
55 | T03.19.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
56 | T03.19.06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
57 | T03.19.07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
58 | T03.19.08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
59 | T03.19.09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
60 | T03.19.10 | DLA - Reserve | 0 | 0 | 0 | 0 | 0 | -254690.8 | -254690.8 | 0 | 0 | 0 | 0 | -254690.8 | 0 | -254690.8 | 0 | 0 | 0 | -254690.8 | -254690.8 | 3489 |  | -251201.8 | 251202 | 0.2 | 0
61 | T03.01-19 | Subtotal DLA | 2738204.02 | 366452 | 88462.5385 | 65055.7692 | -23406.7692 | 70253.2 | 135308.9692 | 0 | 0 | 0 | 0 | 3239964.9892 | 3243454.12 | -3489.1308 | 2862498.5123 | 380955.6077 | 3243454.12 | -3489.1308 | 3239964.9892 | 3489 | 0 | 3243453.9892 | 251202 | 3494655.9892 | 3494655.7892
62 | T03.20 | D&W-General Advice | 664652 | 25104 | 21280 | 4924 | -16356 | 7616 | 12540 | 0 | 0 | 0 | 0 | 702296 | 718652 | -16356 | 745652.0769 | -27000.0769 | 718652 | -16356 | 702296 |  |  | 702296 |  | 702296 | 702296
63 | T03.21 | D&W-TRO's | 277991.6003 | 40975 | 50000 | 46020 | -3980 | 121005 | 167025 | 0 | 0 | 0 | 0 | 485991.6003 | 485991.6003 | 0 | 801982.6001 | -315990.9998 | 485991.6003 | 0 | 485991.6003 |  |  | 485991.6003 |  | 485991.6003 | 485991.6003
64 | T03.22 | D&W-Property | 615367 | 408583.5385 | -159131 | 47140 | 206271 | 52070 | 99210 | 0 | 0 | 0 | 0 | 1123160.5385 | 874819.5385 | 248341 | 841934 | 32885.5385 | 874819.5385 | 248341 | 1123160.5385 |  |  | 1123160.5385 |  | 1123160.5385 | 1123160.5385
65 | T03.23 | D&W-Planning Monitoring | 167742 | 13511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181253 | 207462 | -26209 | 292542 | -85080 | 207462 | -26209 | 181253 |  |  | 181253 |  | 181253 | 181253
66 | T03.24 | D&W-TDWG | 87860 | -1878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85982 | 87860 | -1878 | 87860 | 0 | 87860 | -1878 | 85982 |  |  | 85982 |  | 85982 | 85982
67 | T03.25 | D&W -Public Realm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
68 | T03.26 | D&W-Litigation | 260 | 10230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10490 | 14490 | -4000 | 260 | 14230 | 14490 | -4000 | 10490 |  |  | 10490 |  | 10490 | 10490
69 | T03.27 | D&W-Secondments | 152123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152123 | 152123 | 0 | 152123 | 0 | 152123 | 0 | 152123 |  |  | 152123 |  | 152123 | 152123
70 | T03.28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
71 | T03.29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
72 | T03.30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
73 | T03.31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
74 | T03.32 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
75 | T03.33 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
76 | T03.34 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
77 | T03.35 |  | 0 | 0 | 0 | 0 | 0 | -88691 | -88691 | 0 | 0 | 0 | 0 | -88691 | 0 | -88691 | 0 | 0 | 0 | -88691 | -88691 | -111207 |  | -199898 | 199898 | 0 | 0
78 | T03.20-35 | Subtotal D&W | 1965995.6003 | 496525.5385 | -87851 | 98084 | 185935 | 92000 | 190084 | 0 | 0 | 0 | 0 | 2652605.1387 | 2541398.1387 | 111207 | 2922353.677 | -380955.5383 | 2541398.1387 | 111207 | 2652605.1387 | -111207 | 0 | 2541398.1387 | 199898 | 2741296.1387 | 2741296.1387
79 | T03.35 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
80 | T03.36 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
81 | T03.37 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
82 | T03.38 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
83 | T03.39 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
84 | T03.40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
85 | T03.41 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
86 | T03.42 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
87 | T03.43 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
88 | T03.44 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
89 | T03.45 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
90 | T03.35-45 | Subtotal Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | T03 | Total LEGALS | 4704199.6203 | 862977.5385 | 611.5385 | 163139.7692 | 162528.2308 | 162253.2 | 325392.9692 | 0 | 0 | 0 | 0 | 5892570.128 | 5784852.2587 | 107717.8692 | 5784852.1893 | 0.06941 | 5784852.2587 | 107717.8692 | 5892570.128 | -107718 | 0 | 5784852.128 | 451100 | 6235952.128 | 6235951.928
92
93 | T04.01 | Design Services under SDS | 11665951.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11665951.25 | 11665951.25 | 0 | 11665951.25 | 0 | 11665951.25 | 0 | 11665951.25 |  |  | 11665951.25 |  | 11665951.25 | 11665951.25
94 | T04.01.01 | Overall Value Main Works ( Unallocated ) | 468601 | 4734882.7442 | 654623.5754 | 730145.6452 | 75522.0698 | 1738447.2258 | 2468592.871 | 1087978.1935 | 102581.2903 | 0 | 0 | 8862636.099 | 5982253.3319 | 2880382.7671 | 5857253.3319 | 125000 | 5982253.3319 | 2880382.7671 | 8862636.099 |  |  | 8862636.099 |  | 8862636.099 | 8862636.099
95 | T04.01.02 | Section 1 Newhaven Road to Haymarket | 2628790.1526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2628790.1526 | 2628790.1526 | 0 | 2628790.1526 | 0 | 2628790.1526 | 0 | 2628790.1526 |  |  | 2628790.1526 |  | 2628790.1526 | 2628790.1526
96 | T04.01.03 | Section 2 Haymarket Corridor | 243792.9765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243792.9765 | 243792.9765 | 0 | 243792.9765 | 0 | 243792.9765 | 0 | 243792.9765 |  |  | 243792.9765 |  | 243792.9765 | 243792.9765
97 | T04.01.03 | Section 3 Haymarket to Granton Sq | 2172265.8672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172265.8672 | 2172265.8672 | 0 | 2172265.8672 | 0 | 2172265.8672 | 0 | 2172265.8672 |  |  | 2172265.8672 |  | 2172265.8672 | 2172265.8672
98 | T04.01.04 | Section 3 1B deduction | -1858755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1858755 | -1858755 | 0 | -1858755 | 0 | -1858755 | 0 | -1858755 |  |  | -1858755 |  | -1858755 | -1858755
99 | T04.01.05 | Section 4 Granton Sq to Newhaven Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
100 | T04.01.06 | Section 5 Roseburn Junction to Gogar | 1453607.1771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1453607.1771 | 1453607.1771 | 0 | 1453607.1771 | 0 | 1453607.1771 | 0 | 1453607.1771 |  |  | 1453607.1771 |  | 1453607.1771 | 1453607.1771
101 | T04.01.07 | Section 6 Gogar Depot | 328781.4435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328781.4435 | 328781.4435 | 0 | 328781.4435 | 0 | 328781.4435 | 0 | 328781.4435 |  |  | 328781.4435 |  | 328781.4435 | 328781.4435
102 | T04.01.08 | Section 7 Gogar to Edinburgh Airport | 443207.1446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 443207.1446 | 443207.1446 | 0 | 443207.1446 | 0 | 443207.1446 | 0 | 443207.1446 |  |  | 443207.1446 |  | 443207.1446 | 443207.1446
103 | T04.01.09 | Section 8 Ingliston West / Newbridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
104 | T04.01.10 | MUDFA / Utilities | 552625.2348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552625.2348 | 552625.2348 | 0 | 552625.2348 | 0 | 552625.2348 | 0 | 552625.2348 |  |  | 552625.2348 |  | 552625.2348 | 552625.2348
105 | T04.01.11 | Claim | 1925000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1925000 | 1925000 | 0 | 1925000 | 0 | 1925000 | 0 | 1925000 |  |  | 1925000 |  | 1925000 | 1925000
106 | T04.01.12 | Variations | 0 | 0 | 0 | 0 | 0 | -1345029.5806 | -1345029.5806 | -1087978.1935 | -102581.2903 | 0 | 0 | -2535589.0645 | 0 | -2535589.0645 | 0 | 0 | 0 | -2535589.0645 | -2535589.0645 | -344794 |  | -2880383.0645 |  | -2880383.0645 | 0
107 | T04.01.13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
108 | T04.01.14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
109 | T04.01.15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
110 | T04.01.16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
111 | T04.01.17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
112 | T04.01.18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
113 | T04.01.19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
114 | T04.01.20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
115 | T04.02 | Site Investigation under SDS | 1415000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1415000 | 1415000 | 0 | 1415000 | 0 | 1415000 | 0 | 1415000 |  |  | 1415000 |  | 1415000 | 1415000
116 | T04.03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
117 | T04.04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
118 | T04.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
119 | T04.06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
120 | T04.07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
121 | T04.08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
122 | T04.09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
123 | T04.10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
124 | T04 | Total SDS | 21438867.2463 | 4734882.7442 | 654623.5754 | 730145.6452 | 75522.0698 | 393417.6452 | 1123563.2903 | 0 | 0 | 0 | 0 | 27297313.2809 | 26952519.5782 | 344793.7026 | 26827519.5782 | 125000 | 26952519.5782 | 344793.7026 | 27297313.2809 | -344794 | 0 | 26952519.2809 | 0 | 26952519.2809 | 29832902.3454
125
126 | T05.01 | Integrated Transport Model | 1747713.1575 | 352747.3238 | 68012.31 | 93412.3077 | 25399.9977 | 103394.6923 | 196807 | 125000 | 13000 | 0 | 0 | 2435267.4813 | 2454444.3975 | -19176.9162 | 2454444.3975 | 0 | 2454444.3975 | -19176.9162 | 2435267.4813 | 19177 |  | 2454444.4813 |  | 2454444.4813 | 2454444.4813
127 | T05.02 | Surveys (MM) | 165588.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165588.78 | 165588.78 | 0 | 165588.78 | 0 | 165588.78 | 0 | 165588.78 |  |  | 165588.78 |  | 165588.78 | 165588.78
128 | T05.03 | Consultancy (Halcrow) | 9916.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9916.21 | 9916.21 | 0 | 9916.21 | 0 | 9916.21 | 0 | 9916.21 |  |  | 9916.21 |  | 9916.21 | 9916.21
129 | T05.04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
130 | T05.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
131 | T05.06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
132 | T05.07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
133 | T05.08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
134 | T05.09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
135 | T05.10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
136 | T05 | Total JRC | 1923218.1475 | 352747.3238 | 68012.31 | 93412.3077 | 25399.9977 | 103394.6923 | 196807 | 125000 | 13000 | 0 | 0 | 2610772.4713 | 2629949.3875 | -19176.9162 | 2629949.3875 | 0 | 2629949.3875 | -19176.9162 | 2610772.4713 | 19177 | 0 | 2629949.4713 | 0 | 2629949.4713 | 2629949.4713
137
138 | T06.01 | Technical Services | 8052774.4403 | 1287600.366 | 166367.99 | 223375 | 57007.01 | 111249.6592 | 334624.6592 | 0 | 0 | 0 | 0 | 9674999.4655 | 9649558.7903 | 25440.6752 | 9302558.7903 | 347000 | 9649558.7903 | 25440.6752 | 9674999.4655 | -25441 |  | 9649558.4655 | 570980 | 10220538.4655 | 10220538.4196
139 | T06.02 | Land agreement/negotiations | 113000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113000 | 113000 | 0 | 113000 | 0 | 113000 | 0 | 113000 |  |  | 113000 |  | 113000 | 113000
140 | T06.04 | TSS Second to CEC-Approvals support | 92381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92381 | 92381 | 0 | 92381 | 0 | 92381 | 0 | 92381 |  |  | 92381 |  | 92381 | 92381
141 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
142 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
143 | T06.01-03 | Subtotal TSS | 8258155.4403 | 1287600.366 | 166367.99 | 223375 | 57007.01 | 111249.6592 | 334624.6592 | 0 | 0 | 0 | 0 | 9880380.4655 | 9854939.7903 | 25440.6752 | 9507939.7903 | 347000 | 9854939.7903 | 25440.6752 | 9880380.4655 | -25441 | 0 | 9854939.4655 | 570980 | 10425919.4655 | 10425919.4196
144 | T06.03 | CEC staff costs | 735277 | 391955.49 | 41045 | 147676 | 106631 | 80924 | 228600 | 0 | 0 | 0 | 0 | 1355832.49 | 1368277.49 | -12445 | 1168277.49 | 200000 | 1368277.49 | -12445 | 1355832.49 | 12445 |  | 1368277.49 | 311251 | 1679528.49 | 1679528.49
145 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
146 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
147 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
148 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
149 | T06.04 | Subtotal CEC | 735277 | 391955.49 | 41045 | 147676 | 106631 | 80924 | 228600 | 0 | 0 | 0 | 0 | 1355832.49 | 1368277.49 | -12445 | 1168277.49 | 200000 | 1368277.49 | -12445 | 1355832.49 | 12445 | 0 | 1368277.49 | 311251 | 1679528.49 | 1679528.49
150 | T06.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
151 | T06.06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
152 | T06.07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
153 | T06.08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
154 | T06.09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
155 | T06.10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
156 | T06.05-10 | Subtotal other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
157 | T06 | Total TSS and CEC | 8993432.4403 | 1679555.856 | 207412.99 | 371051 | 163638.01 | 192173.6592 | 563224.6592 | 0 | 0 | 0 | 0 | 11236212.9555 | 11223217.2803 | 12995.6752 | 10676217.2803 | 547000 | 11223217.2803 | 12995.6752 | 11236212.9555 | -12996 | 0 | 11223216.9555 | 882231 | 12105447.9555 | 12105447.9096
158
159 | T07.01 | Consultancies | 20521.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20521.46 | 20521.46 | 0 | 20521.46 | 0 | 20521.46 | 0 | 20521.46 |  |  | 20521.46 |  | 20521.46 | 20521.46
160 | T07.02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
161 | T07.03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
162 | T07.04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
163 | T07.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
164 | T07 | Total UTILITIES | 20521.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20521.46 | 20521.46 | 0 | 20521.46 | 0 | 20521.46 | 0 | 20521.46 | 0 | 0 | 20521.46 | 0 | 20521.46 | 20521.46
165
166 | T08.01 | Tech. Advisors-Parl.Support | 268642.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268642.76 | 268642.76 | 0 | 268642.76 | 0 | 268642.76 | 0 | 268642.76 |  |  | 268642.76 |  | 268642.76 | 268642.76
167 | T08.02 | Tech. Advisors-Parl.Support-PM | 29382.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29382.99 | 29382.99 | 0 | 29382.99 | 0 | 29382.99 | 0 | 29382.99 |  |  | 29382.99 |  | 29382.99 | 29382.99
168 | T08.03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
169 | T08.04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
170 | T08.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
171 | T08 | Total DESIGN SUPPORT | 298025.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298025.75 | 298025.75 | 0 | 298025.75 | 0 | 298025.75 | 0 | 298025.75 | 0 | 0 | 298025.75 | 0 | 298025.75 | 298025.75
172
173 | T09.01 | Network Rail Legal Costs | 0 | 0 | 0 | 0 | 0 | -68050 | -68050 | 0 | 0 | 0 | 0 | -68050 | 0 | -68050 | 0 | 0 | 0 | -68050 | -68050 |  |  | -68050 | 68050 | 0 | 0
174 | T09.01.01 | Network Rail (PM) | 322555.71 | 526086 | 106075 | 103408 | -2667 | 185575 | 288983 | 0 | 0 | 0 | 0 | 1137624.71 | 990791.71 | 146833 | 437342.71 | 553449 | 990791.71 | 146833 | 1137624.71 | -78783 |  | 1058841.71 | 78783 | 1137624.71 | 1137624.71
175 | T09.01.02 | Network Rail (Legal) | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | 0 | 7500 | 0 | 7500 | 0 | 7500 |  |  | 7500 |  | 7500 | 7500
176 | T09.02 | BAA legal costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
177 | T09.03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
178 | T09.04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
179 | T09.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
180 | T09.06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
181 | T09.07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
182 | T09.08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
183 | T09.09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
184 | T09.10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
185 | T09 | Total 3RD PARTY NEGOTIATIONS | 330055.71 | 526086 | 106075 | 103408 | -2667 | 117525 | 220933 | 0 | 0 | 0 | 0 | 1077074.71 | 998291.71 | 78783 | 444842.71 | 553449 | 998291.71 | 78783 | 1077074.71 | -78783 | 0 | 998291.71 | 146833 | 1145124.71 | 1145124.71
186
187 | T10.01 | D&W (10.01 &11.01) | 25843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25843 | 25843 | 0 | 25843 | 0 | 25843 | 0 | 25843 |  |  | 25843 |  | 25843 | 25843
188 | T10.02 | Advisors (Colliers / DV) | 140489 | -573.23 | 9507.69 | 9507.6923 | 0.0023077 | 31697.3077 | 41205 | 0 | 0 | 0 | 0 | 181120.77 | 201120.75 | -19999.98 | 201120.75 | 0 | 201120.75 | -19999.98 | 181120.77 |  |  | 181120.77 |  | 181120.77 | 181120.77
189 | T10.03 | Technical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
190 | T10.04 | Advance Purchases 05/06 (Fees) | 60181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60181 | 60181 | 0 | 60181 | 0 | 60181 | 0 | 60181 |  |  | 60181 |  | 60181 | 60181
191 | T10.05.01 | Advance Purchases (GVD) | 11726953 | 0 | 0 | 5687 | 5687 | 24313 | 30000 | 0 | 0 | 0 | 0 | 11756953 | 11726953 | 30000 | 13486953 | -1760000 | 11726953 | 30000 | 11756953 |  |  | 11756953 |  | 11756953 | 11756953
192 | T10.05.02 | Advance Purchases (gifted / free issue) | 4298297 | 0 | 508989 | 508989 | 0 | 0 | 508989 | 0 | 0 | 0 | 0 | 4807286 | 4807286 | 0 | 4807286 | 0 | 4807286 | 0 | 4807286 |  |  | 4807286 |  | 4807286 | 4807286
193 | T10.05.03 | Haymarket station compensation | 0 | 157000 | 704000 | 0 | -704000 | 704000 | 704000 | 0 | 162357 | 0 | 0 | 1023357 | 1753357 | -730000 | 0 | 1753357 | 1753357 | -730000 | 1023357 |  |  | 1023357 | -162357 | 861000 | 1652357
194 | T10.05.04 | BAA Legal Agreement | 0 | 111880 | -111880 | 0 | 111880 | 0 | 0 | 0 | 0 | 0 | 0 | 111880 | 0 | 111880 | 0 | 0 | 0 | 111880 | 111880 |  |  | 111880 |  | 111880 | 111880
195 | T10.05.05 | BAA PM Costs | 0 | 309758 | -309758 | 73448.2759 | 383206.2759 | 224827.5862 | 298275.8621 | 0 | 0 | 0 | 0 | 608033.8621 | 0 | 608033.8621 | 0 | 0 | 0 | 608033.8621 | 608033.8621 | 86 |  | 608119.8621 | 410000 | 1018119.8621 | 1018120
196 | T10.05.06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
197 | T10.05.07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
198 | T10.05.08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
199 | T10.05.09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
200 | T10.05.10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
201 | T10.01-.05 | Subtotal Land | 16251763 | 578064.77 | 800858.69 | 597631.9682 | -203226.7218 | 984837.8939 | 1582469.8621 | 0 | 162357 | 0 | 0 | 18574654.6321 | 18574740.75 | -86.1179 | 18581383.75 | -6643 | 18574740.75 | -86.1179 | 18574654.6321 | 86 | 0 | 18574740.6321 | 247643 | 18822383.6321 | 19613740.77 | No deduction for £234k TS opportunity
202 | T10.06.01 | Business Support Primary payment | 568800 | 1069200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1638000 | 1638000 | 0 | 1599791 | 38209 | 1638000 | 0 | 1638000 |  |  | 1638000 |  | 1638000 | 1638000
203 | T10.06.02 | Business Support Enhanced payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | -350000 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
204 | T10.06.03 | Business Support Admin | 16614 | 26198 | 5538 | 5538 | 0 | 1650 | 7188 | 0 | 0 | 0 | 0 | 50000 | 50000 | 0 | 50000 | 0 | 50000 | 0 | 50000 |  |  | 50000 |  | 50000 | 50000
205 | T10.06.04 | Sundry costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
206 | T10.06.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
207 | T10.06.06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
208 | T10.06.07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
209 | T10.06.08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
210 | T10.06.09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
211 | T10.06.10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
212 | T10.06 | Subtotal Business Support | 585414 | 1095398 | 5538 | 5538 | 0 | 1650 | 7188 | 0 | 0 | 0 | 0 | 1688000 | 1688000 | 0 | 1999791 | -311791 | 1688000 | 0 | 1688000 | 0 | 0 | 1688000 | 0 | 1688000 | 1688000
213 | T10.07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
214 | T10.08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
215 | T10.09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
216 | T10.10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
217 | T10.11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
218 | T10.12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
219 | T10.13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
220 | T10.07-13 | Subtotal Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
221 | T10 | Total LAND & PROPERTY | 16837177 | 1673462.77 | 806396.69 | 603169.9682 | -203226.7218 | 986487.8939 | 1589657.8621 | 0 | 162357 | 0 | 0 | 20262654.6321 | 20262740.75 | -86.1179 | 20581174.75 | -318434 | 20262740.75 | -86.1179 | 20262654.6321 | 86 | 0 | 20262740.6321 | 247643 | 20510383.6321 | 21301740.77
222
223 | T11.01 | Legal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
224 | T11.02 | TRO's - Technnical | 1312.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.95 | 1312.95 | 0 | 1312.95 | 0 | 1312.95 | 0 | 1312.95 |  |  | 1312.95 |  | 1312.95 | 1312.95
225 | T11.03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
226 | T11.04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
227 | T11.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
228 | T11.06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
229 | T11.07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
230 | T11.08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
231 | T11.09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
232 | T11.10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
233 | T11 | Total TROs | 1312.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.95 | 1312.95 | 0 | 1312.95 | 0 | 1312.95 | 0 | 1312.95 | 0 | 0 | 1312.95 | 0 | 1312.95 | 1312.95
234
235 | T12.01 | Fees / production Items - WS | 767027.8 | 41126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 808153.8 | 851027.8 | -42874 | 851027.8 | 0 | 851027.8 | -42874 | 808153.8 |  |  | 808153.8 |  | 808153.8 | 808153.8
236 | T12.02 | Fees / production Items - MH | 268692.9 | 128327 | 19500 | 31845 | 12345 | 106150 | 137995 | 0 | 0 | 0 | 0 | 535014.9 | 577692.9 | -42678 | 658692.9 | -81000 | 577692.9 | -42678 | 535014.9 |  |  | 535014.9 |  | 535014.9 | 535014.9
237 | T12.03 | Tram branding | 37500 | 560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38060 | 37500 | 560 | 37500 | 0 | 37500 | 560 | 38060 |  |  | 38060 |  | 38060 | 38060
238 | T12.04 | PR Support | 0 | 20381 | 6000 | 0 | -6000 | 20000 | 20000 | 26000 | 0 | 0 | 0 | 66381 | 90750 | -24369 | 0 | 90750 | 90750 | -24369 | 66381 |  |  | 66381 |  | 66381 | 66381
239 | T12.05 | Business development and marketing | 901 | 0 | 0 | 9645.25 | 9645.25 | 5000 | 14645.25 | 6500 | 0 | 0 | 0 | 22046.25 | 901 | 21145.25 | 901 | 0 | 901 | 21145.25 | 22046.25 |  |  | 22046.25 |  | 22046.25 | 22046.25
240 | T12.06 | Media monitoring | 16455 | -4375 | 0 | 0 | 0 | 750 | 750 | 4875 | 0 | 0 | 0 | 17705 | 31080.3077 | -13375.3077 | 31080.3077 | 0 | 31080.3077 | -13375.3077 | 17705 |  |  | 17705 |  | 17705 | 17705
241 | T12.07 | Media training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19500 | -19500 | 19500 | 0 | 19500 | -19500 | 0 |  |  | 0 |  | 0 | 0
242 | T12.08 | Promotional materials | 7826 | 136150 | 12000 | 4000 | -8000 | 40000 | 44000 | 52000 | 0 | 0 | 0 | 239976 | 80951 | 159025 | 80951 | 0 | 80951 | 159025 | 239976 |  |  | 239976 |  | 239976 | 239976
243 | T12.09 | Websites | 490 | 26941 | 1500 | 1000 | -500 | 5000 | 6000 | 6500 | 0 | 0 | 0 | 39931 | 78490 | -38559 | 78490 | 0 | 78490 | -38559 | 39931 |  |  | 39931 |  | 39931 | 39931
244 | T12.10 | Events | 0 | 13115 | 0 | 3400 | 3400 | 1333.3333 | 4733.3333 | 0 | 0 | 0 | 0 | 17848.3333 | 19000 | -1151.6667 | 39000 | -20000 | 19000 | -1151.6667 | 17848.3333 |  |  | 17848.3333 |  | 17848.3333 | 17848.3333
245 | T12.11 | Advertising | 32618 | 12852 | 3000 | 6800 | 3800 | 10000 | 16800 | 13000 | 0 | 0 | 0 | 75270 | 91118 | -15848 | 91118 | 0 | 91118 | -15848 | 75270 |  |  | 75270 |  | 75270 | 75270
246 | T12.12 | Internal communications | 3835 | 4736 | 1500 | 0 | -1500 | 5000 | 5000 | 6500 | 0 | 0 | 0 | 20071 | 13585 | 6486 | 13585 | 0 | 13585 | 6486 | 20071 |  |  | 20071 |  | 20071 | 20071
247 | T12.23 | Sponsorship | 0 | 17225 | 4500 | 0 | -4500 | 15000 | 15000 | 19500 | 0 | 0 | 0 | 51725 | 31000 | 20725 | 0 | 31000 | 31000 | 20725 | 51725 |  |  | 51725 |  | 51725 | 51725
248 | T12.24 | Communication consultancy services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
249 | T12.25 | Sundries | 0 | 0 | 0 | 0 | 0 | 29609 | 29609 | -72463 | 0 | 0 | 0 | -42854 | 0 | -42854 | 0 | 0 | 0 | -42854 | -42854 | 33268 |  | -9586 | -33268 | -42854 | 0
250 | T12.26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
251 | T12.27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
252 | T12.28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
253 | T12.29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
254 | T12.30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
255 | T12.31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
256 | T12.32 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
257 | T12.33 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
258 | T12.34 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
259 | T12.35 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
260 | T12.36 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
261 | T12.37 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
262 | T12.38 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
263 | T12.39 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
264 | T12.40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
265 | T12.01-12,23-40 | Subtotal Communications | 1135345.7 | 397038 | 48000 | 56690.25 | 8690.25 | 237842.3333 | 294532.5833 | 62412 | 0 | 0 | 0 | 1889328.2833 | 1922596.0077 | -33267.7244 | 1901846.0077 | 20750 | 1922596.0077 | -33267.7244 | 1889328.2833 | 33268 | 0 | 1922596.2833 | -33268 | 1889328.2833 | 1932182.2833
266 | T12.13 | S/H – Wider Community Consultations | 2024 | 34231 | 16038 | 0 | -16038 | 78029 | 78029 | 165823 | 0 | 0 | 0 | 280107 | 321921 | -41814 | 573176 | -251255 | 321921 | -41814 | 280107 | -31956 |  | 248151 | 31956 | 280107 | 280107
267 | T12.14 | S/H – Events | 4649 | 12149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16798 | 24649 | -7851 | 4649 | 20000 | 24649 | -7851 | 16798 |  |  | 16798 |  | 16798 | 16798
268 | T12.15 | S/H – Open for Business | 19745 | 203867 | 75735 | 90587 | 14852 | 237592 | 328179 | 0 | 0 | 0 | 0 | 551791 | 551791 | 0 | 19745 | 532046 | 551791 | 0 | 551791 |  |  | 551791 |  | 551791 | 551791
269 | T12.16 | S/H – Communications - MUDFA | 26800 | 52065 | 0 | 2922 | 2922 | 0 | 2922 | 0 | 0 | 0 | 0 | 81787 | 26800 | 54987 | 26800 | 0 | 26800 | 54987 | 81787 |  |  | 81787 |  | 81787 | 81787
270 | T12.17 | S/H – Communications - Infraco | 0 | 41650 | 0 | -15016 | -15016 | 0 | -15016 | 0 | 0 | 0 | 0 | 26634 | 0 | 26634 | 0 | 0 | 0 | 26634 | 26634 |  |  | 26634 |  | 26634 | 26634
271 | T12.18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
272 | T12.19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
273 | T12.20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
274 | T12.21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
275 | T12.22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
276 | T12.13-22 | Subtotal Stakeholder | 53218 | 343962 | 91773 | 78493 | -13280 | 315621 | 394114 | 165823 | 0 | 0 | 0 | 957117 | 925161 | 31956 | 624370 | 300791 | 925161 | 31956 | 957117 | -31956 | 0 | 925161 | 31956 | 957117 | 957117
277 | T12.41 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
278 | T12.42 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
279 | T12.43 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
280 | T12.44 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
281 | T12.45 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
282 | T12.46 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
283 | T12.47 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
284 | T12.48 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
285 | T12.49 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
286 | T12.50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
287 | T12.41-50 | Subtotal Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
288 | T12 | Total COMMS / MARKETING | 1188563.7 | 741000 | 139773 | 135183.25 | -4589.75 | 553463.3333 | 688646.5833 | 228235 | 0 | 0 | 0 | 2846445.2833 | 2847757.0077 | -1311.7244 | 2526216.0077 | 321541 | 2847757.0077 | -1311.7244 | 2846445.2833 | 1312 | 0 | 2847757.2833 | -1312 | 2846445.2833 | 2889299.2833
289
290 | T13.01 | Non Executive Board | 34352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34352 | 34352 | 0 | 34352 | 0 | 34352 | 0 | 34352 |  |  | 34352 |  | 34352 | 34352
291 | T13.02 | Search Fees | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 0 | 5000 | 0 | 5000 | 0 | 5000 |  |  | 5000 |  | 5000 | 5000
292 | T13.03 | Overheads | 1180095 | 677000 | 157000 | 96200 | -60800 | 314200 | 410400 | 778050 | 635968 | 0 | 0 | 3681513 | 2683781 | 997732 | 2683781 | 0 | 2683781 | 997732 | 3681513 |  |  | 3681513 |  | 3681513 | 3681513
293 | T13.04 |  | 0 | 0 | 0 | 0 | 0 | 174600 | 174600 | -536650 | -635968 | 0 | 0 | -998018 | 0 | -998018 | 0 | 0 | 0 | -998018 | -998018 | 286 |  | -997732 | 997732 | 0 | 0
294 | T13.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
295 | T13 | Total TEL | 1219447 | 677000 | 157000 | 96200 | -60800 | 488800 | 585000 | 241400 | 0 | 0 | 0 | 2722847 | 2723133 | -286 | 2723133 | 0 | 2723133 | -286 | 2722847 | 286 | 0 | 2723133 | 997732 | 3720865 | 3720865
296
297 | T14.01 | Operator Consultancy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
298 | T14.02 | Financial Consultancy | 174893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174893 | 174893 | 0 | 174893 | 0 | 174893 | 0 | 174893 |  |  | 174893 |  | 174893 | 174893
299 | T14.03 | WP1 modelling (FM) | 17184.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17184.03 | 17184.03 | 0 | 17184.03 | 0 | 17184.03 | 0 | 17184.03 |  |  | 17184.03 |  | 17184.03 | 17184.03
300 | T14.04 | WP2 modelling (MVA) | 11148.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148.39 | 11148.39 | 0 | 11148.39 | 0 | 11148.39 | 0 | 11148.39 |  |  | 11148.39 |  | 11148.39 | 11148.39
301 | T14.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
302 | T14 | Total SERVICE INTEGRATION | 203225.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203225.42 | 203225.42 | 0 | 203225.42 | 0 | 203225.42 | 0 | 203225.42 | 0 | 0 | 203225.42 | 0 | 203225.42 | 203225.42
303
304 | T15.01 | INFRACO (PUK) | 259886.64 | 5034 | 0 | -3069 | -3069 | 3069 | 0 | 0 | 0 | 0 | 0 | 264920.64 | 264920.64 | 0 | 264920.64 | 0 | 264920.64 | 0 | 264920.64 |  |  | 264920.64 |  | 264920.64 | 264920.64
305 | T15.02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
306 | T15.03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
307 | T15.04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
308 | T15.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
309 | T15 | Total PUK | 259886.64 | 5034 | 0 | -3069 | -3069 | 3069 | 0 | 0 | 0 | 0 | 0 | 264920.64 | 264920.64 | 0 | 264920.64 | 0 | 264920.64 | 0 | 264920.64 | 0 | 0 | 264920.64 | 0 | 264920.64 | 264920.64
310
311 | T16.01 | Financial advisor 05/06 | 285286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285286 | 285286 | 0 | 285286 | 0 | 285286 | 0 | 285286 |  |  | 285286 |  | 285286 | 285286
312 | T16.02 |  | 0 | 0 | 9042 | 21266 | 12224 | 0 | 21266 | 0 | 0 | 0 | 0 | 21266 | 21266 | 0 | 0 | 21266 | 21266 | 0 | 21266 |  |  | 21266 |  | 21266 | 21266
313 | T16.03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
314 | T16.04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
315 | T16.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
316 | T16 | Total FINANCIAL ADVISOR | 285286 | 0 | 9042 | 21266 | 12224 | 0 | 21266 | 0 | 0 | 0 | 0 | 306552 | 306552 | 0 | 285286 | 21266 | 306552 | 0 | 306552 | 0 | 0 | 306552 | 0 | 306552 | 306552
317
318 | T17.01 | Insurance consultancy | 177118.2444 | 22908.589 | 16105.1392 | 4566.6702 | -11538.469 | 71277.2529 | 75843.9231 | 60000 | 0 | 0 | 0 | 335870.7565 | 362118.2444 | -26247.4879 | 362118.2444 | 0 | 362118.2444 | -26247.4879 | 335870.7565 |  |  | 335870.7565 |  | 335870.7565 | 335870.7565
319 | T17.02 | OCIP | 307222.1528 | 999134.6176 | 234427.0533 | 224040.0187 | -10387.0346 | 906328.1185 | 1130368.1372 | 1180683 | 0 | 0 | 0 | 3617407.9075 | 3591000.3407 | 26407.5668 | 3591000.3407 | 0 | 3591000.3407 | 26407.5668 | 3617407.9075 |  |  | 3617407.9075 |  | 3617407.9075 | 3617407.9075
320 | T17.03 | Claims below deductible | 20811 | -20599 | 75478.1538 | 0.38462 | -75477.7692 | 327347 | 327347.3846 | 125000 | 100000 | 0 | 0 | 552559.3846 | 554350 | -1790.6154 | 554350 | 0 | 554350 | -1790.6154 | 552559.3846 |  |  | 552559.3846 |  | 552559.3846 | 552559.3846
321 | T17.04 | Insurance Claims professional fees | 0 | 2070 | 0 | -276 | -276 | 0 | -276 | 0 | 0 | 0 | 0 | 1794 | 0 | 1794 | 0 | 0 | 0 | 1794 | 1794 |  |  | 1794 |  | 1794 | 1794
322 | T17.05 | Recoverable insurance claims - MUDFA | 0 | 83875 | 0 | 14088 | 14088 | -14088 | 0 | 0 | 0 | 0 | 0 | 83875 | 83875 | 0 | 0 | 83875 | 83875 | 0 | 83875 |  |  | 83875 |  | 83875 | 83875
323 | T17.06 | Non-recoverable insurance claims - MUDFA | 0 | 448 | 0 | 62 | 62 | -62 | 0 | 0 | 0 | 0 | 0 | 448 | 448 | 0 | 0 | 448 | 448 | 0 | 448 | -163 |  | 285 | 163 | 448 | 448
324 | T17.07 | Recoverable insurance claims - Infraco | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
325 | T17.08 | Non-recoverable insurance claims - Infraco | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
326 | T17.09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
327 | T17.10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
328 | T17.11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
329 | T17.12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
330 | T17.13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
331 | T17.14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
332 | T17.15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
333 | T17.16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
334 | T17.17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
335 | T17.18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
336 | T17.19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
337 | T17.20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
338 | T17 | Total INSURANCE | 505151.3971 | 1087837.2066 | 326010.3463 | 242481.0735 | -83529.2728 | 1290802.3714 | 1533283.4449 | 1365683 | 100000 | 0 | 0 | 4591955.0486 | 4591791.585 | 163.4636 | 4507468.585 | 84323 | 4591791.585 | 163.4636 | 4591955.0486 | -163 | 0 | 4591792.0486 | 163 | 4591955.0486 | 4591955.0486
339
340 | T18.01.01 | Pre-construction Services | 0 | 0 | 0 | 0 | 0 | 8743 | 8743 | 0 | 0 | 0 | 0 | 8743 | 0 | 8743 | 0 | 0 | 0 | 8743 | 8743 |  |  | 8743 |  | 8743 | 8743
341 | T18.01.02 | Contract prelims | 133504 | 4579467 | 1049000 | 951000 | -98000 | 415000 | 1366000 | 0 | 0 | 0 | 0 | 6078971 | 5761971 | 317000 | 2498294 | 3263677 | 5761971 | 317000 | 6078971 |  |  | 6078971 |  | 6078971 | 6078971
342 | T18.01.03 | Section 1a | 674275 | 3263204 | 0 | 579210 | 579210 | 0 | 579210 | 0 | 0 | 0 | 0 | 4516689 | 3937479 | 579210 | 4745026 | -807547 | 3937479 | 579210 | 4516689 |  |  | 4516689 |  | 4516689 | 4516689
343 | T18.01.04 | Section 1b | 724219 | 808413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1532632 | 1532632 | 0 | 1432072 | 100560 | 1532632 | 0 | 1532632 |  |  | 1532632 |  | 1532632 | 1532632
344 | T18.01.05 | Section 1c | 401641 | 3476903 | 0 | 584589 | 584589 | 113900 | 698489 | 0 | 0 | 0 | 0 | 4577033 | 3878544 | 698489 | 3098049 | 780495 | 3878544 | 698489 | 4577033 |  |  | 4577033 |  | 4577033 | 4577033
345 | T18.01.06 | Section 1d | 218376 | 2623511 | 0 | 330000 | 330000 | 0 | 330000 | 0 | 0 | 0 | 0 | 3171887 | 2841887 | 330000 | 3132338 | -290451 | 2841887 | 330000 | 3171887 |  |  | 3171887 |  | 3171887 | 3171887
346 | T18.01.07 | Section 2 | 0 | 2109689 | 0 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 2209689 | 2109689 | 100000 | 3318721 | -1209032 | 2109689 | 100000 | 2209689 |  |  | 2209689 |  | 2209689 | 2209689
347 | T18.01.08 | Section 3a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
348 | T18.01.09 | Section 3b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
349 | T18.01.10 | Section 3c | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
350 | T18.01.11 | Section 4a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
351 | T18.01.12 | Section 4b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
352 | T18.01.13 | Section 5a | 158424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158424 | 158424 | 0 | 158424 | 0 | 158424 | 0 | 158424 |  |  | 158424 |  | 158424 | 158424
353 | T18.01.14 | Section 5b | 0 | 601934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 601934 | 601934 | 0 | 0 | 601934 | 601934 | 0 | 601934 |  |  | 601934 |  | 601934 | 601934
354 | T18.01.15 | Section 5c | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
355 | T18.01.16 | Section 6 | -67800 | 2083312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2015512 | 2015512 | 0 | 285046 | 1730466 | 2015512 | 0 | 2015512 |  |  | 2015512 |  | 2015512 | 2015512
356 | T18.01.17 | Section 7 | 29598 | 2937193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2966791 | 2966791 | 0 | 4767438 | -1800647 | 2966791 | 0 | 2966791 |  |  | 2966791 |  | 2966791 | 2966791
357 | T18.01.18 | Unallocated to section | 9561224.0699 | 4681861 | 566953 | 1765520 | 1198567 | 870400 | 2635920 | 0 | 0 | 0 | 0 | 16879005.0699 | 14748688.0699 | 2130317 | 11417922.0699 | 3330766 | 14748688.0699 | 2130317 | 16879005.0699 | -4028359 |  | 12850646.0699 |  | 12850646.0699 | 16879005.0699
358 | T18.01.19 | Variations | 1021632 | 1875246 | 0 | 0 | 0 | -135400 | -135400 | 0 | 0 | 0 | 0 | 2761478 | 2896878 | -135400 | 1937162 | 959716 | 2896878 | -135400 | 2761478 |  |  | 2761478 |  | 2761478 | 2896878
359 | T18.01.20 | Reserve | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
360 | T18.01.21 | Claim(s) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
361 | T18.01.22 | Transfer to / from Infraco | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | -125000 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
362 | T18.01.23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
363 | T18.01.24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
364 | T18.01.25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
365 | T18.01.26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
366 | T18.01.27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
367 | T18.01.28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
368 | T18.01.29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
369 | T18.01.30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
370 | T18.01 | Subtotal MUDFA | 12855093.0699 | 29040733 | 1615953 | 4310319 | 2694366 | 1272643 | 5582962 | 0 | 0 | 0 | 0 | 47478788.0699 | 43450429.0699 | 4028359 | 36915492.0699 | 6534937 | 43450429.0699 | 4028359 | 47478788.0699 | -4028359 | 0 | 43450429.0699 | 0 | 43450429.0699 | 47614188.0699
371 | T18.02.01 | Pre-construction Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
372 | T18.02.02 | Contract prelims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
373 | T18.02.03 | Section 1a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
374 | T18.02.04 | Section 1b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
375 | T18.02.05 | Section 1c | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
376 | T18.02.06 | Section 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
377 | T18.02.07 | Section 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
378 | T18.02.08 | Section 3a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
379 | T18.02.09 | Section 3b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
380 | T18.02.10 | Section 3c | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
381 | T18.02.11 | Section 4a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
382 | T18.02.12 | Section 4b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
383 | T18.02.13 | Section 5a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
384 | T18.02.14 | Section 5b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
385 | T18.02.15 | Section 5c | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
386 | T18.02.16 | Section 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
387 | T18.02.17 | Section 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
388 | T18.02.18 | Unallocated to section | 5516945.77 | 4356513 | 0 | -1135816 | -1135816 | -750000 | -1885816 | 0 | 0 | 0 | 0 | 7987642.77 | 9873458.77 | -1885816 | 11627213.77 | -1753755 | 9873458.77 | -1885816 | 7987642.77 | 1885516 |  | 9873158.77 |  | 9873158.77 | 7987642.77
389 | T18.02.19 | Variations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
390 | T18.02.20 | Reserve | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
391 | T18.02.21 | Claim(s) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
392 | T18.02.22 | Transfer to infraco | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
393 | T18.02.23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
394 | T18.02.24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
395 | T18.02.25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
396 | T18.02.26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
397 | T18.02.27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
398 | T18.02.28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
399 | T18.02.29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
400 | T18.02.30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
401 | T18.02 | Subtotal utilities | 5516945.77 | 4356513 | 0 | -1135816 | -1135816 | -750000 | -1885816 | 0 | 0 | 0 | 0 | 7987642.77 | 9873458.77 | -1885816 | 11627213.77 | -1753755 | 9873458.77 | -1885816 | 7987642.77 | 1885516 | 0 | 9873158.77 | 0 | 9873158.77 | 7987642.77
402 | T18 | Total MUDFA / Utilities | 18372038.8399 | 33397246 | 1615953 | 3174503 | 1558550 | 522643 | 3697146 | 0 | 0 | 0 | 0 | 55466430.8399 | 53323887.8399 | 2142543 | 48542705.8399 | 4781182 | 53323887.8399 | 2142543 | 55466430.8399 | -2142843 | 0 | 53323587.8399 | 0 | 53323587.8399 | 55601830.8399
403
404 | T19.01.01 | Prelims | 0 | 17381623.1454 | 4701963.2821 | 4701963.183 | -0.099088 | 14698851.6357 | 19400814.8188 | 12328751.3411 | 4218532.2756 | 0 | 0 | 53329721.5808 | 53329721.6799 | -0.099088 | 53329721.6799 | 0 | 53329721.6799 | -0.099088 | 53329721.5808 |  |  | 53329721.5808 |  | 53329721.5808 | 53329721.5808
405 | T19.01.02 | Infraco early mobilisation | 1537744.63 | 7000000.37 | -0.37 | 0 | 0.37 | 0 | 0 | 0 | 0 | 0 | 0 | 8537745 | 8537744.63 | 0.37 | 8537744.63 | 0 | 8537744.63 | 0.37 | 8537745 |  |  | 8537745 |  | 8537745 | 8537745
406 | T19.01.03 | Advanced purchases | 18000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000000 | 18000000 | 0 | 18000000 | 0 | 18000000 | 0 | 18000000 |  |  | 18000000 |  | 18000000 | 18000000
407 | T19.01.04 | Transfer to / from MUDFA | 27287 | 0 | 0 | -27287 | -27287 | 0 | -27287 | 0 | 0 | 0 | 0 | 0 | 27287 | -27287 | 27287 | 0 | 27287 | -27287 | 0 |  |  | 0 |  | 0 | 0
408 | T19.01.05 | Section 1a | 0 | 0 | 16.2259 | 0 | -16.2259 | 4321923.4278 | 4321923.4278 | 6660790.5158 | 4709897.6124 | 0 | 0 | 15692611.5559 | 15692627.7819 | -16.2259 | 15692627.7819 | 0 | 15692627.7819 | -16.2259 | 15692611.5559 |  |  | 15692611.5559 |  | 15692611.5559 | 15692611.5559
409 | T19.01.06 | Section 1b | 0 | 107878.3804 | 5.9394 | 0 | -5.9394 | 2238064.0187 | 2238064.0187 | 2287813.5683 | 2073729.5367 | 0 | 0 | 6707485.5041 | 6707491.4436 | -5.9394 | 6707491.4436 | 0 | 6707491.4436 | -5.9394 | 6707485.5041 |  |  | 6707485.5041 |  | 6707485.5041 | 6707485.5041
410 | T19.01.07 | Section 1c | 0 | 0 | 77087.5908 | 0 | -77087.5908 | 2484104.4122 | 2484104.4122 | 6066463.4396 | 1265123.4162 | 0 | 0 | 9815691.2681 | 9815693.0039 | -1.7358 | 9815693.0039 | 0 | 9815693.0039 | -1.7358 | 9815691.2681 |  |  | 9815691.2681 |  | 9815691.2681 | 9815691.2681
411 | T19.01.08 | Section 1d | 0 | 56211.6749 | 155664.316 | 246836.1547 | 91171.8387 | 2430988.766 | 2677824.9208 | 3370505.6045 | 7692.7181 | 0 | 0 | 6112234.9182 | 6112236.1346 | -1.2164 | 6112236.1346 | 0 | 6112236.1346 | -1.2164 | 6112234.9182 |  |  | 6112234.9182 |  | 6112234.9182 | 6112234.9182
412 | T19.01.09 | Section 2 | 0 | 378837.0343 | 123599.0761 | 0 | -123599.0761 | 4313737.9138 | 4313737.9138 | 809092.5296 | 0 | 0 | 0 | 5501667.4778 | 5501667.2031 | 0.27465 | 5501667.2031 | 0 | 5501667.2031 | 0.27465 | 5501667.4778 |  |  | 5501667.4778 |  | 5501667.4778 | 5501667.4778
413 | T19.01.10 | Section 3a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
414 | T19.01.11 | Section 3b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
415 | T19.01.12 | Section 3c | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
416 | T19.01.13 | Section 4a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
417 | T19.01.14 | Section 4b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
418 | T19.01.15 | Section 5a | 0 | 417311.8393 | -42111.5552 | -159441.7176 | -117330.1624 | 6692911.8125 | 6533470.0949 | 8622499.8847 | 3456525.0528 | 0 | 0 | 19029806.8717 | 19029806.3921 | 0.47958 | 19029806.3921 | 0 | 19029806.3921 | 0.47958 | 19029806.8717 |  |  | 19029806.8717 |  | 19029806.8717 | 19029806.8717
419 | T19.01.16 | Section 5b | 0 | 1298137.1266 | 177153.4715 | 0 | -177153.4715 | 15132846.3642 | 15132846.3642 | 3600194.4834 | 10534.0675 | 0 | 0 | 20041712.0417 | 20041708.9132 | 3.1285 | 20041708.9132 | 0 | 20041708.9132 | 3.1285 | 20041712.0417 |  |  | 20041712.0417 |  | 20041712.0417 | 20041712.0417
420 | T19.01.17 | Section 5c | 0 | 112688.5099 | -10767.0587 | -10767.3556 | -0.29689 | 7187504.5335 | 7176737.1778 | 3767583.887 | 0 | 0 | 0 | 11057009.5748 | 11057009.8717 | -0.29689 | 11057009.8717 | 0 | 11057009.8717 | -0.29689 | 11057009.5748 |  |  | 11057009.5748 |  | 11057009.5748 | 11057009.5748
421 | T19.01.18 | Section 6 | 0 | 18537.6328 | 185375.6735 | 0 | -185375.6735 | 8862651.7967 | 8862651.7967 | 4085875.9067 | 0 | 0 | 0 | 12967065.3362 | 12967064.682 | 0.65416 | 12967064.682 | 0 | 12967064.682 | 0.65416 | 12967065.3362 |  |  | 12967065.3362 |  | 12967065.3362 | 12967065.3362
422 | T19.01.19 | Section 7 | 0 | 397288.8552 | 37545.9156 | 0 | -37545.9156 | 2031128.0038 | 2031128.0038 | 8700758.6314 | 409.09 | 0 | 0 | 11129584.5805 | 11129563.9561 | 20.6244 | 11129563.9561 | 0 | 11129563.9561 | 20.6244 | 11129584.5805 |  |  | 11129584.5805 |  | 11129584.5805 | 11129584.5805
423 | T19.01.20 | Unallocated to section | 18240000 | 0 | 0 | 0 | 0 | -25746571 | -25746571 | 0 | 0 | 0 | 0 | -7506571 | 18240000 | -25746571 | 18240000 | 0 | 18240000 | -25746571 | -7506571 |  |  | -7506571 |  | -7506571 | 18240000
424 | T19.01.21 | NR Immunisation | 0 | 225845.7692 | 62770.8464 | 0 | -62770.8464 | 2008783.6364 | 2008783.6364 | 739272.4091 | 26097.9545 | 0 | 0 | 2999999.7692 | 3000000.231 | -0.46177 | 3000000.231 | 0 | 3000000.231 | -0.46177 | 2999999.7692 |  |  | 2999999.7692 |  | 2999999.7692 | 2999999.7692
425 | T19.01.22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
426 | T19.01.23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
427 | T19.01.24 | Report adjustment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7641400.7439 | -3935737.502 | 0 | 0 | -11577138.2459 | 0 | -11577138.2459 | 0 | 0 | 0 | -11577138.2459 | -11577138.2459 | 289157 |  | -11287981.2459 |  | -11287981.2459 | 0
428 | T19.01.05-24 | Subtotal Construction | 37805031.63 | 27394360.3379 | 5468303.3535 | 4751303.2645 | -717000.0889 | 46656925.3213 | 51408228.5859 | 53398201.4576 | 11832804.2217 | 0 | 0 | 181838626.2331 | 219189622.923 | -37350996.6899 | 219189622.923 | 0 | 219189622.923 | -37350996.6899 | 181838626.2331 | 289157 | 0 | 182127783.2331 | 0 | 182127783.2331 | 219162335.479
429 | T19.01.25 | Testing and commissioning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
430 | T19.01.26 | Maintenance mobilisation and spare parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1255163.2857 | 1540217.7143 | 0 | 0 | 2795381 | 2795381 | 0 | 2795381 | 0 | 2795381 | 0 | 2795381 |  |  | 2795381 |  | 2795381 | 2795381
431 | T19.01.35 | Variations - Prelims | 0 | 125297 | -125297 | -78565 | 46732 | 755000 | 676435 | 1010000 | 2700000 | 0 | 0 | 4511732 | 9262 | 4502470 | 0 | 9262 | 9262 | 4502470 | 4511732 |  |  | 4511732 |  | 4511732 | 4511732
432 | T19.01.36 | Variations - Section 1a | 0 | 14067 | 8814 | 47973 | 39159 | 109688 | 157661 | 5000 | 50000 | 0 | 0 | 226728 | 22881 | 203847 | 0 | 22881 | 22881 | 203847 | 226728 |  |  | 226728 |  | 226728 | 226728
433 | T19.01.37 | Variations - Section 1b | 0 | 558625 | -548325 | -245655 | 302670 | 491112 | 245457 | 1900000 | 480000 | 0 | 0 | 3184082 | 11507 | 3172575 | 0 | 11507 | 11507 | 3172575 | 3184082 |  |  | 3184082 |  | 3184082 | 3184082
434 | T19.01.38 | Variations - Section 1c | 0 | 0 | 0 | 10768 | 10768 | 619941 | 630709 | 439652 | 0 | 0 | 0 | 1070361 | 0 | 1070361 | 0 | 0 | 0 | 1070361 | 1070361 |  |  | 1070361 |  | 1070361 | 1070361
435 | T19.01.39 | Variations - Section 1d | 0 | 91547 | -91547 | 577308 | 668855 | 2147889 | 2725197 | 150000 | 0 | 0 | 0 | 2966744 | 0 | 2966744 | 0 | 0 | 0 | 2966744 | 2966744 |  |  | 2966744 |  | 2966744 | 2966744
436 | T19.01.40 | Variations - Section 2 | 0 | 54251 | -13984 | 41186 | 55170 | 310852 | 352038 | 8043 | 0 | 0 | 0 | 414332 | 40267 | 374065 | 0 | 40267 | 40267 | 374065 | 414332 |  |  | 414332 |  | 414332 | 414332
437 | T19.01.41 | Variations - Section 3a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
438 | T19.01.42 | Variations - Section 3b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
439 | T19.01.43 | Variations - Section 3c | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
440 | T19.01.44 | Variations - Section 4a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
441 | T19.01.45 | Variations - Section 4b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
442 | T19.01.46 | Variations - Section 5a | 0 | 62074 | -47074 | 28762 | 75836 | 5782333 | 5811095 | 155000 | 0 | 0 | 0 | 6028169 | 108332 | 5919837 | 0 | 108332 | 108332 | 5919837 | 6028169 |  |  | 6028169 |  | 6028169 | 6028169
443 | T19.01.47 | Variations - Section 5b | 0 | 83015 | 88266.33 | 108107 | 19840.67 | 3787834 | 3895941 | 115694 | 0 | 0 | 0 | 4094650 | 649045.99 | 3445604.01 | 0 | 649045.99 | 649045.99 | 3445604.01 | 4094650 |  |  | 4094650 |  | 4094650 | 4094650
444 | T19.01.48 | Variations - Section 5c | 0 | 0 | 15747.55 | 26759 | 11011.45 | 1867816 | 1894575 | 155000 | 0 | 0 | 0 | 2049575 | 222737.99 | 1826837.01 | 0 | 222737.99 | 222737.99 | 1826837.01 | 2049575 |  |  | 2049575 |  | 2049575 | 2049575
445 | T19.01.49 | Variations - Section 6 | 0 | 171963 | -160647 | 1312223 | 1472870 | 265797 | 1578020 | 0 | 0 | 0 | 0 | 1749983 | 1463833 | 286150 | 0 | 1463833 | 1463833 | 286150 | 1749983 |  |  | 1749983 |  | 1749983 | 1749983
446 | T19.01.50 | Variations - Section 7 | 0 | 265892 | -221541 | 85816 | 307357 | 4446305 | 4532121 | 75000 | 0 | 0 | 0 | 4873013 | 76937 | 4796076 | 0 | 76937 | 76937 | 4796076 | 4873013 |  |  | 4873013 |  | 4873013 | 4873013
447 | T19.01.27 | Variations - Unallocated to section | 0 | 918714 | -464979.81 | 111257 | 576236.81 | 3939902 | 4051159 | 1900000 | 0 | 0 | 0 | 6869873 | 1677210.05 | 5192662.95 | 0 | 1677210.05 | 1677210.05 | 5192662.95 | 6869873 |  |  | 6869873 |  | 6869873 | 6869873
448 | T19.01.51 | Variations - NR Immunisation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
449 | T19.01.52 | Variations - Princes Street | 0 | 59123 | -59123 | 111496 | 170619 | 176069.0952 | 287565.0952 | 0 | 0 | 0 | 0 | 346688.0952 | 0 | 346688.0952 | 0 | 0 | 0 | 346688.0952 | 346688.0952 |  |  | 346688.0952 |  | 346688.0952 | 346688.0952
450 | T19.01.53 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
451 | T19.01.54 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
452 | T19.01.27, 35-54 | Subtotal Variations / Changes | 0 | 2404568 | -1619689.93 | 2137435 | 3757124.93 | 24700538.0952 | 26837973.0952 | 7168552.2857 | 4770217.7143 | 0 | 0 | 41181311.0952 | 7077394.03 | 34103917.0652 | 2795381 | 4282013.03 | 7077394.03 | 34103917.0652 | 41181311.0952 | 0 | 0 | 41181311.0952 | 0 | 41181311.0952 | 41181311.0952
453 | T19.01.28 | Infraco contingency | 0 | 17226 | 15112 | 37831.86 | 22719.86 | 44942 | 82773.86 | 0 | 0 | 0 | 0 | 99999.86 | 100000 | -0.14 | 16395328 | -16295328 | 100000 | -0.14 | 99999.86 |  |  | 99999.86 |  | 99999.86 | 99999.86
454 | T19.01.29 | Contingency (VE) | 0 | 184615.3846 | 138461.106 | 138461.5385 | 0.43243 | 461538.4615 | 600000 | 415384.6154 | 0 | 0 | 0 | 1200000 | 1199999.5676 | 0.43243 | 1199999.5676 | 0 | 1199999.5676 | 0.43243 | 1200000 |  |  | 1200000 |  | 1200000 | 1200000
455 | T19.01.30 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
456 | T19.01.31 | EAL - Burnside road | 0 | 139263 | 146666 | -139263 | -285929 | 0 | -139263 | 0 | 0 | 0 | 0 | 0 | 1000000 | -1000000 | 1000000 | 0 | 1000000 | -1000000 | 0 |  |  | 0 |  | 0 | 0
457 | T19.01.32 | Provisional sum saving | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -350000 | 350000 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
458 | T19.01.33 | Tapered poles | 0 | 0 | -1.819e-11 | 0 | 1.819e-11 | 70552.4 | 70552.4 | 105828.6 | 0 | 0 | 0 | 176381 | 176381 | 0 | 176381 | 0 | 176381 | 0 | 176381 |  |  | 176381 |  | 176381 | 176381
459 | T19.01.34 | Power for comissioning | 0 | 0 | 0 | 0 | 0 | 171666.6667 | 171666.6667 | 743888.8889 | 114444.4444 | 0 | 0 | 1030000 | 1030000 | 0 | 1030000 | 0 | 1030000 | 0 | 1030000 |  |  | 1030000 |  | 1030000 | 1030000
460 | T19.01.55 | Allowance for demolition of existing Leith Walk substation (if required) | 0 | 0 | 50000 | 0 | -50000 | 200000 | 200000 | 0 | 0 | 0 | 0 | 200000 | 55662 | 144338 | 0 | 55662 | 55662 | 144338 | 200000 |  |  | 200000 |  | 200000 | 200000
461 | T19.01.56 | Accommodation Works | 0 | 0 | 0 | 1844 | 1844 | 350000 | 351844 | 648156 | 0 | 0 | 0 | 1000000 | 1000000 | 0 | 0 | 1000000 | 1000000 | 0 | 1000000 |  |  | 1000000 |  | 1000000 | 1000000
462 | T19.01.57 | PICOPS / COSS / Possession Protection Staff support when undertaking works adjacent or over the railway | 0 | 45000 | 30000 | 30000 | 0 | 140000 | 170000 | 235000 | 0 | 0 | 0 | 450000 | 655307 | -205307 | 0 | 655307 | 655307 | -205307 | 450000 |  |  | 450000 |  | 450000 | 450000
463 | T19.01.58 | Additional Crew Relief Facilities at Haymarket | 0 | 0 | 0 | 0 | 0 | 130000 | 130000 | 0 | 0 | 0 | 0 | 130000 | 49950 | 80050 | 0 | 49950 | 49950 | 80050 | 130000 |  |  | 130000 |  | 130000 | 130000
464 | T19.01.59 | RBS requirement for enhancement of Gogarburn Tramstop | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
465 | T19.01.60 | Pumped surface water outfall at A8 underpass (by depot) | 0 | 0 | 10000 | 0 | -10000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 100000 | 100000 | 0 | 0 | 100000 | 100000 | 0 | 100000 |  |  | 100000 |  | 100000 | 100000
466 | T19.01.61 | Relocation of Ancient Monuments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
467 | T19.01.62 | Extra over for revised alignment to Picardy Pl, York Pl and London Rd junctions (see also next item) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 0 | 0 | 0 | 2950000 | 3340324 | -390324 | 350000 | 2990324 | 3340324 | -390324 | 2950000 |  |  | 2950000 |  | 2950000 | 2950000
468 | T19.01.63 | Extra over for major utility diversions Picardy Pl, York Pl and London Rd junctions | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 700000 | 0 | 0 | 0 | 1000000 | 2650000 | -1650000 | -350000 | 3000000 | 2650000 | -1650000 | 1000000 |  |  | 1000000 |  | 1000000 | 1000000
469 | T19.01.64 | Extra over for shell grip at junctions | 0 | 0 | 0 | 0 | 0 | 185000 | 185000 | 134343 | 0 | 0 | 0 | 319343 | 319343 | 0 | 0 | 319343 | 319343 | 0 | 319343 |  |  | 319343 |  | 319343 | 319343
470 | T19.01.65 | Allowance for SP connections to new street lights and new traffic signals | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 40287 | 0 | 0 | 0 | 115287 | 115287 | 0 | 0 | 115287 | 115287 | 0 | 115287 |  |  | 115287 |  | 115287 | 115287
471 | T19.01.66 | UTC associated with the delivery of the alignment | 0 | 0 | 13332 | 50000 | 36668 | 675000 | 725000 | 2175000 | 280000 | 0 | 0 | 3180000 | 2400000 | 780000 | 0 | 2400000 | 2400000 | 780000 | 3180000 |  |  | 3180000 |  | 3180000 | 3180000
472 | T19.01.67 | Various FP requirements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
473 | T19.01.68 | FP requirements at Ocean Terminal amendments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
474 | T19.01.69 | Allowance for minor utility diversions | 0 | 0 | 40000 | 21000 | -19000 | 329000 | 350000 | 375000 | 25000 | 0 | 0 | 750000 | 750000 | 0 | 0 | 750000 | 750000 | 0 | 750000 |  |  | 750000 |  | 750000 | 750000
475 | T19.01.70 | Archaeological Officer – impact on productivity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405755 | 0 | 0 | 0 | 405755 | 405755 | 0 | 0 | 405755 | 405755 | 0 | 405755 |  |  | 405755 |  | 405755 | 405755
476 | T19.01.71 | UTC associated with the wider area impacts | 0 | 0 | 387700 | 0 | -387700 | 639000 | 639000 | 1352300 | 0 | 0 | 0 | 1991300 | 2482300 | -491000 | -17700 | 2500000 | 2482300 | -491000 | 1991300 |  |  | 1991300 |  | 1991300 | 1991300
477 | T19.01.72 | FP requirements for design and construction of by-pass road to adoptable standard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
478 | T19.01.73 | FP requirements for Lindsay Rd amendments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
479 | T19.01.74 | NR compliant ballast | 0 | 0 | 0 | 0 | 0 | 90000 | 90000 | 210000 | 0 | 0 | 0 | 300000 | 300000 | 0 | 0 | 300000 | 300000 | 0 | 300000 |  |  | 300000 |  | 300000 | 300000
480 | T19.01.75 | SP connections to the depot and IPR | 0 | 723725 | -505294.3613 | 0 | 505294.3613 | 250000 | 250000 | 350000 | 40994 | 0 | 0 | 1364719 | 750000 | 614719 | 0 | 750000 | 750000 | 614719 | 1364719 |  |  | 1364719 |  | 1364719 | 1364719
481 | T19.01.76 | SP connections to Phase 1a sub-stations | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000 | 0 | 0 | 400000 | 400000 | 0 | 400000 |  |  | 400000 |  | 400000 | 400000
482 | T19.01.77 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
483 | T19.01.78 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
484 | T19.01.79 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
485 | T19.01.80 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
486 | T19.01.81 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
487 | T19.01.82 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
488 | T19.01.83 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
489 | T19.01.84 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
490 | T19.01.85 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
491 | T19.01.86 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
492 | T19.01.87 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
493 | T19.01.88 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
494 | T19.01.89 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
495 | T19.01.90 | Prov sum balancing code | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626524 | 0 | 0 | 0 | 626524 | -65875 | 692399 | 0 | -65875 | -65875 | 692399 | 626524 |  |  | 626524 |  | 626524 | 626524
496 | T19.01.55-90 | Subtotal Provisional sums | 0 | 1509829.3846 | 325976.7448 | 139874.3985 | -186102.3463 | 4211699.5282 | 4351573.9267 | 11467467.1043 | 460438.4444 | 0 | 0 | 17789308.86 | 19214433.5676 | -1425124.7076 | 3488680.5676 | 15725753 | 19214433.5676 | -1425124.7076 | 17789308.86 | 0 | 0 | 17789308.86 | 0 | 17789308.86 | 17789308.86
497 | T19.01.91 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
498 | T19.01.92 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
499 | T19.01.93 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
500 | T19.01.94 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
501 | T19.01.95 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
502 | T19.01.96 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
503 | T19.01.97 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
504 | T19.01.98 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
505 | T19.01.99 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
506 | T19.01.100 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
507 | T19.01.101 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
508 | T19.01.102 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
509 | T19.01.103 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
510 | T19.01.104 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
511 | T19.01.105 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
512 | T19.01.106 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
513 | T19.01.107 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
514 | T19.01.108 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
515 | T19.01.109 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
516 | T19.01.110 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
517 | T19.01.111 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
518 | T19.01.112 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
519 | T19.01.113 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
520 | T19.01.114 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
521 | T19.01.115 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
522 | T19.01.116 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
523 | T19.01.117 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
524 | T19.01.118 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
525 | T19.01.119 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
526 | T19.01.120 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
527 | T19.01.121 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
528 | T19.01.122 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
529 | T19.01.123 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
530 | T19.01.124 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
531 | T19.01.125 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
532 | T19.01 | Subtotal Infraco main works | 37805031.63 | 31308757.7226 | 4174590.1682 | 7028612.663 | 2854022.4948 | 75569162.9448 | 82597775.6078 | 72034220.8476 | 17063460.3805 | 0 | 0 | 240809246.1883 | 245481450.5206 | -4672204.3322 | 241419012.4906 | 4062438.03 | 245481450.5206 | -4672204.3322 | 240809246.1883 | 289157 | 0 | 241098403.1883 | 0 | 241098403.1883 | 278132955.4342
533 | T19.04.01 | Advanced purchases | -15500000 | 21249.2345 | 44919.0116 | 25707.2428 | -19211.7688 | 6041579.9916 | 6067287.2344 | 7122027.6533 | 2289435.9517 | 0 | 0 | 0.073933 | -0.00033569 | 0.074269 | -0.00033569 | 0 | -0.00033569 | 0.074269 | 0.073933 |  |  | 0.073933 |  | 0.073933 | 0.073933
534 | T19.04.02 | ??????????????? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
535 | T19.04.03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
536 | T19.04.04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
537 | T19.04.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
538 | T19.04 | Subtotal Funding adjustment | -15500000 | 21249.2345 | 44919.0116 | 25707.2428 | -19211.7688 | 6041579.9916 | 6067287.2344 | 7122027.6533 | 2289435.9517 | 0 | 0 | 0.073933 | -0.00033569 | 0.074269 | -0.00033569 | 0 | -0.00033569 | 0.074269 | 0.073933 | 0 | 0 | 0.073933 | 0 | 0.073933 | 0.073933
539 | T19.02.01 | SRU Murrayfield pitches | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
540 | T19.02.02 | Relocate historic monuments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 | -42000 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
541 | T19.02.03 | Environ. impacts - badgers | 24900 | 5012 | 0 | -3186 | -3186 | 0 | -3186 | 0 | 0 | 0 | 0 | 26726 | 29912 | -3186 | 32000 | -2088 | 29912 | -3186 | 26726 | 3186 |  | 29912 |  | 29912 | 26726
542 | T19.02.04 | Invasive species | 92379 | 80024 | 30000 | 33186 | 3186 | 62538 | 95724 | 0 | 0 | 0 | 0 | 268127 | 269917 | -1790 | 299917 | -30000 | 269917 | -1790 | 268127 | 1790 |  | 269917 |  | 269917 | 268127
543 | T19.02.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
544 | T19.02.06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
545 | T19.02.07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
546 | T19.02.08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
547 | T19.02.09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
548 | T19.02.10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
549 | T19.02.11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
550 | T19.02.12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
551 | T19.02.13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
552 | T19.02.14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
553 | T19.02.15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
554 | T19.02 | Subtotal advance works | 117279 | 85036 | 30000 | 30000 | 0 | 62538 | 92538 | 0 | 0 | 0 | 0 | 294853 | 299829 | -4976 | 373917 | -74088 | 299829 | -4976 | 294853 | 4976 | 0 | 299829 | 0 | 299829 | 294853
555 | T19.03.01 | Unallocated | 134574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134574 | 134574 | 0 | 134574 | 0 | 134574 | 0 | 134574 |  |  | 134574 |  | 134574 | 134574
556 | T19.03.02 | Set up / mobilisation | 179741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179741 | 179741 | 0 | 179741 | 0 | 179741 | 0 | 179741 |  |  | 179741 |  | 179741 | 179741
557 | T19.03.03 | Phase 1 (150,000m3) | 2914685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2914685 | 2914685 | 0 | 2914685 | 0 | 2914685 | 0 | 2914685 |  |  | 2914685 |  | 2914685 | 2914685
558 | T19.03.04 | Phase 2 (100,000m3) | 2209987 | -609 | 609 | 0 | -609 | 0 | 0 | 0 | 0 | 0 | 0 | 2209378 | 2209987 | -609 | 2209987 | 0 | 2209987 | -609 | 2209378 | 609 |  | 2209987 |  | 2209987 | 2209378
559 | T19.03.05 | Phase 3 (94,093m3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
560 | T19.03.06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
561 | T19.03.07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
562 | T19.03.08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
563 | T19.03.09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
564 | T19.03.10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
565 | T19.03 | Subtotal depot advance works | 5438987 | -609 | 609 | 0 | -609 | 0 | 0 | 0 | 0 | 0 | 0 | 5438378 | 5438987 | -609 | 5438987 | 0 | 5438987 | -609 | 5438378 | 609 | 0 | 5438987 | 0 | 5438987 | 5438378
566 | T19.06.01 | VE - Optimise the work site lengths wherever practical to ensure efficient construction outputs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
567 | T19.06.02 | VE - Accept more disruption over shorter period to maximise efficiency of construction operations - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
568 | T19.06.03 | VE - Option to lease UPS provision from Supplier rather than purchase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
569 | T19.06.04 | VE - PM Integration including shared resources and co-location. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
570 | T19.06.05 | VE - Further project management integration over 3 years | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
571 | T19.06.06 | VE - SDS design scope economy, variation and reduction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
572 | T19.06.07 | VE - Edinburgh Park Bridge - 7 span to 2 , utilise steel beams in lieu of concrete Edinburgh Park Viaduct | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
573 | T19.06.08 | VE - Carricknowe Bridge Parapet - down grade from P6 / P5 to N2 (reduced cost of parapet plus knock on effect on deck design/cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
574 | T19.06.09 | VE - A8 Underpass various initiatives | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
575 | T19.06.10 | VE - Roseburn Street viaduct various initiatives | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
576 | T19.06.11 | VE - Water of Leith various intiatives | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
577 | T19.06.12 | VE - Eight maintenance walkway structures - delete or reduce | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
578 | T19.06.13 | VE - Class 7 material conversion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
579 | T19.06.14 | VE - Value engineer finishes on EPV and other structures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
580 | T19.06.15 | VE - Tramstops, standard finishes to circa 20-30% of stops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
581 | T19.06.16 | VE - Delete depot pumping station/storm tanks by utilising existing gravity system. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
582 | T19.06.17 | VE - Depot - Build part now with provision to expand in the future/reduce size of car park facilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
583 | T19.06.18 | VE - Depot - delete split vehicle accommodation system - requirement dependant on tram vehicle selection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
584 | T19.06.19 | VE - Depot - Track Maintenance Equipment - rationalise scope requirement and consider renting. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
585 | T19.06.20 | VE - Depot - deletion of one pavement (inner) . | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
586 | T19.06.21 | VE - Depot - delete requirement for concrete apron to security fence | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
587 | T19.06.22 | VE - Consolidated VE items 7, 10, 11, 19 which results from changes to initial Depot design driven by proximity to BAA runway and EARL decision. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
588 | T19.06.23 | VE - Delete standby generator and substitute with hardstanding and power connection for portable generator. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
589 | T19.06.24 | VE - Material recovery and reprocessing (Infraco); 2 options - reconstituted planings & Type 1R | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
590 | T19.06.25 | VE - Reduce Kerb and associated re-instatement of pavement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
591 | T19.06.26 | VE - Reduce drainage run from guideway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
592 | T19.06.27 | VE - UTC associated with wider area impacts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
593 | T19.06.28 | VE - Picardy place level flexing - MUDFA savings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
594 | T19.06.29 | VE - Picardy place level flexing - construction savings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
595 | T19.06.30 | VE - Noise attenuation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
596 | T19.06.31 | VE - Reduce ballast thickness | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
597 | T19.06.32 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
598 | T19.06.33 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
599 | T19.06.34 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
600 | T19.06.35 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
601 | T19.06.36 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
602 | T19.06.37 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
603 | T19.06.38 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
604 | T19.06.39 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
605 | T19.06.40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
606 | T19.06.41 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
607 | T19.06.42 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
608 | T19.06.43 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
609 | T19.06.44 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
610 | T19.06.45 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
611 | T19.06.46 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
612 | T19.06.47 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
613 | T19.06.48 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
614 | T19.06.49 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
615 | T19.06.50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
616 | T19.06.51 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
617 | T19.06.52 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
618 | T19.06.53 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
619 | T19.06.54 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
620 | T19.06.55 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
621 | T19.06.56 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
622 | T19.06.57 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
623 | T19.06.58 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
624 | T19.06.59 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
625 | T19.06.60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
626 | T19.06.01-60 | Subtotal VE - Infraco | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
627 | T19.06.61 | VE - Marerial recovery / reprocessing - MUDFA | 0 | 0 | 0 | 0 | 0 | -90000 | -90000 | -30000 | 0 | 0 | 0 | -120000 | -120000 | 0 | -120000 | 0 | -120000 | 0 | -120000 |  |  | -120000 |  | -120000 | -120000
628 | T19.06.62 | VE - Reduction in extent of road reinstatement | 0 | 0 | 0 | 0 | 0 | -87000 | -87000 | -29000 | 0 | 0 | 0 | -116000 | -116000 | 0 | -116000 | 0 | -116000 | 0 | -116000 |  |  | -116000 |  | -116000 | -116000
629 | T19.06.63 | VE - Deferred Leasing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2961000 | 0 | 0 | -2961000 | -2961000 | 0 | -2961000 | 0 | -2961000 | 0 | -2961000 |  |  | -2961000 |  | -2961000 | -2961000
630 | T19.06.64 | VE - Network Reinforcement | 0 | -1363000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1363000 | -1363000 | 0 | -1363000 | 0 | -1363000 | 0 | -1363000 |  |  | -1363000 |  | -1363000 | -1363000
631 | T19.06.65 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
632 | T19.06.66 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
633 | T19.06.67 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
634 | T19.06.68 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
635 | T19.06.69 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
636 | T19.06.70 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
637 | T19.06.71 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
638 | T19.06.72 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
639 | T19.06.73 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
640 | T19.06.74 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
641 | T19.06.75 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
642 | T19.06.76 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
643 | T19.06.77 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
644 | T19.06.78 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
645 | T19.06.79 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
646 | T19.06.80 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
647 | T19.06.81 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
648 | T19.06.82 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
649 | T19.06.83 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
650 | T19.06.84 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
651 | T19.06.85 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
652 | T19.06.86 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
653 | T19.06.87 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
654 | T19.06.88 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
655 | T19.06.89 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
656 | T19.06.90 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
657 | T19.06.91 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
658 | T19.06.92 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
659 | T19.06.93 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
660 | T19.06.94 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
661 | T19.06.95 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
662 | T19.06.96 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
663 | T19.06.97 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
664 | T19.06.98 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
665 | T19.06.99 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
666 | T19.06.100 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
667 | T19.06.61-100 | Subtotal VE - Non-Infraco | 0 | -1363000 | 0 | 0 | 0 | -177000 | -177000 | -59000 | -2961000 | 0 | 0 | -4560000 | -4560000 | 0 | -4560000 | 0 | -4560000 | 0 | -4560000 | 0 | 0 | -4560000 | 0 | -4560000 | -4560000
668 | T19.06 | Subtotal VE | 0 | -1363000 | 0 | 0 | 0 | -177000 | -177000 | -59000 | -2961000 | 0 | 0 | -4560000 | -4560000 | 0 | -4560000 | 0 | -4560000 | 0 | -4560000 | 0 | 0 | -4560000 | 0 | -4560000 | -4560000
669 | T19.07.01 | NR Lift and shift | 40880 | 131802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172682 | 172682 | 0 | 172682 | 0 | 172682 | 0 | 172682 |  |  | 172682 |  | 172682 | 172682
670 | T19.07.02 | NR Immunisation Implementation | 4152 | -4152 | 75228.4 | 57759.4 | -17469 | 71255 | 129014.4 | 0 | 0 | 0 | 0 | 129014.4 | 129014.4 | 0 | 4152.4 | 124862 | 129014.4 | 0 | 129014.4 |  |  | 129014.4 |  | 129014.4 | 129014.4
671 | T19.07.03 | NR Immunisation development | 51310 | 69647 | 15332.5 | 10332.5 | -5000 | 13565 | 23897.5 | 0 | 0 | 0 | 0 | 144854.5 | 144854.5 | 0 | 823165.5031 | -678311.0031 | 144854.5 | 0 | 144854.5 |  |  | 144854.5 |  | 144854.5 | 144854.5
672 | T19.07.04 | Power - Network reinforcement | 0 | 1579674 | 6.5484e-11 | 0 | -6.5484e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 1579674 | 1579674 | 0 | 1579674 | 0 | 1579674 | 0 | 1579674 |  |  | 1579674 |  | 1579674 | 1579674
673 | T19.07.05 | Ticket machines | 0 | 0 | 0 | 0 | 0 | 140625 | 140625 | 609375 | 0 | 0 | 0 | 750000 | 750000 | 0 | 750000 | 0 | 750000 | 0 | 750000 |  |  | 750000 |  | 750000 | 750000
674 | T19.07.06 | IPR2 contingency | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 0 | 300000 | 0 | 300000 | 0 | 300000 |  |  | 300000 |  | 300000 | 300000
675 | T19.07.07 | Traffic signal and UTC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
676 | T19.07.08 | Murrayfield modifications | 0 | 208726 | 0 | 0 | 0 | 790010 | 790010 | 0 | 0 | 0 | 0 | 998736 | 998736 | 0 | 940010 | 58726 | 998736 | 0 | 998736 |  |  | 998736 |  | 998736 | 998736
677 | T19.07.16 |  | 0 | 0 | -370000 | 0 | 370000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
678 | T19.07.10 | Office land rental | 0 | 59358.18 | -113459.42 | 8875.7 | 122335.12 | 49392 | 58267.7 | 67656 | 24416 | 0 | 0 | 209697.88 | 209608.34 | 89.54 | 0.34 | 209608 | 209608.34 | 89.54 | 209697.88 |  |  | 209697.88 |  | 209697.88 | 209697.88
679 | T19.07.11 | Leith goods yard | 0 | 8615.3846 | 6461.6185 | 6461.5385 | -0.08 | 21538.4615 | 28000 | 19384.6154 | 0 | 0 | 0 | 56000 | 56000.08 | -0.08 | 0 | 56000.08 | 56000.08 | -0.08 | 56000 |  |  | 56000 |  | 56000 | 56000
680 | T19.07.12 | Traffic management design | 0 | 23125 | -0.33333 | 31256 | 31256.3333 | 103535.1562 | 134791.1562 | 155136.7188 | 86947.125 | 0 | 0 | 400000 | 399999.6667 | 0.33333 | 0 | 399999.6667 | 399999.6667 | 0.33333 | 400000 |  |  | 400000 |  | 400000 | 400000
681 | T19.07.17 |  | 0 | 0 | 50000 | 234546 | 184546 | 2835454 | 3070000 | 0 | 0 | 0 | 0 | 3070000 | 0 | 3070000 | 0 | 0 | 0 | 3070000 | 3070000 |  |  | 3070000 |  | 3070000 | 3070000
682 | T19.07.18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
683 | T19.07.19 |  | 0 | 0 | 12500 | 0 | -12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
684 | T19.07.20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
685 | T19.07.21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
686 | T19.07.22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
687 | T19.07.23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
688 | T19.07.24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
689 | T19.07.25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
690 | T19.01-08, 10-12,17-20 | Subtotal non Infraco works | 96342 | 2376795.5646 | -323937.2349 | 349231.1385 | 673168.3733 | 4025374.6178 | 4374605.7562 | 851552.3341 | 111363.125 | 0 | 0 | 7810658.78 | 4740568.9867 | 3070089.7933 | 4569684.2431 | 170884.7436 | 4740568.9867 | 3070089.7933 | 7810658.78 | 0 | 0 | 7810658.78 | 0 | 7810658.78 | 7810658.78
691 | T19.07.26 | SW Global Resourcing | 0 | 0 | 0 | 181522 | 181522 | 268478 | 450000 | 0 | 0 | 0 | 0 | 450000 | 0 | 450000 | 0 | 0 | 0 | 450000 | 450000 |  |  | 450000 |  | 450000 | 450000
692 | T19.07.27 | Capcis | 0 | 0 | 0 | 30137 | 30137 | 39863 | 70000 | 5000 | 0 | 0 | 0 | 75000 | 0 | 75000 | 0 | 0 | 0 | 75000 | 75000 |  |  | 75000 |  | 75000 | 75000
693 | T19.07.28 | Manhole at Balbirnie Place (Frontline cost) | 0 | 0 | 0 | 0 | 0 | 45000 | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | 45000 | 0 | 0 | 0 | 45000 | 45000 |  |  | 45000 |  | 45000 | 45000
694 | T19.07.29 | EWS Storage Area (Frontline) | 0 | 0 | 0 | 43565 | 43565 | 0 | 43565 | 0 | 0 | 0 | 0 | 43565 | 0 | 43565 | 0 | 0 | 0 | 43565 | 43565 |  |  | 43565 |  | 43565 | 43565
695 | T19.07.30 | Crash Gate 10 | 0 | 0 | 0 | 167500 | 167500 | 7500 | 175000 | 0 | 0 | 0 | 0 | 175000 | 0 | 175000 | 0 | 0 | 0 | 175000 | 175000 |  |  | 175000 |  | 175000 | 175000
696 | T19.07.31 |  | 0 | 0 | 0 | 13422 | 13422 | 19970 | 33392 | 0 | 0 | 0 | 0 | 33392 | 0 | 33392 | 0 | 0 | 0 | 33392 | 33392 |  |  | 33392 |  | 33392 | 33392
697 | T19.07.32 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
698 | T19.07.33 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
699 | T19.07.34 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
700 | T19.07.35 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
701 | T19.07.36 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
702 | T19.07.37 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
703 | T19.07.38 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
704 | T19.07.39 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
705 | T19.07.40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
706 | T19.07.41 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
707 | T19.07.42 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
708 | T19.07.43 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
709 | T19.07.44 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
710 | T19.07.45 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
711 | T19.07.46 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
712 | T19.07.47 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
713 | T19.07.48 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
714 | T19.07.26-48 | Subtotal non Infraco changes | 0 | 0 | 0 | 436146 | 436146 | 380811 | 816957 | 5000 | 0 | 0 | 0 | 821957 | 0 | 821957 | 0 | 0 | 0 | 821957 | 821957 | 0 | 0 | 821957 | 0 | 821957 | 821957
715 | T19.07.09 | Fastlink alternative | 0 | 370000 | 0 | 49241 | 49241 | 71759 | 121000 | 0 | 0 | 0 | 0 | 491000 | 0 | 491000 | 0 | 0 | 0 | 491000 | 491000 |  |  | 491000 |  | 491000 | 491000
716 | T19.07.13 | Ancient monuments | 0 | 0 | 0 | 25000 | 25000 | 110000 | 135000 | 26575 | 0 | 0 | 0 | 161575 | 161575 | 0 | 0 | 161575 | 161575 | 0 | 161575 |  |  | 161575 |  | 161575 | 161575
717 | T19.07.14 | TMi cycle integration study | 0 | 0 | 0 | 16118 | 16118 | 1582 | 17700 | 0 | 0 | 0 | 0 | 17700 | 17700 | 0 | 17700 | 0 | 17700 | 0 | 17700 |  |  | 17700 |  | 17700 | 17700
718 | T19.07.15 | Siemens out of hours monitoring | 0 | 0 | 0 | 13332 | 13332 | 33330 | 46662 | 43329 | 10009 | 0 | 0 | 100000 | 100000 | 0 | 0 | 100000 | 100000 | 0 | 100000 |  |  | 100000 |  | 100000 | 100000
719 | T19.07.49 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
720 | T19.07.50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
721 | T19.07.51 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
722 | T19.07.52 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
723 | T19.07.53 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
724 | T19.07.54 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
725 | T19.07.55 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
726 | T19.07.56 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
727 | T19.07.57 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
728 | T19.07.58 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
729 | T19.07.59 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
730 | T19.07.60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
731 | T19.07.61 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
732 | T19.07.62 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
733 | T19.07.63 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
734 | T19.07.64 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
735 | T19.07.65 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
736 | T19.07.66 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
737 | T19.07.67 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
738 | T19.07.09,13-15,49-67 | Subtotal non Infraco Provisional Sums | 0 | 370000 | 0 | 103691 | 103691 | 216671 | 320362 | 69904 | 10009 | 0 | 0 | 770275 | 279275 | 491000 | 17700 | 261575 | 279275 | 491000 | 770275 | 0 | 0 | 770275 | 0 | 770275 | 770275
739 | T19.07 | Subtotal Non Infraco works | 96342 | 2746795.5646 | -323937.2349 | 889068.1385 | 1213005.3733 | 4622856.6178 | 5511924.7562 | 926456.3341 | 121372.125 | 0 | 0 | 9402890.78 | 5019843.9867 | 4383046.7933 | 4587384.2431 | 432459.7436 | 5019843.9867 | 4383046.7933 | 9402890.78 | 0 | 0 | 9402890.78 | 0 | 9402890.78 | 9402890.78
740 | T19 | Total Infraco | 27957639.63 | 32798229.5217 | 3926180.9449 | 7973388.0443 | 4047207.0993 | 86119137.5541 | 94092525.5984 | 80023704.835 | 16513268.4572 | 0 | 0 | 251385368.0423 | 251680110.5069 | -294742.4646 | 247259300.7333 | 4420809.7736 | 251680110.5069 | -294742.4646 | 251385368.0423 | 294742 | 0 | 251680110.0423 | 0 | 251680110.0423 | 288709077.2881
741
742 | T20.01.01 | Prelims | 6000 | 215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6215 | 6478 | -263 | 0 | 6478 | 6478 | -263 | 6215 |  |  | 6215 |  | 6215 | 6215
743 | T20.01.02 | Tramco early mobilisation | 250000 | -250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
744 | T20.01.03 | Approval of preliminary design | 0 | 1100832.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100832.5 | 1102616.6402 | -1784.1402 | 1102616.6402 | 0 | 1102616.6402 | -1784.1402 | 1100832.5 |  |  | 1100832.5 |  | 1100832.5 | 1100832.5
745 | T20.01.04 | Delivery of mock up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
746 | T20.01.05 | Approval of final design / mock up | 0 | 1651248.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1651248.75 | 1653924.9603 | -2676.2103 | 1653924.9603 | 0 | 1653924.9603 | -2676.2103 | 1651248.75 |  |  | 1651248.75 |  | 1651248.75 | 1651248.75
747 | T20.01.06 | Approvals and consents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
748 | T20.01.07 | Commencenent of tram works | 0 | 9687325.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9687325.98 | 9703026.4338 | -15700.4538 | 9703026.4338 | 0 | 9703026.4338 | -15700.4538 | 9687325.98 |  |  | 9687325.98 |  | 9687325.98 | 9687325.98
749 | T20.01.08 | Completion 1st set bodyshells | 0 | 0 | 3302497 | 3302497 | 0 | 0 | 3302497 | 0 | 0 | 0 | 0 | 3302497 | 3307849.9206 | -5352.9206 | 3307849.9206 | 0 | 3307849.9206 | -5352.9206 | 3302497 |  |  | 3302497 |  | 3302497 | 3302497
750 | T20.01.09 | Completion 1st set bogies | 0 | 0 | 3302497.49 | 3302497.49 | 0 | 0 | 3302497.49 | 0 | 0 | 0 | 0 | 3302497.49 | 3307849.9206 | -5352.4306 | 3307849.9206 | 0 | 3307849.9206 | -5352.4306 | 3302497.49 |  |  | 3302497.49 |  | 3302497.49 | 3302497.49
751 | T20.01.10 | Completion 1st tram assembly | 0 | 0 | 0 | 0 | 0 | 3302497.49 | 3302497.49 | 0 | 0 | 0 | 0 | 3302497.49 | 3307849.9206 | -5352.4306 | 3307849.9206 | 0 | 3307849.9206 | -5352.4306 | 3302497.49 |  |  | 3302497.49 |  | 3302497.49 | 3302497.49
752 | T20.01.11 | Completion factory based type testing | 0 | 0 | 0 | 0 | 0 | 3852913.74 | 3852913.74 | 0 | 0 | 0 | 0 | 3852913.74 | 3859158.2407 | -6244.5007 | 3859158.2407 | 0 | 3859158.2407 | -6244.5007 | 3852913.74 |  |  | 3852913.74 |  | 3852913.74 | 3852913.74
753 | T20.01.12 | Delivery of preliminary tram maintenance manuals | 0 | 0 | 0 | 0 | 0 | 3302497.49 | 3302497.49 | 0 | 0 | 0 | 0 | 3302497.49 | 3307849.9206 | -5352.4306 | 3307849.9206 | 0 | 3307849.9206 | -5352.4306 | 3302497.49 |  |  | 3302497.49 |  | 3302497.49 | 3302497.49
754 | T20.01.13 | Delivery of spares | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100832.5 | 0 | 0 | 0 | 1100832.5 | 1102616.6402 | -1784.1402 | 1102616.6402 | 0 | 1102616.6402 | -1784.1402 | 1100832.5 |  |  | 1100832.5 |  | 1100832.5 | 1100832.5
755 | T20.01.14 | Delivery of final documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 789197.5 | 0 | 0 | 789197.5 | 1102616.6402 | -313419.1402 | 1102616.6402 | 0 | 1102616.6402 | -313419.1402 | 789197.5 |  |  | 789197.5 |  | 789197.5 | 1100832.5
756 | T20.01.15 | Delivery of special tools | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550416.25 | 0 | 0 | 550416.25 | 551308.3201 | -892.0701 | 551308.3201 | 0 | 551308.3201 | -892.0701 | 550416.25 |  |  | 550416.25 |  | 550416.25 | 550416.25
757 | T20.01.16 | Completion of driver training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550416.25 | 0 | 0 | 0 | 550416.25 | 551308.3201 | -892.0701 | 551308.3201 | 0 | 551308.3201 | -892.0701 | 550416.25 |  |  | 550416.25 |  | 550416.25 | 550416.25
758 | T20.01.17 | Completion of maintainer training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550416.25 | 0 | 0 | 0 | 550416.25 | 551308.3201 | -892.0701 | 551308.3201 | 0 | 551308.3201 | -892.0701 | 550416.25 |  |  | 550416.25 |  | 550416.25 | 550416.25
759 | T20.01.18 | Completion of integrated system testing | 0 | 0 | 0 | 0 | 0 | 550416.25 | 550416.25 | 0 | 0 | 0 | 0 | 550416.25 | 551308.3201 | -892.0701 | 551308.3201 | 0 | 551308.3201 | -892.0701 | 550416.25 |  |  | 550416.25 |  | 550416.25 | 550416.25
760 | T20.01.19 | Commencement of shadow running | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550416.25 | 0 | 0 | 550416.25 | 551308.3201 | -892.0701 | 551308.3201 | 0 | 551308.3201 | -892.0701 | 550416.25 |  |  | 550416.25 |  | 550416.25 | 550416.25
761 | T20.01.20 | Opening for passenger service | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550416.25 | 0 | 0 | 550416.25 | 551308.3201 | -892.0701 | 551308.3201 | 0 | 551308.3201 | -892.0701 | 550416.25 |  |  | 550416.25 |  | 550416.25 | 550416.25
762 | T20.01.21 | Supply chain mobilisation | 11003863.3471 | 77745.5049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11081608.852 | 11026166.402 | 55442.45 | 11026166.402 | 0 | 11026166.402 | 55442.45 | 11081608.852 |  |  | 11081608.852 |  | 11081608.852 | 11081608.852
763 | T20.01.22 | Adjustment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
764 | T20.01.23 | Delivery of trams | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4520728 | 0 | 0 | 0 | 4520728 | 4520728.2248 | -0.22484 | 4520728.2248 | 0 | 4520728.2248 | -0.22484 | 4520728 |  |  | 4520728 |  | 4520728 | 4520728
765 | T20.01.24 | Testing and commissioning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4520728 | 0 | 0 | 0 | 4520728 | 4520728.2248 | -0.22484 | 4520728.2248 | 0 | 4520728.2248 | -0.22484 | 4520728 |  |  | 4520728 |  | 4520728 | 4520728
766 | T20.01.25 | Advance maintenance mobilisation | 0 | 317346.3098 | 0 | -317346 | -317346 | 1262907.8262 | 945561.8262 | 688431.38 | 0 | 0 | 0 | 1951339.516 | 2274883.9414 | -323544.4254 | 2274883.9414 | 0 | 2274883.9414 | -323544.4254 | 1951339.516 |  |  | 1951339.516 |  | 1951339.516 | 1957816.516
767 | T20.01.26 | Depot equipment | 147941.8212 | 59.9888 | 0 | 317346 | 317346 | 481005.87 | 798351.87 | 111001.35 | 0 | 0 | 0 | 1057355.03 | 739709.1058 | 317645.9242 | 739709.1058 | 0 | 739709.1058 | 317645.9242 | 1057355.03 |  |  | 1057355.03 |  | 1057355.03 | 1057355.03
768 | T20.01.27 | Variations / changes | 0 | 0 | 0 | 318986 | 318986 | 0 | 318986 | 0 | 0 | 0 | 0 | 318986 | 0 | 318986 | 0 | 0 | 0 | 318986 | 318986 | 105 |  | 319091 |  | 319091 | 318986
769 | T20.01.28 | Contingency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
770 | T20.01.29 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
771 | T20.01.30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
772 | T20.01.31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
773 | T20.01.32 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
774 | T20.01.33 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
775 | T20.01.34 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
776 | T20.01.35 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
777 | T20.01.36 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
778 | T20.01.37 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
779 | T20.01.38 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
780 | T20.01.39 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
781 | T20.01.40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
782 | T20.01.41 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
783 | T20.01.42 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
784 | T20.01.43 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
785 | T20.01.44 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
786 | T20.01.45 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
787 | T20.01.46 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
788 | T20.01.47 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
789 | T20.01.48 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
790 | T20.01.49 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
791 | T20.01.50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
792 | T20.01 | Subtotal Tramco main works | 11407805.1683 | 12584774.0336 | 6604994.49 | 6923980.49 | 318986 | 12752238.6662 | 19676219.1562 | 12042553.73 | 2440446.25 | 0 | 0 | 58151798.3381 | 58151903.0574 | -104.7193 | 58145425.0574 | 6478 | 58151903.0574 | -104.7193 | 58151798.3381 | 105 | 0 | 58151903.3381 | 0 | 58151903.3381 | 58469910.3381
793 | T20.02.01 |  | -8700000 | 0 | 2175000 | 1127777 | -1047223 | 7572223 | 8700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
794 | T20.02.02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
795 | T20.02.03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
796 | T20.02.04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
797 | T20.02.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
798 | T20.02.06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
799 | T20.02.07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
800 | T20.02.08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
801 | T20.02.09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
802 | T20.02.10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
803 | T20.02 | Subtotal Funding adjustment | -8700000 | 0 | 2175000 | 1127777 | -1047223 | 7572223 | 8700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
804 | T20.03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
805 | T20.04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
806 | T20.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
807 | T20.06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
808 | T20.07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
809 | T20.08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
810 | T20.09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
811 | T20.10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
812 | T20.11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
813 | T20.12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
814 | T20.13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
815 | T20.14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
816 | T20.15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
817 | T20.16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
818 | T20.17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
819 | T20.18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
820 | T20.19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
821 | T20.20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
822 | T20.21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
823 | T20.22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
824 | T20.23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
825 | T20.24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
826 | T20.25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
827 | T20.26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
828 | T20.27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
829 | T20.28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
830 | T20.29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
831 | T20.30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
832 | T20.03-30 | Subtotal other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
833 | T20 | Total Tramco | 2707805.1683 | 12584774.0336 | 8779994.49 | 8051757.49 | -728237 | 20324461.6662 | 28376219.1562 | 12042553.73 | 2440446.25 | 0 | 0 | 58151798.3381 | 58151903.0574 | -104.7193 | 58145425.0574 | 6478 | 58151903.0574 | -104.7193 | 58151798.3381 | 105 | 0 | 58151903.3381 | 0 | 58151903.3381 | 58469910.3381
834
835 | T21.01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
836 | T21.02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
837 | T21.03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
838 | T21.04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
839 | T21.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
840 | T21.06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
841 | T21.07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
842 | T21.08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
843 | T21.09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
844 | T21.10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
845 | T21.11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
846 | T21.12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
847 | T21.13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
848 | T21.14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
849 | T21.15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
850 | T21.16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
851 | T21.17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
852 | T21.18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
853 | T21.19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
854 | T21.20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
855 | T21 | Total ABC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
856
857 | T22.01 | Spare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
858 | T22.02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
859 | T22.03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
860 | T22.04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
861 | T22.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
862 | T22.06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
863 | T22.07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
864 | T22.08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
865 | T22.09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
866 | T22.10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
867 | T22.11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
868 | T22.12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
869 | T22.13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
870 | T22.14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
871 | T22.15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
872 | T22.16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
873 | T22.17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
874 | T22.18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
875 | T22.19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
876 | T22.20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
877 | T22 | Total ABC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
878
879 | T23.01 | Spare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
880 | T23.02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
881 | T23.03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
882 | T23.04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
883 | T23.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
884 | T23.06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
885 | T23.07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
886 | T23.08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
887 | T23.09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
888 | T23.10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
889 | T23 | Total ABC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
890
891 | T24.01 | Spare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
892 | T24.02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
893 | T24.03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
894 | T24.04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
895 | T24.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
896 | T24.06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
897 | T24.07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
898 | T24.08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
899 | T24.09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
900 | T24.10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
901 | T24.11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
902 | T24.12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
903 | T24.13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
904 | T24.14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
905 | T24.15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
906 | T24.16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
907 | T24.17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
908 | T24.18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
909 | T24.19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
910 | T24.20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
911 | T24 | Total ABC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
912
913 | T25.01 | Spare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
914 | T25.02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
915 | T25.03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
916 | T25.04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
917 | T25.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
918 | T25.06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
919 | T25.07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
920 | T25.08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
921 | T25.09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
922 | T25.10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
923 | T25.11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
924 | T25.12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
925 | T25.13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
926 | T25.14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
927 | T25.15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
928 | T25.16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
929 | T25.17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
930 | T25.18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
931 | T25.19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
932 | T25.20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
933 | T25 | Total ABC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
934
935 | T44.01 | Specified risk | 0 | 0 | 1924285.2685 | 0 | -1924285.2685 | 8061647.5098 | 8061647.5098 | 18103088.5064 | 4915017.4936 | 0 | 0 | 31079753.5098 | 19168851 | 11910902.5098 | 30336196 | -11167345 | 19168851 | 11910902.5098 | 31079753.5098 | 2371273 | 21500000 | 54951026.5098 | 22099000 | 77050026.5098 | 0
936 | T44.02 | Contingency | 0 | 0 | 26618.6038 | 0 | -26618.6038 | 200000 | 200000 | 924014.5154 | 250715.4846 | 0 | 0 | 1374730 | 574729.8833 | 800000.1167 | -0.37 | 574730.2533 | 574729.8833 | 800000.1167 | 1374730 |  |  | 1374730 |  | 1374730 | 0
937 | T44.03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
938 | T44.04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
939 | T44.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
940 | T44.06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
941 | T44.07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
942 | T44.08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
943 | T44.09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
944 | T44.10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
945 | T44.11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
946 | T44.12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
947 | T44.13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
948 | T44.14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
949 | T44.15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
950 | T44.16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
951 | T44.17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
952 | T44.18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
953 | T44.19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
954 | T44.20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
955 | T44 | Total Risk | 0 | 0 | 1950903.8723 | 0 | -1950903.8723 | 8261647.5098 | 8261647.5098 | 19027103.0218 | 5165732.9782 | 0 | 0 | 32454483.5098 | 19743580.8833 | 12710902.6264 | 30336195.63 | -10592614.7467 | 19743580.8833 | 12710902.6264 | 32454483.5098 | 2371273 | 21500000 | 56325756.5098 | 22099000 | 78424756.5098 | 0
956
957 | T99.01 | Miscellaneous | 163278.74 | 997 | 6143.07 | 4451.6923 | -1691.3777 | 22168.6923 | 26620.3846 | 22100 | 22620 | 0 | 0 | 235616.1246 | 235615.71 | 0.41462 | 265615.71 | -30000 | 235615.71 | 0.41462 | 235616.1246 |  |  | 235616.1246 |  | 235616.1246 | 235616.1246
958 | T99.02 | Previous years | 3093000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3093000 | 3093000 | 0 | 3093000 | 0 | 3093000 | 0 | 3093000 |  |  | 3093000 |  | 3093000 | 3093000
959 | T99.03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
960 | T99.04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
961 | T99.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
962 | T99.06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
963 | T99.07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
964 | T99.08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
965 | T99.09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
966 | T99.10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
967 | T99 | Total Miscellaneous | 3256278.74 | 997 | 6143.07 | 4451.6923 | -1691.3777 | 22168.6923 | 26620.3846 | 22100 | 22620 | 0 | 0 | 3328616.1246 | 3328615.71 | 0.41462 | 3358615.71 | -30000 | 3328615.71 | 0.41462 | 3328616.1246 | 0 | 0 | 3328616.1246 | 0 | 3328616.1246 | 3328616.1246
968
969 | T999 | Total | 130040313.9912 | 100978889.928 | 21022944.6488 | 23461519.3322 | 2438574.6834 | 126622677.2434 | 150084196.5756 | 118853049.7438 | 27142433.8954 | 0 | 0 | 527098884.1339 | 512017007.8856 | 15081876.2483 | 512017007.7892 | 0.096333 | 512017007.8856 | 15081876.2483 | 527098884.1339 | 0 | 26500000 | 553598884.1339 | 24823390 | 578422274.1339 | 542469194.1963
|  | Base Costs | [11 empty] | 494644400.6241 | 492273427.0022 | 2370973.6219 | 481680812.1592 | 10592614.843 | 492273427.0022 | 2370973.6219 | 494644400.6241 | -2371273 | 5000000 | 497273127.6241 | 2724390 | 499997517.6241 | 542469194.1963
|  | Risk | [11 empty] | 32454483.5098 | 19743580.8833 | 12710902.6264 | 30336195.63 | -10592614.7467 | 19743580.8833 | 12710902.6264 | 32454483.5098 | 2371273 | 21500000 | 56325756.5098 | 22099000 | 78424756.5098 | 0
|  | Total | [11 empty] | 527098884.1339 | 512017007.8856 | 15081876.2483 | 512017007.7892 | 0.096333 | 512017007.8856 | 15081876.2483 | 527098884.1339 | 0 | 26500000 | 553598884.1339 | 24823390 | 578422274.1339 | 542469194.1963
Check totals
| Infraco subtotals added |  | 27957639.63 | 32798229.5217 | 3926180.9449 | 7973388.0443 | 4047207.0993 | 86119137.5541 | 94092525.5984 | 80023704.835 | 16513268.4572 | 0 | 0 | 251385368.0423 | 251680110.5069 | -294742.4646
| Difference |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| All Subtotals added |  | 130040313.9912 | 100978889.928 | 21022944.6488 | 23461519.3322 | 2438574.6834 | 126622677.2434 | 150084196.5756 | 118853049.7438 | 27142433.8954 | 0 | 0 | 527098884.1339 | 512017007.8856 | 15081876.2483
| Difference |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| All Individual costs added |  | 130040313.9912 | 100978889.928 | 21022944.6488 | 23461519.3322 | 2438574.6834 | 126622677.2434 | 150084196.5756 | 118853049.7438 | 27142433.8954 | 0 | 0 | 527098884.1339 | 512017007.8856 | 15081876.2483
| Difference |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal years agreed to above |  | 130040313.9912 | 100978889.928 |  |  |  |  | 150084196.5756 | 118853049.7438 | 27142433.8954 | 4004462.6135 | 14635171.9059 | 527098884.1339 | 512017007.8856 | 15081876.2483
| Difference |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | -4004462.6135 | -14635171.9059 | 0 | 0 | -2.5705e-07

## Ranging Doc - Change
Infraco Contract
Change - Ranging Doc (26/6/09)
Notes / Assumptions
Total cost only allows for TNC / INTC's raised to date.
Where Estimates have not been submitted tie have taken a view of likely final costs.
No Provision for any INTC's to be raised by BSC (which are not known)
No Provision allowed for an further TNC's to be raised by tie (which are not known)
No Provision - Further SDS Design Change (which is not known about)
No Provision - Siemens Design Change (BDDI - IFC), no visibility
No Provision - INTC 397 (Revised Earthworks Specification)
No Provision - INTC 398 (Revised Concrete Specification)
No Provision - Further On-Street Supplemental Agreements.
Provision allowed for additional capping below full depth road make up (allow additional 300mm to all roads)
Provision allowed for additional cost associated with the depot (REfer INTC 203)
INTC No | Change Order | Description |  | Await Estimate | Estimated Final Cost | Disputed value (quantum) | Disputed Value (principle) | External Funding | Tramco | MUDFA | Prov sums | book versus risk item | Contingency/other | Total | Risk Reference | Best Case (Q/S View) | Mid Position | Worst Case | BSC Estimate | Comments
104 |  | Change to IFC Drgs - Balgreen Road Retaining wall | BDDI/IFC | Await Estimate |  | 0 | [7 empty] | 0 |  | 2500000 | 2500000 | 3200000
105 |  | Change to IFC Drgs - Baird Drive Retaining Wall | BDDI/IFC |  | 2500000 | 931295 | [5 empty] | 2500000 |  | 2500000 | 1077 | 2552000 | 2552000 | 3200000 | 3431295
106 |  | Change to IFC Drgs - Murrayfield Stadium Retaining Wall | BDDI/IFC | Await Estimate |  | 0 | [7 empty] | 0 |  | 1150000 | 1750000 | 2000000
107 |  | Change to IFC Drgs - Bankhead Retaining Wall | BDDI/IFC | Await Estimate |  | 0 | [7 empty] | 0 |  | 520000 | 1000000 | 1500000
147 |  | IFC Drawings for Murrayfield Training Pitches | BDDI/IFC | Await Estimate |  | 0 | [7 empty] | 0 |  | 600000 | 600000 | 600000
108 |  | Change to IFC Drgs - Gyle Stop Retaining Wall | BDDI/IFC | Await Estimate |  | 0 | [7 empty] | 0 |  | 150000 | 200000 | 350000
109 |  | Change to IFC Drgs - Murrayfield Underpass | BDDI/IFC | Await Estimate |  | 0 | [7 empty] | 0 |  | 0 | 0 | 0
110 |  | Change to IFC Drgs - South Gyle Access Bridge | BDDI/IFC | Await Estimate |  | 0 | [7 empty] | 0 |  | 0 | 0 | 0
111 |  | Change to IFC Drgs - Gogarburn Bridge (Earthwork Reinforcement) | BDDI/IFC |  | 100000 | 0 | [5 empty] | 100000 |  | 100000 | 1077 | 0 | 0 | 0
111 |  | Change to IFC Drgs - Gogarburn Bridge (Structure) | BDDI/IFC | [10 empty] | 0 |  | 0 | 50000 | 294220 | 294219.78
112 |  | Change to IFC Drgs - Haymarket Viaduct | BDDI/IFC | Await Estimate |  | 0 | [7 empty] | 0 |  | 0 | 0 | 0
113 |  | Change to IFC Drgs - Russell Road Bridge | BDDI/IFC | Await Estimate |  | 0 | [7 empty] | 0 |  | 100000 | 150000 | 200000
114 |  | Change to IFC Drgs - Roseburn Viaduct | BDDI/IFC | Await Estimate |  | 0 | [7 empty] | 0
115 |  | Change to IFC Drgs - Carricknowe Bridge | BDDI/IFC | Await Estimate | 120000 | 163103.17 | [5 empty] | 120000 |  | 120000 | 1077 | 72000 | 95000 | 140718.31 | 283103.17
116 |  | Change to IFC Drgs - Water of Leith Bridge | BDDI/IFC | Await Estimate |  | 0 | [7 empty] | 0 |  | 0 | 25000 | 50000
117 |  | Demolition to Roseburn Rd retaining wall / units / garages | BDDI/IFC | Await Estimate | 25000 | 0 | [6 empty] | 25000 | 25000 |  | 25000 | 25000 | 25000
146 |  | IFC Drawings for Russell Road Retaining Wall 4 | BDDI/IFC |  | 2500000 | 1965015 | [5 empty] | 2500000 |  | 2500000 | 1077 | 2500000 | 2500000 | 3500000 | 4465015
|  | IFC Drawings for Russell Road Retaining Wall 3 | BDDI/IFC | [12 empty] | 998000 | 998000 | 2362000
148 |  | IFC Drawings for Balgreen Road Tram Bridge | BDDI/IFC | Await Estimate |  | 0 | [7 empty] | 0 |  | 0 | 150000 | 300000
152 |  | IFC Drawings - Vertical & Horizontal track alignment sheets for Section 5 | BDDI/IFC | Await Estimate |  | 0 | [7 empty] | 0 |  | 0 | 0 | 0
153 |  | IFC Drawings - Soft Landscaping sheets for section 5 | BDDI/IFC | Await Estimate |  | 0 | [7 empty] | 0 |  | 0 | 200000 | 300000
154 |  | IFC Drawings - OLE sheets for section 5 | BDDI/IFC | Await Estimate |  | 0 | [7 empty] | 0
155 |  | IFC Drawings for Gogarburn Retaining Walls 15A, 15C & 14D | BDDI/IFC |  |  | 1146620 | [7 empty] | 0 |  | 500000 | 900000 | 1146620 | 1146620
156 |  | IFC Drawings for Section 5 Tramstops - Balgreen, Saughton, South Gyle & Edinburgh Park | BDDI/IFC | Await Estimate |  | 0 | [7 empty] | 0 |  | 400000 | 400000 | 400000
160 |  | IFC Drawings for Edinburgh Park Bridge | BDDI/IFC |  | 75000 | 0 | 245010 |  |  |  |  | 75000 |  | 75000 | 1077 | 0 | 50000 | 320010 | 320010
199 |  | IFC Drawings - Balgreen Bridges S22A / S22B | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 0 | 200000 | 300000
200 |  | IFC Drawings - Saughton Bridge S24 | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 0 | 200000 | 300000
201 |  | IFC Drawings - Depot Access Bridge | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 1500000 | 1500000 | 1750000
202 |  | IFC Drawings - Culverts S30, S31 & S34 | BDDI/IFC |  | 0 |  | 47429 | [6 empty] | 0 |  | 0 | 25000 | 47429 | 47429
203 |  | IFC Drawings - Depot Founds | BDDI/IFC |  | 30000 |  | 17782.16 |  |  |  |  | 30000 |  | 30000 | 1077 | 0 | 25000 | 47782 | 47782.16
203 |  | IFC Drawings - Depot Steel | BDDI/IFC |  | 150000 |  | 144618 |  |  |  |  | 150000 |  | 150000 | 1077 | 0 | 150000 | 250000 | 294618
203 |  | IFC Drawings - Soil Nailing | BDDI/IFC |  | 300000 |  | 197194 |  |  |  |  | 300000 |  | 300000 | 1077 | 0 | 200000 | 450000 | 497194
203 |  | IFC Drawings - 1800mm Culvert | BDDI/IFC |  | 0 |  | 144265 |  |  |  |  | 0 |  | 0 |  | 0 | 0 | 144265 | 144265
|  | IFC Drawings - Depot (Not submitted but discussed) | BDDI/IFC | [12 empty] | 1500000 | 2000000 | 3000000
203 |  | IFC Drawings - External Hard Landscaping | BDDI/IFC |  | 100000 |  | 96717 |  |  |  |  | 100000 |  | 100000 | 1077 | 136906 | 136906 | 136095.86 | 196717
204 |  | IFC Drawings - Section 5B Highways | BDDI/IFC |  | 500000 |  | 266200 |  |  |  |  | 500000 |  | 500000 | 1077 | 250000 | 500000 | 766200 | 766200
205 |  | IFC Drawings - Section 5C Highways | BDDI/IFC |  | 400000 |  | 178005 |  |  |  |  | 400000 |  | 400000 | 1077 | 150000 | 350000 | 578005 | 578005
206 |  | IFC Drawings - Section 5B, Bankhead Tramstop | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 0 | 75000 | 100000
209 |  | IFC Drawings - Balfour Street / MacDonald Road Tramstops | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 0 | 150000 | 200000
210 |  | IFC Drawings - Roads, St Lighting, Landscping, Drainage, section 1B | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 0 | 250000 | 350000
211 |  | IFC Drawings - Haymarket Tramstop, Section 2 | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 0 | 75000 | 100000
212 |  | IFC Drawings - Roads, St Lighting, Landscping, Drainage, section 2A | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 0 | 150000 | 350000
213 |  | IFC Drawings - Haymarket Terrace Substation | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 0 | 50000 | 75000
251 |  | IFC Drawings - Section 1C OLE Layout | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0 | 0
252 |  | IFC Drawings - Section 1C Track Horizontal Alignment | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 0 | 50000 | 125000
253 |  | IFC Drawings - Section 1C Track Vertical Alignment | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 0 | 50000 | 125000
254 |  | IFC Drawings - Section 1C Traffic Management | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 0 | 50000 | 75000
255 |  | IFC Drawings - Section 1C, 1D - Princes St Central Reservation | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 25000
261 |  | IFC Drawings - Balfour St Tram Stop | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 0 | 50000 | 75000
262 |  | IFC Drawing Change - Section 5B Track Drainage | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 0 | 125000 | 300000
263 |  | IFC Drawings - Victoria Dock Bridge | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 0 | 50000 | 75000
311 |  | IFC Drawings - Section 1A | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 0 | 125000 | 250000
312 |  | IFC Drawings - Leith Walk | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 0 | 150000 | 275000
313 |  | IFC Drawings - Section 7, Soft Landscaping | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 0 | 125000 | 175000
314 |  | IFC Drawings - Horizontal / Vertical Alignment | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 0 | ` | 275000
315 |  | IFC Drawings - Section 7 Drainage - Gogarburn | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 125000 | 200000 | 350000
316 |  | IFC Drawings - Princes Street | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0
318 |  | IFC Drawings - Gogarburn Retaining Walls 14 & 15 | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0 | 0
|  | IFC Drgs - St Andrews Square (Tram route only) | BDDI/IFC |  | 300000 | [6 empty] | 300000 |  | 300000 | 1077 | 300000 | 750000 | 1000000
230 |  | IFC Drawings - Tower Bridge | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | -100000 | 0 | 0
231 |  | IFC Drawings - Section 1C Drainage | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 0 | 75000 | 150000
232 |  | IFC Drawings - Section 1C Roads | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 0 | 75000 | 150000
233 |  | IFC Drawings - Section 1C Lighting | BDDI/IFC | Await Estimate | [9 empty] | 0 |  | 0 | 75000 | 200000
|  | Guided Busway | BDDI/IFC |  | 500000 | 280059 | [6 empty] | 500000 | 500000 |  | 500000 | 500000 | 780059 | 780059
118 | 64 | IFC Drawing Change Catherdral Lane Sub Station | BDDI/IFC |  | 1230 | 0 | [5 empty] | 1230 |  | 1230 | 1077 | 1230 | 1230 | 1230 | 1230
397 |  | IFC Changes to Series 600 Earthworks Specification | BDDI/IFC | Await Estimate | [9 empty] | 0
398 |  | IFC Changes to Series 1700 Concrete Specification | BDDI/IFC | Await Estimate | [9 empty] | 0
6 |  | Gogarburn surcharge | Contam | Await Estimate | 1020000 | 0 | [5 empty] | 1020000 |  | 1020000 | 172 | 1020000 | 1200000 | 1500000
1 |  | V31design delivery programme | EOT1 |  | 2500000 | 4549000 | [5 empty] | 2500000 |  | 2500000 | 343 | 2500000 | 3000000 | 3500000 | 7049000
402 |  | Section 5B Groundworks - Additional Starter and Capping Layers | Ground |  | 2000000 | 745762 | [5 empty] | 2000000 |  | 2000000 | 1091 | 1400000 | 1500000 | 1600000 | 2745762
403 |  | Section 5C Groundworks - Additional Starter and Capping Layers | Ground | Await Estimate | 1500000 | [6 empty] | 1500000 |  | 1500000 | 1091 | 756000 | 756000 | 890000
403A |  | Section 5A Groundworks - Additional Starter and Capping Layers | Ground | [12 empty] | 300000 | 400000 | 600000 | 600000
|  | Section 7 Groundworks | Ground | [12 empty] | 1200000 | 1200000 | 1500000 | 1500000
|  | Princes Street - Actual Cost - Tender Allowance | Roads |  | 2010908 | [6 empty] | 1000000 |  | 1000000 | 35 | 1000000 | 1000000 | 1000000
|  | Princes Street - Actual Cost - Tender Allowance | Ground | [8 empty] | 1010908 |  | 1010908 | 1091 | 1010908 | 1010908 | 1010908
362 |  | Edinburgh Park Bridge - North and South Approach ramps additional Earthworks | Ground |  | 185000 | 179664 | [5 empty] | 185000 |  | 185000 | 1091 | 164651 | 175000 | 325565 | 364664
272 | 11 | Unsuitable Material Carrick Knowe (INTC NOT RECEIVED) | Ground |  | 83028 | [6 empty] | 83028 |  | 83028 | 1091 | 83028 | 83028 | 83028 | 83028
296 | 39 | Formation Level of Gogarburn Bridge West Abutment | Ground |  | 11556 | 0 | [5 empty] | 11556 |  | 11556 | 1091 | 11556 | 11556 | 11556 | 11556
297 | 40 | Formation Level of Gogarburn Bridge East Abutment | Ground |  | 7280 | 0 | [5 empty] | 7280 |  | 7280 | 1091 | 7280 | 7280 | 7280 | 7280
309 |  | Edinburgh Park Bridge South Abutment Base Formation | Ground |  | 5493 | 14729 | [5 empty] | 5493 |  | 5493 | 1091 | 5493 | 7500 | 10000 | 20222
390 | 53 | Carrick Knowe Subgrade Improvement | Ground |  | 84700 | 0 | [5 empty] | 84700 |  | 84700 | 1091 | 84700 | 84700 | 84700 | 84700
188 |  | Contaminated Material at Carrickknowne (Works to be carried out by Frontline) | Haz |  | 275000 | 0 | [5 empty] | 275000 |  | 275000 | 173 | 275000 | 275000 | 275000 | 275000
125 |  | Haymarket - Additional retaining Wall | Haz | Design | 5000 | 12204 | [5 empty] | 5000 |  | 5000 | 173 | 17204 | 17204 | 17204 | 17204
|  | Haymarket - Additional retaining Wall (Temp works + Construct) | Haz | Await Estimate | [11 empty] | 100000 | 100000 | 150000
307 |  | Contaminated Soil at Haymarket Depot | Haz |  | 46520 | 0 | [5 empty] | 46520 |  | 46520 | 173 | 46520 | 46520 | 46520 | 46520
308 |  | Additional excavation at Carrick Knowe South Abutment | Haz |  | 43 | [6 empty] | 43 |  | 43 | 173 | 0 | 0 | 43 | 43
50 | 22 | Traffic Signal Works | MUDFA |  | 30550 | 0 | 0 |  |  | 30550 |  |  | 0 | 30550 |  | 30550 | 30550 | 30550 | 30550
51 | 6 | Utility Diversions - Section 5A | MUDFA |  | 64192 | 0 |  |  |  | 64192 |  |  |  | 64192 |  | 64192 | 64192 | 64192 | 64192
51 |  | Allow - Provisional Sums | MUDFA |  | 44140 |  |  |  |  | 44140 |  |  |  | 44140 |  | 25000 | 50000 | 75000
52 | 7 | Utility Diversions - Section 5B | MUDFA |  | 75694 | 0 |  |  |  | 75694 |  |  |  | 75694 |  | 75694 | 75694 | 75694 | 75694
52 |  | Allow - Provisional Sums | MUDFA |  | 44141 |  |  |  |  | 44141 |  |  |  | 44141 |  | 25000 | 50000 | 75000
53 | 3 | Utility Diversions - Section 5C | MUDFA |  | 33723 | 0 |  |  |  | 33723 |  |  |  | 33723 |  | 33723 | 33723 | 33723 | 33723
53 |  | Utility Diversions - Section 5C (Provisional Sum - Watermain Diversion) | MUDFA |  | 110000 | 0 |  |  |  | 110000 |  |  |  | 110000 |  | 110000 | 110000 | 110000 | 110000
86 |  | MUDFA Transfer of Utilities Diversions Section 1A, 1B, 1C, 1D | MUDFA | Await Estimate | 750000 | 0 |  |  |  | 750000 |  |  |  | 750000 |  | 750000 | 750000 | 750000
17 |  | Sewer at South Gyle Access Bridge | MUDFA | Await Estimate | 350000 | 0 |  |  |  | 350000 |  |  |  | 350000 |  | 150000 | 250000 | 350000
17 |  | Sewer at South Gyle Access Bridge | MUDFA |  | 162528 | 124031 |  |  |  | 162528 |  |  |  | 162528 |  | 162528 | 162528 | 200000 | 286559
60 |  | Gogar Bridge Sewer Diversion | MUDFA |  | 35000 | 10000 |  |  |  | 35000 |  |  |  | 35000 |  | 35000 | 40000 | 40000 | 45000
87 | 4 & 13 | Duct Installation to Leith Walk | MUDFA |  | 300 | 0 |  |  |  | 300 |  |  |  | 300 |  | 300 | 300 | 300 | 300
151 |  | Excavate and replace existing BO material within existing utility trenches | MUDFA |  | 47456 | 0 |  |  |  | 47456 |  |  |  | 47456 |  | 47456 | 47456 | 47456 | 47456
157 | 50 | Survey of Existing Drainage (Gogar Landfill) | MUDFA |  | 4334 | 0 |  |  |  | 4334 |  |  |  | 4334 |  | 4334 | 4334 | 4334 | 4334
207 | 30 | Trial Investigations Culvert No.2 (SGN Main Protection) | MUDFA |  | 1083 |  |  |  |  | 1083 |  |  |  | 1083 |  | 1083 | 1083 | 1083 | 1083
267 |  | Scottish Water Diversion - Gogar Roundabout | MUDFA |  | 116553 |  |  |  |  | 116553 |  |  |  | 116553 |  | 116553 | 116553 | 116553 | 116553
268 |  | Scottish Power Diversion - Gogar Roundabout | MUDFA |  | 14617 |  |  |  |  | 14617 |  |  |  | 14617 |  | 14617 | 14617 | 14617 | 14617
294 | 38 | Reinstate access ramp at Gogar Depot | MUDFA |  | 8507 |  |  |  |  | 8507 |  |  |  | 8507 |  | 8507 | 8507 | 8507 | 8507
295 | 30 | Carry out works to protect existing SGN gas main at Culvert No, 2 | MUDFA |  | 13040 | 0 |  |  |  | 13040 |  |  |  | 13040 |  | 13040 | 13040 | 13040 | 13040
310 |  | Gogar Landfill Scottish Water Utility Diversion | MUDFA | Await Estimate | 35000 |  |  |  |  | 35000 |  |  |  | 35000 |  | 35000 | 35000 | 35000
361 | 55 | SP _Diversion Murrayfield Underpass | MUDFA |  | 7473 |  |  |  |  | 7473 |  |  |  | 7473 |  | 7473 | 7473 | 7473 | 7473
364 | 70 | Manhole at Balbirnie Place | MUDFA |  | 1498 | 0 |  |  |  | 1498 |  |  |  | 1498 |  | 1498 | 1498 | 1498 | 1498
371 | 75 | Utility Diversion 5C/BT/D/05 | MUDFA |  | 856 |  |  |  |  | 856 |  |  |  | 856 |  | 856 | 856 | 856 | 856
372 |  | Utility Diversion 5A/SP/D/08 | MUDFA | Await Estimate | 25000 |  |  |  |  | 25000 |  |  |  | 25000 |  | 25000 | 25000 | 25000
373 | 74 | Utility Diversion 5C/TE/D/05 | MUDFA |  | 3269 |  |  |  |  | 3269 |  |  |  | 3269 |  | 3269 | 3269 | 3269 | 3269
62 |  | S.Power quotation for connections | PS |  | 1981719 | 0 |  |  |  |  | 1981719 |  |  | 1981719 |  | 0 | 0 | 0 | 0
158 |  | Provisional Sum - Crew Facilities at Haymarket Station Viaduct | PS |  | 140401 | 0 |  |  |  |  | 140401 |  |  | 140401
167 | 56 | Alterations to Murrayfield Wanderers Clubhouse | PS |  | 166275 | 0 |  |  |  |  | 166275 |  |  | 166275
179 |  | Gatehouse works to Murrayfield Stadium | PS |  | 108663 | -108663 |  |  |  |  | 108663 |  |  | 108663 |  | 0 | 0 | 0
179 |  |  | PS | Await Estimate | 300000 | [5 empty] | 300000 |  |  | 300000 |  | 0 | 0 | 0
184 | 47 | Leith Walk Utilities | PS |  | 265 | [5 empty] | 265 |  |  | 265 |  | 265 | 265 | 265 | 265
185 |  | Leith Walk Utilities | PS | Await Estimate | 1000 | [5 empty] | 1000 |  |  | 1000 |  | 1000 | 1000 | 1000
85 |  | Lindsay Road Retaining Walls | PS |  | 750000 | 0 |  |  |  |  | 750000 |  |  | 750000
174 |  | Discovery of new BT ducts under kerb line in Section 1B | PS | Await Estimate | 1000 | 0 |  |  |  |  | 1000 |  |  | 1000 |  | 1000 | 1000 | 1000
189 |  | Leith Walk Utilities | PS | Await Estimate | 500 | [5 empty] | 500 |  |  | 500 |  | 500 | 500 | 500
190 |  | Leith Walk Utilities | PS | Await Estimate | 500 | [5 empty] | 500 |  |  | 500 |  | 500 | 500 | 500
191 |  | Leith Walk Utilities | PS | Await Estimate | 500 | [5 empty] | 500 |  |  | 500 |  | 500 | 500 | 500
192 | 14 | Leith Walk Utilities | PS |  | 161 | [5 empty] | 161 |  |  | 161 |  | 161 | 161 | 161 | 161
193 | 46 | Leith Walk Utilities | PS |  | 391 | [5 empty] | 391 |  |  | 391 |  | 391 | 391 | 391 | 391
194 |  | Leith Walk Utilities | PS | Await Estimate | 500 | [5 empty] | 500 |  |  | 500 |  | 500 | 500 | 500
195 | 45 | Leith Walk Utilities | PS |  | 1041 | [5 empty] | 1041 |  |  | 1041 |  | 1041 | 1041 | 1041 | 1041
215 |  | Demolition and Alteration at Leith Walk Bus Depot | PS |  | 200000 | 339585 |  |  |  |  | 200000 |  |  | 200000 |  | 200000 | 200000 | 200000 | 539585
216 | 31 | Leith Walk Utilities | PS |  | 854 | [5 empty] | 854 |  |  | 854 |  | 854 | 854 | 854 | 854
217 |  | Leith Walk Utilities | PS | Await Estimate | 500 | [5 empty] | 500 |  |  | 500 |  | 500 | 500 | 500 | 500
218 | 32 | Leith Walk Utilities | PS |  | 256 | 0 |  |  |  |  | 256 |  |  | 256 |  | 256 | 256 | 256 | 256
219 |  | Leith Walk Utilities | PS | Await Estimate | 500 | [5 empty] | 500 |  |  | 500 |  | 500 | 500 | 500 | 500
220 | 33 | Leith Walk Utilities | PS |  | 127 | [5 empty] | 127 |  |  | 127 |  | 127 | 127 | 127 | 127
221 |  | Leith Walk Utilities | PS | Await Estimate | 500 | [5 empty] | 500 |  |  | 500 |  | 500 | 500 | 500 | 500
222 | 66 | Leith Walk Utilities | PS |  | 617 | [5 empty] | 617 |  |  | 617 |  | 617 | 617 | 617 | 617
223 | 34 | Stone Culvert Section 1B | PS |  | 1017 | 0 |  |  |  |  | 1017 |  |  | 1017 |  | 1017 | 1017 | 1017 | 1017
224 |  | Scottish Power Cable Section 1B | PS | Await Estimate | 500 | [5 empty] | 500 |  |  | 500 |  | 500 | 500 | 500 | 500
225 | 35 | Repairs to footpath to allow pedestrian access Section 1B | PS |  | 474 | [5 empty] | 474 |  |  | 474 |  | 474 | 474 | 474 | 474
234 |  | Leith Walk Utilities | PS |  | 9053 | [5 empty] | 9053 |  |  | 9053 |  | 9053 | 9053 | 9053 | 9053
235 |  | Leith Walk Utilities | PS | Await Estimate | 1200 | [5 empty] | 1200 |  |  | 1200 |  | 1200 | 1200 | 1200
240 |  | Removal and reinstatement of BT Phone Box | PS |  | 11405 | [5 empty] | 11405 |  |  | 11405 |  | 11405 | 11405 | 11405 | 11405
265 |  | IFC Drawings - 2A access retaining wall (Verity House) | PS |  | 25000 |  | 57797 |  |  |  | 25000 |  |  | 25000 |  | 25000 | 25000 | 82797 | 82797
|  | RC Track Slab (READA City Design) | READA |  | 1000000 | [6 empty] | 1000000 |  | 1000000 | 1077 | 3162000 | 3162000 | 3738600
|  | Vibration Quilt (READA City Design) | READA |  | 500000 | [7 empty] | 500000 | 500000 |  | 500000 | 600000 | 750000
341 |  | Princes Street - Reinforced Concrete Slab above Track Box | READA | Await Estimate | 400000 | [6 empty] | 400000 |  | 400000 | 1077 | 560000 | 560000 | 670000
|  | Additional Bitumen Surfacing (Add Thickness) - Picardy Place - Newhaven | Roads |  | 2280000 | [6 empty] | 2280000 |  | 2280000 | 35 | 3780000 | 3780000 | 3780000
|  | Additional Bitumen Surfacing (Add Thickness) - Princess St/St Andrews Sq | Roads |  | 500000 | [6 empty] | 500000 |  | 500000 | 35 | 500000 | 500000 | 500000
|  | Additional Road capping (Allow additional 300mm) | Roads | [12 empty] | 1000000 | 1300000 | 1300000
271 | 19 | Road Construction Details - Construction Methodology | Roads |  | 372540 |  | 0 |  |  |  |  | 372540 |  | 372540 | 35 | 372540 | 372540 | 372540 | 372540
187 | 28 | Additional Excavated material at Depot | Topo |  | 1425174 | [6 empty] | 1425174 |  | 1425174 | 974 | 1425174 | 1425174 | 1425174 | 1425174
149 |  | Relocation of Spoil in Section 7 (Assume RBS Bund) | Topo | Await Estimate | 150000 | 0 | [5 empty] | 150000 |  | 150000 | 974 | 150000 | 150000 | 150000
49 |  | Revised work scope at Bernard Street | TPF |  | 850000 | 0 | 0 | 850000 | [5 empty] | 850000 |  | 0 | 0 | 0 | 0
54 |  | St Andrews Square - Estimate | TPF |  | 7000000 | 0 | 0 | 7000000 | [5 empty] | 7000000 |  | 0 | 0 | 0 | 0
64 |  | Revised Finishes at Ocean Terminal | TPF |  | 3500 | 0 | 0 | 3500 | [5 empty] | 3500 |  | 0 | 0 | 0 | 0
64A |  | Revised Finishes at Ocean Terminal (Amended layout) | TPF | Await Estimate | 1200000 | 0 |  | 1200000 | [5 empty] | 1200000 |  | 0 | 0 | 0 | 0
66 |  | Revised specification - RBS Gogarburn Tramstop | TPF |  | 1750000 | 0 | 0 | 1750000 | [5 empty] | 1750000 |  | 0 | 0 | 0 | 0
258 |  | Future Proofing on behalf of New Ingilston / Highland Properties | TPF |  | 1262768 |  |  | 1262768 | [5 empty] | 1262768
301 |  | Develop & seek approval for enabling works for diversionary route from Princes Street to George Street / Queen Street | TPF |  | 138040 |  |  | 138040 | [5 empty] | 138040 |  | 138040 | 138040 | 138040 | 138040
76 |  | Gogar Trainstop | TPF | Validated | 743869 | 0 |  | 743869 | [5 empty] | 743869 |  | 0 | 0 | 0 | 0
76 |  | Gogar Trainstop | TPF | Await Estimate | 3000000 | 0 |  | 3000000 | [5 empty] | 3000000 |  | 0 | 0 | 0 | 0
141 | 24 | West End Tram Stop | TPF |  | 17761 | 0 |  | 17761 | [5 empty] | 17761
303 | 29 | Change to interior tram layout | Tramco |  | 335635 |  |  |  | 335635 |  |  |  |  | 335635 |  | 335635 | 335635 | 335635 | 335635
2 |  | Hilton Hotel Car Park |  |  | 0 |  | 90067 | [6 empty] | 0 |  | 0 | 25000 | 50000 | 90067
3 | 43 | Road Surveys | Roads |  | 77498 | 0 | [6 empty] | 77498 | 77498 |  | 77498 | 77498 | 77498 | 77498
4 |  | Russel Road Bridge |  | Await Estimate |  | 0 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
5 |  | Haymarket viaduct |  | Await Estimate |  | 0 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
7 | 17 | Hardstanding at Haymarket Yards |  |  | 881 | 0 | [6 empty] | 881 | 881 |  | 881 | 881 | 881 | 881
18 |  | Consortium Office |  | Await Estimate | 36732 | 0 | [6 empty] | 36732 | 36732 |  | 36732 | 45000 | 50000
19 | 1 | Archeological Works CAH |  |  | 5201 | 0 | [5 empty] | 5201 |  | 5201 | 105 | 5201 | 5201 | 5201 | 5201
21 | 2 | Asbestos work at CAH |  |  | 5268 | 0 | [5 empty] | 5268 |  | 5268 | 105 | 5268 | 5268 | 5268 | 5268
23 | 12 | Demolish Access steps at CAH |  |  | 2020 | 0 | 0 | [5 empty] | 2020 | 2020 |  | 2020 | 2020 | 2020 | 2020
24 |  | Verity House Access road |  | No Cost |  | 0 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
25 |  | Demolition of CAH |  | No Cost |  | 0 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
42 | 42 | SDS Delay to ravelston Tramstop |  |  | 2409 | 0 | [6 empty] | 2409 | 2409 |  | 2409 | 2409 | 2409 | 2409
44 |  | Amendements to Ocean Terminal | Client |  | 75000 | 50932 | 0 | [5 empty] | 75000 | 75000 |  | 75000 | 75000 | 75000 | 125932
48 | 15 | Additional TRO drgs |  |  | 3550 | 0 | [6 empty] | 3550 | 3550 |  | 3550 | 3550 | 3550 | 3550
59 | 5 | Removal of Asbestos to buildings to be demolished |  |  | 26048 | 0 | [5 empty] | 26048 |  | 26048 | 865 | 26048 | 26048 | 26048 | 26048
61 |  | Re-location of Archeological Arisings |  |  | 35000 | 75000 | [6 empty] | 35000 | 35000 |  | 35000 | 35000 | 35000 | 110000
63 |  | Tensioning of overhead contact system |  | No Change |  | 0 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
65 |  | Murrayfield - Patterned Finish | Client |  | 3348 | 818 | [6 empty] | 3348 | 3348 |  | 4166 | 4166 | 4166 | 4166
65 |  | Murrayfield - Patterned Finish | Client | Await Estimate | 30000 | 0 | [6 empty] | 30000 | 30000 |  | 30000 | 30000 | 30000
67 |  | Provide second access stair, Murrayfield Tramstop | Client |  | 32648 | 0 | [6 empty] | 32648 | 32648 |  | 32648 | 32648 | 32648 | 32648
67 |  | Provide second access stair, Murrayfield Tramstop | Client | Await Estimate | 125000 | 0 | [6 empty] | 125000 | 125000 |  | 125000 | 125000 | 125000
68 |  | Lack of Scottish Water Consents - Edinburgh Park to Carrick Knowe |  | Await Estimate |  | 0 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
73 |  | Contamination of land Knotweed - Russell Rd Retaining Wall |  | Await Estimate |  | 0 | [7 empty] | 0 |  | 50000 | 50000 | 75000
74 | 63 | Divert existing 300mm diam sewer - gogar landfill |  |  | 1434 | 0 | [6 empty] | 1434 | 1434 |  | 1434 | 1434 | 1434 | 1434
74 |  | Additional works - Revised drg / expolratory works being undertaken |  | Await Estimate | 25000 | 0 | [6 empty] | 25000 | 25000 |  | 25000 | 50000 | 75000
75 | 27 | Install temporary ramp - Depot |  |  | 14189 | 0 | [6 empty] | 14189 | 14189 |  | 14189 | 14189 | 14189 | 14189
77 |  | Amend line of route design section 5C (Add Hedge) |  |  | 4018 | 0 | [6 empty] | 4018 | 4018 |  | 4018 | 4018 | 4018 | 4018
77 |  | Amend line of route design section 5C (Add Hedge) |  |  | 10000 | 51948 | [6 empty] | 10000 | 10000 |  | 10000 | 30000 | 61948 | 61948
78 |  | Alterations to design of Edinburgh Airport | Client |  | 48620 | 0 | [6 empty] | 48620 | 48620 |  | 48620 | 48620 | 48620 | 48620
78 |  | Alterations to design of Edinburgh Airport | Client | Await Estimate | 200000 | 0 | [6 empty] | 200000 | 200000 |  | 200000 | 200000 | 200000
79 |  | Haymarket Junction Re-Design | Client |  | 53856 | 0 | 0 | [5 empty] | 53856 | 53856 |  | 53856 | 53856 | 53856 | 53856
79 |  | Haymarket Junction Re-Design | Client | Await Estimate | 200000 | 0 | [6 empty] | 200000 | 200000 |  | 200000 | 200000 | 200000
80 |  | CEC requesting change to finish of Gogarburn Retaining wall | Client |  | 4998 | 0 | [6 empty] | 4998 | 4998 |  | 4998 | 4998 | 4998 | 4998
81 |  | CEC requested using 42 watt pit lamp (Bat Lighting) | Client |  | 11010 | 0 | [6 empty] | 11010 | 11010 |  | 11010 | 11010 | 11010 | 11010
81 |  | CEC requested using 42 watt pit lamp (Bat Lighting) | Client | Await Estimate | 25000 | 0 | [6 empty] | 25000 | 25000 |  | 25000 | 25000 | 25000 | 25000
82 |  | Contamination: Fly tipping, oil pollution, contaminated material, household waste, giant hogweed |  | Await Estimate |  | 0 | [7 empty] | 0 |  | 20000 | 35000 | 50000
83 |  | Roseburn Street Temporary Traffic Lights |  | Await Estimate |  | 0 | [7 empty] | 0 |  | 0 | 0 | 75000
84 | 18 | Burnside Road Diversion |  |  | 963 | 0 |  | 0 |  |  |  |  | 963 | 963 |  | 963 | 963 | 963 | 963
88 |  | Power Supplies (tie Notice of Change Number 14) - BUDGET COST |  | Duplicated | 0 | 0 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
89 |  | Balfour Street Crossing | Client | Validated | 9242 | 0 | [6 empty] | 9242 | 9242 |  | 9242 | 9242 | 9242 | 9242
89 |  | Balfour Street Crossing | Client |  | 100000 | 0 | [6 empty] | 100000 | 100000 |  | 100000 | 100000 | 100000
90 |  | SDS Development Workshop (Pre-Novation Change) |  |  | 0 | 0 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
91 |  | ENT 002 - Edinburgh Park Strucrure (Foundations / sub-structure) | Ground |  | 75000 | 330631 | [5 empty] | 75000 |  | 75000 | 1077 | 35000 | 75000 | 75000 | 405631
92 |  | Re-design Russell Road retaining Wall to avoid clash with exg sewer |  |  | 0 | 0 | 0 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
93 |  | Design Estimate - Prior Approvals/Planning Application (SDS) |  |  | 0 | 0 | 47637 | [6 empty] | 0 |  | 0 | 0 | 0 | 47637
94 |  | Hilton Hotel Car Park full planning |  |  | 0 | 0 | 11462 | [6 empty] | 0 |  | 0 | 0 | 0 | 11462
95 |  | Depot Prior Approvals |  |  | 0 | 0 | 17176 | [6 empty] | 0 |  | 0 | 0 | 0 | 17176
96 |  | Amendments to Shandwick Place Design | Client |  | 71908 | 0 | 0 | [5 empty] | 71908 | 71908 |  | 71908 | 71908 | 71908 | 71908
96 |  | Amendments to Shandwick Place Design | Client | Await Estimate | 150000 | 0 | [6 empty] | 150000 | 150000 |  | 150000 | 150000 | 150000
97 |  | Balgreen Road Bridge Technical Design | Client |  | 2988 | 0 | [6 empty] | 2988 | 2988 |  | 2988 | 2988 | 2988 | 2988
102 |  | Section 5C - Gogar Church & Gogar Castle |  |  |  | 0 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
103 |  | Change to IFC Drgs - A8 Underpass | BDDI/IFC |  | 0 | 0 | [7 empty] | 0 |  | 175000 | 300000 | 450000
119 |  | IFC Drawing change Leith Walk Sub Station |  |  |  | 0 | [7 empty] | 0 |  | 0 | 25000 | 50000
120 |  | IFC Drawings Demolition and Reinforcing of existing building for Leith Walk Sub Station, sub station now positioned in area of building to be demolished |  | Await Estimate |  | 0 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
121 |  | UTC associated with delivery of alignment |  | Await Estimate |  | 0 | [7 empty] | 0
122 |  | Delay in receipt of CEC prior approval Sections 1A1 & 1A2 |  | Await Estimate |  | 0 | [7 empty] | 0 |  | 10000 | 25000 | 75000
123 |  | Forth Ports Agreement & Design Completion | Client | Validated | 55842 | 0 | [6 empty] | 55842 | 55842 |  | 55842 | 55842 | 55842 | 55842
123 |  |  | Client | Await Estimate | 150000 | [7 empty] | 150000 | 150000 |  | 50000 | 120000 | 150000
124 |  | Requirement of Principal Contractors License for Network Rail related works |  |  |  |  | 1021439 | [6 empty] | 0 |  | 0 | 0 | 0 | 1021439
126 |  | Revised drawing for OLE poles in Section 1B |  | Await Estimate |  | 0 | [7 empty] | 0 |  | 0 | 0 | 0
127 |  | Split packages for Prior Approvals; Ocean Terminal to Port of Leith |  |  | 5734 | 0 | [6 empty] | 5734 | 5734 |  | 5734 | 5734 | 5734 | 5734
128 |  | CEC request for change to roads design at Edinburgh Park Station Interchange |  | Await Estimate |  | 0 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
129 |  | CEC's request for extension of time for Prior Approvals 1/01a, 1/01b & 1/01C |  | Delay - Prior Approvals |  | 0 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
130 |  | Delayed issue of IFC Drawings - Ingilston Park and Ride Tram Stop |  | Delay - IFC Drgs |  | 0 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
131 |  | Section 1B Delay & Disruption |  | Delay, Disruption |  | 0 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
132 |  | War Memorial Relocation (Prov Sum) |  |  |  | 0 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
136 |  | Section 1C - Picardy Place - Modifications to design, additional design work outwith LOD & additional works to pavement in front of Playhouse |  | Await Estimate |  | 0 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
137 |  | Sections 1A1 & 1A2 - CEC's proposed amendments to tree build outs adjacent to Constitution St. |  | Await Estimate |  | 0 | [7 empty] | 0 |  | 0 | 0 | 35000
138 |  | Redesign Water of Leith Bridge Foundations | Client | Validated | 33567 | 0 | [6 empty] | 33567 | 33567 |  | 33567 | 33567 | 33567 | 33567
138 |  |  | Client | Await Estimate | 75000 | 0 | [6 empty] | 75000 | 75000 |  | 50000 | 50000 | 95000
139 |  | Revised Location of OLE poles in section 1A at the request of CEC | Client | Await Estimate | 8333 | 0 | [6 empty] | 8333 | 8333 |  | 0 | 0 | 8333
140 |  | Delay to issue of IFC Submissions |  | Delay |  | 0 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
142 |  | Christmas & Festival Embargo's - conflict of information |  | Prolongation issue |  | 0 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
143 |  | CEC's intent to adopt private roads between Lochside Crescent & Lochside Ave | Client | Await Estimate | 20000 | 0 | [6 empty] | 20000 | 20000 |  | 20000 | 20000 | 20000
143 |  |  | Client | Await Estimate | 50000 | [7 empty] | 50000 | 50000 |  | 50000 | 50000 | 50000
144 |  | Land Drain encountered in pastured areas | Client | Await Estimate | 3000 | 0 | [6 empty] | 3000 | 3000 |  | 0 | 0 | 0
145 |  | Additional work arising from CEC's additional comments on Section 5C technical approvals |  | Await Estimate |  | 0 | [7 empty] | 0 |  | 0 | 5000 | 18246
150 |  | IFC Drawings - Roseburn Street Viaduct |  | Await Estimate |  | 0 | [7 empty] | 0 |  | 0 | 0 | 300000
159 | 23 | Provisional Sum - Relocation of Ancient Monuments |  |  | 3993 | 0 | [6 empty] | 3993 | 3993 |  | 3993 | 3993 | 3993 | 3993
161 |  | Traffic Management - Temporary traffic signals |  | Await Estimate |  | 0 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
162 |  | Bus Tracker, TPDS & Radio |  |  | 0 | 0 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
163 |  | Haymarket Taxi Stance | Client | Validated | 26662 | 0 | [6 empty] | 26662 | 26662 |  | 26662 | 26662 | 26662 | 26662
163 |  |  | Client |  | 15000 | 0 | [6 empty] | 15000 | 15000 |  | 15000 | 30000 | 50000
164 |  | Delayed Listed Building Consent Applications |  | Delay |  | 0 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
165 |  | Delay to issue of IFC Submissions |  | Delay |  | 0 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
166 | 8 | Demolition of Garage Building - Ocean Drive |  |  | 17023 | 0 | [6 empty] | 17023 | 17023 |  | 17023 | 17023 | 17023 | 17023
168 | 16 | Demolition of Building 33 Ocean Drive |  |  | 5858 | 0 | [6 empty] | 5858 | 5858 |  | 5858 | 5858 | 5858 | 5858
169 | 48 | Demolition of Police Box Coffee Bar - Picardy Place |  |  | 9329 | 0 | [6 empty] | 9329 | 9329 |  | 9329 | 9329 | 9329 | 9329
169 |  | Remove and re-locate Palozzi's stones |  |  | 10323 | 0 | [6 empty] | 10323 | 10323 |  | 10323 | 10323 | 10323 | 10323
170 |  | Demolition of Cathedral Lane Toilet Block |  | Await Estimate | 20000 | 0 | [6 empty] | 20000 | 20000 |  | 20000 | 40000 | 40000
171 | 73 | Contract with Faber Maunsell for Transyt & Linsig Modelling Assessments |  |  | 64809 | 0 | [6 empty] | 64809 | 64809 |  | 64809 | 64809 | 64809 | 64809
172 |  | Traffic Modelling - Pedestrian Crossing Timing Standards |  | Validated | 43290 | 0 | [6 empty] | 43290 | 43290 |  | 43290 | 43290 | 43290 | 43290
172 |  |  |  | Await Estimate | 120000 | [7 empty] | 120000 | 120000 |  | 120000 | 120000 | 120000
173 |  | Discovery of underground petrol tank at NCR site |  |  | 4813 | 0 | [6 empty] | 4813 | 4813 |  | 4813 | 4813 | 4813 | 4813
175 |  | SDS Prov Sums - Extended Construction support and design team support |  | Await Estimate | 0 | 0 | [7 empty] | 0 |  | 0 | 0 | 0
176 | 9 | Various Works to Section 5c - Gogar Church & Gogar Castle |  |  | 6643 | 0 | [6 empty] | 6643 | 6643 |  | 6643 | 6643 | 6643 | 6643
177 |  | Harbour Trackwork |  |  | 0 | 0 | 130620 | [6 empty] | 0 |  | 0 | 0 | 0 | 130620
178 |  | Prov Sum: Mandatory tie Change (Missed Trigger Dates) |  | Await Estimate | 0 | 0 | [7 empty] | 0 |  | 0 | 0 | 0
180 |  | Reduced land available at Murrayfield |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0
181 |  | CEC requested additional Temp Traffic Light |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 75000
182 |  | Edinburgh Tramstop Kiosk | Client | Validated | 13621 | [7 empty] | 13621 | 13621 |  | 13621 | 13621 | 13621 | 13621
182 |  | Edinburgh Tramstop Kiosk | Client | Await Estimate | 75000 | [7 empty] | 75000 | 75000 |  | 75000 | 120000 | 175000
183 |  | Temporary Lining to Leith Walk |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0
186 |  | Specification Requirements to additional bus shelters at George St |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 120000
196 |  | Little King Street Works (Design Only, Construction within Picardy Place Prov) |  | Validated | 10768 | [7 empty] | 10768 | 10768 |  | 10768 | 10768 | 10768 | 10768
197 |  | Cyclepath near gyle tramstop | Client | Validated | 12146 | [7 empty] | 12146 | 12146 |  | 12146 | 12146 | 12146 | 12146
197 |  | Cyclepath near gyle tramstop | Client | Await Estimate | 200000 | [7 empty] | 200000 | 200000 |  | 200000 | 200000 | 200000
198 |  | Gogar Roundabout Lighting | Client | Validated | 4985 | [7 empty] | 4985 | 4985 |  | 4985 | 4985 | 4985 | 4985
198 |  | Gogar Roundabout Lighting | Client | Await Estimate | 145000 | [7 empty] | 145000 | 145000 |  | 145000 | 145000 | 145000
208 |  | Christmas Embargo Leith Walk | Client |  | 233356 | [7 empty] | 233356 | 233356 |  | 125000 | 150000 | 250037 | 250037
214 |  | Princes St Construction Works |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0 | 0
226 |  | Operational design review of Depot |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0 | 0
227 |  | Operational design review of Depot b |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0 | 0
228 |  | Relocation of Busstop outwith LOD |  | Await Estimate | 5941 | [7 empty] | 5941 | 5941 |  | 0 | 5941 | 5941 | 5941
[16 empty] | 0 | 15000 | 15000 | 15000
229 |  | INTC NOT ISSUED | [11 empty] | 0 |  | 0 | 0 | 0 | 0
236 |  | Outfall at the airport |  | Await Estimate | 15000 | [7 empty] | 15000 | 15000 |  | 0 | 0 | 30000
237 | 10 | Move Site Boundary at Haymarket Station to Accomodate Rugby Supporters on 8th & 15th November |  |  | 849 | [7 empty] | 849 | 849 |  | 849 | 849 | 849 | 849
238 |  | Temporary Traffic Lights opposite Manderson Street (Incomplete MUDFA) |  |  | 14078 | [7 empty] | 14078 | 14078 |  | 14078 | 14078 | 14078 | 14078
239 |  | Additional Trial Holes at Ch 145 - 160 (Section 1B) |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0
|  | Removal of Phone Boxes / Utility Diversions | [13 empty] | 150000 | 150000 | 150000
241 |  | MUDFA Delay at Bankhead Drive |  | Delay | [9 empty] | 0 |  | 0 | 0 | 0 | 0
242 |  | TRO Presentations by SDS at Public Meetings |  | Await Estimate | 50000 | [7 empty] | 50000 | 50000 |  | 20000 | 35000 | 50000
243 | 69 | Forth Ports Substation |  |  | 8270 | [7 empty] | 8270 | 8270 |  | 8270 | 8270 | 8270 | 8270
244 |  | Building Fixing Owner Agreements |  | Validated | 17750 | [7 empty] | 17750 | 17750 |  | 17750 | 17750 | 17750 | 17750
244 |  |  |  |  | 50000 | [7 empty] | 50000 | 50000 |  | 50000 | 50000 | 50000 | 50000
245 |  | Major Event - Murrayfield - 17 June 2009 |  | Delay | [9 empty] | 0 |  | 0 | 0 | 0 | 0
250 |  | Closure / Additional Works Leith Walk |  |  | 50000 | 11627 | [6 empty] | 50000 | 50000 |  | 35000 | 50000 | 61627 | 61627
256 |  | INTC NOT ISSUED | [11 empty] | 0 |  | 0 | 0 | 0 | 0
257 | 44 | Forth Ports access to ADM Milling | Client |  | 2071 | [7 empty] | 2071 | 2071 |  | 2071 | 2071 | 2071 | 2071
259 | 72 | IFC Drawing - Section 5B Cycleway at Edinburgh Park Station | Client |  | 52095 | [7 empty] | 52095 | 52095 |  | 52095 | 52095 | 52095 | 52095
260 | 36 | Relocate existing control box | Client |  | 1109 | 0 | [6 empty] | 1109 | 1109 |  | 1109 | 1109 | 1109 | 1109
264 |  | Section 1A - 4 Groundworks |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 150000
266 |  | Track Monitoring at Gogar Depot |  |  | 4673 | [7 empty] | 4673 | 4673 |  | 4673 | 4673 | 4673 | 4673
269 | 20 | Instructions arising from Trackform Development Workshop |  |  | 371058 |  | 0 | [5 empty] | 371058 | 371058 |  | 371058 | 371058 | 371058 | 371058
270 |  | RBS Tramstop - Provide Estimate for the diversion of LV Power and Water Supplies crossing the Tram Track |  | Await Estimate | [9 empty] | 0 |  | 5000 | 75000 | 15000
273 | 65 | Gogarburn Retaining Wall W14 - Redesign to Accomodate Water Mains and Gas Mains |  |  | 1157 | [7 empty] | 1157 | 1157 |  | 1157 | 1157 | 1157 | 1157
274 | 21 | Princes St Construction Works - Closure to Traffic during Construction Works |  |  | 6547 |  | 0 | [5 empty] | 6547 | 6547 |  | 6547 | 6547 | 6547 | 6547
275 |  | EAL Tramstop - BAA Interface | Client | Validated | 6824 | [7 empty] | 6824 | 6824 |  | 6824 | 6824 | 6824 | 6824
|  | EAL Tramstop - BAA Interface | Client |  | 33176 | [7 empty] | 33176 | 33176 |  | 33176 | 33176 | 33176 | 33176
276 |  | OLE Design Changes in Area between Haymarket and Newhaven |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0
277 |  | Airport Canopy tie in options | Client | Validated | 50428 | [7 empty] | 50428 | 50428 |  | 50428 | 50428 | 50428 | 50428
278 |  | Wider Area Modelling Proposals |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0
279 |  | West Pilton Tramstop |  | Deleted | [9 empty] | 0 |  | 0 | 0 | 0 | 0
280 |  | Change to demarcation requirements | [11 empty] | 0 |  | 0 | 15000 | 26882 | 26882
281 |  | Revised Proposals for Cathedral Lane Substation | Client | Await Estimate | 150000 | [7 empty] | 150000 | 150000 |  | 75000 | 75000 | 75000
282 |  | Request for instruction to deal with Japanese Knotweed at rear of Scotrail Depot Depot - Retaining Wall W4 |  | Await Estimate | 24283 | [7 empty] | 24283 | 24283 |  | 24283 | 24283 | 24283
283 |  | Edinburgh Park Bridge (S27) - Pier 3 Base Formation |  |  | 10675 | 0 | [6 empty] | 10675 | 10675 |  | 10675 | 10675 | 10675 | 10675
284 |  | Russell Road Retaining Wall - Options Report |  | Await Estimate | 10000 | [7 empty] | 10000 | 10000 |  | 0 | 0 | 10000
285 |  | Notified Departure, V40 Design Delivery Programme |  | Prolongation | [9 empty] | 0 |  | 0 | 0 | 0 | 0
286 |  | Princes Street Construction Works - Full Depth Reconstruction |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0
287 |  | Forth Ports Traffic Signal - Section 1A4 - Widened Crossing Required |  |  | 9577 | [7 empty] | 9577 | 9577 |  | 9577 | 9577 | 9577 | 9577
288 |  | Deviation Road Rail Vehicle Payload |  | Await Estimate | [9 empty] | 0 |  | 0 | 20000 | 25000
289 |  | Cycleway change at Hawthornevale - Section 1A4 |  | Await Estimate | [9 empty] | 0 |  | 15000 | 25000 | 30000
292 |  | Additional Ramp / Steps at Lindsay Road Retaining Wall |  | Await Estimate | 25000 | [7 empty] | 25000 | 25000 |  | 25000 | 35000 | 50000
293 | 37 | Gogar Castle Road tree felling |  |  | 1162 |  | 0 | [5 empty] | 1162 | 1162 |  | 1162 | 1162 | 1162 | 1162
298 |  | Revised Access arrangement to Depot |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0
299 |  | IFC Drawing Changes - Edinburgh Park Bridge (Piers, Bearings) |  |  | 136 | [7 empty] | 136 | 136 |  | 0 | 136 | 136 | 136
300 |  | Network Rail requirement for CAT 3 checking |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0
302 |  | Protection of live utilities at Russell Road Bridge during construction |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0
304 |  | Provisional Sum for Extra Over for Shell Grip at Junctions |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0
305 |  | Crawley Tunnel - Insufficient ground cover |  | Await Estimate | [9 empty] | 0 |  | 0 | 25000 | 45000
306 |  | Discovery of Underground structure on Leith Walk |  | Await Estimate | 25000 | [7 empty] | 25000 | 25000 |  | 25000 | 35000 | 50000
319 |  | Shandwick Place TRO Signage |  |  | 8386 | [7 empty] | 8386 | 8386 |  | 8386 | 8386 | 8386 | 8386
319 | [13 empty] | 0 |  | 15000 | 25000 | 30000
320 |  | Proposed CEC Changes to demarcation requirements | Client |  | 26881 | [7 empty] | 26881 | 26881 |  | 26881 | 26881 | 26881 | 26881
321 |  | Revised Alignment to Picardy Place, York Place & London Road Junctions |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0 | 0
322 |  | Carrickknowe Underbridge Obstructions |  |  | 2745 | [7 empty] | 2745 | 2745 |  | 0 | 0 | 2745 | 2745
323 |  | A8 Underpass Phase 1 Pile Toe Levels |  |  | 25000 | 13331 | [6 empty] | 25000 | 25000 |  | 0 | 20000 | 34319.38 | 34319.38
324 | 51 | A8 Underpass Phase 1 Piling Obstructions |  |  | 4015 | [7 empty] | 4015 | 4015 |  | 4015 | 4015 | 4015 | 4015
325 |  | Advertising Consents |  |  | 50000 |  | 218778 | [5 empty] | 50000 | 50000 |  | 0 | 50000 | 50000 | 268778
325 |  | Advertising Consents | [11 empty] | 0 |  | 0 | 150000 | 150000
326 |  | Expose existing gully connections at CH272 - 328 RHS |  |  | 5111 | [7 empty] | 5111 | 5111 |  | 5111 | 5111 | 5111 | 5111
327 | 41 | Section 1B - Carry out dye test |  |  | 619 | 0 | [6 empty] | 619 | 619 |  | 619 | 619 | 619 | 619
328 | 42 | Section 1B - Reinstate slabbed footway after MUDFA works |  |  | 1206 | 0 | [6 empty] | 1206 | 1206 |  | 1206 | 1206 | 1206 | 1206
329 |  | Section 1B - Breakout Foamed Concrete Backfill |  |  | 10106 | [7 empty] | 10106 | 10106 |  | 10106 | 10106 | 10106 | 10106
330 | 49 | Section 1B - Install additional gully CH250 RHS |  |  | 3060 | [7 empty] | 3060 | 3060 |  | 3060 | 3060 | 3060 | 3060
331 |  | Section 6 - Partial handover fo Depot Site |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0
333 |  | Investigate and reinstate existing batters north of Gogar Depot (W/Drawn) | [11 empty] | 0 |  | 0 | 0 | 0 | 0
334 |  | Access at New Ingilston |  |  | 8545 | [7 empty] | 8545 | 8545 |  | 3000 | 5000 | 6955 | 6955
337 |  | Section 1B - Testing to carriageway at Leith Walk |  |  | 14422 | [7 empty] | 14422 | 14422 |  | 14422 | 14422 | 14422 | 14422
338 | 57 | Section 1B - Removal of Ornamental Iron Balls from Groathill Depot |  |  | 354 | [7 empty] | 354 | 354 |  | 354 | 354 | 354 | 354
339 |  | Section 1B - Remove Spoil from Groathill Depot |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0 | 0
340 | 52 | Section 5B - Edinburgh Park bridge South Abutment Base - Existing Service |  |  | 531 | [7 empty] | 531 | 531 |  | 531 | 531 | 531 | 531
342 |  | Section 5C - Edinburgh Park Private Utilities |  | Await Estimate | [9 empty] | 0 |  | 15000 | 25000 | 30000
343 |  | Section 6A - Street Lighting |  |  | 2494.75 | [7 empty] | 2495 | 2495 |  | 2494.75 | 2494.75 | 2494.75 | 2495
343 | [13 empty] | 0 |  | 0 | 5000 | 15000 | 15000
344 |  | Disposal of Surplus excavated material at Depot (Refer INTC 187) |  | Await Estimate | [9 empty] | 0 | 974 | 0 | 0 | 0
345 |  | MUDFA use of Hippo Wheelwash |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0
346 |  | Edinburgh Park Bridge Structural Fill |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0
347 |  | Section 1D - Traffic Flow and Remodel at Lothian Road Junction |  | Await Estimate | 5000 | [7 empty] | 5000 | 5000 |  | 5000 | 15000 | 30000
348 |  | Section 1D - Additional signs on Queen Street |  |  | 289 | [7 empty] | 289 | 289 |  | 289 | 289 | 289 | 289
349 | 61 | Section 1C / 1D - TM Contingency for Emergency Utility Works |  |  | 405 | [7 empty] | 405 | 405 |  | 405 | 405 | 405 | 405
350 | 64 | Protected Species Mitigation Measures |  |  | 9262 | [7 empty] | 9262 | 9262 |  | 9262 | 9262 | 9262 | 9262
351 |  | Section 1C / 1D - Reversal of One Way System to Rose Street |  |  | 0 | [7 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
352 | 69 | Off peak taxi rank at George Street |  |  | 2213 | [7 empty] | 2213 | 2213 |  | 2213 | 2213 | 2213 | 2213
353 |  | Section 1C / 1D - Additional Measures at George Street |  |  | 5241 | [7 empty] | 5241 | 5241 |  | 0 | 1500 | 4816 | 4816
354 |  | Section 1C / 1D - Provide Corex Signs and Double Yellow Lines on George Street |  |  | 3332 | [7 empty] | 3332 | 3332 |  | 0 | 1500 | 3062 | 3062
355 |  | Section 1C / 1D - Additional Signage at George Street / St Andrews Square |  |  | 3215 | [7 empty] | 3215 | 3215 |  | 0 | 1500 | 2954 | 2954
356 |  | Section 1C / 1D - Replace MASS Barriers at George St., Hanover St & Frederick St. |  |  | 2536 | [7 empty] | 2536 | 2536 |  | 0 | 1500 | 2536 | 2536
357 |  | Section 1C / 1D - Trial Holes at Princes Street |  | Await Estimate | 2000 | [7 empty] | 2000 | 2000 |  | 2000 | 5000 | 7500
358 |  | Section 1C - Incomplete MUDFA Works at Princes Street |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0
359 |  | Haymarket Junction - Underground Chamber at Clifton Terrace |  | Await Estimate | 45000 | [7 empty] | 45000 | 45000 |  | 45000 | 45000 | 125000
360 | 54 | Alteration of Design at Forth Ports Road 8 |  |  | 11933 | 0 | [6 empty] | 11933 | 11933 |  | 11933 | 11933 | 11933 | 11933
363 |  | Provide Wider Area Signage to Princes Street |  |  | 12948 | [7 empty] | 12948 | 12948 |  | 0 | 5000 | 12948 | 12948
365 |  | Wider Area Fly P&R Survey |  | Await Estimate | [9 empty] | 0 |  | 5000 | 5000 | 5000
366 |  | Water Ingress Gogarburn East Abutment |  |  | 0 |  | 4096 | [5 empty] | 4096 | 4096 |  | 0 | 0 | 4096 | 4096
367 |  | Haymarket Rail Station - Network Rail Access Door |  | Await Estimate | [9 empty] | 0 |  | 15000 | 25000 | 30000
368 |  | Demolish all Structures on Plots 97 & 102 near Roseburn Street |  | Await Estimate | 45000 | [7 empty] | 45000 | 45000 |  | 45000 | 45000 | 45000
369 |  | Existing Services A8 Underpass Phase 1 |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0 | 0
370 |  | Existing Ground Levels at Edinburgh Park Bridge |  | Await Estimate | [9 empty] | 0 |  | 0 | 25000 | 50000
374 |  | Soil Nailing and Reinforced Earth Gogar Landfill |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0
375 |  | Revise OLE founds and layout section 1 - Design |  |  | 250000 | 107000 | [6 empty] | 250000 | 250000 |  | 250000 | 250000 | 300000 | 357000
375 |  | Revise OLE founds and layout section 1 - Construction | [13 empty] | 500000 | 500000 | 500000
376 |  | Revise OLE founds and layout - line 2 |  | Incl INTC 375 | [9 empty] | 0 |  | 0 | 0 | 0 | 0
377 |  | Amend SDS Design documents |  | Incl INTC 375 | [9 empty] | 0 |  | 0 | 0 | 0 | 0
378 |  | OHLE Building fixing loads and locations |  | Incl INTC 375 | [9 empty] | 0 |  | 0 | 0 | 0 | 0
379 |  | Combined OLE Lighting Poles |  | Incl INTC 375 | [9 empty] | 0 |  | 0 | 0 | 0 | 0
380 |  | OHLE Fixings at Depot Access Bridge |  | Incl INTC 375 | [9 empty] | 0 |  | 0 | 0 | 0 | 0
381 |  | Charlotte Square West End - On Parking |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0
382 |  | Bus Gate at Shandwick Place |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0
383 |  | Princes Street Rhino Barrier | Client | Await Estimate | [9 empty] | 0 |  | 80000 | 80000 | 80000
384 |  | Saturn Studs at George Street and Frederick Street |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0
385 | 62 | Additional MASS barriers on Great Stuart Street | Client |  | 915 | [7 empty] | 915 | 915 |  | 915 | 915 | 915 | 915
386 |  | Additional Traffic Management Princes Street | Client | Await Estimate | [9 empty] | 0 |  | 15000 | 20000 | 30000
387 |  | Bus Stand St Andrews Square |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0
388 |  | VMS Signs on Princes St Contingency Route | Client | Await Estimate | [9 empty] | 0 |  | 5000 | 10000 | 15000
389 |  | Production of As-Built Drawings for Princes Street | Client | Await Estimate | [9 empty] | 0 |  | 5000 | 10000 | 10000
392 |  | Edinburgh Park Bridge - Pier 1 Base Formation |  |  | 629 | [7 empty] | 629 | 629 |  | 629 | 629 | 629 | 629
393 |  | Section 5B - Edinburgh Park Approach Ramp Sub-Grade |  | Await Estimate | [9 empty] | 0 |  | 0 | 0 | 0
400 |  | Bicyle Provision at haymarket Steps |  |  | 8043 | [7 empty] | 8043 | 8043 |  | 8043 | 8043 | 8043 | 8043
404 |  | Section 5D - Drainage Ditches |  |  | -6225 | [7 empty] | -6225 | -6225 |  | -6225 | -6225 | -6225 | -6225
405 |  | Additional Retaining wall at Tower Bridge Pumping Station | [11 empty] | 0 |  | 75000 | 125000 | 250000
406 |  | Gogar Depot Earthworks - North Boundary Drainage Design |  |  | 7849 | [7 empty] | 7849 | 7849 |  | 7849 | 7849 | 7849 | 7849
406 |  | Gogar Depot Earthworks - North Boundary Drainage Design | [11 empty] | 0 |  | 25000 | 25000 | 25000
407 |  | Hard Material within Gogar Depot Excavation |  | Await Estimate | 40000 | [7 empty] | 40000 | 40000 |  | 40000 | 40000 | 40000
|  | Over excavation - Soft Material (Depot) | [13 empty] | 40000 | 40000 | 40000
408 |  | IFC Changes to Ductwork Specification | [11 empty] | 0
409 | 70a | Forth Ports New Construction at Ocean Drive - Design Only |  |  | 2817.6 | [7 empty] | 2818 | 2818 |  | 2817.6 | 2818 | 2818 | 2818
410 | [13 empty] | 0 |  | 0 | 0 | 0 | 0
411 | [13 empty] | 0 |  | 0 | 0 | 0 | 0
412 |  | Depot Floor - Pit for manual bogie turntable | [11 empty] | 0 |  | 15000 | 15000 | 15000 | 15000
413 |  | Expose & Protect existing private drain - Section 7 |  |  | 2696 | [7 empty] | 2696 | 2696 |  | 2696 | 2696 | 2696 | 2696
414 | [13 empty] | 0 |  | 0 | 0 | 0 | 0
415 |  | Pumping Station at Depot | [11 empty] | 0
416 |  | Side Entry Manhole Princes Street 1C2/D/MH/6901 | [11 empty] | 0 |  | 45000 | 45000 | 45000
417 |  | BAA Dual Future Proofing - Eastfield Avenue | [11 empty] | 0
| 60 | Additional Office Rental cost (SDS) |  |  | 150000 | [7 empty] | 150000 | 150000 |  | 150000 | 150000 | 150000 | 150000
|  | Amended Prelim % (Change Orders Issued) |  |  | 338459 | [7 empty] | 338459 | 338459 |  | 338459 | 338459 | 338459 | 338459
|  | Additional slabbing works - Leith Walk (outwith Minimal scope) |  |  | 40000 | [7 empty] | 40000 | 40000 |  | 40000 | 75000 | 120000
|  | Base Date Design Information | [11 empty] | 0 |  | 0 | 0 | 0 | 0
|  | Leith Walk - Miscellaneous Utility Diversions (Not Uncovered) | [11 empty] | 0
| . | Leith Walk Embargo | [11 empty] | 0
|  | St Andrews Square - Restriction |  |  | 200000 | [7 empty] | 200000 | 200000 |  | 0 | 0 | 0 | 0
|  | Prolongation (Further Claim) | [11 empty] | 0
|  | Removal of contaminated material (Incl Knotweed) |  |  | 50000 | [6 empty] | 50000 |  | 50000 | 173 | 35000 | 45000 | 100000
|  | Oncost - Fauber Mansell (17.4% x £200k) - Incl INTC 171 | [11 empty] | 0 |  | 0 | 0 | 0 | 0
|  | Provision - Rhino Barrier (Princess Street) |  |  | 80000 | [7 empty] | 80000 | 80000 |  | 0 | 0 | 0 | 0
|  | Provision, Actual Cost - Milestone (Leith Walk) |  |  | 250000 | [7 empty] | 250000 | 250000 |  | 50000 | 100000 | 250000
|  | Provision, Actual Cost - Milestone (Princess Street) | [11 empty] | 0
|  | SGN Gas Diversion - Culvert | [11 empty] | 0 |  | 250000 | 250000 | 250000
|  | SGN Gas Diversion - A8 Underpass | [11 empty] | 0 |  | 302000 | 302000 | 302000 | 302000
|  | OLE Development Workshop |  |  | 70000 | [7 empty] | 70000 | 70000 |  | 70000 | 70000 | 70000
Amended OGL's from Topo Surveys
Siemens Design Change (BDDI - IFC)
Further Supplemental Agreements
|  | Provision - Further INTC's to be raised | [13 empty] | 0 | 0 | 0
|  | Provision - Further SDS Design Change | [13 empty] | 0 | 0 | 0
[5 empty] | 51655734.35 | 10993691.17 | 2936292.16 | 15965938 | 335635 | 1978954 | 3704919 | 23099989 | 6574396 | 51659831 |  | 46832705.35 | 55638406.75 | 71146886.3 | 35283913.49
Non-BSC
|  | Logistics - Potential Additional Cost (Provision) |  |  | 450000 | [7 empty] | 450000 |  |  | 560000 | 560000 | 600000
|  | Stray Current Monitoring - Capcis |  |  | 75000 | [7 empty] | 75000 |  |  | 75000 | 75000 | 75000 | 75000
364 |  | Manhole at Balbirnie Place (Frontline cost) |  |  | 45000 |  |  |  |  | 45000 | [5 empty] | 45000 | 45000 | 45000 | 0
|  | EWS Storage Area (Frontline) |  |  | 43565 | [7 empty] | 43565 |  |  | 43565 | 43565 | 43565 | 43565
|  | Crash Gate 10 |  |  | 175000 | [7 empty] | 175000 |  |  | 175000 | 175000 | 175000 | 175000
[5 empty] | 788565 | 0 | 0 | 0 | 0 | 45000 | 0 | 0 | 743565 | 0 |  | 898565 | 898565 | 938565 | 293565
April Risk
Allowance
|  |  | BDDI/IFC |  | 7601230 | 4486092.17 | 1337220.16 | 0 | 0 | 0 | 0 | 7076230 | 525000 | 7601230 |  | 16605136 | 22933136 | 33689634.17 | 12339280
|  |  | READA |  | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 500000 | 1900000 |  | 4222000 | 4322000 | 5158600
|  |  | Roads |  | 5240946 | 0 | 0 | 0 | 0 | 0 | 0 | 4152540 | 77498 | 4230038 |  | 6730038 | 7030038 | 7030038 | 3511690
|  |  | Ground |  | 3952057 | 1270786 | 0 | 0 | 0 | 0 | 0 | 4962965 | 0 | 4962965 |  | 5058616 | 5310972 | 6198037 | 6437900
|  |  | Contam |  | 1020000 | 0 | 0 | 0 | 0 | 0 | 0 | 1020000 | 0 | 1020000 |  | 1020000 | 1200000 | 1500000 | 1291510
|  |  | Haz |  | 326563 | 12204 | 0 | 0 | 0 | 0 | 0 | 326563 | 0 | 326563 |  | 438724 | 438724 | 488767 | 293400
|  |  | Topo |  | 1575174 | 0 | 0 | 0 | 0 | 0 | 0 | 1575174 | 0 | 1575174 |  | 1575174 | 1575174 | 1575174 | 2651800
|  |  | EOT1 |  | 2500000 | 4549000 | 0 | 0 | 0 | 0 | 0 | 2500000 | 0 | 2500000 |  | 2500000 | 3000000 | 3500000 | 2500000
|  |  | MUDFA |  | 1978954 | 134031 | 0 | 0 | 0 | 1978954 | 0 | 0 | 0 | 1978954 |  | 1740673 | 1895673 | 2083145
|  |  | PS |  | 3704919 | 230922 | 57797 | 0 | 0 | 0 | 3704919 | 0 | 0 | 3704919 |  | 257861 | 257861 | 315658
|  |  | TPF |  | 15965938 | 0 | 0 | 15965938 | 0 | 0 | 0 | 0 | 0 | 15965938 |  | 138040 | 138040 | 138040
|  |  | Client |  | 2588629 | 51750 | 0 | 0 | 0 | 0 | 0 | 0 | 2588629 | 2588629 |  | 2374758 | 2544758 | 2818128 | 1970000
|  |  | Tramco |  | 335635 | 0 | 0 | 0 | 335635 | 0 | 0 | 0 | 0 | 335635 |  | 335635 | 335635 | 335635
|  |  | Other |  | 2965689.35 | 258906 | 1541275 | 0 | 0 | 0 | 0 | 86517 | 2883269 | 2969786 |  | 3836050.35 | 4656395.75 | 6316030.13
[5 empty] | 51655734.35 | 10993691.17 | 2936292.16 | 15965938 | 335635 | 1978954 | 3704919 | 23099989 | 6574396 | 51659831 |  | 46832705.35 | 55638406.75 | 71146886.3 | 30995580 | Less £1,955k drawn
[18 empty] | 343 | 11729840 | Delay
[18 empty] | 169 | 168650 | Other Proj
[18 empty] | 952 | 1768510 | Wide Area Infrastructure
[18 empty] | 931 | 754500 | Unexpected utilities
[19 empty] | 1759750 | Burnside Road
[19 empty] | 4290000 | VE Undeliverable
[19 empty] | 2289000 | Design
[19 empty] | 1644170 | Other Risks
[19 empty] | 55400000 | Infraco and design risks
Note on D330: SMcGarrity: Paid by Henderson?
Note on Q196: SMcGarrity: Moving track to middle of road
Note on Q204: SMcGarrity: Client instn

## Jan 09 Range Review
| ETP - PHASE 1A COSTS AND FUNDING REVIEW | ETP - PHASE 1 COSTS AND FUNDING REVIEW - RANGE FOR JAN 09 BOARD
1 |  |  | Cum 07/08 | Actual YTD P10 | Spent to P10 07/08 | Outturn P10 Report | Increases | Estimated Outturn High |  | Estimated Outturn High | Opp'ties | Estimated Outturn Low
[9 empty] | 9 | 10=8+9
2
|  | Project management Staff Costs |  |  | 17162.2852 | 26881.9014 | 3527 | 30408.9014 |  | 30408.9014 | -700 | 29708.9014
|  | ICT & Accommodation Costs |  |  | 3306.586 | 5346.7266 | 1050 | 6396.7266 |  | 6396.7266 |  | 6396.7266
|  | Overheads |  |  | 4115.8648 | 5504.7478 |  | 5504.7478 |  | 5504.7478 |  | 5504.7478
|  | Other PM costs |  |  | 821.6274 | 1235.1298 |  | 1235.1298 |  | 1235.1298 |  | 1235.1298
23 | T01 | Total tie PM COSTS | 0 | 0 | 25406.3634 | 38968.5057 | 4577 | 43545.5057 | 0 | 43545.5057 | -700 | 42845.5057
24
25 | T02.01 | Core Team | 1238.1946 | 322.0975 | 1560.292 | 7631.16 |  | 7631.16 |  | 7631.16 |  | 7631.16
30 | T02 | Total DPOF | 1238.1946 | 322.0975 | 1560.292 | 7631.16 | 0 | 7631.16 | 0 | 7631.16 | 0 | 7631.16
31
32 | T03.01 | DLA-SDS | 132.2269 | 8.386 | 140.6129 | 140.6129 |  | 140.6129 |  | 140.6129 |  | 140.6129
33 | T03.02 | DLA-TSS | 31.9994 | 0 | 31.9994 | 31.9994 |  | 31.9994 |  | 31.9994 |  | 31.9994
34 | T03.03 | DLA- Site Investigation | 1.1162 | 0 | 1.1162 | 1.1162 |  | 1.1162 |  | 1.1162 |  | 1.1162
35 | T03.04 | DLA-MUDFA | 674.1943 | 20.17 | 694.3643 | 694.3643 |  | 694.3643 |  | 694.3643 |  | 694.3643
36 | T03.05 | DLA-Network Rail / Scotrail | 115.3474 | -0.788 | 114.5594 | 114.5594 |  | 114.5594 |  | 114.5594 |  | 114.5594
37 | T03.06 | DLA-JRC | 27.3828 | 0 | 27.3828 | 27.3828 |  | 27.3828 |  | 27.3828 |  | 27.3828
38 | T03.07 | DLA-Infraco | 1063.4399 | 182.024 | 1245.4639 | 1415.0469 |  | 1415.0469 |  | 1415.0469 |  | 1415.0469
39 | T03.08 | DLA-Vehicles & Driver supply contract | 461.0147 | 10.214 | 471.2287 | 471.2287 |  | 471.2287 |  | 471.2287 |  | 471.2287
40 | T03.09 | DLA-BAA | 22.1998 | 2.013 | 24.2128 | 24.2128 |  | 24.2128 |  | 24.2128 |  | 24.2128
41 | T03.10 | DLA-Land & Property (3rd parties) | 25.9462 | 0 | 25.9462 | 25.9462 |  | 25.9462 |  | 25.9462 |  | 25.9462
42 | T03.11 | DLA-Ticketing Agreements | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
43 | T03.12 | DLA-DPOF | 85.711 | -0.749 | 84.962 | 84.962 |  | 84.962 |  | 84.962 |  | 84.962
44 | T03.13 | DLA-Tram Netwk/Roads Interface | 22.1495 | 0 | 22.1495 | 22.1495 |  | 22.1495 |  | 22.1495 |  | 22.1495
45 | T03.14 | DLA-EARL interface | 39.2174 | 0 | 39.2174 | 39.2174 |  | 39.2174 |  | 39.2174 |  | 39.2174
46 | T03.15 | DLA-Commissioning Svcs Agmt | 6.8925 | 0 | 6.8925 | 6.8925 |  | 6.8925 |  | 6.8925 |  | 6.8925
47 | T03.16 | OCIP | 24.2801 | 2.806 | 27.0861 | 27.0861 |  | 27.0861 |  | 27.0861 |  | 27.0861
48 | T03.17 | Infraco Enabling | 3.9506 | 0.432 | 4.3826 | 4.3826 |  | 4.3826 |  | 4.3826 |  | 4.3826
49 | T03.18 | HR Issues | -0.00031 | 0 | -0.00031 | -0.00031 |  | -0.00031 |  | -0.00031 |  | -0.00031
50 | T03.19 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
51 | T03.19.01 | Ingliston Park & Ride | -0.0005 | 0 | -0.0005 | -0.0005 |  | -0.0005 |  | -0.0005 |  | -0.0005
52 | T03.19.02 | Mass Earthworks | 1.1361 | -1.136 | 6e-05 | 6e-05 |  | 6e-05 |  | 6e-05 |  | 6e-05
60 | T03.19.10 | DLA - Reserve | 0 | 0 | 0 | 25.031 |  | 25.031 |  | 25.031 |  | 25.031
61 | T03.01-19 | Subtotal DLA | 2738.204 | 223.372 | 2961.576 | 3156.19 | 0 | 3156.19 | 0 | 3156.19 | 0 | 3156.19
62 | T03.20 | D&W-General Advice | 664.652 | 15.572 | 680.224 | 689.213 |  | 689.213 |  | 689.213 |  | 689.213
63 | T03.21 | D&W-TRO's | 277.9916 | 53 | 330.9916 | 485.9916 |  | 485.9916 |  | 485.9916 |  | 485.9916
64 | T03.22 | D&W-Property | 615.367 | 338.3175 | 953.6845 | 1024.3695 |  | 1024.3695 |  | 1024.3695 |  | 1024.3695
65 | T03.23 | D&W-Planning Monitoring | 167.742 | 13.511 | 181.253 | 181.253 |  | 181.253 |  | 181.253 |  | 181.253
66 | T03.24 | D&W-TDWG | 87.86 | -1.878 | 85.982 | 85.982 |  | 85.982 |  | 85.982 |  | 85.982
67 | T03.25 | D&W -Public Realm | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
68 | T03.26 | D&W-Litigation | 0.26 | 9.97 | 10.23 | 10.23 |  | 10.23 |  | 10.23 |  | 10.23
69 | T03.27 | D&W-Secondments | 152.123 | 0 | 152.123 | 152.123 |  | 152.123 |  | 152.123 |  | 152.123
78 | T03.20-35 | Subtotal D&W | 1965.9956 | 428.4925 | 2394.4881 | 2629.1621 | 0 | 2629.1621 | 0 | 2629.1621 | 0 | 2629.1621
91 | T03 | Total LEGALS | 4704.1996 | 651.8645 | 5356.0642 | 5785.3522 | 0 | 5785.3522 | 0 | 5785.3522 | 0 | 5785.3522
92
93 | T04.01 | Design Services under SDS | 11665.9513 | 0 | 11665.9513 | 9890.9516 |  | 9890.9516 |  | 9890.9516 |  | 9890.9516
94 | T04.01.01 | Overall Value Main Works ( Unallocated ) | 468.601 | 4028.5152 | 4497.1162 | 7632.2528 |  | 7632.2528 |  | 7632.2528 |  | 7632.2528
95 | T04.01.02 | Section 1 Newhaven Road to Haymarket | 2628.7902 | 0 | 2628.7902 | 2628.7902 |  | 2628.7902 |  | 2628.7902 |  | 2628.7902
96 | T04.01.03 | Section 2 Haymarket Corridor | 243.793 | 0 | 243.793 | 243.793 |  | 243.793 |  | 243.793 |  | 243.793
97 | T04.01.03 | Section 3 Haymarket to Granton Sq | 2172.2659 | 0 | 2172.2659 | 2172.2659 |  | 2172.2659 |  | 2172.2659 |  | 2172.2659
98 | T04.01.04 | Section 3 1B deduction | -1858.755 | 0 | -1858.755 | -1858.755 |  | -1858.755 |  | -1858.755 |  | -1858.755
99 | T04.01.05 | Section 4 Granton Sq to Newhaven Rd | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
100 | T04.01.06 | Section 5 Roseburn Junction to Gogar | 1453.6072 | 0 | 1453.6072 | 1453.6072 |  | 1453.6072 |  | 1453.6072 |  | 1453.6072
101 | T04.01.07 | Section 6 Gogar Depot | 328.7814 | 0 | 328.7814 | 328.7814 |  | 328.7814 |  | 328.7814 |  | 328.7814
102 | T04.01.08 | Section 7 Gogar to Edinburgh Airport | 443.2071 | 0 | 443.2071 | 443.2071 |  | 443.2071 |  | 443.2071 |  | 443.2071
103 | T04.01.09 | Section 8 Ingliston West / Newbridge | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
104 | T04.01.10 | MUDFA / Utilities | 552.6252 | 0 | 552.6252 | 552.6252 |  | 552.6252 |  | 552.6252 |  | 552.6252
105 | T04.01.11 | Claim | 1925 | 0 | 1925 | 1925 |  | 1925 |  | 1925 |  | 1925
106 | T04.01.12 | Variations | 0 | 0 | 0 | 0 |  | 0 |  | 0 | -100 | -100
115 | T04.02 | Site Investigation under SDS | 1415 | 0 | 1415 | 1415 |  | 1415 |  | 1415 |  | 1415
124 | T04 | Total SDS | 21438.8672 | 4028.5152 | 25467.3824 | 26827.5193 | 0 | 26827.5193 | 0 | 26827.5193 | -100 | 26727.5193
125
126 | T05.01 | Integrated Transport Model | 1747.7132 | 250.8402 | 1998.5533 | 2454.4445 |  | 2454.4445 |  | 2454.4445 | -100 | 2354.4445
127 | T05.02 | Surveys (MM) | 165.5888 | 0 | 165.5888 | 165.5888 |  | 165.5888 |  | 165.5888 |  | 165.5888
128 | T05.03 | Consultancy (Halcrow) | 9.9162 | 0 | 9.9162 | 9.9162 |  | 9.9162 |  | 9.9162 |  | 9.9162
136 | T05 | Total JRC | 1923.2181 | 250.8402 | 2174.0583 | 2629.9495 | 0 | 2629.9495 | 0 | 2629.9495 | -100 | 2529.9495
137
138 | T06.01 | Techincal Services | 8052.7744 | 950.4154 | 9003.1898 | 9302.5944 | 794 | 10096.5944 |  | 10096.5944 | -200 | 9896.5944 | Per SmcG workings pending a better answer from PM
139 | T06.02 | Land agreement/negotiations | 113 | 0 | 113 | 113 |  | 113 |  | 113 |  | 113
140 | T06.04 | TSS Second to CEC-Approvals support | 92.381 | 0 | 92.381 | 92.381 |  | 92.381 |  | 92.381 |  | 92.381
143 | T06.01-03 | Subtotal TSS | 8258.1554 | 950.4154 | 9208.5708 | 9507.9754 | 794 | 10301.9754 | 0 | 10301.9754 | -200 | 10101.9754 | Opportunity = Engineering resources
144 | T06.03 | CEC staff costs | 735.277 | 360.6509 | 1095.9279 | 1168.2768 | 862 | 2030.2768 |  | 2030.2768 | -400 | 1630.2768 | Incl £460k recharges and £401k dedicated team 0910 - nothing for parking rev loss.
149 | T06.04 | Subtotal CEC | 735.277 | 360.6509 | 1095.9279 | 1168.2768 | 862 | 2030.2768 | 0 | 2030.2768 | -400 | 1630.2768 | £461k approvals/TM recharges plus £400k permanent team
157 | T06 | Total TSS and CEC | 8993.4324 | 1311.0663 | 10304.4987 | 10676.2522 | 1656 | 12332.2522 | 0 | 12332.2522 | -600 | 11732.2522
158
174 | T09.01.01 | Network Rail (PM) | 322.5557 | 422.582 | 745.1377 | 990.7917 |  | 990.7917 |  | 990.7917 |  | 990.7917
175 | T09.01.02 | Network Rail (Legal) | 7.5 | 0 | 7.5 | 7.5 | 500 | 507.5 |  | 507.5 | -500 | 7.5 | BAA Legal & PM costs
185 | T09 | Total NR/BAA PM& LEGALS | 330.0557 | 422.582 | 752.6377 | 998.2917 | 500 | 1498.2917 | 0 | 1498.2917 | -500 | 998.2917
186
187 | T10.01 | D&W (10.01 &11.01) | 25.843 | 0 | 25.843 | 25.843 |  | 25.843 |  | 25.843 |  | 25.843
188 | T10.02 | Advisors (Colliers / DV) | 140.489 | 36.8911 | 177.3801 | 201.1208 |  | 201.1208 |  | 201.1208 |  | 201.1208
189 | T10.03 | Technical | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
190 | T10.04 | Advance Purchases 05/06 (Fees) | 60.181 | 0 | 60.181 | 60.181 |  | 60.181 |  | 60.181 |  | 60.181
191 | T10.05.01 | Advance Purchases (GVD) | 11726.953 | 0 | 11726.953 | 11726.953 |  | 11726.953 |  | 11726.953 | -1015 | 10711.953 | £785k land values plus £230k from TS re Scotrail
192 | T10.05.02 | Advance Purchases (gifted / free issue) | 4298.297 | 0 | 4298.297 | 4807.286 |  | 4807.286 |  | 4807.286 |  | 4807.286
193 | T10.05.03 | Advance Purchases | 0 | 157 | 157 | 1760 |  | 1760 |  | 1760 |  | 1760
201 | T10.01-.05 | Subtotal Land | 16251.763 | 193.8911 | 16445.6541 | 18581.3838 | 0 | 18581.3838 | 0 | 18581.3838 | -1015 | 17566.3838 | Scotrail settlement and clawback from TS
202 | T10.06.01 | Business Support Primary payment | 568.8 | 1054.2 | 1623 | 1629.25 |  | 1629.25 |  | 1629.25 |  | 1629.25
203 | T10.06.02 | Business Support Enhanced payment | 0 | 0 | 0 | 320.541 |  | 320.541 |  | 320.541 |  | 320.541
204 | T10.06.03 | Business Support Admin | 16.614 | 18.61 | 35.224 | 50 |  | 50 |  | 50 |  | 50
212 | T10.06 | Subtotal Business Support | 585.414 | 1072.81 | 1658.224 | 1999.791 | 0 | 1999.791 | 0 | 1999.791 | 0 | 1999.791
221 | T10 | Total LAND & PROPERTY | 16837.177 | 1266.7011 | 18103.8781 | 20581.1748 | 0 | 20581.1748 | 0 | 20581.1748 | -1015 | 19566.1748
222
235 | T12.01 | Fees / production Items - WS | 767.0278 | 41.126 | 808.1538 | 808.1538 |  | 808.1538 |  | 808.1538 | -50 | 758.1538
236 | T12.02 | Fees / production Items - MH | 268.6929 | 95.144 | 363.8369 | 561.8619 |  | 561.8619 |  | 561.8619 |  | 561.8619
237 | T12.03 | Tram branding | 37.5 | 0.56 | 38.06 | 38.06 |  | 38.06 |  | 38.06 |  | 38.06
238 | T12.04 | PR Support | 0 | 20.381 | 20.381 | 76.887 |  | 76.887 |  | 76.887 |  | 76.887
239 | T12.05 | Business development and marketing | 0.901 | 0 | 0.901 | 15.401 |  | 15.401 |  | 15.401 |  | 15.401
240 | T12.06 | Media monitoring | 16.455 | -4.375 | 12.08 | 17.705 |  | 17.705 |  | 17.705 |  | 17.705
241 | T12.07 | Media training | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
242 | T12.08 | Promotional materials | 7.826 | 105.26 | 113.086 | 229.086 |  | 229.086 |  | 229.086 |  | 229.086
243 | T12.09 | Websites | 0.49 | 21 | 21.49 | 34.49 |  | 34.49 |  | 34.49 |  | 34.49
244 | T12.10 | Events | 0 | 9.33 | 9.33 | 9.33 |  | 9.33 |  | 9.33 |  | 9.33
245 | T12.11 | Advertising | 32.618 | 11.352 | 43.97 | 72.97 |  | 72.97 |  | 72.97 |  | 72.97
246 | T12.12 | Internal communications | 3.835 | 4.736 | 8.571 | 23.071 |  | 23.071 |  | 23.071 |  | 23.071
247 | T12.23 | Sponsorship | 0 | 1 | 1 | 42.4 |  | 42.4 |  | 42.4 |  | 42.4
265 | T12.01-12,23-40 | Subtotal Communications | 1135.3457 | 305.514 | 1440.8597 | 1929.4157 | 0 | 1929.4157 | 0 | 1929.4157 | -50 | 1879.4157
266 | T12.13 | S/H – Wider Community Consultations | 2.024 | 25.381 | 27.405 | 278.455 |  | 278.455 |  | 278.455 |  | 278.455
267 | T12.14 | S/H – Events | 4.649 | 9.979 | 14.628 | 14.628 |  | 14.628 |  | 14.628 |  | 14.628
268 | T12.15 | S/H – Open for Business | 19.745 | 124.146 | 143.891 | 240 |  | 240 |  | 240 |  | 240
269 | T12.16 | S/H – Communications - MUDFA | 26.8 | 34.274 | 61.074 | 61.074 |  | 61.074 |  | 61.074 |  | 61.074
270 | T12.17 | S/H – Communications - Infraco | 0 | 11.493 | 11.493 | 11.493 |  | 11.493 |  | 11.493 |  | 11.493
276 | T12.13-22 | Subtotal Stakeholder | 53.218 | 205.273 | 258.491 | 605.65 | 0 | 605.65 | 0 | 605.65 | 0 | 605.65
288 | T12 | Total COMMS / MARKETING | 1188.5637 | 510.787 | 1699.3507 | 2535.0657 | 0 | 2535.0657 | 0 | 2535.0657 | -50 | 2485.0657
289
290 | T13.01 | Non Executive Board | 34.352 | 0 | 34.352 | -1536.896 | 1571 | 34.104 |  | 34.104 |  | 34.104
291 | T13.02 | Search Fees | 5 | 0 | 5 | 5 |  | 5 |  | 5 |  | 5
292 | T13.03 | Overheads | 1180.095 | 553 | 1733.095 | 4255.029 | 375 | 4630.029 |  | 4630.029 | -300 | 4330.029 | Increase from TPB paper.
295 | T13 | Total TEL | 1219.447 | 553 | 1772.447 | 2723.133 | 1946 | 4669.133 | 0 | 4669.133 | -300 | 4369.133
296
316 | T7/8/11/14/15/16 | Total HISTORIC CONSULTANCIES | 1068.2582 | 1.964 | 1070.2222 | 1073 |  | 1073 |  | 1073 |  | 1073
317
318 | T17.01 | Insurance consultancy | 177.1182 | 18.3021 | 195.4204 | 341.3879 |  | 341.3879 |  | 341.3879 |  | 341.3879
319 | T17.02 | OCIP | 307.2222 | 791.9996 | 1099.2217 | 3611.7377 | 480 | 4091.7377 |  | 4091.7377 | -516 | 3575.7377 | +6m cost. Opps on Marine (£300k), Env (£135k),consulatancy (£81k)
320 | T17.03 | Claims below deductible | 20.811 | -20.811 | 0 | 552.745 |  | 552.745 |  | 552.745 |  | 552.745
321 | T17.04 | Insurance Claims professional fees | 0 | 1.446 | 1.446 | 1.446 |  | 1.446 |  | 1.446 |  | 1.446
322 | T17.05 | Recoverable insurance claims - MUDFA | 0 | 40.818 | 40.818 | 0 |  | 0 |  | 0 |  | 0
323 | T17.06 | Non-recoverable insurance claims - MUDFA | 0 | 0.63 | 0.63 | 0 |  | 0 |  | 0 |  | 0
324 | T17.07 | Recoverable insurance claims - Infraco | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
325 | T17.08 | Non-recoverable insurance claims - Infraco | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
338 | T17 | Total INSURANCE | 505.1514 | 832.3847 | 1337.5361 | 4507.3166 | 480 | 4987.3166 | 0 | 4987.3166 | -516 | 4471.3166
339
340 | T18.01.01 | Pre-construction Services | 0 | 0 | 0 | 8.743 |  | 8.743 |  | 8.743 |  | 8.743
341 | T18.01.02 | Contract prelims | 133.504 | 3136.467 | 3269.971 | 3779.557 |  | 3779.557 |  | 3779.557 |  | 3779.557
342 | T18.01.03 | Section 1a | 674.275 | 3062.822 | 3737.097 | 4516.69 |  | 4516.69 |  | 4516.69 |  | 4516.69
343 | T18.01.04 | Section 1b | 724.219 | 808.413 | 1532.632 | 1532.632 |  | 1532.632 |  | 1532.632 |  | 1532.632
344 | T18.01.05 | Section 1c | 401.641 | 3148.851 | 3550.492 | 3978.544 |  | 3978.544 |  | 3978.544 |  | 3978.544
345 | T18.01.06 | Section 1d | 218.376 | 2158.671 | 2377.047 | 2841.887 |  | 2841.887 |  | 2841.887 |  | 2841.887
346 | T18.01.07 | Section 2 | 0 | 1458.626 | 1458.626 | 2209.689 |  | 2209.689 |  | 2209.689 |  | 2209.689
352 | T18.01.13 | Section 5a | 158.424 | 0 | 158.424 | 158.424 |  | 158.424 |  | 158.424 |  | 158.424
353 | T18.01.14 | Section 5b | 0 | 601.934 | 601.934 | 601.934 |  | 601.934 |  | 601.934 |  | 601.934
355 | T18.01.16 | Section 6 | -67.8 | 1875.312 | 1807.512 | 2015.512 |  | 2015.512 |  | 2015.512 |  | 2015.512
356 | T18.01.17 | Section 7 | 29.598 | 2656.801 | 2686.399 | 2966.791 |  | 2966.791 |  | 2966.791 |  | 2966.791
357 | T18.01.18 | Unallocated to section | 9561.2241 | 774.593 | 10335.8171 | 12478.3641 |  | 12478.3641 |  | 12478.3641 |  | 12478.3641
358 | T18.01.19 | Variations | 1021.632 | 1370.871 | 2392.503 | 2696.634 |  | 2696.634 |  | 2696.634 | -825 | 1871.634
359 | T18.01.20 | Reserve | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
360 | T18.01.21 | Claim(s) | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
361 | T18.01.22 | Transfer to / from Infraco | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
370 | T18.01 | Subtotal MUDFA | 12855.0931 | 21053.361 | 33908.4541 | 39785.4011 | 0 | 39785.4011 | 0 | 39785.4011 | -825 | 38960.4011 | £600k SGN betterment opp on Mound and £225k Logistics support
388 | T18.02.18 | Unallocated to section | 5516.9458 | 5856.46 | 11373.4058 | 10127.2138 |  | 10127.2138 |  | 10127.2138 | -1000 | 9127.2138
389 | T18.02.19 | Variations | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
390 | T18.02.20 | Reserve | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
391 | T18.02.21 | Claim(s) | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
401 | T18.02 | Subtotal utilities | 5516.9458 | 5856.46 | 11373.4058 | 10127.2138 | 0 | 10127.2138 | 0 | 10127.2138 | -1000 | 9127.2138 | £1,000k net betterment opp from BT
402 | T18 | Total MUDFA / Utilities | 18372.0388 | 26909.821 | 45281.8598 | 49912.6148 | 0 | 49912.6148 | 0 | 49912.6148 | -1825 | 48087.6148
403
404 | T19.01.01 | Prelims | 0 | 12095.0446 | 12095.0446 | 53329.7216 |  | 53329.7216 |  | 53329.7216 |  | 53329.7216
405 | T19.01.02 | Infraco early mobilisation | 1537.7446 | 7000.0004 | 8537.745 | 8537.745 |  | 8537.745 |  | 8537.745 |  | 8537.745
406 | T19.01.03 | Advanced purchases | 18000 | 0 | 18000 | 18000 |  | 18000 |  | 18000 |  | 18000
407 | T19.01.04 | Transfer to / from MUDFA | 27.287 | 0 | 27.287 | 27.287 |  | 27.287 |  | 27.287 |  | 27.287
408 | T19.01.05 | Section 1a | 0 | 0 | 0 | 15692.6278 |  | 15692.6278 |  | 15692.6278 |  | 15692.6278
409 | T19.01.06 | Section 1b | 0 | 89.8987 | 89.8987 | 6707.4914 |  | 6707.4914 |  | 6707.4914 |  | 6707.4914
410 | T19.01.07 | Section 1c | 0 | 0 | 0 | 9815.693 |  | 9815.693 |  | 9815.693 |  | 9815.693
411 | T19.01.08 | Section 1d | 0 | 0 | 0 | 6112.2361 |  | 6112.2361 |  | 6112.2361 |  | 6112.2361
412 | T19.01.09 | Section 2 | 0 | 301.4618 | 301.4618 | 5501.6675 |  | 5501.6675 |  | 5501.6675 |  | 5501.6675
413 | T19.01.10 | Section 3a | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
414 | T19.01.11 | Section 3b | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
415 | T19.01.12 | Section 3c | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
416 | T19.01.13 | Section 4a | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
417 | T19.01.14 | Section 4b | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
418 | T19.01.15 | Section 5a | 0 | 134.5335 | 134.5335 | 19029.8064 |  | 19029.8064 |  | 19029.8064 |  | 19029.8064
419 | T19.01.16 | Section 5b | 0 | 238.9715 | 238.9715 | 20041.7089 |  | 20041.7089 |  | 20041.7089 |  | 20041.7089
420 | T19.01.17 | Section 5c | 0 | 0 | 0 | 11057.0099 |  | 11057.0099 |  | 11057.0099 |  | 11057.0099
421 | T19.01.18 | Section 6 | 0 | 0 | 0 | 12967.0647 |  | 12967.0647 |  | 12967.0647 |  | 12967.0647
422 | T19.01.19 | Section 7 | 0 | 42.8719 | 42.8719 | 11129.5637 |  | 11129.5637 |  | 11129.5637 |  | 11129.5637
423 | T19.01.20 | Unallocated to section | 18240 | 0 | 18240 | 18240 |  | 18240 |  | 18240 |  | 18240
424 | T19.01.21 | NR Immunisation | 0 | 0 | 0 | 3000 |  | 3000 |  | 3000 |  | 3000 | Possible gain share here?
427 | T19.01.24 | Report adjustment | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
428 | T19.01.01-24 | Subtotal Construction | 37805.0316 | 19902.7824 | 57707.8141 | 219189.623 | 0 | 219189.623 | 0 | 219189.623 | 0 | 219189.623
429 | T19.01.25 | Testing and commissioning | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
430 | T19.01.26 | Maintenance mobilisation and spare parts | 0 | 0 | 0 | 2795.381 |  | 2795.381 |  | 2795.381 |  | 2795.381
431 | T19.01.35 | Variations - Prelims | 0 | 81.732 | 81.732 | 0 |  | 0 |  | 0 |  | 0
432 | T19.01.36 | Variations - Section 1a | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
433 | T19.01.37 | Variations - Section 1b | 0 | 1 | 1 | 0 |  | 0 |  | 0 |  | 0
434 | T19.01.38 | Variations - Section 1c | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
435 | T19.01.39 | Variations - Section 1d | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
436 | T19.01.40 | Variations - Section 2 | 0 | 51.349 | 51.349 | 0 |  | 0 |  | 0 |  | 0
437 | T19.01.41 | Variations - Section 3a | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
438 | T19.01.42 | Variations - Section 3b | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
439 | T19.01.43 | Variations - Section 3c | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
440 | T19.01.44 | Variations - Section 4a | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
441 | T19.01.45 | Variations - Section 4b | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
442 | T19.01.46 | Variations - Section 5a | 0 | 2.727 | 2.727 | 0 |  | 0 |  | 0 |  | 0
443 | T19.01.47 | Variations - Section 5b | 0 | 250 | 250 | 0 |  | 0 |  | 0 |  | 0
444 | T19.01.48 | Variations - Section 5c | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
445 | T19.01.49 | Variations - Section 6 | 0 | 20.991 | 20.991 | 0 |  | 0 |  | 0 |  | 0
446 | T19.01.50 | Variations - Section 7 | 0 | 90 | 90 | 0 |  | 0 |  | 0 |  | 0
447 | T19.01.27 | Variations - Unallocated to section | 0 | 145.779 | 145.779 | 0 |  | 0 |  | 0 |  | 0
448 | T19.01.51 | Variations - NR Immunisation | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
449 | T19.01.52 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
450 | T19.01.53 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
451 | T19.01.54 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
452 | T19.01.27, 35-54 | Subtotal Variations / Changes | 0 | 643.578 | 643.578 | 0 | 0 | 0 | 0 | 0 | 0 | 0
453 | T19.01.28 | Provisional sums DO NOT USE | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
454 | T19.01.29 | Contingency | 0 | 46.1538 | 46.1538 | 1200 |  | 1200 |  | 1200 |  | 1200 | Additional provision against VE through Risk Allow
455 | T19.01.30 | Claims | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
456 | T19.01.31 | EAL - Burnside road | 0 | 25 | 25 | 1000 | 2500 | 3500 |  | 3500 | -1000 | 2500 | Estimate per SB
457 | T19.01.32 | Provisional sum saving | 0 | 0 | 0 | -350 |  | -350 |  | -350 |  | -350
458 | T19.01.33 | Tapered poles | 0 | 0 | 0 | 176.381 |  | 176.381 |  | 176.381 | -176 | 0.381
459 | T19.01.34 | Power for comissioning | 0 | 0 | 0 | 1030 |  | 1030 |  | 1030 |  | 1030
460 | T19.01.55 | Allowance for demolition of existing Leith Walk substation (if required) | 0 | 0 | 0 | 55.662 |  | 55.662 |  | 55.662 |  | 55.662
461 | T19.01.56 | Accommodation Works | 0 | 0 | 0 | 1000 |  | 1000 |  | 1000 |  | 1000
462 | T19.01.57 | PICOPS / COSS / Possession Protection Staff support when undertaking works adjacent or over the railway | 0 | 10 | 10 | 755.307 |  | 755.307 |  | 755.307 |  | 755.307
463 | T19.01.58 | Additional Crew Relief Facilities at Haymarket | 0 | 0 | 0 | 49.95 |  | 49.95 |  | 49.95 |  | 49.95
464 | T19.01.59 | RBS requirement for enhancement of Gogarburn Tramstop | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
465 | T19.01.60 | Pumped surface water outfall at A8 underpass (by depot) | 0 | 0 | 0 | 100 |  | 100 |  | 100 |  | 100
466 | T19.01.61 | Relocation of Ancient Monuments | 0 | 0 | 0 | 53.7 |  | 53.7 |  | 53.7 |  | 53.7
467 | T19.01.62 | Extra over for revised alignment to Picardy Pl, York Pl and London Rd junctions (see also next item) | 0 | 0 | 0 | 3340.324 |  | 3340.324 |  | 3340.324 | -1000 | 2340.324
468 | T19.01.63 | Extra over for major utility diversions Picardy Pl, York Pl and London Rd junctions | 0 | 0 | 0 | 3000 |  | 3000 |  | 3000 | -2000 | 1000
469 | T19.01.64 | Extra over for shell grip at junctions | 0 | 0 | 0 | 319.343 |  | 319.343 |  | 319.343 |  | 319.343
470 | T19.01.65 | Allowance for SP connections to new street lights and new traffic signals | 0 | 0 | 0 | 115.287 |  | 115.287 |  | 115.287 |  | 115.287
471 | T19.01.66 | UTC associated with the delivery of the alignment | 0 | 0 | 0 | 2500 |  | 2500 |  | 2500 |  | 2500
472 | T19.01.67 | Various FP requirements | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
473 | T19.01.68 | FP requirements at Ocean Terminal amendments | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
474 | T19.01.69 | Allowance for minor utility diversions | 0 | 0 | 0 | 750 |  | 750 |  | 750 |  | 750
475 | T19.01.70 | Archaeological Officer – impact on productivity | 0 | 0 | 0 | 405.755 |  | 405.755 |  | 405.755 |  | 405.755
476 | T19.01.71 | UTC associated with the wider area impacts | 0 | 0 | 0 | 1905 |  | 1905 |  | 1905 |  | 1905
477 | T19.01.72 | FP requirements for design and construction of by-pass road to adoptable standard | 0 | 0 | 0 | 0.0004 |  | 0.0004 |  | 0.0004 |  | 0.0004
478 | T19.01.73 | FP requirements for Lindsay Rd amendments | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
479 | T19.01.74 | NR compliant ballast | 0 | 0 | 0 | 300 |  | 300 |  | 300 |  | 300
480 | T19.01.75 | SP connections to the depot and IPR | 0 | 0 | 0 | 750 |  | 750 |  | 750 |  | 750
481 | T19.01.76 | SP connections to Phase 1a sub-stations | 0 | 0 | 0 | 400 |  | 400 |  | 400 |  | 400
482 | T19.01.77 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
483 | T19.01.78 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
496 | T19.01.55-90 | Subtotal Provisional sums | 0 | 10 | 10 | 15800.3284 | 0 | 15800.3284 | 0 | 15800.3284 | -3000 | 12800.3284 | Net of 3rd party items - no review of balances incorporated
532 | T19.01 | Subtotal Infraco main works | 37805.0316 | 20627.5143 | 58432.5459 | 240841.7134 | 2500 | 243341.7134 | 0 | 243341.7134 | -4176 | 239165.7134
533 | T19.04.01 | Advanced purchases | -15500 | 4.0574 | -15495.9426 | -0.00025533 |  | -0.00025533 |  | -0.00025533 |  | -0.00025533
538 | T19.04 | Subtotal Funding adjustment | -15500 | 4.0574 | -15495.9426 | -0.00025533 | 0 | -0.00025533 | 0 | -0.00025533 | 0 | -0.00025533
539 | T19.02.01 | SRU Murrayfield pitches | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
540 | T19.02.02 | Relocate historic monuments | 0 | 0 | 0 | 42 |  | 42 |  | 42 |  | 42
541 | T19.02.03 | Environ. impacts - badgers | 24.9 | 18.812 | 43.712 | 92 |  | 92 |  | 92 |  | 92
542 | T19.02.04 | Invasive species | 92.379 | 65 | 157.379 | 269.917 |  | 269.917 |  | 269.917 |  | 269.917
554 | T19.02 | Subtotal advance works | 117.279 | 83.812 | 201.091 | 403.917 | 0 | 403.917 | 0 | 403.917 | 0 | 403.917
555 | T19.03.01 | Unallocated | 134.574 | 0 | 134.574 | 134.574 |  | 134.574 |  | 134.574 |  | 134.574
556 | T19.03.02 | Set up / mobilisation | 179.741 | 0 | 179.741 | 179.741 |  | 179.741 |  | 179.741 |  | 179.741
557 | T19.03.03 | Phase 1 (150,000m3) | 2914.685 | 0 | 2914.685 | 2914.685 |  | 2914.685 |  | 2914.685 |  | 2914.685
558 | T19.03.04 | Phase 2 (100,000m3) | 2209.987 | -0.609 | 2209.378 | 2209.378 |  | 2209.378 |  | 2209.378 |  | 2209.378
565 | T19.03 | Subtotal depot advance works | 5438.987 | -0.609 | 5438.378 | 5438.378 | 0 | 5438.378 | 0 | 5438.378 | 0 | 5438.378
626 | T19.06.01-60 | Subtotal VE - Infraco | #REF! | #REF! | 0 | 0 | 0 | 0 |  |  | 0 | 0
627 | T19.06.61 | Marerial recovery / reprocessing - MUDFA | 0 | 0 | 0 | -120 | 120 | 0 |  | 0 | -120 | -120
628 | T19.06.62 | Reduction in extent of road reinstatement | 0 | 0 | 0 | -116 | 116 | 0 |  | 0 | -116 | -116
629 | T19.06.63 | Deferred Leasing | 0 | 0 | 0 | -2961 |  | -2961 |  | -2961 |  | -2961 | Tfr to operating Budget as a benefit
630 | T19.06.64 | Network Reinforcement | 0 | 0 | 0 | -1363 |  | -1363 |  | -1363 |  | -1363 | See T19.07.04 below
667 | T19.06.61-100 | Subtotal VE - Non-Infraco | 0 | 0 | 0 | -4560 | 236 | -4324 | 0 | -4324 | -236 | -4560
668 | T19.06 | Subtotal VE | #REF! | #REF! | 0 | -4560 | 236 | -4324 | 0 | -4324 | -236 | -4560
669 | T19.07.01 | NR Lift and shift | 40.88 | 131.802 | 172.682 | 172.682 |  | 172.682 |  | 172.682 |  | 172.682
670 | T19.07.02 | NR Immunisation Implementation | 4.152 | -4.152 | 0 | 129.014 |  | 129.014 |  | 129.014 |  | 129.014
671 | T19.07.03 | NR Immunisation development | 51.31 | 67.579 | 118.889 | 144.8525 |  | 144.8525 |  | 144.8525 |  | 144.8525
672 | T19.07.04 | Power - Network reinforcement | 0 | 0 | 0 | 1579.674 |  | 1579.674 |  | 1579.674 |  | 1579.674 | Add £217k (net of £(1,363)k VE) to Provisional Sum allowance
673 | T19.07.05 | Ticket machines | 0 | 0 | 0 | 750 |  | 750 |  | 750 |  | 750 | OK per AR
674 | T19.07.06 | IPR2 contingency | 0 | 300 | 300 | 300 |  | 300 |  | 300 |  | 300 | Spent
675 | T19.07.07 | Traffic signal and UTC | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
676 | T19.07.08 | Murrayfield modifications | 0 | 150 | 150 | 940.01 |  | 940.01 |  | 940.01 |  | 940.01
677 | T19.07.09 | Fastlink alternative | 0 | 104.855 | 104.855 | 595 |  | 595 |  | 595 |  | 595 | Alloc from Prov Sum. TSS costs incl?
678 | T19.07.10 | Office land rental | 0 | 31.8926 | 31.8926 | 0 |  | 0 |  | 0 |  | 0
679 | T19.07.11 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
680 | T19.07.12 | Traffic management design | 0 | 16.9605 | 16.9605 | 0.6 |  | 0.6 |  | 0.6 |  | 0.6
738 | T19.07.70 | NR Immunisation take out | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
739 | T19.07 | Subtotal Non Infraco works | 96.342 | 798.9371 | 895.2791 | 4611.8325 | 0 | 4611.8325 | 0 | 4611.8325 | 0 | 4611.8325
740 | T19 | Total INFRACO | #REF! | #REF! | 49471.3513 | 246735.8406 | 2736 | 249471.8406 | 0 | 249471.8406 | -4412 | 245059.8406
741
742 | T20.01.01 | Prelims | 6 | 1 | 7 | 7 |  | 7 |  | 7 |  | 7
743 | T20.01.02 | Tramco early mobilisation | 250 | -250 | 0 | 0 |  | 0 |  | 0 |  | 0
744 | T20.01.03 | Approval of preliminary design | 0 | 1100.8325 | 1100.8325 | 1100.8325 |  | 1100.8325 |  | 1100.8325 |  | 1100.8325
745 | T20.01.04 | Delivery of mock up | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
746 | T20.01.05 | Approval of final design / mock up | 0 | 0 | 0 | 1651.2487 |  | 1651.2487 |  | 1651.2487 |  | 1651.2487
747 | T20.01.06 | Approvals and consents | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
748 | T20.01.07 | Commencenent of tram works | 0 | 9687.326 | 9687.326 | 9687.326 |  | 9687.326 |  | 9687.326 |  | 9687.326
749 | T20.01.08 | Completion 1st set bodyshells | 0 | 0 | 0 | 3302.4975 |  | 3302.4975 |  | 3302.4975 |  | 3302.4975
750 | T20.01.09 | Completion 1st set bogies | 0 | 0 | 0 | 3302.4975 |  | 3302.4975 |  | 3302.4975 |  | 3302.4975
751 | T20.01.10 | Completion 1st tram assembly | 0 | 0 | 0 | 3302.4975 |  | 3302.4975 |  | 3302.4975 |  | 3302.4975
752 | T20.01.11 | Completion factory based type testing | 0 | 0 | 0 | 3852.9137 |  | 3852.9137 |  | 3852.9137 |  | 3852.9137
753 | T20.01.12 | Delivery of preliminary tram maintenance manuals | 0 | 0 | 0 | 3302.4975 |  | 3302.4975 |  | 3302.4975 |  | 3302.4975
754 | T20.01.13 | Delivery of spares | 0 | 0 | 0 | 1100.8325 |  | 1100.8325 |  | 1100.8325 |  | 1100.8325
755 | T20.01.14 | Delivery of final documentation | 0 | 0 | 0 | 1100.8325 |  | 1100.8325 |  | 1100.8325 |  | 1100.8325
756 | T20.01.15 | Delivery of special tools | 0 | 0 | 0 | 550.4162 |  | 550.4162 |  | 550.4162 |  | 550.4162
757 | T20.01.16 | Completion of driver training | 0 | 0 | 0 | 550.4162 |  | 550.4162 |  | 550.4162 |  | 550.4162
758 | T20.01.17 | Completion of maintainer training | 0 | 0 | 0 | 550.4162 |  | 550.4162 |  | 550.4162 |  | 550.4162
759 | T20.01.18 | Completion of integrated system testing | 0 | 0 | 0 | 550.4162 |  | 550.4162 |  | 550.4162 |  | 550.4162
760 | T20.01.19 | Commencement of shadow running | 0 | 0 | 0 | 550.4162 |  | 550.4162 |  | 550.4162 |  | 550.4162
761 | T20.01.20 | Opening for passenger service | 0 | 0 | 0 | 550.4162 |  | 550.4162 |  | 550.4162 |  | 550.4162
762 | T20.01.21 | Supply chain mobilisation | 11003.8633 | 79.2995 | 11083.1629 | 11083.1629 |  | 11083.1629 |  | 11083.1629 |  | 11083.1629
763 | T20.01.22 | Adjustment | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
764 | T20.01.23 | Delivery of trams | 0 | 0 | 0 | 4520.728 |  | 4520.728 |  | 4520.728 |  | 4520.728
765 | T20.01.24 | Testing and commissioning | 0 | 0 | 0 | 4520.728 |  | 4520.728 |  | 4520.728 |  | 4520.728
766 | T20.01.25 | Advance maintenance mobilisation | 0 | 0 | 0 | 2275.1629 |  | 2275.1629 |  | 2275.1629 |  | 2275.1629
767 | T20.01.26 | Depot equipment | 147.9418 | 0.059989 | 148.0018 | 740.009 |  | 740.009 |  | 740.009 |  | 740.009
768 | T20.01.27 | Variations / changes | 0 | 0 | 0 | 0 | 200 | 200 |  | 200 |  | 200
769 | T20.01.28 | Contingency | 0 | 0 | 0 | -1.361 |  | -1.361 |  | -1.361 |  | -1.361
770 | T20.01.29 | Claims | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
792 | T20.01 | Subtotal Tramco main works | 11407.8052 | 10618.518 | 22026.3231 | 58151.9032 | 200 | 58351.9032 | 0 | 58351.9032 | 0 | 58351.9032
793 | T20.02.01 |  | -8700 | 0 | -8700 | 0 |  | 0 |  | 0 |  | 0
803 | T20.02 | Subtotal Funding adjustment | -8700 | 0 | -8700 | 0 | 0 | 0 | 0 | 0 | 0 | 0
833 | T20 | Total TRAMCO | 2707.8052 | 10618.518 | 13326.3231 | 58151.9032 | 200 | 58351.9032 | 0 | 58351.9032 | 0 | 58351.9032
834
957 | T99.01 | Miscellaneous | 163.2787 | 4.494 | 167.7727 | 235.6157 | -67 | 168.6157 |  | 168.6157 |  | 168.6157
958 | T99.02 | Previous years | 3093 | 0 | 3093 | 3093 |  | 3093 |  | 3093 |  | 3093
967 | T99 | Total MISC | 3256.2787 | 4.494 | 3260.7727 | 3328.6157 | -67 | 3261.6157 | 0 | 3261.6157 | 0 | 3261.6157
968
969 |  | Total BASE COSTS | #REF! | #REF! | 206345.0379 | 483065.695 | 12028 | 495093.695 | 0 | 495093.695 | -10118 | 484975.695
955 | T44 | Total RISK ALLOWANCE | 0 | 0 | 0 | 28949.968 | 15787.0195 | 44736.9875 |  | 44736.9875 | -8086 | 36650.9875
|  | Total PH1A COST ESTIMATE | #REF! | #REF! | 206345.0379 | 512015.663 | 27815.0195 | 539830.6825 | 0 | 539830.6825 | -18204 | 521626.6825
|  | Phase 1b Cancellation Costs Infraco | [5 empty] | 3200 |  |  |  | 3200
|  | Phase 1b Design Costs spent | [5 empty] | 3000 |  |  |  | 3000
|  | Total Costs to be Funded | [5 empty] | 546030.6825 |  |  |  | 527826.6825
Risk Allowance
|  | Infraco |  |  |  | 17479.92 | 13947.1658 | 31427.0858 |  |  | -6250 | 25177.0858
|  | MUFA/Utilities |  |  |  | 6652.77 | -218.869 | 6433.901 |  |  | 0 | 6433.901
|  | Design |  |  |  | 411.07 | -31.6906 | 379.3794 |  |  | 0 | 379.3794
|  | Land & Property |  |  |  | 1084.27 | -103.3799 | 980.8901 |  |  | -981 | -0.10993
|  | TROs |  |  |  | 927.38 | -72.2752 | 855.1048 |  |  | -855 | 0.10484
|  | Non-delivery of VE in Infraco price |  |  |  | 2000 | 2290 | 4290 |  |  | 0 | 4290
|  | Other |  |  |  | 395.49 | -24.8636 | 370.6264 |  |  | 0 | 370.6264
[6 empty] | 28950.9 | 15786.0875 | 44736.9875 | 0 | 0 | -8086 | 36650.9875
[5 empty] | Categ | Risk ID | Cause | P10 PM Reports | Revised Estimate | Approved Budget | Change | Opps
[5 empty] | 1.1 Land & Property | 352 | Increase in land values | 852.7942 | 852.7942 | 947.36 | -94.5658 | -853
[5 empty] | 1.1 Land & Property | 10 | Costs of obtaining access rights are unknown | 128.0958 | 128.0958 | 136.91 | -8.8142 | -128
[5 empty] | 5 PARLIAMENTARY PROCESS/ APPROVALS | 977 | Legal challenge. Extension of statutory consultation process. Large number of objections. TRO process is subject to a public hearing process. | 855.1048 | 855.1048 | 927.38 | -72.2752 | -855
[5 empty] | 7.3 Infraco | 279 |  | 712.5874 | 712.5874 | 772.82 | -60.2326 | -500
[5 empty] | 7.3 Infraco | 952 | Scope of works relating to Wide Area Modelling (WAM) have not been agreed with SDS because they consider this to be out with the scope of their contract. | 1802.4692 | 1802.4692 | 1958.78 | -156.3108 | -1000
[5 empty] | 7.3 Infraco | 911 | Scottish Power own and maintain a cable tunnel in the vicinity of Leith Walk that may or may not interfere with Tram construction and operation; exact location and depth of tunnel is unknown; condition of tunnel is unknown. | 506.9719 | 506.9719 | 549.55 | -42.5781 | -250
[5 empty] | 7.3 Infraco | 35 |  | 2280.8208 | 2280.8208 | 0 | 2280.8208 | -1500
[5 empty] | 7.3 Infraco | 49 | Lack of visibility of design changes between November 2007 and May 2008 and in general | 6081.9571 | 6081.9571 | 0 | 6081.9571 | -3000
[7 empty] | QRA Total | 13220.8012 | 13220.8012 | 5292.8 | 7928.0012 | -8086