## Design Drawing Tracker
| Updated to : |  | 2007-06-25 |  |  | Drawings Issued to AMIS for Buildability |  | Buildability Thumbnail Sketches Prepared by AMIS |  | Buildability Thumbnail Sketches Issued to SDS |  | Provision of C4 Info from SUC's & Issued to SDS |  | Original Issue | Supplementary Issue to SUC for Comment / Review (with Buildability) |  | SUC Approval |  |  | Issue IFC to tie |  | tie Issue Comments on IFC to SDS |  | Issue Approved IFC to tie |  | Construction Start (Rev 05 Programme)
| 1370 |  |  |  |  | 186 | 164 | 126 | 75 | 124 | 79 | 948 | 107 | 1334 | 1334 | 137 | 1334 | 123 | 123 | 1329 | 30 | 1209 | 0 | 1334 | 5 | 1370 | 1370
Sub-Section | Drawing No | Sheet No | Utility | Service Conflict | Status | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | Original Issue PLANNED | PLANNED | ACTUAL | PLANNED | ACTUAL | Approval | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | VARIANCE | COMMENTS
1A1 | ULE90130-01-UTL-01801 | 0 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-02-03 | 2007-02-03 | 2007-02-03 | 2007-03-09 | 2007-03-09 | Written |  |  |  |  | 2007-03-16 | 2007-03-16 | 2007-04-02 | 17 | COMPLETE
1A1 | ULE90130-01-UTL-01802 | 0 | 01 - Scotland Gas Networks | Conflict | Programmed | 2007-02-16 | 2007-03-02 | 2007-03-02 | 2007-03-02 | 2007-03-02 | 2007-03-02 | 2007-03-02 | 2007-03-02 | 2007-02-03 | 2007-02-03 | 2007-02-03 | 2007-03-09 | 2007-03-09 | Written |  |  |  |  | 2007-03-16 | 2007-03-16 | 2007-04-02 | 17 | COMPLETE
1A1 | ULE90130-01-UTL-01803 | 0 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-02-16 | 2007-01-12 | 2007-03-02 | 2007-03-02 | 2007-03-02 | 2007-03-02 |  |  | 2007-02-03 | 2007-02-03 | 2007-02-03 | 2007-03-09 | 2007-03-09 | Written |  |  |  |  | 2007-03-16 | 2007-03-16 | 2007-04-02 | 17 | COMPLETE
1A1 | ULE90130-01-UTL-01804 | 0 | 05 - BT Openreach | Conflict | Programmed | [7 empty] | 2007-04-12 | 2007-02-03 | 2007-02-03 | 2007-02-03 | 2007-03-09 | 2007-03-09 | Written |  |  |  |  | 2007-03-16 | 2007-03-16 | 2007-04-02 | 17 | COMPLETE
1A1 | ULE90130-01-UTL-01805 | 0 | 02 - Scottish Power | Conflict | Programmed | [7 empty] | 2007-04-12 | 2007-02-03 | 2007-02-03 | 2007-02-03 | 2007-03-09 | 2007-02-06 | Written |  |  |  |  | 2007-03-16 | 2007-03-16 | 2007-04-02 | 17 | COMPLETE
1A1 | ULE90130-01-UTL-00013 | 13 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 |  |  | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31
1A1 | ULE90130-01-UTL-00113 | 13 | 01 - Scotland Gas Networks | Conflict | Programmed | 2007-04-05 | 2007-04-02 | 2007-04-19 | 2007-04-02 | 2007-04-20 | 2007-04-12 | 2007-04-13 | 2007-05-18 | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 | 2007-06-22 | Written | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31
1A1 | ULE90130-01-UTL-00213 | 13 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-04-13 | 2007-05-18 | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 | 2007-02-06 | Written | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31
1A1 | ULE90130-01-UTL-00313 | 13 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-04-05 | 2007-01-12 | 2007-04-19 | 2007-04-05 | 2007-04-20 | 2007-04-12 |  |  | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 | 2007-06-14 | Written | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31
1A1 | ULE90130-01-UTL-00413 | 13 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-04-13 | 2007-05-18 | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 |  |  | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31 | Awaiting Outcome of Sewer Survey
1A1 | ULE90130-01-UTL-00513 | 13 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-04-13 | 2007-05-18 | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 | 2007-06-02 | Written | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31
1A1 | ULE90130-01-UTL-00713 | 13 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-04-13 | 2007-05-18 | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 | 2007-06-08 | Verbal to SDS | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31 | John Low to contact VM to get written approval (20-Jun-2007)
1A1 | ULE90130-01-UTL-00813 | 13 | 08 - Cable & Wireless | Conflict | Programmed | [6 empty] | 2007-04-13 | 2007-05-18 | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 | 2007-06-07 | Written | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31
1A1 | ULE90130-01-UTL-00913 | 13 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-04-13 | 2007-05-18 | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 | 2007-06-19 | Written | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31
1A1 | ULE90130-01-UTL-01713 | 13 | 17 - Forth Ports | Conflict | Programmed | [6 empty] | 2007-04-13 | 2007-05-18 | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 | 2007-05-23 | Written | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31
1A1 | ULE90130-01-UTL-00014 | 14 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 |  |  | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31
1A1 | ULE90130-01-UTL-00114 | 14 | 01 - Scotland Gas Networks | No Conflict | Programmed | 2007-04-05 | 2007-04-19 | 2007-04-19 | 2007-04-19 | 2007-04-20 | 2007-04-12 | 2007-04-13 | 2007-05-18 | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 | 2007-06-22 | Written | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31
1A1 | ULE90130-01-UTL-00214 | 14 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-04-13 | 2007-05-18 | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 | 2007-02-06 | Written | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31
1A1 | ULE90130-01-UTL-00314 | 14 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-04-05 | 2007-01-12 | 2007-04-19 | 2007-04-05 | 2007-04-20 | 2007-04-12 |  |  | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 | 2007-06-14 | Written | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31
1A1 | ULE90130-01-UTL-00414 | 14 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-04-13 | 2007-05-18 | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 |  |  | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31 | Awaiting Outcome of Sewer Survey
1A1 | ULE90130-01-UTL-00514 | 14 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-04-13 | 2007-05-18 | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 | 2007-06-02 | Written | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31
1A1 | ULE90130-01-UTL-00714 | 14 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-04-13 | 2007-05-18 | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 | 2007-06-08 | Verbal to SDS | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31 | John Low to contact VM to get written approval (20-Jun-2007)
1A1 | ULE90130-01-UTL-00814 | 14 | 08 - Cable & Wireless | Conflict | Programmed | [6 empty] | 2007-04-13 | 2007-05-18 | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 | 2007-06-07 | Written | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31
1A1 | ULE90130-01-UTL-00914 | 14 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-04-13 | 2007-05-18 | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 | 2007-06-19 | Written | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31
1A1 | ULE90130-01-UTL-01714 | 14 | 17 - Forth Ports | Conflict | Programmed | [6 empty] | 2007-04-13 | 2007-05-18 | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 | 2007-05-23 | Written | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31
1A1 | ULE90130-01-UTL-00015 | 15 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 |  |  | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31
1A1 | ULE90130-01-UTL-00115 | 15 | 01 - Scotland Gas Networks | Conflict | Programmed | 2007-04-05 | 2007-04-02 | 2007-04-19 | 2007-04-02 | 2007-04-20 | 2007-04-12 | 2007-04-13 | 2007-05-18 | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 | 2007-06-22 | Written | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31
1A1 | ULE90130-01-UTL-00215 | 15 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-04-13 | 2007-05-18 | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 | 2007-02-06 | Written | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31
1A1 | ULE90130-01-UTL-00315 | 15 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-04-05 | 2007-01-12 | 2007-04-19 | 2007-04-05 | 2007-04-20 | 2007-04-12 |  |  | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 | 2007-06-14 | Written | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31
1A1 | ULE90130-01-UTL-00415 | 15 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-04-13 | 2007-05-18 | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 |  |  | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31 | Awaiting Outcome of Sewer Survey
1A1 | ULE90130-01-UTL-00515 | 15 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-04-13 | 2007-05-18 | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 | 2007-06-02 | Written | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31
1A1 | ULE90130-01-UTL-00715 | 15 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-04-13 | 2007-05-18 | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 | 2007-06-08 | Verbal to SDS | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31 | John Low to contact VM to get written approval (20-Jun-2007)
1A1 | ULE90130-01-UTL-00815 | 15 | 08 - Cable & Wireless | Conflict | Programmed | [6 empty] | 2007-04-13 | 2007-05-18 | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 | 2007-06-07 | Written | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31
1A1 | ULE90130-01-UTL-00915 | 15 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-04-13 | 2007-05-18 | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 | 2007-06-19 | Written | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31
1A1 | ULE90130-01-UTL-01715 | 15 | 17 - Forth Ports | Conflict | Programmed | [6 empty] | 2007-04-13 | 2007-05-18 | 2007-05-04 | 2007-05-04 | 2007-06-01 | 2007-05-11 | 2007-05-23 | Written | 2007-06-01 | 2007-06-25 | 2007-06-01 |  | 2007-06-01 |  | 2007-07-02 | 31
1B | ULE90130-01-UTL-00031 | 31 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-04-20 | 2007-06-06 |  | 2007-06-18 |  |  | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-06 | 38
1B | ULE90130-01-UTL-00131 | 31 | 01 - Scotland Gas Networks | Conflict | Programmed | 2007-05-08 | 2007-05-03 | 2007-05-22 | 2007-05-03 | 2007-05-23 | 2007-05-10 | 2007-05-16 |  | 2007-04-20 | 2007-06-06 | 2007-06-09 | 2007-06-18 |  |  | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-06 | 38
1B | ULE90130-01-UTL-00231 | 31 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-05-16 |  | 2007-04-20 | 2007-06-06 | 2007-05-01 | 2007-06-18 | 2007-03-29 | Written | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-06 | 38
1B | ULE90130-01-UTL-00331 | 31 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-05-08 | 2007-02-06 | 2007-05-22 | 2007-05-03 | 2007-05-23 | 2007-05-10 |  |  | 2007-04-20 | 2007-06-06 | 2007-06-16 | 2007-06-18 |  |  | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-06 | 38
1B | ULE90130-01-UTL-00431 | 31 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-05-16 |  | 2007-04-20 | 2007-06-06 |  | 2007-06-18 |  |  | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-06 | 38
1B | ULE90130-01-UTL-00531 | 31 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-05-16 | 2007-06-07 | 2007-04-20 | 2007-06-06 | 2007-06-09 | 2007-06-18 |  |  | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-06 | 38
1B | ULE90130-01-UTL-00731 | 31 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-05-16 |  | 2007-04-20 | 2007-06-06 | 2007-06-09 | 2007-06-18 |  |  | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-06 | 38
1B | ULE90130-01-UTL-00831 | 31 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-05-16 |  | 2007-04-20 | 2007-06-06 | 2007-06-09 | 2007-06-18 | 2007-06-10 | Written | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-06 | 38
1B | ULE90130-01-UTL-00931 | 31 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-05-16 |  | 2007-04-20 | 2007-06-06 | 2007-06-09 | 2007-06-18 |  |  | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-06 | 38
1B | ULE90130-01-UTL-00029 | 29 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-04-20 | 2007-06-06 |  | 2007-06-18 |  |  | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-13 | 45
1B | ULE90130-01-UTL-00129 | 29 | 01 - Scotland Gas Networks | Conflict | Programmed | 2007-05-08 | 2007-05-04 | 2007-05-22 | 2007-05-04 | 2007-05-23 | 2007-05-10 | 2007-05-16 | 2007-05-18 | 2007-04-20 | 2007-06-06 | 2007-06-09 | 2007-06-18 |  |  | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-13 | 45
1B | ULE90130-01-UTL-00229 | 29 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-05-16 | 2007-05-18 | 2007-04-20 | 2007-06-06 | 2007-05-01 | 2007-06-18 | 2007-03-29 | Written | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-13 | 45
1B | ULE90130-01-UTL-00329 | 29 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-05-08 | 2007-02-06 | 2007-05-22 | 2007-05-03 | 2007-05-23 | 2007-05-10 |  |  | 2007-04-20 | 2007-06-06 | 2007-06-16 | 2007-06-18 |  |  | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-13 | 45
1B | ULE90130-01-UTL-00429 | 29 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-05-16 | 2007-05-18 | 2007-04-20 | 2007-06-06 |  | 2007-06-18 |  |  | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-13 | 45
1B | ULE90130-01-UTL-00529 | 29 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-05-16 | 2007-05-18 | 2007-04-20 | 2007-06-06 | 2007-06-09 | 2007-06-18 |  |  | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-13 | 45
1B | ULE90130-01-UTL-00729 | 29 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-05-16 | 2007-05-18 | 2007-04-20 | 2007-06-06 | 2007-06-09 | 2007-06-18 |  |  | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-13 | 45
1B | ULE90130-01-UTL-00829 | 29 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-05-16 | 2007-05-18 | 2007-04-20 | 2007-06-06 | 2007-06-09 | 2007-06-18 | 2007-06-10 | Written | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-13 | 45
1B | ULE90130-01-UTL-00929 | 29 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-05-16 | 2007-05-18 | 2007-04-20 | 2007-06-06 | 2007-06-09 | 2007-06-18 |  |  | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-13 | 45
1B | ULE90130-01-UTL-00030 | 30 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-04-20 | 2007-06-06 |  | 2007-06-18 |  |  | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-13 | 45
1B | ULE90130-01-UTL-00130 | 30 | 01 - Scotland Gas Networks | Conflict | Programmed | 2007-05-08 | 2007-05-03 | 2007-05-22 | 2007-05-03 | 2007-05-23 | 2007-05-10 | 2007-05-16 | 2007-05-18 | 2007-04-20 | 2007-06-06 | 2007-06-09 | 2007-06-18 |  |  | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-13 | 45
1B | ULE90130-01-UTL-00230 | 30 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-05-16 | 2007-05-18 | 2007-04-20 | 2007-06-06 | 2007-05-01 | 2007-06-18 | 2007-03-29 | Written | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-13 | 45
1B | ULE90130-01-UTL-00330 | 30 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-05-08 | 2007-02-06 | 2007-05-22 | 2007-05-03 | 2007-05-23 | 2007-05-10 |  |  | 2007-04-20 | 2007-06-06 | 2007-06-16 | 2007-06-18 |  |  | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-13 | 45
1B | ULE90130-01-UTL-00430 | 30 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-05-16 | 2007-05-18 | 2007-04-20 | 2007-06-06 |  | 2007-06-18 |  |  | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-13 | 45
1B | ULE90130-01-UTL-00530 | 30 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-05-16 | 2007-05-18 | 2007-04-20 | 2007-06-06 | 2007-06-09 | 2007-06-18 |  |  | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-13 | 45
1B | ULE90130-01-UTL-00730 | 30 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-05-16 | 2007-05-18 | 2007-04-20 | 2007-06-06 | 2007-06-09 | 2007-06-18 |  |  | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-13 | 45
1B | ULE90130-01-UTL-00830 | 30 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-05-16 | 2007-05-18 | 2007-04-20 | 2007-06-06 | 2007-06-09 | 2007-06-18 | 2007-06-10 | Written | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-13 | 45
1B | ULE90130-01-UTL-00930 | 30 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-05-16 | 2007-05-18 | 2007-04-20 | 2007-06-06 | 2007-06-09 | 2007-06-18 |  |  | 2007-06-25 |  | 2007-06-27 |  | 2007-06-29 |  | 2007-08-13 | 45
5A | ULE90130-05-UTL-00001 | 01 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
5A | ULE90130-05-UTL-00101 | 01 | 01 - Scotland Gas Networks | Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
5A | ULE90130-05-UTL-00201 | 01 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 | 2007-06-01 | 2007-06-15 | 2007-04-18 | Written | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
5A | ULE90130-05-UTL-00301 | 01 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-05-03 | 2007-06-11 | 2007-05-17 | 2007-06-12 | 2007-05-18 | 2007-06-13 |  |  | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
5A | ULE90130-05-UTL-00401 | 01 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
5A | ULE90130-05-UTL-00501 | 01 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52 | BT Higlighted that they have not started on C4
5A | ULE90130-05-UTL-00701 | 01 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 | 2007-05-28 | 2007-06-15 | 2007-06-07 | Verbal | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
5A | ULE90130-05-UTL-00801 | 01 | 08 - Cable & Wireless | Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
5A | ULE90130-05-UTL-00901 | 01 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
6A | ULE90130-06-UTL-00001 | 01 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
6A | ULE90130-06-UTL-00101 | 01 | 01 - Scotland Gas Networks | Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
6A | ULE90130-06-UTL-00201 | 01 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 | 2007-05-01 | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
6A | ULE90130-06-UTL-00301 | 01 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-05-03 | 2007-01-08 | 2007-05-17 | 2007-05-11 | 2007-05-18 | 2007-05-15 |  |  | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
6A | ULE90130-06-UTL-00401 | 01 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
6A | ULE90130-06-UTL-00501 | 01 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 | 2007-06-01 | 2007-06-15 | 2007-06-08 | Written | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
6A | ULE90130-06-UTL-00701 | 01 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 | 2007-06-01 | 2007-06-15 | 2007-06-08 | Written | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
6A | ULE90130-06-UTL-00801 | 01 | 08 - Cable & Wireless | Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
6A | ULE90130-06-UTL-00901 | 01 | 09 - Thus | Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
5A | ULE90130-05-UTL-00002 | 02 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
5A | ULE90130-05-UTL-00102 | 02 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
5A | ULE90130-05-UTL-00202 | 02 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 | 2007-06-01 | 2007-06-15 | 2007-04-18 | Written | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
5A | ULE90130-05-UTL-00302 | 02 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-05-03 | 2007-06-11 | 2007-05-17 | 2007-06-12 | 2007-05-18 | 2007-06-13 |  |  | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
5A | ULE90130-05-UTL-00402 | 02 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
5A | ULE90130-05-UTL-00502 | 02 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52 | BT Higlighted that they have not started on C4
5A | ULE90130-05-UTL-00702 | 02 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 | 2007-05-28 | 2007-06-15 | 2007-06-07 | Verbal | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
5A | ULE90130-05-UTL-00802 | 02 | 08 - Cable & Wireless | Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
5A | ULE90130-05-UTL-00902 | 02 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
6A | ULE90130-06-UTL-00002 | 02 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
6A | ULE90130-06-UTL-00102 | 02 | 01 - Scotland Gas Networks | Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
6A | ULE90130-06-UTL-00202 | 02 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 | 2007-05-01 | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
6A | ULE90130-06-UTL-00302 | 02 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-05-03 | 2007-01-08 | 2007-05-17 | 2007-05-11 | 2007-05-18 | 2007-05-15 |  |  | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
6A | ULE90130-06-UTL-00402 | 02 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
6A | ULE90130-06-UTL-00502 | 02 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 | 2007-06-01 | 2007-06-15 | 2007-06-08 | Written | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
6A | ULE90130-06-UTL-00702 | 02 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 | 2007-06-01 | 2007-06-15 | 2007-06-08 | Written | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
6A | ULE90130-06-UTL-00802 | 02 | 08 - Cable & Wireless | Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
6A | ULE90130-06-UTL-00902 | 02 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-01 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-20 | 52
5A | ULE90130-05-UTL-00003 | 03 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-15 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-27 | 59
5A | ULE90130-05-UTL-00103 | 03 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-15 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-27 | 59
5A | ULE90130-05-UTL-00203 | 03 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-15 | 2007-06-01 | 2007-06-01 | 2007-06-15 | 2007-04-18 | Written | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-27 | 59
5A | ULE90130-05-UTL-00303 | 03 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-05-03 | 2007-06-11 | 2007-05-17 | 2007-06-12 | 2007-05-18 | 2007-06-13 |  |  | 2007-06-15 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-27 | 59
5A | ULE90130-05-UTL-00403 | 03 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-15 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-27 | 59
5A | ULE90130-05-UTL-00503 | 03 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-15 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-27 | 59 | BT Higlighted that they have not started on C4
5A | ULE90130-05-UTL-00703 | 03 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-15 | 2007-06-01 | 2007-05-28 | 2007-06-15 | 2007-06-07 | Verbal | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-27 | 59
5A | ULE90130-05-UTL-00803 | 03 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-15 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-27 | 59
5A | ULE90130-05-UTL-00903 | 03 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-15 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-27 | 59
5A | ULE90130-05-UTL-01403 | 03 | 06 - Verizon | No Conflict | Programmed | [6 empty] | 2007-05-11 |  | 2007-06-15 | 2007-06-01 |  | 2007-06-15 |  |  | 2007-06-22 |  | 2007-06-26 |  | 2007-06-29 |  | 2007-08-27 | 59
1A1 | ULE90130-01-UTL-00011 | 11 | 00 - Composite | Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-09-10 | 101 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00111 | 11 | 01 - Scotland Gas Networks | No Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-09-10 | 101 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00211 | 11 | 02 - Scottish Power | No Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-05-04 | 2007-05-01 | 2007-05-18 | 2007-02-06 | Written | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-09-10 | 101 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00311 | 11 | 03 - Scottish Water - Clean | Conflict | Re-Programme | 2007-01-12 | 2007-01-12 | 2007-04-24 | 2007-04-05 | 2007-04-25 | 2007-04-05 |  |  | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-09-10 | 101 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00411 | 11 | 04 - Scottish Water - Foul | Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-09-10 | 101 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00511 | 11 | 05 - BT Openreach | Conflict | Re-Programme | [7 empty] | 2007-06-07 | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-09-10 | 101 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00711 | 11 | 07 - Virgin Media | No Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-09-10 | 101 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00811 | 11 | 08 - Cable & Wireless | No Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-09-10 | 101 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00911 | 11 | 09 - Thus | No Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-09-10 | 101 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-01711 | 11 | 17 - Forth Ports | Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-09-10 | 101 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00012 | 12 | 00 - Composite | Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-04-13 |  | 2007-04-27 |  |  | 2007-05-01 |  |  |  | 2007-05-04 |  | 2007-09-10 | 129 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00112 | 12 | 01 - Scotland Gas Networks | No Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-04-13 |  | 2007-04-27 |  |  | 2007-05-01 |  |  |  | 2007-05-04 |  | 2007-09-10 | 129 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00212 | 12 | 02 - Scottish Power | Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-04-13 | 2007-05-01 | 2007-04-27 | 2007-02-06 | Written | 2007-05-01 |  |  |  | 2007-05-04 |  | 2007-09-10 | 129 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00312 | 12 | 03 - Scottish Water - Clean | Conflict | Re-Programme | 2007-01-12 | 2007-01-12 | 2007-04-03 |  | 2007-04-04 |  |  |  | 2007-06-01 | 2007-04-13 |  | 2007-04-27 |  |  | 2007-05-01 |  |  |  | 2007-05-04 |  | 2007-09-10 | 129 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00412 | 12 | 04 - Scottish Water - Foul | Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-04-13 |  | 2007-04-27 |  |  | 2007-05-01 |  |  |  | 2007-05-04 |  | 2007-09-10 | 129 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00512 | 12 | 05 - BT Openreach | Conflict | Re-Programme | [7 empty] | 2007-06-07 | 2007-06-01 | 2007-04-13 |  | 2007-04-27 |  |  | 2007-05-01 |  |  |  | 2007-05-04 |  | 2007-09-10 | 129 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00712 | 12 | 07 - Virgin Media | Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-04-13 |  | 2007-04-27 |  |  | 2007-05-01 |  |  |  | 2007-05-04 |  | 2007-09-10 | 129 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00812 | 12 | 08 - Cable & Wireless | Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-04-13 |  | 2007-04-27 |  |  | 2007-05-01 |  |  |  | 2007-05-04 |  | 2007-09-10 | 129 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00912 | 12 | 09 - Thus | No Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-04-13 |  | 2007-04-27 |  |  | 2007-05-01 |  |  |  | 2007-05-04 |  | 2007-09-10 | 129 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-01712 | 12 | 17 - Forth Ports | Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-04-13 |  | 2007-04-27 |  |  | 2007-05-01 |  |  |  | 2007-05-04 |  | 2007-09-10 | 129 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | Off Constitution St | TBA | 00 - Composite |  | Re-Programme | [20 empty] | 2007-09-10 | 39335 | Works Outside LOD - Plates to be defined
1A1 | Off Constitution St | TBA | 01 - Scotland Gas Networks |  | Re-Programme | [20 empty] | 2007-09-10 | 39335 | Works Outside LOD - Plates to be defined
1A1 | Off Constitution St | TBA | 02 - Scottish Power |  | Re-Programme | [20 empty] | 2007-09-10 | 39335 | Works Outside LOD - Plates to be defined
1A1 | Off Constitution St | TBA | 04 - Scottish Water - Foul |  | Re-Programme | [20 empty] | 2007-09-10 | 39335 | Works Outside LOD - Plates to be defined
1A1 | Off Constitution St | TBA | 05 - BT Openreach |  | Re-Programme | [20 empty] | 2007-09-10 | 39335 | Works Outside LOD - Plates to be defined
1A1 | Off Constitution St | TBA | 07 - Virgin Media |  | Re-Programme | [20 empty] | 2007-09-10 | 39335 | Works Outside LOD - Plates to be defined
1A1 | Off Constitution St | TBA | 08 - Cable & Wireless |  | Re-Programme | [20 empty] | 2007-09-10 | 39335 | Works Outside LOD - Plates to be defined
1A1 | Off Constitution St | TBA | 09 - Thus |  | Re-Programme | [20 empty] | 2007-09-10 | 39335 | Works Outside LOD - Plates to be defined
1A1 | Off Constitution St | TBA | 03 - Scottish Water - Clean |  | Re-Programme | 2007-01-12 | 2007-01-12 | [18 empty] | 2007-09-10 | 39335 | Works Outside LOD - Plates to be defined
7B | ULE90130-07-UTL-00007 | 07 | 00 - Composite | Conflict | Re-Programme | [20 empty] | 2007-10-01 | 39356 | To be programmed AMIS/JE - EARL Interface
7B | ULE90130-07-UTL-00107 | 07 | 01 - Scotland Gas Networks | Conflict | Re-Programme | [20 empty] | 2007-10-01 | 39356 | To be programmed AMIS/JE - EARL Interface
7B | ULE90130-07-UTL-00207 | 07 | 02 - Scottish Power | Conflict | Re-Programme | [20 empty] | 2007-10-01 | 39356 | To be programmed AMIS/JE - EARL Interface
7B | ULE90130-07-UTL-00307 | 07 | 03 - Scottish Water - Clean | No Conflict | Re-Programme | 2007-05-15 | 2007-05-15 | [18 empty] | 2007-10-01 | 39356 | To be programmed AMIS/JE - EARL Interface
7B | ULE90130-07-UTL-00407 | 07 | 04 - Scottish Water - Foul | No Conflict | Re-Programme | [20 empty] | 2007-10-01 | 39356 | To be programmed AMIS/JE - EARL Interface
7B | ULE90130-07-UTL-00507 | 07 | 05 - BT Openreach | No Conflict | Re-Programme | [20 empty] | 2007-10-01 | 39356 | To be programmed AMIS/JE - EARL Interface
7B | ULE90130-07-UTL-00707 | 07 | 07 - Virgin Media | No Conflict | Re-Programme | [20 empty] | 2007-10-01 | 39356 | To be programmed AMIS/JE - EARL Interface
7B | ULE90130-07-UTL-00807 | 07 | 08 - Cable & Wireless | Conflict | Re-Programme | [20 empty] | 2007-10-01 | 39356 | To be programmed AMIS/JE - EARL Interface
7B | ULE90130-07-UTL-00907 | 07 | 09 - Thus | No Conflict | Re-Programme | [20 empty] | 2007-10-01 | 39356 | To be programmed AMIS/JE - EARL Interface
7B | ULE90130-07-UTL-00008 | 08 | 00 - Composite | Conflict | Re-Programme | [20 empty] | 2007-10-01 | 39356 | To be programmed AMIS/JE - EARL Interface
7B | ULE90130-07-UTL-00108 | 08 | 01 - Scotland Gas Networks | No Conflict | Re-Programme | [20 empty] | 2007-10-01 | 39356 | To be programmed AMIS/JE - EARL Interface
7B | ULE90130-07-UTL-00208 | 08 | 02 - Scottish Power | Conflict | Re-Programme | [20 empty] | 2007-10-01 | 39356 | To be programmed AMIS/JE - EARL Interface
7B | ULE90130-07-UTL-00308 | 08 | 03 - Scottish Water - Clean | No Conflict | Re-Programme | 2007-05-15 | 2007-05-15 | [18 empty] | 2007-10-01 | 39356 | To be programmed AMIS/JE - EARL Interface
7B | ULE90130-07-UTL-00408 | 08 | 04 - Scottish Water - Foul | No Conflict | Re-Programme | [20 empty] | 2007-10-01 | 39356 | To be programmed AMIS/JE - EARL Interface
7B | ULE90130-07-UTL-00508 | 08 | 05 - BT Openreach | Conflict | Re-Programme | [20 empty] | 2007-10-01 | 39356 | To be programmed AMIS/JE - EARL Interface
7B | ULE90130-07-UTL-00708 | 08 | 07 - Virgin Media | No Conflict | Re-Programme | [20 empty] | 2007-10-01 | 39356 | To be programmed AMIS/JE - EARL Interface
7B | ULE90130-07-UTL-00808 | 08 | 08 - Cable & Wireless | No Conflict | Re-Programme | [20 empty] | 2007-10-01 | 39356 | To be programmed AMIS/JE - EARL Interface
7B | ULE90130-07-UTL-00908 | 08 | 09 - Thus | No Conflict | Re-Programme | [20 empty] | 2007-10-01 | 39356 | To be programmed AMIS/JE - EARL Interface
1A1 | ULE90130-01-UTL-00009 | 09 | 00 - Composite | Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-10-01 | 122 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00109 | 09 | 01 - Scotland Gas Networks | Conflict | Re-Programme | 2007-04-02 | 2007-04-02 | 2007-04-24 | 2007-04-02 | 2007-04-25 | 2007-04-02 |  |  | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-10-01 | 122 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00209 | 09 | 02 - Scottish Power | Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-05-04 | 2007-05-01 | 2007-05-18 | 2007-02-06 | Written | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-10-01 | 122 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00309 | 09 | 03 - Scottish Water - Clean | Conflict | Re-Programme | 2007-01-12 | 2007-01-12 | 2007-04-24 |  | 2007-04-25 | 2007-04-02 |  |  | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-10-01 | 122 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00409 | 09 | 04 - Scottish Water - Foul | Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-10-01 | 122 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00509 | 09 | 05 - BT Openreach | Conflict | Re-Programme | [7 empty] | 2007-06-07 | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-10-01 | 122 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00709 | 09 | 07 - Virgin Media | Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-10-01 | 122 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00809 | 09 | 08 - Cable & Wireless | No Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-10-01 | 122 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00909 | 09 | 09 - Thus | No Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-10-01 | 122 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-01709 | 09 | 17 - Forth Ports | Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-10-01 | 122 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00010 | 10 | 00 - Composite | Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-10-01 | 122 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00110 | 10 | 01 - Scotland Gas Networks | No Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-10-01 | 122 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00210 | 10 | 02 - Scottish Power | No Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-05-04 | 2007-05-01 | 2007-05-18 | 2007-02-06 | Written | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-10-01 | 122 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00310 | 10 | 03 - Scottish Water - Clean | Conflict | Re-Programme | 2007-01-12 | 2007-01-12 | 2007-04-24 |  | 2007-04-25 |  |  |  | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-10-01 | 122 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00410 | 10 | 04 - Scottish Water - Foul | Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-10-01 | 122 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00510 | 10 | 05 - BT Openreach | Conflict | Re-Programme | [7 empty] | 2007-06-07 | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-10-01 | 122 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00710 | 10 | 07 - Virgin Media | Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-10-01 | 122 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00810 | 10 | 08 - Cable & Wireless | Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-10-01 | 122 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00910 | 10 | 09 - Thus | No Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-10-01 | 122 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-01710 | 10 | 17 - Forth Ports | Conflict | Re-Programme | [8 empty] | 2007-06-01 | 2007-05-04 |  | 2007-05-18 |  |  | 2007-05-25 |  |  |  | 2007-06-01 |  | 2007-10-01 | 122 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
5B | ULE90130-05-UTL-00011 | 11 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00111 | 11 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00211 | 11 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 | 2007-06-22 | 2007-07-06 | 2007-04-20 | Written | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00311 | 11 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-05-24 | 2007-03-29 | 2007-06-07 | 2007-06-06 | 2007-06-08 | 2007-06-07 |  |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00411 | 11 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00511 | 11 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00711 | 11 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 | 2007-05-28 | 2007-07-06 | 2007-06-07 | Verbal | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00811 | 11 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00911 | 11 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00012 | 12 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00112 | 12 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00212 | 12 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 | 2007-06-22 | 2007-07-06 | 2007-04-20 | Written | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00312 | 12 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-05-24 | 2007-03-29 | [6 empty] | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00412 | 12 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00512 | 12 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00712 | 12 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 | 2007-05-28 | 2007-07-06 | 2007-06-07 | Verbal | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00812 | 12 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00912 | 12 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00013 | 13 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00113 | 13 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00213 | 13 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 | 2007-06-22 | 2007-07-06 | 2007-04-20 | Written | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00313 | 13 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-05-24 | 2007-03-29 | 2007-06-07 | 2007-06-06 | 2007-06-08 | 2007-06-07 |  |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00413 | 13 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00513 | 13 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00713 | 13 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 | 2007-05-28 | 2007-07-06 | 2007-06-07 | Verbal | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00813 | 13 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00913 | 13 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00014 | 14 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00114 | 14 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00214 | 14 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 | 2007-06-22 | 2007-07-06 | 2007-04-20 | Written | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00314 | 14 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-05-24 | 2007-03-29 | 2007-06-07 | 2007-06-06 | 2007-06-08 | 2007-06-07 |  |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00414 | 14 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00514 | 14 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00714 | 14 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 | 2007-05-28 | 2007-07-06 | 2007-06-07 | Verbal | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00814 | 14 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00914 | 14 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-15 | 87 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00016 | 16 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-01 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00116 | 16 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-01 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00216 | 16 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-01 | 2007-07-06 |  | 2007-07-20 | 2007-04-20 | Written | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00316 | 16 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-06-07 | 2007-03-29 | [6 empty] | 2007-06-01 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00416 | 16 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-01 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00516 | 16 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-01 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00716 | 16 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-01 | 2007-07-06 | 2007-05-28 | 2007-07-20 | 2007-06-07 | Verbal | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00816 | 16 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-01 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00916 | 16 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-01 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00017 | 17 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-01 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00117 | 17 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-01 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00217 | 17 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-01 | 2007-07-06 |  | 2007-07-20 | 2007-04-20 | Written | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00317 | 17 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-06-07 | 2007-03-29 | [6 empty] | 2007-06-01 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00417 | 17 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-01 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00517 | 17 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-01 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00717 | 17 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-01 | 2007-07-06 | 2007-05-28 | 2007-07-20 | 2007-06-07 | Verbal | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00817 | 17 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-01 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00917 | 17 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-01 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00018 | 18 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-01 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00118 | 18 | 01 - Scotland Gas Networks | Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-01 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00218 | 18 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-01 | 2007-07-06 |  | 2007-07-20 | 2007-04-20 | Written | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00318 | 18 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-06-07 | 2007-03-29 | [6 empty] | 2007-06-01 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00418 | 18 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-01 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00518 | 18 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-01 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00718 | 18 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-01 | 2007-07-06 | 2007-05-28 | 2007-07-20 | 2007-06-07 | Verbal | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00818 | 18 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-01 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00918 | 18 | 09 - Thus | Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-01 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-10-15 | 73 | BT have highlighted that C4 available on ~15-Jun-07
5C | ULE90130-05-UTL-00024 | 24 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00124 | 24 | 01 - Scotland Gas Networks | Conflict | Programmed | 2007-05-10 | 2007-05-21 | 2007-05-24 | 2007-05-21 | 2007-05-25 | 2007-05-23 | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00224 | 24 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00324 | 24 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-05-10 | 2007-05-01 | 2007-05-24 | 2007-05-21 | 2007-05-25 | 2007-05-23 |  |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00424 | 24 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00524 | 24 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00724 | 24 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00824 | 24 | 08 - Cable & Wireless | Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00924 | 24 | 09 - Thus | Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-01024 | 24 | 10 - Easynet | Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00025 | 25 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00125 | 25 | 01 - Scotland Gas Networks | Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00225 | 25 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00325 | 25 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-05-10 | 2007-05-01 | 2007-05-24 | 2007-05-21 | 2007-05-25 | 2007-05-23 |  |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00425 | 25 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00525 | 25 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00725 | 25 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00825 | 25 | 08 - Cable & Wireless | Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00925 | 25 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00026 | 26 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00126 | 26 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00226 | 26 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00326 | 26 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-05-10 | 2007-05-01 | 2007-05-24 | 2007-05-11 | 2007-05-25 | 2007-05-15 |  |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00426 | 26 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00526 | 26 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00726 | 26 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00826 | 26 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00926 | 26 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00027 | 27 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00127 | 27 | 01 - Scotland Gas Networks | No Conflict | Programmed | 2007-05-10 | 2007-05-21 | 2007-05-24 | 2007-05-21 | 2007-05-25 | 2007-05-23 | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00227 | 27 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00327 | 27 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-05-10 | 2007-05-01 | 2007-05-24 | 2007-05-21 | 2007-05-25 | 2007-05-23 |  |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00427 | 27 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00527 | 27 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00727 | 27 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00827 | 27 | 08 - Cable & Wireless | Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-00927 | 27 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5C | ULE90130-05-UTL-01027 | 27 | 10 - Easynet | No Conflict | Programmed | [6 empty] | 2007-05-18 |  | 2007-06-01 | 2007-06-08 |  | 2007-06-22 |  |  | 2007-06-29 |  | 2007-07-03 |  | 2007-07-06 |  | 2007-10-15 | 101
5B | ULE90130-05-UTL-00009 | 09 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-22 | 94 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00109 | 09 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-22 | 94 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00209 | 09 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 | 2007-06-22 | 2007-07-06 | 2007-04-20 | Written | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-22 | 94 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00309 | 09 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-05-24 | 2007-03-29 | [6 empty] | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-22 | 94 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00409 | 09 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-22 | 94 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00509 | 09 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-22 | 94 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00709 | 09 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 | 2007-05-28 | 2007-07-06 | 2007-06-07 | Verbal | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-22 | 94 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00809 | 09 | 08 - Cable & Wireless | Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-22 | 94 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00909 | 09 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-22 | 94 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00010 | 10 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-22 | 94 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00110 | 10 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-22 | 94 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00210 | 10 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 | 2007-06-22 | 2007-07-06 | 2007-04-20 | Written | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-22 | 94 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00310 | 10 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-05-24 | 2007-03-29 | [6 empty] | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-22 | 94 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00410 | 10 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-22 | 94 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00510 | 10 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-22 | 94 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00710 | 10 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 | 2007-05-28 | 2007-07-06 | 2007-06-07 | Verbal | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-22 | 94 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00810 | 10 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-22 | 94 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00910 | 10 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-01 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-22 | 94 | BT have highlighted that C4 available on ~15-Jun-07
1B | ULE90130-01-UTL-00028 | 28 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-01 | 2007-06-06 |  | 2007-06-20 |  |  | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-22 | 110
1B | ULE90130-01-UTL-00128 | 28 | 01 - Scotland Gas Networks | Conflict | Programmed |  |  | 2007-05-22 | 2007-06-12 | 2007-05-23 | 2007-06-13 | 2007-05-16 | PART | 2007-06-01 | 2007-06-06 | 2007-06-09 | 2007-06-20 |  |  | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-22 | 110
1B | ULE90130-01-UTL-00228 | 28 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-05-16 | PART | 2007-06-01 | 2007-06-06 | 2007-05-01 | 2007-06-20 | 2007-03-29 | Written | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-22 | 110
1B | ULE90130-01-UTL-00328 | 28 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-05-08 | 2007-02-06 | 2007-05-22 | 2007-05-03 | 2007-05-23 | 2007-05-10 |  |  | 2007-06-01 | 2007-06-06 | 2007-06-16 | 2007-06-20 |  |  | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-22 | 110
1B | ULE90130-01-UTL-00428 | 28 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-05-16 | PART | 2007-06-01 | 2007-06-06 |  | 2007-06-20 |  |  | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-22 | 110
1B | ULE90130-01-UTL-00528 | 28 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-05-16 | 2007-06-07 | 2007-06-01 | 2007-06-06 | 2007-06-09 | 2007-06-20 |  |  | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-22 | 110
1B | ULE90130-01-UTL-00728 | 28 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-05-16 | PART | 2007-06-01 | 2007-06-06 | 2007-06-09 | 2007-06-20 |  |  | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-22 | 110
1B | ULE90130-01-UTL-00828 | 28 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-05-16 | PART | 2007-06-01 | 2007-06-06 | 2007-06-09 | 2007-06-20 | 2007-06-10 | Written | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-22 | 110
1B | ULE90130-01-UTL-00928 | 28 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-05-16 | PART | 2007-06-01 | 2007-06-06 | 2007-06-09 | 2007-06-20 |  |  | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-22 | 110
5A | ULE90130-05-UTL-00004 | 04 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2007-10-29 | 73 | Trial Pits week commencing 25-Jun-07
5A | ULE90130-05-UTL-00104 | 04 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2007-10-29 | 73 | Trial Pits week commencing 25-Jun-07
5A | ULE90130-05-UTL-00204 | 04 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 | 2007-04-18 | Written | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2007-10-29 | 73 | Trial Pits week commencing 25-Jun-07
5A | ULE90130-05-UTL-00304 | 04 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-06-21 | [7 empty] | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2007-10-29 | 73 | Trial Pits week commencing 25-Jun-07
5A | ULE90130-05-UTL-00404 | 04 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2007-10-29 | 73 | Trial Pits week commencing 25-Jun-07
5A | ULE90130-05-UTL-00504 | 04 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2007-10-29 | 73 | Trial Pits week commencing 25-Jun-07
5A | ULE90130-05-UTL-00704 | 04 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 | 2007-05-28 | 2007-08-03 | 2007-06-07 | Verbal | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2007-10-29 | 73 | Trial Pits week commencing 25-Jun-07
5A | ULE90130-05-UTL-00804 | 04 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2007-10-29 | 73 | Trial Pits week commencing 25-Jun-07
5A | ULE90130-05-UTL-00904 | 04 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2007-10-29 | 73 | Trial Pits week commencing 25-Jun-07
5A | ULE90130-05-UTL-00005 | 05 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2007-10-29 | 73 | Trial Pits week commencing 25-Jun-07
5A | ULE90130-05-UTL-00105 | 05 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2007-10-29 | 73 | Trial Pits week commencing 25-Jun-07
5A | ULE90130-05-UTL-00205 | 05 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 | 2007-04-18 | Written | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2007-10-29 | 73 | Trial Pits week commencing 25-Jun-07
5A | ULE90130-05-UTL-00305 | 05 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-06-21 |  | 2007-07-05 |  | 2007-07-06 |  |  |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2007-10-29 | 73 | Trial Pits week commencing 25-Jun-07
5A | ULE90130-05-UTL-00405 | 05 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2007-10-29 | 73 | Trial Pits week commencing 25-Jun-07
5A | ULE90130-05-UTL-00505 | 05 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2007-10-29 | 73 | Trial Pits week commencing 25-Jun-07
5A | ULE90130-05-UTL-00705 | 05 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2007-10-29 | 73 | Trial Pits week commencing 25-Jun-07
5A | ULE90130-05-UTL-00805 | 05 | 08 - Cable & Wireless | Conflict | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2007-10-29 | 73 | Trial Pits week commencing 25-Jun-07
5A | ULE90130-05-UTL-00905 | 05 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2007-10-29 | 73 | Trial Pits week commencing 25-Jun-07
5B | ULE90130-05-UTL-00006 | 06 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-22 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00106 | 06 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-22 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00206 | 06 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-22 | 2007-06-22 | 2007-06-22 | 2007-07-06 | 2007-04-20 | Written | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00306 | 06 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-05-24 | 2007-03-29 | [6 empty] | 2007-06-22 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00406 | 06 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-22 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00506 | 06 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-22 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00706 | 06 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-22 | 2007-06-22 | 2007-05-28 | 2007-07-06 | 2007-06-07 | Verbal | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00806 | 06 | 08 - Cable & Wireless | Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-22 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00906 | 06 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-22 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00007 | 07 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-06-22 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00107 | 07 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-22 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00207 | 07 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-22 | 2007-06-22 | 2007-06-22 | 2007-07-06 | 2007-04-20 | Written | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00307 | 07 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-05-24 | 2007-03-29 | [6 empty] | 2007-06-22 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00407 | 07 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-22 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00507 | 07 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-22 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00707 | 07 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-22 | 2007-06-22 | 2007-05-28 | 2007-07-06 | 2007-06-07 | Verbal | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00807 | 07 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-22 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00907 | 07 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-22 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00008 | 08 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-22 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00108 | 08 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-22 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00208 | 08 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-22 | 2007-06-22 | 2007-06-22 | 2007-07-06 | 2007-04-20 | Written | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00308 | 08 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-05-24 | 2007-03-29 | 2007-06-07 | 2007-06-06 | 2007-06-08 | 2007-06-07 |  |  | 2007-06-22 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00408 | 08 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-22 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00508 | 08 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-22 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00708 | 08 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-22 | 2007-06-22 | 2007-05-28 | 2007-07-06 | 2007-06-07 | Verbal | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00808 | 08 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-22 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
5B | ULE90130-05-UTL-00908 | 08 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-06-01 |  | 2007-06-22 | 2007-06-22 |  | 2007-07-06 |  |  | 2007-07-13 |  | 2007-07-17 |  | 2007-07-20 |  | 2007-10-29 | 101 | BT have highlighted that C4 available on ~15-Jun-07
1B | ULE90130-01-UTL-00026 | 26 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-01 | 2007-06-06 |  | 2007-06-20 |  |  | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-29 | 117 | Plate 26 affected by change in alignment. IFC date under threat.
1B | ULE90130-01-UTL-00126 | 26 | 01 - Scotland Gas Networks | Conflict | Programmed | [6 empty] | 2007-05-16 | PART | 2007-06-01 | 2007-06-06 |  | 2007-06-20 |  |  | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-29 | 117 | Plate 26 affected by change in alignment. IFC date under threat.
1B | ULE90130-01-UTL-00226 | 26 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-05-16 | PART | 2007-06-01 | 2007-06-06 | 2007-05-01 | 2007-06-20 |  |  | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-29 | 117 | Plate 26 affected by change in alignment. IFC date under threat.
1B | ULE90130-01-UTL-00326 | 26 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-05-08 | 2007-02-06 | 2007-05-22 | 2007-05-14 | 2007-05-23 | 2007-05-17 |  |  | 2007-06-01 | 2007-06-06 |  | 2007-06-20 |  |  | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-29 | 117 | Plate 26 affected by change in alignment. IFC date under threat.
1B | ULE90130-01-UTL-00426 | 26 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-05-16 | PART | 2007-06-01 | 2007-06-06 |  | 2007-06-20 |  |  | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-29 | 117 | Plate 26 affected by change in alignment. IFC date under threat.
1B | ULE90130-01-UTL-00526 | 26 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-05-16 | 2007-06-07 | 2007-06-01 | 2007-06-06 |  | 2007-06-20 |  |  | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-29 | 117 | Plate 26 affected by change in alignment. IFC date under threat.
1B | ULE90130-01-UTL-00726 | 26 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-05-16 | PART | 2007-06-01 | 2007-06-06 |  | 2007-06-20 |  |  | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-29 | 117 | Plate 26 affected by change in alignment. IFC date under threat.
1B | ULE90130-01-UTL-00826 | 26 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-05-16 | PART | 2007-06-01 | 2007-06-06 |  | 2007-06-20 |  |  | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-29 | 117 | Plate 26 affected by change in alignment. IFC date under threat.
1B | ULE90130-01-UTL-00926 | 26 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-05-16 | PART | 2007-06-01 | 2007-06-06 |  | 2007-06-20 |  |  | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-29 | 117 | Plate 26 affected by change in alignment. IFC date under threat.
1B | ULE90130-01-UTL-00027 | 27 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-01 | 2007-06-06 |  | 2007-06-20 |  |  | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-29 | 117
1B | ULE90130-01-UTL-00127 | 27 | 01 - Scotland Gas Networks | Conflict | Programmed | 2007-05-08 | 2007-05-04 | 2007-05-22 | 2007-05-04 | 2007-05-23 | 2007-05-10 | 2007-05-16 | PART | 2007-06-01 | 2007-06-06 | 2007-06-09 | 2007-06-20 |  |  | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-29 | 117
1B | ULE90130-01-UTL-00227 | 27 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-05-16 | PART | 2007-06-01 | 2007-06-06 | 2007-05-01 | 2007-06-20 | 2007-03-29 | Written | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-29 | 117
1B | ULE90130-01-UTL-00327 | 27 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-05-08 | 2007-02-06 | 2007-05-22 | 2007-05-03 | 2007-05-23 | 2007-05-10 |  |  | 2007-06-01 | 2007-06-06 | 2007-06-16 | 2007-06-20 |  |  | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-29 | 117
1B | ULE90130-01-UTL-00427 | 27 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-05-16 | PART | 2007-06-01 | 2007-06-06 |  | 2007-06-20 |  |  | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-29 | 117
1B | ULE90130-01-UTL-00527 | 27 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-05-16 | 2007-06-07 | 2007-06-01 | 2007-06-06 | 2007-06-09 | 2007-06-20 |  |  | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-29 | 117
1B | ULE90130-01-UTL-00727 | 27 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-05-16 | PART | 2007-06-01 | 2007-06-06 | 2007-06-09 | 2007-06-20 |  |  | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-29 | 117
1B | ULE90130-01-UTL-00827 | 27 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-05-16 | PART | 2007-06-01 | 2007-06-06 | 2007-06-09 | 2007-06-20 | 2007-06-10 | Written | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-29 | 117
1B | ULE90130-01-UTL-00927 | 27 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-05-16 | PART | 2007-06-01 | 2007-06-06 | 2007-06-09 | 2007-06-20 |  |  | 2007-06-27 |  | 2007-07-01 |  | 2007-07-04 |  | 2007-10-29 | 117
1C2 | ULE90130-01-UTL-00042 | 42 | 00 - Composite |  | Programmed | [8 empty] | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00142 | 42 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-06-08 |  | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00242 | 42 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-06-08 |  | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00342 | 42 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-05-31 |  | 2007-06-14 |  | 2007-06-15 |  |  |  | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00442 | 42 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-06-08 |  | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00542 | 42 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-06-08 | 2007-06-07 | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00742 | 42 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-06-08 |  | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00842 | 42 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-06-08 |  | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00942 | 42 | 09 - Thus |  | Programmed | [6 empty] | 2007-06-08 |  | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00043 | 43 | 00 - Composite |  | Programmed | [8 empty] | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00143 | 43 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-06-08 |  | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00243 | 43 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-06-08 |  | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00343 | 43 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-05-31 |  | 2007-06-14 |  | 2007-06-15 |  |  |  | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00443 | 43 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-06-08 |  | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00543 | 43 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-06-08 | 2007-06-07 | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00743 | 43 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-06-08 |  | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00843 | 43 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-06-08 |  | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00943 | 43 | 09 - Thus |  | Programmed | [6 empty] | 2007-06-08 |  | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00044 | 44 | 00 - Composite |  | Programmed | [8 empty] | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00144 | 44 | 01 - Scotland Gas Networks | Conflict | Programmed | [6 empty] | 2007-06-08 |  | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00244 | 44 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-06-08 |  | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00344 | 44 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-05-31 |  | 2007-06-14 |  | 2007-06-15 |  |  |  | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00444 | 44 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-06-08 |  | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00544 | 44 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-06-08 | 2007-06-07 | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00744 | 44 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-06-08 |  | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00844 | 44 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-06-08 |  | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1C2 | ULE90130-01-UTL-00944 | 44 | 09 - Thus |  | Programmed | [6 empty] | 2007-06-08 |  | 2007-06-01 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  | 2007-07-24 |  | 2007-07-27 |  | 2007-10-29 | 94
1A2 | ULE90130-01-UTL-00018 | 18 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-05 | 66
1A2 | ULE90130-01-UTL-00118 | 18 | 01 - Scotland Gas Networks | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-05 | 66
1A2 | ULE90130-01-UTL-00218 | 18 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-05 | 66
1A2 | ULE90130-01-UTL-00318 | 18 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-07-05 | 2007-05-17 | 2007-07-19 |  | 2007-07-20 |  |  |  | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-05 | 66
1A2 | ULE90130-01-UTL-00418 | 18 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-05 | 66
1A2 | ULE90130-01-UTL-00518 | 18 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-05 | 66
1A2 | ULE90130-01-UTL-00718 | 18 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-05 | 66
1A2 | ULE90130-01-UTL-00818 | 18 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-05 | 66
1A2 | ULE90130-01-UTL-00918 | 18 | 09 - Thus | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-05 | 66
1A2 | ULE90130-01-UTL-00019 | 19 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-05 | 66
1A2 | ULE90130-01-UTL-00119 | 19 | 01 - Scotland Gas Networks | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-05 | 66
1A2 | ULE90130-01-UTL-00219 | 19 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-05 | 66
1A2 | ULE90130-01-UTL-00319 | 19 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-07-05 | 2007-05-17 | 2007-07-19 |  | 2007-07-20 |  |  |  | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-05 | 66
1A2 | ULE90130-01-UTL-00419 | 19 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-05 | 66
1A2 | ULE90130-01-UTL-00519 | 19 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-05 | 66
1A2 | ULE90130-01-UTL-00719 | 19 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-05 | 66
1A2 | ULE90130-01-UTL-00819 | 19 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-05 | 66
1A2 | ULE90130-01-UTL-00919 | 19 | 09 - Thus | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-05 | 66
1A2 | ULE90130-01-UTL-00021 | 21 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-05-18 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-11-05 | 94 | Excludes plate 20 as this is part of Constitution St
1A2 | ULE90130-01-UTL-00121 | 21 | 01 - Scotland Gas Networks | Conflict | Programmed | [6 empty] | 2007-06-15 | PART | 2007-05-18 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-11-05 | 94 | Excludes plate 20 as this is part of Constitution St
1A2 | ULE90130-01-UTL-00221 | 21 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-06-15 | PART | 2007-05-18 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-11-05 | 94 | Excludes plate 20 as this is part of Constitution St
1A2 | ULE90130-01-UTL-00321 | 21 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-06-07 | 2007-05-17 | 2007-06-21 |  | 2007-06-22 |  |  |  | 2007-05-18 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-11-05 | 94 | Excludes plate 20 as this is part of Constitution St
1A2 | ULE90130-01-UTL-00421 | 21 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-06-15 | PART | 2007-05-18 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-11-05 | 94 | Excludes plate 20 as this is part of Constitution St
1A2 | ULE90130-01-UTL-00521 | 21 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-06-15 | PART | 2007-05-18 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-11-05 | 94 | Excludes plate 20 as this is part of Constitution St
1A2 | ULE90130-01-UTL-00721 | 21 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-06-15 | PART | 2007-05-18 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-11-05 | 94 | Excludes plate 20 as this is part of Constitution St
1A2 | ULE90130-01-UTL-00821 | 21 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-06-15 | PART | 2007-05-18 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-11-05 | 94 | Excludes plate 20 as this is part of Constitution St
1A2 | ULE90130-01-UTL-00921 | 21 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-06-15 | PART | 2007-05-18 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-11-05 | 94 | Excludes plate 20 as this is part of Constitution St
1B | ULE90130-01-UTL-00022 | 22 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-05-18 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-11-05 | 94 | Excludes plate 20 as this is part of Constitution St
1B | ULE90130-01-UTL-00122 | 22 | 01 - Scotland Gas Networks | Conflict | Programmed | 2007-06-07 | 2007-05-14 | 2007-06-21 | 2007-05-14 | 2007-06-22 | 2007-05-22 | 2007-06-15 | PART | 2007-05-18 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-11-05 | 94 | Excludes plate 20 as this is part of Constitution St
1B | ULE90130-01-UTL-00222 | 22 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-06-15 | PART | 2007-05-18 | 2007-07-06 | 2007-05-01 | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-11-05 | 94 | Excludes plate 20 as this is part of Constitution St
1B | ULE90130-01-UTL-00322 | 22 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-06-07 | 2007-02-06 | 2007-06-21 | 2007-05-04 | 2007-06-22 | 2007-05-22 |  |  | 2007-05-18 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-11-05 | 94 | Excludes plate 20 as this is part of Constitution St
1B | ULE90130-01-UTL-00422 | 22 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-06-15 | PART | 2007-05-18 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-11-05 | 94 | Excludes plate 20 as this is part of Constitution St
1B | ULE90130-01-UTL-00522 | 22 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-06-15 | 2007-06-07 | 2007-05-18 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-11-05 | 94 | Excludes plate 20 as this is part of Constitution St
1B | ULE90130-01-UTL-00722 | 22 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-06-15 | PART | 2007-05-18 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-11-05 | 94 | Excludes plate 20 as this is part of Constitution St
1B | ULE90130-01-UTL-00822 | 22 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-06-15 | PART | 2007-05-18 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-11-05 | 94 | Excludes plate 20 as this is part of Constitution St
1B | ULE90130-01-UTL-00922 | 22 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-06-15 | PART | 2007-05-18 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2007-11-05 | 94 | Excludes plate 20 as this is part of Constitution St
1A2 | ULE90130-01-UTL-00020 | 20 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-12 | 73
1A2 | ULE90130-01-UTL-00120 | 20 | 01 - Scotland Gas Networks | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-12 | 73
1A2 | ULE90130-01-UTL-00220 | 20 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-12 | 73
1A2 | ULE90130-01-UTL-00320 | 20 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-07-05 | 2007-05-17 | 2007-07-19 |  | 2007-07-20 |  |  |  | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-12 | 73
1A2 | ULE90130-01-UTL-00420 | 20 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-12 | 73
1A2 | ULE90130-01-UTL-00520 | 20 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-12 | 73
1A2 | ULE90130-01-UTL-00720 | 20 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-12 | 73
1A2 | ULE90130-01-UTL-00820 | 20 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-12 | 73
1A2 | ULE90130-01-UTL-00920 | 20 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-06-01 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2007-11-12 | 73
2A | ULE90130-02-UTL-00001 | 01 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-18 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2007-11-26 | 80
2A | ULE90130-02-UTL-00101 | 01 | 01 - Scotland Gas Networks | Conflict | Programmed | 2007-07-12 | 2007-04-13 |  |  |  |  | 2007-07-20 |  | 2007-06-18 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2007-11-26 | 80
2A | ULE90130-02-UTL-00201 | 01 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-07-20 |  | 2007-06-18 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2007-11-26 | 80
2A | ULE90130-02-UTL-00301 | 01 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-07-12 | 2007-04-13 | [6 empty] | 2007-06-18 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2007-11-26 | 80
2A | ULE90130-02-UTL-00401 | 01 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-07-20 |  | 2007-06-18 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2007-11-26 | 80
2A | ULE90130-02-UTL-00501 | 01 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-07-20 |  | 2007-06-18 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2007-11-26 | 80
2A | ULE90130-02-UTL-00701 | 01 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-07-20 |  | 2007-06-18 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2007-11-26 | 80
2A | ULE90130-02-UTL-00801 | 01 | 08 - Cable & Wireless | Conflict | Programmed | [6 empty] | 2007-07-20 |  | 2007-06-18 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2007-11-26 | 80
2A | ULE90130-02-UTL-00901 | 01 | 09 - Thus | Conflict | Programmed | [6 empty] | 2007-07-20 |  | 2007-06-18 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2007-11-26 | 80
5B | ULE90130-05-UTL-00019 | 19 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-03 | 115
5B | ULE90130-05-UTL-00119 | 19 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-03 | 115
5B | ULE90130-05-UTL-00219 | 19 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 | 2007-04-20 | Written | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-03 | 115
5B | ULE90130-05-UTL-00319 | 19 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-06-14 | 2007-03-29 | [6 empty] | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-03 | 115
5B | ULE90130-05-UTL-00419 | 19 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-03 | 115
5B | ULE90130-05-UTL-00519 | 19 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-03 | 115
5B | ULE90130-05-UTL-00719 | 19 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 | 2007-05-28 | 2007-07-27 | 2007-06-07 | Verbal | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-03 | 115
5B | ULE90130-05-UTL-00819 | 19 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-03 | 115
5B | ULE90130-05-UTL-00919 | 19 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-03 | 115
5B | ULE90130-05-UTL-00020 | 20 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-03 | 115
5B | ULE90130-05-UTL-00120 | 20 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-03 | 115
5B | ULE90130-05-UTL-00220 | 20 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 | 2007-04-20 | Written | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-03 | 115
5B | ULE90130-05-UTL-00320 | 20 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-06-14 | 2007-03-29 | [6 empty] | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-03 | 115
5B | ULE90130-05-UTL-00420 | 20 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-03 | 115
5B | ULE90130-05-UTL-00520 | 20 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-03 | 115
5B | ULE90130-05-UTL-00720 | 20 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-03 | 115
5B | ULE90130-05-UTL-00820 | 20 | 08 - Cable & Wireless | Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-03 | 115
5B | ULE90130-05-UTL-00920 | 20 | 09 - Thus | Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-03 | 115
5C | ULE90130-05-UTL-00021 | 21 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00121 | 21 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00221 | 21 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00321 | 21 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-06-14 | 2007-05-01 | [6 empty] | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00421 | 21 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00521 | 21 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00721 | 21 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00821 | 21 | 08 - Cable & Wireless | Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00921 | 21 | 09 - Thus | Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00022 | 22 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00122 | 22 | 01 - Scotland Gas Networks | Conflict | Programmed | 2007-06-14 | 2007-05-21 | 2007-06-28 | 2007-05-21 | 2007-06-29 | 2007-05-23 | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00222 | 22 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00322 | 22 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-06-14 | 2007-05-01 | 2007-06-28 | 2007-05-21 | 2007-06-29 | 2007-05-23 |  |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00422 | 22 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00522 | 22 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00722 | 22 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00822 | 22 | 08 - Cable & Wireless | Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00922 | 22 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00023 | 23 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00123 | 23 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00223 | 23 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00323 | 23 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-06-14 | 2007-05-01 | 2007-06-28 | 2007-05-21 | 2007-06-29 | 2007-05-23 |  |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00423 | 23 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00523 | 23 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00723 | 23 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00823 | 23 | 08 - Cable & Wireless | Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-00923 | 23 | 09 - Thus | Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
5C | ULE90130-05-UTL-01023 | 23 | 10 - Easynet | Conflict | Programmed | [6 empty] | 2007-06-22 |  | 2007-06-22 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  | 2007-08-07 |  | 2007-08-10 |  | 2007-12-10 | 122
1D | ULE90130-01-UTL-00050 | 50 | 00 - Composite |  | Programmed | [8 empty] | 2007-06-22 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-01-04 | 112
1D | ULE90130-01-UTL-00150 | 50 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-07-27 |  | 2007-06-22 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-01-04 | 112
1D | ULE90130-01-UTL-00250 | 50 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-07-27 |  | 2007-06-22 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-01-04 | 112
1D | ULE90130-01-UTL-00350 | 50 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-07-19 |  | 2007-08-02 |  | 2007-08-03 |  |  |  | 2007-06-22 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-01-04 | 112
1D | ULE90130-01-UTL-00450 | 50 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-07-27 |  | 2007-06-22 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-01-04 | 112
1D | ULE90130-01-UTL-00550 | 50 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-07-27 |  | 2007-06-22 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-01-04 | 112
1D | ULE90130-01-UTL-00750 | 50 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-07-27 |  | 2007-06-22 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-01-04 | 112
1D | ULE90130-01-UTL-00850 | 50 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-07-27 |  | 2007-06-22 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-01-04 | 112
1D | ULE90130-01-UTL-00950 | 50 | 09 - Thus |  | Programmed | [6 empty] | 2007-07-27 |  | 2007-06-22 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-01-04 | 112
5B | ULE90130-05-UTL-00015 | 15 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-22 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-01-07 | 157
5B | ULE90130-05-UTL-00115 | 15 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-22 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-01-07 | 157
5B | ULE90130-05-UTL-00215 | 15 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-22 | 2007-07-06 |  | 2007-07-20 | 2007-04-20 | Written | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-01-07 | 157
5B | ULE90130-05-UTL-00315 | 15 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-06-07 | 2007-03-29 | 2007-06-21 | 2007-06-06 | 2007-06-22 | 2007-06-07 |  |  | 2007-06-22 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-01-07 | 157
5B | ULE90130-05-UTL-00415 | 15 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-22 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-01-07 | 157
5B | ULE90130-05-UTL-00515 | 15 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-22 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-01-07 | 157
5B | ULE90130-05-UTL-00715 | 15 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-22 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-01-07 | 157
5B | ULE90130-05-UTL-00815 | 15 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-22 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-01-07 | 157
5B | ULE90130-05-UTL-00915 | 15 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-22 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-01-07 | 157
1C2 | ULE90130-01-UTL-00045 | 45 | 00 - Composite |  | Programmed | [8 empty] | 2007-06-22 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-01-07 | 143
1C2 | ULE90130-01-UTL-00145 | 45 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-22 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-01-07 | 143
1C2 | ULE90130-01-UTL-00245 | 45 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-22 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-01-07 | 143
1C2 | ULE90130-01-UTL-00345 | 45 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-06-21 |  | 2007-07-05 |  | 2007-07-06 |  |  |  | 2007-06-22 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-01-07 | 143
1C2 | ULE90130-01-UTL-00445 | 45 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-22 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-01-07 | 143
1C2 | ULE90130-01-UTL-00545 | 45 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-06-29 | 2007-06-07 | 2007-06-22 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-01-07 | 143
1C2 | ULE90130-01-UTL-00745 | 45 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-22 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-01-07 | 143
1C2 | ULE90130-01-UTL-00845 | 45 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-22 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-01-07 | 143
1C2 | ULE90130-01-UTL-00945 | 45 | 09 - Thus |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-22 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-01-07 | 143
1C2 | ULE90130-01-UTL-00046 | 46 | 00 - Composite |  | Programmed | [8 empty] | 2007-06-22 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-01-07 | 143
1C2 | ULE90130-01-UTL-00146 | 46 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-22 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-01-07 | 143
1C2 | ULE90130-01-UTL-00246 | 46 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-22 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-01-07 | 143
1C2 | ULE90130-01-UTL-00346 | 46 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-06-21 |  | 2007-07-05 |  | 2007-07-06 |  |  |  | 2007-06-22 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-01-07 | 143
1C2 | ULE90130-01-UTL-00446 | 46 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-22 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-01-07 | 143
1C2 | ULE90130-01-UTL-00546 | 46 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-06-29 | 2007-06-07 | 2007-06-22 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-01-07 | 143
1C2 | ULE90130-01-UTL-00746 | 46 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-22 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-01-07 | 143
1C2 | ULE90130-01-UTL-00846 | 46 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-22 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-01-07 | 143
1C2 | ULE90130-01-UTL-00946 | 46 | 09 - Thus |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-22 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-01-07 | 143
7B | ULE90130-07-UTL-00009 | 09 | 00 - Composite | Conflict | Re-Programme | [20 empty] | 2008-01-14 | 39461 | To be programmed AMIS/JE - EARL Interface
7B | ULE90130-07-UTL-00109 | 09 | 01 - Scotland Gas Networks | No Conflict | Re-Programme | [20 empty] | 2008-01-14 | 39461 | To be programmed AMIS/JE - EARL Interface
7B | ULE90130-07-UTL-00209 | 09 | 02 - Scottish Power | No Conflict | Re-Programme | [20 empty] | 2008-01-14 | 39461 | To be programmed AMIS/JE - EARL Interface
7B | ULE90130-07-UTL-00309 | 09 | 03 - Scottish Water - Clean | No Conflict | Re-Programme | 2007-05-15 | 2007-05-15 | [18 empty] | 2008-01-14 | 39461 | To be programmed AMIS/JE - EARL Interface
7B | ULE90130-07-UTL-00409 | 09 | 04 - Scottish Water - Foul | No Conflict | Re-Programme | [20 empty] | 2008-01-14 | 39461 | To be programmed AMIS/JE - EARL Interface
7B | ULE90130-07-UTL-00509 | 09 | 05 - BT Openreach | Conflict | Re-Programme | [20 empty] | 2008-01-14 | 39461 | To be programmed AMIS/JE - EARL Interface
7B | ULE90130-07-UTL-00709 | 09 | 07 - Virgin Media | No Conflict | Re-Programme | [20 empty] | 2008-01-14 | 39461 | To be programmed AMIS/JE - EARL Interface
7B | ULE90130-07-UTL-00809 | 09 | 08 - Cable & Wireless | No Conflict | Re-Programme | [20 empty] | 2008-01-14 | 39461 | To be programmed AMIS/JE - EARL Interface
7B | ULE90130-07-UTL-00909 | 09 | 09 - Thus | No Conflict | Re-Programme | [20 empty] | 2008-01-14 | 39461 | To be programmed AMIS/JE - EARL Interface
1B | ULE90130-01-UTL-00025 | 25 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-29 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-01-28 | 178
1B | ULE90130-01-UTL-00125 | 25 | 01 - Scotland Gas Networks | Conflict | Programmed | 2007-06-07 | 2007-05-14 | 2007-06-21 | 2007-05-14 | 2007-06-22 | 2007-05-22 | 2007-06-15 |  | 2007-06-29 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-01-28 | 178
1B | ULE90130-01-UTL-00225 | 25 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-29 | 2007-07-06 | 2007-05-01 | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-01-28 | 178
1B | ULE90130-01-UTL-00325 | 25 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-06-07 | 2007-02-06 | 2007-06-21 | 2007-05-21 | 2007-06-22 | 2007-05-23 |  |  | 2007-06-29 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-01-28 | 178
1B | ULE90130-01-UTL-00425 | 25 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-29 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-01-28 | 178
1B | ULE90130-01-UTL-00525 | 25 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-06-15 | 2007-06-07 | 2007-06-29 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-01-28 | 178
1B | ULE90130-01-UTL-00725 | 25 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-29 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-01-28 | 178
1B | ULE90130-01-UTL-00825 | 25 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-29 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-01-28 | 178
1B | ULE90130-01-UTL-00925 | 25 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-29 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-01-28 | 178
1A1 | ULE90130-01-UTL-00006 | 06 | 00 - Composite | Conflict | Re-Programme | [8 empty] | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00106 | 06 | 01 - Scotland Gas Networks | Conflict | Re-Programme | 2007-04-02 | 2007-04-02 | 2007-06-05 | 2007-04-02 | 2007-06-06 | 2007-04-02 |  |  | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00206 | 06 | 02 - Scottish Power | Conflict | Re-Programme | [8 empty] | 2007-06-29 | 2007-06-15 | 2007-05-01 | 2007-06-29 | 2007-02-06 | Written | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00306 | 06 | 03 - Scottish Water - Clean | Conflict | Re-Programme | 2007-01-12 | 2007-01-12 | 2007-06-05 |  | 2007-06-06 | 2007-04-02 |  |  | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00406 | 06 | 04 - Scottish Water - Foul | Conflict | Re-Programme | [8 empty] | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00506 | 06 | 05 - BT Openreach | Conflict | Re-Programme | [7 empty] | 2007-06-07 | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00706 | 06 | 07 - Virgin Media | No Conflict | Re-Programme | [8 empty] | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00806 | 06 | 08 - Cable & Wireless | No Conflict | Re-Programme | [8 empty] | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00906 | 06 | 09 - Thus | No Conflict | Re-Programme | [8 empty] | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-01706 | 06 | 17 - Forth Ports | Conflict | Re-Programme | [8 empty] | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00007 | 07 | 00 - Composite | Conflict | Re-Programme | [8 empty] | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00107 | 07 | 01 - Scotland Gas Networks | Conflict | Re-Programme | 2007-04-02 | 2007-04-02 | 2007-06-05 | 2007-04-02 | 2007-06-06 | 2007-04-02 |  |  | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00207 | 07 | 02 - Scottish Power | No Conflict | Re-Programme | [8 empty] | 2007-06-29 | 2007-06-15 | 2007-05-01 | 2007-06-29 | 2007-02-06 | Written | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00307 | 07 | 03 - Scottish Water - Clean | Conflict | Re-Programme | 2007-01-12 | 2007-01-12 | 2007-06-05 |  | 2007-06-06 | 2007-04-02 |  |  | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00407 | 07 | 04 - Scottish Water - Foul | No Conflict | Re-Programme | [8 empty] | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00507 | 07 | 05 - BT Openreach | Conflict | Re-Programme | [7 empty] | 2007-06-07 | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00707 | 07 | 07 - Virgin Media | No Conflict | Re-Programme | [8 empty] | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00807 | 07 | 08 - Cable & Wireless | No Conflict | Re-Programme | [8 empty] | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00907 | 07 | 09 - Thus | No Conflict | Re-Programme | [8 empty] | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-01707 | 07 | 17 - Forth Ports | Conflict | Re-Programme | [8 empty] | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00008 | 08 | 00 - Composite | Conflict | Re-Programme | [8 empty] | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00108 | 08 | 01 - Scotland Gas Networks | Conflict | Re-Programme | 2007-04-02 | 2007-04-02 | 2007-06-05 | 2007-04-02 | 2007-06-06 | 2007-04-02 |  |  | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00208 | 08 | 02 - Scottish Power | Conflict | Re-Programme | [8 empty] | 2007-06-29 | 2007-06-15 | 2007-05-01 | 2007-06-29 | 2007-02-06 | Written | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00308 | 08 | 03 - Scottish Water - Clean | Conflict | Re-Programme | 2007-01-12 | 2007-01-12 | 2007-06-05 |  | 2007-06-06 | 2007-04-02 |  |  | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00408 | 08 | 04 - Scottish Water - Foul | No Conflict | Re-Programme | [8 empty] | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00508 | 08 | 05 - BT Openreach | Conflict | Re-Programme | [7 empty] | 2007-06-07 | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00708 | 08 | 07 - Virgin Media | No Conflict | Re-Programme | [8 empty] | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00808 | 08 | 08 - Cable & Wireless | No Conflict | Re-Programme | [8 empty] | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00908 | 08 | 09 - Thus | No Conflict | Re-Programme | [8 empty] | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-01708 | 08 | 17 - Forth Ports | No Conflict | Re-Programme | [8 empty] | 2007-06-29 | 2007-06-15 |  | 2007-06-29 |  |  | 2007-07-06 |  |  |  | 2007-07-13 |  | 2008-02-04 | 206 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A2 | ULE90130-01-UTL-00017 | 17 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2008-02-04 | 157
1A2 | ULE90130-01-UTL-00117 | 17 | 01 - Scotland Gas Networks | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-07-27 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2008-02-04 | 157
1A2 | ULE90130-01-UTL-00217 | 17 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-07-27 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2008-02-04 | 157
1A2 | ULE90130-01-UTL-00317 | 17 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-07-05 | 2007-05-17 | 2007-07-19 |  | 2007-07-20 |  |  |  | 2007-07-27 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2008-02-04 | 157
1A2 | ULE90130-01-UTL-00417 | 17 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-07-27 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2008-02-04 | 157
1A2 | ULE90130-01-UTL-00517 | 17 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-07-27 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2008-02-04 | 157
1A2 | ULE90130-01-UTL-00717 | 17 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-07-27 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2008-02-04 | 157
1A2 | ULE90130-01-UTL-00817 | 17 | 08 - Cable & Wireless | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-07-27 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2008-02-04 | 157
1A2 | ULE90130-01-UTL-00917 | 17 | 09 - Thus | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-07-27 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2008-02-04 | 157
1D | ULE90130-01-UTL-00047 | 47 | 00 - Composite |  | Programmed | [8 empty] | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-02-04 | 171
1D | ULE90130-01-UTL-00147 | 47 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-02-04 | 171
1D | ULE90130-01-UTL-00247 | 47 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-02-04 | 171
1D | ULE90130-01-UTL-00347 | 47 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-06-21 |  | 2007-07-05 |  | 2007-07-06 |  |  |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-02-04 | 171
1D | ULE90130-01-UTL-00447 | 47 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-02-04 | 171
1D | ULE90130-01-UTL-00547 | 47 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-02-04 | 171
1D | ULE90130-01-UTL-00747 | 47 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-02-04 | 171
1D | ULE90130-01-UTL-00847 | 47 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-02-04 | 171
1D | ULE90130-01-UTL-00947 | 47 | 09 - Thus |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-02-04 | 171
1D | ULE90130-01-UTL-00048 | 48 | 00 - Composite |  | Programmed | [8 empty] | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-02-11 | 178
1D | ULE90130-01-UTL-00148 | 48 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-02-11 | 178
1D | ULE90130-01-UTL-00248 | 48 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-02-11 | 178
1D | ULE90130-01-UTL-00348 | 48 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-06-21 |  | 2007-07-05 |  | 2007-07-06 |  |  |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-02-11 | 178
1D | ULE90130-01-UTL-00448 | 48 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-02-11 | 178
1D | ULE90130-01-UTL-00548 | 48 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-02-11 | 178
1D | ULE90130-01-UTL-00748 | 48 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-02-11 | 178
1D | ULE90130-01-UTL-00848 | 48 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-02-11 | 178
1D | ULE90130-01-UTL-00948 | 48 | 09 - Thus |  | Programmed | [6 empty] | 2007-06-29 |  | 2007-06-29 | 2007-07-20 |  | 2007-08-03 |  |  | 2007-08-10 |  | 2007-08-14 |  | 2007-08-17 |  | 2008-02-11 | 178
1D | ULE90130-01-UTL-00049 | 49 | 00 - Composite |  | Programmed | [8 empty] | 2007-06-29 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-02-18 | 157
1D | ULE90130-01-UTL-00149 | 49 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-07-27 |  | 2007-06-29 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-02-18 | 157
1D | ULE90130-01-UTL-00249 | 49 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-07-27 |  | 2007-06-29 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-02-18 | 157
1D | ULE90130-01-UTL-00349 | 49 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-07-19 |  | 2007-08-02 |  | 2007-08-03 |  |  |  | 2007-06-29 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-02-18 | 157
1D | ULE90130-01-UTL-00449 | 49 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-07-27 |  | 2007-06-29 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-02-18 | 157
1D | ULE90130-01-UTL-00549 | 49 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-07-27 |  | 2007-06-29 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-02-18 | 157
1D | ULE90130-01-UTL-00749 | 49 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-07-27 |  | 2007-06-29 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-02-18 | 157
1D | ULE90130-01-UTL-00849 | 49 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-07-27 |  | 2007-06-29 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-02-18 | 157
1D | ULE90130-01-UTL-00949 | 49 | 09 - Thus |  | Programmed | [6 empty] | 2007-07-27 |  | 2007-06-29 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-02-18 | 157
2A | ULE90130-02-UTL-00002 | 02 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-07-02 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2008-03-03 | 178
2A | ULE90130-02-UTL-00102 | 02 | 01 - Scotland Gas Networks | No Conflict | Programmed | 2007-07-12 | 2007-04-13 |  |  |  |  | 2007-07-20 |  | 2007-07-02 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2008-03-03 | 178
2A | ULE90130-02-UTL-00202 | 02 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-07-20 |  | 2007-07-02 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2008-03-03 | 178
2A | ULE90130-02-UTL-00302 | 02 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-07-12 | 2007-04-13 | [6 empty] | 2007-07-02 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2008-03-03 | 178
2A | ULE90130-02-UTL-00402 | 02 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-07-20 |  | 2007-07-02 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2008-03-03 | 178
2A | ULE90130-02-UTL-00502 | 02 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-07-20 |  | 2007-07-02 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2008-03-03 | 178
2A | ULE90130-02-UTL-00702 | 02 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-07-20 |  | 2007-07-02 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2008-03-03 | 178
2A | ULE90130-02-UTL-00802 | 02 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-07-20 |  | 2007-07-02 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2008-03-03 | 178
2A | ULE90130-02-UTL-00902 | 02 | 09 - Thus | Conflict | Programmed | [6 empty] | 2007-07-20 |  | 2007-07-02 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2008-03-03 | 178
2A | ULE90130-02-UTL-00003 | 03 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-07-02 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2008-03-03 | 178
2A | ULE90130-02-UTL-00103 | 03 | 01 - Scotland Gas Networks | No Conflict | Programmed | 2007-07-12 | 2007-04-13 |  |  |  |  | 2007-07-20 |  | 2007-07-02 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2008-03-03 | 178
2A | ULE90130-02-UTL-00203 | 03 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-07-20 |  | 2007-07-02 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2008-03-03 | 178
2A | ULE90130-02-UTL-00303 | 03 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-07-12 | 2007-04-13 | [6 empty] | 2007-07-02 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2008-03-03 | 178
2A | ULE90130-02-UTL-00403 | 03 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-07-20 |  | 2007-07-02 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2008-03-03 | 178
2A | ULE90130-02-UTL-00503 | 03 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-07-20 |  | 2007-07-02 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2008-03-03 | 178
2A | ULE90130-02-UTL-00703 | 03 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-07-20 |  | 2007-07-02 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2008-03-03 | 178
2A | ULE90130-02-UTL-00803 | 03 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-07-20 |  | 2007-07-02 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2008-03-03 | 178
2A | ULE90130-02-UTL-00903 | 03 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-07-20 |  | 2007-07-02 | 2007-08-10 |  | 2007-08-24 |  |  | 2007-08-31 |  | 2007-09-04 |  | 2007-09-07 |  | 2008-03-03 | 178
1B | ULE90130-01-UTL-00024 | 24 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-06-29 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-03-03 | 213
1B | ULE90130-01-UTL-00124 | 24 | 01 - Scotland Gas Networks | Conflict | Programmed | 2007-06-07 | 2007-05-14 | 2007-06-21 | 2007-05-14 | 2007-06-22 | 2007-05-22 | 2007-06-15 |  | 2007-06-29 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-03-03 | 213
1B | ULE90130-01-UTL-00224 | 24 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-29 | 2007-07-06 | 2007-05-01 | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-03-03 | 213
1B | ULE90130-01-UTL-00324 | 24 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-06-07 | 2007-02-06 | 2007-06-21 | 2007-05-14 | 2007-06-22 | 2007-05-17 |  |  | 2007-06-29 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-03-03 | 213
1B | ULE90130-01-UTL-00424 | 24 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-29 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-03-03 | 213
1B | ULE90130-01-UTL-00524 | 24 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-06-15 | 2007-06-07 | 2007-06-29 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-03-03 | 213
1B | ULE90130-01-UTL-00724 | 24 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-29 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-03-03 | 213
1B | ULE90130-01-UTL-00824 | 24 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-29 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-03-03 | 213
1B | ULE90130-01-UTL-00924 | 24 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-06-29 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-03-03 | 213
7A | ULE90130-07-UTL-00001 | 01 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00101 | 01 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00201 | 01 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00301 | 01 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-07-26 | 2007-05-15 | 2007-08-09 | 2007-06-14 | 2007-08-10 |  |  |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00401 | 01 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00501 | 01 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 | 2007-06-08 | Written | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00701 | 01 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 | 2007-04-19 | Written | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00801 | 01 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00901 | 01 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00002 | 02 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00102 | 02 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00202 | 02 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00302 | 02 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-07-26 | 2007-05-15 | [6 empty] | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00402 | 02 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00502 | 02 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 | 2007-06-08 | Written | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00702 | 02 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 | 2007-04-19 | Written | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00802 | 02 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00902 | 02 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00003 | 03 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00103 | 03 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00203 | 03 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00303 | 03 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-07-26 | 2007-05-15 | [6 empty] | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00403 | 03 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00503 | 03 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 | 2007-06-08 | Written | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00703 | 03 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 | 2007-04-19 | Written | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00803 | 03 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
7A | ULE90130-07-UTL-00903 | 03 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-10 | 171
1D | ULE90130-01-UTL-00051 | 51 | 00 - Composite |  | Programmed | [8 empty] | 2007-07-06 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-03-10 | 178
1D | ULE90130-01-UTL-00151 | 51 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-07-27 |  | 2007-07-06 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-03-10 | 178
1D | ULE90130-01-UTL-00251 | 51 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-07-27 |  | 2007-07-06 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-03-10 | 178
1D | ULE90130-01-UTL-00351 | 51 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-07-19 |  | 2007-08-02 |  | 2007-08-03 |  |  |  | 2007-07-06 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-03-10 | 178
1D | ULE90130-01-UTL-00451 | 51 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-07-27 |  | 2007-07-06 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-03-10 | 178
1D | ULE90130-01-UTL-00551 | 51 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-07-27 |  | 2007-07-06 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-03-10 | 178
1D | ULE90130-01-UTL-00751 | 51 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-07-27 |  | 2007-07-06 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-03-10 | 178
1D | ULE90130-01-UTL-00851 | 51 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-07-27 |  | 2007-07-06 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-03-10 | 178
1D | ULE90130-01-UTL-00951 | 51 | 09 - Thus |  | Programmed | [6 empty] | 2007-07-27 |  | 2007-07-06 | 2007-08-17 |  | 2007-08-31 |  |  | 2007-09-07 |  | 2007-09-11 |  | 2007-09-14 |  | 2008-03-10 | 178
7A | ULE90130-07-UTL-00005 | 05 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-24 | 185
7A | ULE90130-07-UTL-00105 | 05 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-24 | 185
7A | ULE90130-07-UTL-00205 | 05 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-24 | 185
7A | ULE90130-07-UTL-00305 | 05 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-07-26 | 2007-05-15 | [6 empty] | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-24 | 185
7A | ULE90130-07-UTL-00405 | 05 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-24 | 185
7A | ULE90130-07-UTL-00505 | 05 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 | 2007-06-08 | Written | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-24 | 185
7A | ULE90130-07-UTL-00705 | 05 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 | 2007-04-19 | Written | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-24 | 185
7A | ULE90130-07-UTL-00805 | 05 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-24 | 185
7A | ULE90130-07-UTL-00905 | 05 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-24 | 185
7A | ULE90130-07-UTL-00006 | 06 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-24 | 185
7A | ULE90130-07-UTL-00106 | 06 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-24 | 185
7A | ULE90130-07-UTL-00206 | 06 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-24 | 185
7A | ULE90130-07-UTL-00306 | 06 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-07-26 | 2007-05-15 | 2007-08-09 | 2007-06-14 | 2007-08-10 |  |  |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-24 | 185
7A | ULE90130-07-UTL-00406 | 06 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-24 | 185
7A | ULE90130-07-UTL-00506 | 06 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 | 2007-06-08 | Written | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-24 | 185
7A | ULE90130-07-UTL-00706 | 06 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 | 2007-04-19 | Written | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-24 | 185
7A | ULE90130-07-UTL-00806 | 06 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-24 | 185
7A | ULE90130-07-UTL-00906 | 06 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-24 | 185
1A2 | ULE90130-01-UTL-00016 | 16 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-08-10 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2008-03-24 | 206
1A2 | ULE90130-01-UTL-00116 | 16 | 01 - Scotland Gas Networks | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-08-10 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2008-03-24 | 206
1A2 | ULE90130-01-UTL-00216 | 16 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-08-10 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2008-03-24 | 206
1A2 | ULE90130-01-UTL-00316 | 16 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-07-05 | 2007-05-17 | 2007-07-19 |  | 2007-07-20 |  |  |  | 2007-08-10 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2008-03-24 | 206
1A2 | ULE90130-01-UTL-00416 | 16 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-08-10 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2008-03-24 | 206
1A2 | ULE90130-01-UTL-00516 | 16 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-08-10 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2008-03-24 | 206
1A2 | ULE90130-01-UTL-00716 | 16 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-08-10 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2008-03-24 | 206
1A2 | ULE90130-01-UTL-00816 | 16 | 08 - Cable & Wireless | Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-08-10 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2008-03-24 | 206
1A2 | ULE90130-01-UTL-00916 | 16 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-07-13 |  | 2007-08-10 | 2007-08-03 |  | 2007-08-17 |  |  | 2007-08-24 |  | 2007-08-28 |  | 2007-08-31 |  | 2008-03-24 | 206
7A | ULE90130-07-UTL-00004 | 04 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-31 | 192
7A | ULE90130-07-UTL-00104 | 04 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-31 | 192
7A | ULE90130-07-UTL-00204 | 04 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-31 | 192
7A | ULE90130-07-UTL-00304 | 04 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-07-26 | 2007-05-15 | [6 empty] | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-31 | 192
7A | ULE90130-07-UTL-00404 | 04 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-31 | 192
7A | ULE90130-07-UTL-00504 | 04 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 | 2007-06-08 | Written | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-31 | 192
7A | ULE90130-07-UTL-00704 | 04 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 | 2007-04-19 | Written | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-31 | 192
7A | ULE90130-07-UTL-00804 | 04 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-31 | 192
7A | ULE90130-07-UTL-00904 | 04 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-08-03 |  | 2007-07-06 | 2007-08-24 |  | 2007-09-07 |  |  | 2007-09-14 |  | 2007-09-18 |  | 2007-09-21 |  | 2008-03-31 | 192
1A1 | ULE90130-01-UTL-00003 | 03 | 00 - Composite | Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  |  |  | 2007-08-10 |  | 2008-04-07 | 241 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00103 | 03 | 01 - Scotland Gas Networks | Conflict | Re-Programme | 2007-04-02 | 2007-04-02 | 2007-07-03 | 2007-04-02 | 2007-07-04 | 2007-04-02 |  |  | 2007-07-13 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  |  |  | 2007-08-10 |  | 2008-04-07 | 241 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00203 | 03 | 02 - Scottish Power | Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-07-13 | 2007-05-01 | 2007-07-27 | 2007-02-06 | Written | 2007-08-03 |  |  |  | 2007-08-10 |  | 2008-04-07 | 241 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00303 | 03 | 03 - Scottish Water - Clean | Conflict | Re-Programme | 2007-01-12 | 2007-01-12 | 2007-07-03 |  | 2007-07-04 | 2007-04-02 |  |  | 2007-07-13 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  |  |  | 2007-08-10 |  | 2008-04-07 | 241 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00403 | 03 | 04 - Scottish Water - Foul | Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  |  |  | 2007-08-10 |  | 2008-04-07 | 241 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00503 | 03 | 05 - BT Openreach | Conflict | Re-Programme | [7 empty] | 2007-06-07 | 2007-07-13 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  |  |  | 2007-08-10 |  | 2008-04-07 | 241 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00703 | 03 | 07 - Virgin Media | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  |  |  | 2007-08-10 |  | 2008-04-07 | 241 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00803 | 03 | 08 - Cable & Wireless | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  |  |  | 2007-08-10 |  | 2008-04-07 | 241 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00903 | 03 | 09 - Thus | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  |  |  | 2007-08-10 |  | 2008-04-07 | 241 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-01703 | 03 | 17 - Forth Ports | Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-07-13 |  | 2007-07-27 |  |  | 2007-08-03 |  |  |  | 2007-08-10 |  | 2008-04-07 | 241 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00004 | 04 | 00 - Composite | Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  |  |  | 2007-07-27 |  | 2008-04-07 | 255 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00104 | 04 | 01 - Scotland Gas Networks | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  |  |  | 2007-07-27 |  | 2008-04-07 | 255 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00204 | 04 | 02 - Scottish Power | Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-06-29 | 2007-05-01 | 2007-07-13 | 2007-02-06 | Written | 2007-07-20 |  |  |  | 2007-07-27 |  | 2008-04-07 | 255 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00304 | 04 | 03 - Scottish Water - Clean | Conflict | Re-Programme | 2007-01-12 | 2007-01-12 | 2007-06-19 |  | 2007-06-20 |  |  |  | 2007-07-13 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  |  |  | 2007-07-27 |  | 2008-04-07 | 255 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00404 | 04 | 04 - Scottish Water - Foul | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  |  |  | 2007-07-27 |  | 2008-04-07 | 255 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00504 | 04 | 05 - BT Openreach | Conflict | Re-Programme | [7 empty] | 2007-06-07 | 2007-07-13 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  |  |  | 2007-07-27 |  | 2008-04-07 | 255 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00704 | 04 | 07 - Virgin Media | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  |  |  | 2007-07-27 |  | 2008-04-07 | 255 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00804 | 04 | 08 - Cable & Wireless | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  |  |  | 2007-07-27 |  | 2008-04-07 | 255 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00904 | 04 | 09 - Thus | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  |  |  | 2007-07-27 |  | 2008-04-07 | 255 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-01704 | 04 | 17 - Forth Ports | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  |  |  | 2007-07-27 |  | 2008-04-07 | 255 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00005 | 05 | 00 - Composite | Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  |  |  | 2007-07-27 |  | 2008-04-07 | 255 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00105 | 05 | 01 - Scotland Gas Networks | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  |  |  | 2007-07-27 |  | 2008-04-07 | 255 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00205 | 05 | 02 - Scottish Power | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-06-29 | 2007-05-01 | 2007-07-13 | 2007-02-06 | Written | 2007-07-20 |  |  |  | 2007-07-27 |  | 2008-04-07 | 255 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00305 | 05 | 03 - Scottish Water - Clean | No Conflict | Re-Programme | 2007-01-12 | 2007-01-12 | [6 empty] | 2007-07-13 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  |  |  | 2007-07-27 |  | 2008-04-07 | 255 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00405 | 05 | 04 - Scottish Water - Foul | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  |  |  | 2007-07-27 |  | 2008-04-07 | 255 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00505 | 05 | 05 - BT Openreach | Conflict | Re-Programme | [7 empty] | 2007-06-07 | 2007-07-13 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  |  |  | 2007-07-27 |  | 2008-04-07 | 255 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00705 | 05 | 07 - Virgin Media | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  |  |  | 2007-07-27 |  | 2008-04-07 | 255 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00805 | 05 | 08 - Cable & Wireless | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  |  |  | 2007-07-27 |  | 2008-04-07 | 255 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00905 | 05 | 09 - Thus | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  |  |  | 2007-07-27 |  | 2008-04-07 | 255 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-01705 | 05 | 17 - Forth Ports | Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-06-29 |  | 2007-07-13 |  |  | 2007-07-20 |  |  |  | 2007-07-27 |  | 2008-04-07 | 255 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1B | ULE90130-01-UTL-00023 | 23 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-08-17 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-04-07 | 248
1B | ULE90130-01-UTL-00123 | 23 | 01 - Scotland Gas Networks | Conflict | Programmed | 2007-06-07 | 2007-05-14 | 2007-06-21 | 2007-05-14 | 2007-06-22 | 2007-05-22 | 2007-06-15 |  | 2007-08-17 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-04-07 | 248
1B | ULE90130-01-UTL-00223 | 23 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-08-17 | 2007-07-06 | 2007-05-01 | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-04-07 | 248
1B | ULE90130-01-UTL-00323 | 23 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-06-07 | 2007-02-06 | 2007-06-21 | 2007-05-04 | 2007-06-22 | 2007-05-22 |  |  | 2007-08-17 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-04-07 | 248
1B | ULE90130-01-UTL-00423 | 23 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-08-17 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-04-07 | 248
1B | ULE90130-01-UTL-00523 | 23 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-06-15 | 2007-06-07 | 2007-08-17 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-04-07 | 248
1B | ULE90130-01-UTL-00723 | 23 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-08-17 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-04-07 | 248
1B | ULE90130-01-UTL-00823 | 23 | 08 - Cable & Wireless | Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-08-17 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-04-07 | 248
1B | ULE90130-01-UTL-00923 | 23 | 09 - Thus | Conflict | Programmed | [6 empty] | 2007-06-15 |  | 2007-08-17 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  | 2007-07-31 |  | 2007-08-03 |  | 2008-04-07 | 248
1C1 | ULE90130-01-UTL-00032 | 32 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00132 | 32 | 01 - Scotland Gas Networks | Conflict | Programmed | 2007-08-30 | 2007-02-08 |  |  |  |  | 2007-09-07 |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00232 | 32 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-13 | 2007-09-28 | 2007-05-01 | 2007-10-12 | 2007-04-12 | Written | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00332 | 32 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-08-30 | 2007-02-08 | 2007-09-13 |  | 2007-09-14 |  |  |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00432 | 32 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00532 | 32 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-09-07 | 2007-06-07 | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00732 | 32 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00832 | 32 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00932 | 32 | 09 - Thus | Conflict | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00033 | 33 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00133 | 33 | 01 - Scotland Gas Networks | Conflict | Programmed | 2007-08-30 | 2007-02-08 |  |  |  |  | 2007-09-07 |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00233 | 33 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-13 | 2007-09-28 | 2007-05-01 | 2007-10-12 | 2007-04-12 | Written | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00333 | 33 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-08-30 | 2007-02-08 | 2007-09-13 |  | 2007-09-14 |  |  |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00433 | 33 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00533 | 33 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-09-07 | 2007-06-07 | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00733 | 33 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00833 | 33 | 08 - Cable & Wireless | Conflict | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00933 | 33 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00034 | 34 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00134 | 34 | 01 - Scotland Gas Networks | Conflict | Programmed | 2007-08-30 | 2007-02-08 |  |  |  |  | 2007-09-07 |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00234 | 34 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-13 | 2007-09-28 | 2007-05-01 | 2007-10-12 | 2007-04-12 | Written | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00334 | 34 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-08-30 | 2007-02-08 | 2007-09-13 |  | 2007-09-14 |  |  |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00434 | 34 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00534 | 34 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-09-07 | 2007-06-07 | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00734 | 34 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00834 | 34 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C1 | ULE90130-01-UTL-00934 | 34 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-04-07 | 164
1C2 | ULE90130-01-UTL-00041 | 41 | 00 - Composite |  | Programmed | [8 empty] | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-04-21 | 192
1C2 | ULE90130-01-UTL-00141 | 41 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-08-24 |  | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-04-21 | 192
1C2 | ULE90130-01-UTL-00241 | 41 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-08-24 |  | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-04-21 | 192
1C2 | ULE90130-01-UTL-00341 | 41 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-08-16 |  | 2007-08-30 |  | 2007-08-31 |  |  |  | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-04-21 | 192
1C2 | ULE90130-01-UTL-00441 | 41 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-08-24 |  | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-04-21 | 192
1C2 | ULE90130-01-UTL-00541 | 41 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-08-24 | 2007-06-07 | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-04-21 | 192
1C2 | ULE90130-01-UTL-00741 | 41 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-08-24 |  | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-04-21 | 192
1C2 | ULE90130-01-UTL-00841 | 41 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-08-24 |  | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-04-21 | 192
1C2 | ULE90130-01-UTL-00941 | 41 | 09 - Thus |  | Programmed | [6 empty] | 2007-08-24 |  | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-04-21 | 192
1C2 | ULE90130-01-UTL-00040 | 40 | 00 - Composite |  | Programmed | [8 empty] | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-05-05 | 206
1C2 | ULE90130-01-UTL-00140 | 40 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-08-24 |  | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-05-05 | 206
1C2 | ULE90130-01-UTL-00240 | 40 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-08-24 |  | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-05-05 | 206
1C2 | ULE90130-01-UTL-00340 | 40 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-08-16 |  | 2007-08-30 |  | 2007-08-31 |  |  |  | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-05-05 | 206
1C2 | ULE90130-01-UTL-00440 | 40 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-08-24 |  | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-05-05 | 206
1C2 | ULE90130-01-UTL-00540 | 40 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-08-24 | 2007-06-07 | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-05-05 | 206
1C2 | ULE90130-01-UTL-00740 | 40 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-08-24 |  | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-05-05 | 206
1C2 | ULE90130-01-UTL-00840 | 40 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-08-24 |  | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-05-05 | 206
1C2 | ULE90130-01-UTL-00940 | 40 | 09 - Thus |  | Programmed | [6 empty] | 2007-08-24 |  | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-05-05 | 206
1A1 | ULE90130-01-UTL-00001 | 01 | 00 - Composite | Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  |  |  | 2007-08-03 |  | 2008-05-26 | 297 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00101 | 01 | 01 - Scotland Gas Networks | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  |  |  | 2007-08-03 |  | 2008-05-26 | 297 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00201 | 01 | 02 - Scottish Power | Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-07-06 | 2007-05-01 | 2007-07-20 | 2007-02-06 | Written | 2007-07-27 |  |  |  | 2007-08-03 |  | 2008-05-26 | 297 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00301 | 01 | 03 - Scottish Water - Clean | Conflict | Re-Programme | 2007-01-12 | 2007-01-12 | 2007-06-26 |  | 2007-06-27 |  |  |  | 2007-07-13 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  |  |  | 2007-08-03 |  | 2008-05-26 | 297 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00401 | 01 | 04 - Scottish Water - Foul | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  |  |  | 2007-08-03 |  | 2008-05-26 | 297 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00501 | 01 | 05 - BT Openreach | Conflict | Re-Programme | [7 empty] | 2007-06-07 | 2007-07-13 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  |  |  | 2007-08-03 |  | 2008-05-26 | 297 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00701 | 01 | 07 - Virgin Media | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  |  |  | 2007-08-03 |  | 2008-05-26 | 297 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00801 | 01 | 08 - Cable & Wireless | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  |  |  | 2007-08-03 |  | 2008-05-26 | 297 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00901 | 01 | 09 - Thus | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  |  |  | 2007-08-03 |  | 2008-05-26 | 297 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-01701 | 01 | 17 - Forth Ports | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  |  |  | 2007-08-03 |  | 2008-05-26 | 297 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00002 | 02 | 00 - Composite | Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  |  |  | 2007-08-03 |  | 2008-05-26 | 297 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00102 | 02 | 01 - Scotland Gas Networks | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  |  |  | 2007-08-03 |  | 2008-05-26 | 297 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00202 | 02 | 02 - Scottish Power | Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-07-06 | 2007-05-01 | 2007-07-20 | 2007-02-06 | Written | 2007-07-27 |  |  |  | 2007-08-03 |  | 2008-05-26 | 297 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00302 | 02 | 03 - Scottish Water - Clean | Conflict | Re-Programme | 2007-01-12 | 2007-01-12 | 2007-06-26 |  | 2007-06-27 |  |  |  | 2007-07-13 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  |  |  | 2007-08-03 |  | 2008-05-26 | 297 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00402 | 02 | 04 - Scottish Water - Foul | Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  |  |  | 2007-08-03 |  | 2008-05-26 | 297 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00502 | 02 | 05 - BT Openreach | Conflict | Re-Programme | [7 empty] | 2007-06-07 | 2007-07-13 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  |  |  | 2007-08-03 |  | 2008-05-26 | 297 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00702 | 02 | 07 - Virgin Media | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  |  |  | 2007-08-03 |  | 2008-05-26 | 297 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00802 | 02 | 08 - Cable & Wireless | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  |  |  | 2007-08-03 |  | 2008-05-26 | 297 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-00902 | 02 | 09 - Thus | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  |  |  | 2007-08-03 |  | 2008-05-26 | 297 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1A1 | ULE90130-01-UTL-01702 | 02 | 17 - Forth Ports | No Conflict | Re-Programme | [8 empty] | 2007-07-13 | 2007-07-06 |  | 2007-07-20 |  |  | 2007-07-27 |  |  |  | 2007-08-03 |  | 2008-05-26 | 297 | Original Dates. Revised dates to be advised. Alignment not yet finalised CEC Forth Ports to agree alignment proposals. RATS review advised
1C1 | ULE90130-01-UTL-00035 | 35 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-06-09 | 227
1C1 | ULE90130-01-UTL-00135 | 35 | 01 - Scotland Gas Networks | Conflict | Programmed | 2007-08-30 | 2007-02-08 |  |  |  |  | 2007-09-07 |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-06-09 | 227
1C1 | ULE90130-01-UTL-00235 | 35 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-13 | 2007-09-28 | 2007-05-01 | 2007-10-12 | 2007-04-12 | Written | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-06-09 | 227
1C1 | ULE90130-01-UTL-00335 | 35 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-08-30 | 2007-02-08 | 2007-09-13 |  | 2007-09-14 |  |  |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-06-09 | 227
1C1 | ULE90130-01-UTL-00435 | 35 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-06-09 | 227
1C1 | ULE90130-01-UTL-00535 | 35 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-09-07 | 2007-06-07 | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-06-09 | 227
1C1 | ULE90130-01-UTL-00735 | 35 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-06-09 | 227
1C1 | ULE90130-01-UTL-00835 | 35 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-06-09 | 227
1C1 | ULE90130-01-UTL-00935 | 35 | 09 - Thus | Conflict | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-06-09 | 227
1C2 | ULE90130-01-UTL-00039 | 39 | 00 - Composite |  | Programmed | [8 empty] | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-06-09 | 241
1C2 | ULE90130-01-UTL-00139 | 39 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-08-24 |  | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-06-09 | 241
1C2 | ULE90130-01-UTL-00239 | 39 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-08-24 |  | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-06-09 | 241
1C2 | ULE90130-01-UTL-00339 | 39 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-08-16 |  | 2007-08-30 |  | 2007-08-31 |  |  |  | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-06-09 | 241
1C2 | ULE90130-01-UTL-00439 | 39 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-08-24 |  | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-06-09 | 241
1C2 | ULE90130-01-UTL-00539 | 39 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-08-24 | 2007-06-07 | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-06-09 | 241
1C2 | ULE90130-01-UTL-00739 | 39 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-08-24 |  | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-06-09 | 241
1C2 | ULE90130-01-UTL-00839 | 39 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-08-24 |  | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-06-09 | 241
1C2 | ULE90130-01-UTL-00939 | 39 | 09 - Thus |  | Programmed | [6 empty] | 2007-08-24 |  | 2007-07-13 | 2007-09-14 |  | 2007-09-28 |  |  | 2007-10-05 |  | 2007-10-09 |  | 2007-10-12 |  | 2008-06-09 | 241
1C1 | ULE90130-01-UTL-00036 | 36 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-06-16 | 234
1C1 | ULE90130-01-UTL-00136 | 36 | 01 - Scotland Gas Networks | Conflict | Programmed | 2007-08-30 | 2007-02-08 |  |  |  |  | 2007-09-07 |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-06-16 | 234
1C1 | ULE90130-01-UTL-00236 | 36 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-13 | 2007-09-28 | 2007-05-01 | 2007-10-12 | 2007-04-12 | Written | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-06-16 | 234
1C1 | ULE90130-01-UTL-00336 | 36 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-08-30 | 2007-02-08 | 2007-09-13 |  | 2007-09-14 |  |  |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-06-16 | 234
1C1 | ULE90130-01-UTL-00436 | 36 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-06-16 | 234
1C1 | ULE90130-01-UTL-00536 | 36 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-09-07 | 2007-06-07 | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-06-16 | 234
1C1 | ULE90130-01-UTL-00736 | 36 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-06-16 | 234
1C1 | ULE90130-01-UTL-00836 | 36 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-06-16 | 234
1C1 | ULE90130-01-UTL-00936 | 36 | 09 - Thus | Conflict | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-13 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-06-16 | 234
1D | ULE90130-01-UTL-00052 | 52 | 00 - Composite |  | Programmed | [8 empty] | 2007-07-13 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-06-23 | 269
1D | ULE90130-01-UTL-00152 | 52 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-13 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-06-23 | 269
1D | ULE90130-01-UTL-00252 | 52 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-13 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-06-23 | 269
1D | ULE90130-01-UTL-00352 | 52 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-08-02 |  | 2007-08-16 |  | 2007-08-17 |  |  |  | 2007-07-13 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-06-23 | 269
1D | ULE90130-01-UTL-00452 | 52 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-13 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-06-23 | 269
1D | ULE90130-01-UTL-00552 | 52 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-13 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-06-23 | 269
1D | ULE90130-01-UTL-00752 | 52 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-13 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-06-23 | 269
1D | ULE90130-01-UTL-00852 | 52 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-13 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-06-23 | 269
1D | ULE90130-01-UTL-00952 | 52 | 09 - Thus |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-13 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-06-23 | 269
1D | ULE90130-01-UTL-00053 | 53 | 00 - Composite |  | Programmed | [8 empty] | 2007-07-13 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-07-07 | 283
1D | ULE90130-01-UTL-00153 | 53 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-13 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-07-07 | 283
1D | ULE90130-01-UTL-00253 | 53 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-13 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-07-07 | 283
1D | ULE90130-01-UTL-00353 | 53 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-08-02 |  | 2007-08-16 |  | 2007-08-17 |  |  |  | 2007-07-13 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-07-07 | 283
1D | ULE90130-01-UTL-00453 | 53 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-13 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-07-07 | 283
1D | ULE90130-01-UTL-00553 | 53 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-13 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-07-07 | 283
1D | ULE90130-01-UTL-00753 | 53 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-13 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-07-07 | 283
1D | ULE90130-01-UTL-00853 | 53 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-13 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-07-07 | 283
1D | ULE90130-01-UTL-00953 | 53 | 09 - Thus |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-13 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-07-07 | 283
1C2 | ULE90130-01-UTL-00037 | 37 | 00 - Composite |  | Programmed | [8 empty] | 2007-07-20 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-07-21 | 269
1C2 | ULE90130-01-UTL-00137 | 37 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-20 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-07-21 | 269
1C2 | ULE90130-01-UTL-00237 | 37 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-20 | 2007-09-28 | 2007-05-01 | 2007-10-12 | 2007-05-10 | Written | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-07-21 | 269
1C2 | ULE90130-01-UTL-00337 | 37 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-08-30 |  | 2007-09-13 |  | 2007-09-14 |  |  |  | 2007-07-20 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-07-21 | 269
1C2 | ULE90130-01-UTL-00437 | 37 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-20 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-07-21 | 269
1C2 | ULE90130-01-UTL-00537 | 37 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-09-07 | 2007-06-07 | 2007-07-20 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-07-21 | 269
1C2 | ULE90130-01-UTL-00737 | 37 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-20 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-07-21 | 269
1C2 | ULE90130-01-UTL-00837 | 37 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-20 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-07-21 | 269
1C2 | ULE90130-01-UTL-00937 | 37 | 09 - Thus |  | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-20 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-07-21 | 269
1D | ULE90130-01-UTL-00054 | 54 | 00 - Composite |  | Programmed | [8 empty] | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-07-21 | 297
1D | ULE90130-01-UTL-00154 | 54 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-07-21 | 297
1D | ULE90130-01-UTL-00254 | 54 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-07-21 | 297
1D | ULE90130-01-UTL-00354 | 54 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-08-02 |  | 2007-08-16 |  | 2007-08-17 |  |  |  | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-07-21 | 297
1D | ULE90130-01-UTL-00454 | 54 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-07-21 | 297
1D | ULE90130-01-UTL-00554 | 54 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-07-21 | 297
1D | ULE90130-01-UTL-00754 | 54 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-07-21 | 297
1D | ULE90130-01-UTL-00854 | 54 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-07-21 | 297
1D | ULE90130-01-UTL-00954 | 54 | 09 - Thus |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-07-21 | 297
3A | ULE90130-03-UTL-00001 | 01 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00101 | 01 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00201 | 01 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00301 | 01 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-06 | 2007-04-19 | [6 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00401 | 01 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00501 | 01 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00601 | 01 | 06 - Verizon | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00701 | 01 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00801 | 01 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00901 | 01 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00002 | 02 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00102 | 02 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00202 | 02 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00302 | 02 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-06 | 2007-04-19 | [6 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00402 | 02 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00502 | 02 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00602 | 02 | 06 - Verizon | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00702 | 02 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00802 | 02 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00902 | 02 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00003 | 03 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00103 | 03 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00203 | 03 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00303 | 03 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-06 | 2007-04-19 | [6 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00403 | 03 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00503 | 03 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00603 | 03 | 06 - Verizon | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00703 | 03 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00803 | 03 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00903 | 03 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00004 | 04 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00104 | 04 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00204 | 04 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00304 | 04 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-06 | 2007-04-19 | [6 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00404 | 04 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00504 | 04 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00604 | 04 | 06 - Verizon | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00704 | 04 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00804 | 04 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00904 | 04 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00005 | 05 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00105 | 05 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00205 | 05 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00305 | 05 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-06 | 2007-04-19 | [6 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00405 | 05 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00505 | 05 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00605 | 05 | 06 - Verizon | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00705 | 05 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00805 | 05 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00905 | 05 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-18 | 290
3A | ULE90130-03-UTL-00006 | 06 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-25 | 297
3A | ULE90130-03-UTL-00106 | 06 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-25 | 297
3A | ULE90130-03-UTL-00206 | 06 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-25 | 297
3A | ULE90130-03-UTL-00306 | 06 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-06 | 2007-04-19 | [6 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-25 | 297
3A | ULE90130-03-UTL-00406 | 06 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-25 | 297
3A | ULE90130-03-UTL-00506 | 06 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-25 | 297
3A | ULE90130-03-UTL-00606 | 06 | 06 - Verizon | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-25 | 297
3A | ULE90130-03-UTL-00706 | 06 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-25 | 297
3A | ULE90130-03-UTL-00806 | 06 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-25 | 297
3A | ULE90130-03-UTL-00906 | 06 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-08-25 | 297
3A | ULE90130-03-UTL-00007 | 07 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00107 | 07 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00207 | 07 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00307 | 07 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-06 | 2007-04-19 | [6 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00407 | 07 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00507 | 07 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00607 | 07 | 06 - Verizon | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00707 | 07 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00807 | 07 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00907 | 07 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00008 | 08 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00108 | 08 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00208 | 08 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00308 | 08 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-06 | 2007-04-19 | [6 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00408 | 08 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00508 | 08 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00608 | 08 | 06 - Verizon | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00708 | 08 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00808 | 08 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00908 | 08 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00009 | 09 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00109 | 09 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00209 | 09 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00309 | 09 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-06 | 2007-04-19 | [6 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00409 | 09 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00509 | 09 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00609 | 09 | 06 - Verizon | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00709 | 09 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00809 | 09 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
3A | ULE90130-03-UTL-00909 | 09 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-01 | 304
1C2 | ULE90130-01-UTL-00038 | 38 | 00 - Composite |  | Programmed | [8 empty] | 2007-07-20 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-09-08 | 318
1C2 | ULE90130-01-UTL-00138 | 38 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-20 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-09-08 | 318
1C2 | ULE90130-01-UTL-00238 | 38 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-20 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-09-08 | 318
1C2 | ULE90130-01-UTL-00338 | 38 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-08-30 |  | 2007-09-13 |  | 2007-09-14 |  |  |  | 2007-07-20 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-09-08 | 318
1C2 | ULE90130-01-UTL-00438 | 38 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-20 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-09-08 | 318
1C2 | ULE90130-01-UTL-00538 | 38 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-09-07 | 2007-06-07 | 2007-07-20 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-09-08 | 318
1C2 | ULE90130-01-UTL-00738 | 38 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-20 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-09-08 | 318
1C2 | ULE90130-01-UTL-00838 | 38 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-20 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-09-08 | 318
1C2 | ULE90130-01-UTL-00938 | 38 | 09 - Thus |  | Programmed | [6 empty] | 2007-09-07 |  | 2007-07-20 | 2007-09-28 |  | 2007-10-12 |  |  | 2007-10-19 |  | 2007-10-23 |  | 2007-10-26 |  | 2008-09-08 | 318
3A | ULE90130-03-UTL-00010 | 10 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-15 | 318
3A | ULE90130-03-UTL-00110 | 10 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-15 | 318
3A | ULE90130-03-UTL-00210 | 10 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-15 | 318
3A | ULE90130-03-UTL-00310 | 10 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-06 | 2007-04-19 | [6 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-15 | 318
3A | ULE90130-03-UTL-00410 | 10 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-15 | 318
3A | ULE90130-03-UTL-00510 | 10 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-15 | 318
3A | ULE90130-03-UTL-00610 | 10 | 06 - Verizon | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-15 | 318
3A | ULE90130-03-UTL-00710 | 10 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-15 | 318
3A | ULE90130-03-UTL-00810 | 10 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-15 | 318
3A | ULE90130-03-UTL-00910 | 10 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-15 | 318
3A | ULE90130-03-UTL-00011 | 11 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-15 | 318
3A | ULE90130-03-UTL-00111 | 11 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-15 | 318
3A | ULE90130-03-UTL-00211 | 11 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-15 | 318
3A | ULE90130-03-UTL-00311 | 11 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-06 | 2007-04-19 | [6 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-15 | 318
3A | ULE90130-03-UTL-00411 | 11 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-15 | 318
3A | ULE90130-03-UTL-00511 | 11 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-15 | 318
3A | ULE90130-03-UTL-00611 | 11 | 06 - Verizon | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-15 | 318
3A | ULE90130-03-UTL-00711 | 11 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-15 | 318
3A | ULE90130-03-UTL-00811 | 11 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-15 | 318
3A | ULE90130-03-UTL-00911 | 11 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-15 | 318
3A | ULE90130-03-UTL-00012 | 12 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00112 | 12 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00212 | 12 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00312 | 12 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-06 | 2007-04-19 | [6 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00412 | 12 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00512 | 12 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00612 | 12 | 06 - Verizon | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00712 | 12 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00812 | 12 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00912 | 12 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00013 | 13 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00113 | 13 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00213 | 13 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00313 | 13 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-06 | 2007-04-19 | [6 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00413 | 13 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00513 | 13 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00613 | 13 | 06 - Verizon | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00713 | 13 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00813 | 13 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00913 | 13 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00014 | 14 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00114 | 14 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00214 | 14 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00314 | 14 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-06 | 2007-04-19 | [6 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00414 | 14 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00514 | 14 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00614 | 14 | 06 - Verizon | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00714 | 14 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00814 | 14 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
3A | ULE90130-03-UTL-00914 | 14 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-09-29 | 332
1D | ULE90130-01-UTL-00055 | 55 | 00 - Composite |  | Programmed | [8 empty] | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-09-29 | 367
1D | ULE90130-01-UTL-00155 | 55 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-09-29 | 367
1D | ULE90130-01-UTL-00255 | 55 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-09-29 | 367
1D | ULE90130-01-UTL-00355 | 55 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-08-02 |  | 2007-08-16 |  | 2007-08-17 |  |  |  | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-09-29 | 367
1D | ULE90130-01-UTL-00455 | 55 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-09-29 | 367
1D | ULE90130-01-UTL-00555 | 55 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-09-29 | 367
1D | ULE90130-01-UTL-00755 | 55 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-09-29 | 367
1D | ULE90130-01-UTL-00855 | 55 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-09-29 | 367
1D | ULE90130-01-UTL-00955 | 55 | 09 - Thus |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-09-29 | 367
3A | ULE90130-03-UTL-00015 | 15 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-13 | 346
3A | ULE90130-03-UTL-00115 | 15 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-13 | 346
3A | ULE90130-03-UTL-00215 | 15 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-13 | 346
3A | ULE90130-03-UTL-00315 | 15 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-06 | 2007-04-19 | [6 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-13 | 346
3A | ULE90130-03-UTL-00415 | 15 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-13 | 346
3A | ULE90130-03-UTL-00515 | 15 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-13 | 346
3A | ULE90130-03-UTL-00615 | 15 | 06 - Verizon | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-13 | 346
3A | ULE90130-03-UTL-00715 | 15 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-13 | 346
3A | ULE90130-03-UTL-00815 | 15 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-13 | 346
3A | ULE90130-03-UTL-00915 | 15 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-13 | 346
1D | ULE90130-01-UTL-00056 | 56 | 00 - Composite |  | Programmed | [8 empty] | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-10-13 | 381
1D | ULE90130-01-UTL-00156 | 56 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-10-13 | 381
1D | ULE90130-01-UTL-00256 | 56 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-10-13 | 381
1D | ULE90130-01-UTL-00356 | 56 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-08-02 |  | 2007-08-16 |  | 2007-08-17 |  |  |  | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-10-13 | 381
1D | ULE90130-01-UTL-00456 | 56 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-10-13 | 381
1D | ULE90130-01-UTL-00556 | 56 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-10-13 | 381
1D | ULE90130-01-UTL-00756 | 56 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-10-13 | 381
1D | ULE90130-01-UTL-00856 | 56 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-10-13 | 381
1D | ULE90130-01-UTL-00956 | 56 | 09 - Thus |  | Programmed | [6 empty] | 2007-08-10 |  | 2007-07-20 | 2007-08-31 |  | 2007-09-14 |  |  | 2007-09-21 |  | 2007-09-25 |  | 2007-09-28 |  | 2008-10-13 | 381
3A | ULE90130-03-UTL-00016 | 16 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-20 | 353
3A | ULE90130-03-UTL-00116 | 16 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-20 | 353
3A | ULE90130-03-UTL-00216 | 16 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-20 | 353
3A | ULE90130-03-UTL-00316 | 16 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-06 | 2007-04-19 | [6 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-20 | 353
3A | ULE90130-03-UTL-00416 | 16 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-20 | 353
3A | ULE90130-03-UTL-00516 | 16 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-20 | 353
3A | ULE90130-03-UTL-00616 | 16 | 06 - Verizon | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-20 | 353
3A | ULE90130-03-UTL-00716 | 16 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-20 | 353
3A | ULE90130-03-UTL-00816 | 16 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-20 | 353
3A | ULE90130-03-UTL-00916 | 16 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-20 | 353
3A | ULE90130-03-UTL-00017 | 17 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-27 | 360
3A | ULE90130-03-UTL-00117 | 17 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-27 | 360
3A | ULE90130-03-UTL-00217 | 17 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-27 | 360
3A | ULE90130-03-UTL-00317 | 17 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-06 | 2007-04-19 | [6 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-27 | 360
3A | ULE90130-03-UTL-00417 | 17 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-27 | 360
3A | ULE90130-03-UTL-00517 | 17 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-27 | 360
3A | ULE90130-03-UTL-00617 | 17 | 06 - Verizon | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-27 | 360
3A | ULE90130-03-UTL-00717 | 17 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-27 | 360
3A | ULE90130-03-UTL-00817 | 17 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-27 | 360
3A | ULE90130-03-UTL-00917 | 17 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-27 | 360
3A | ULE90130-03-UTL-00018 | 18 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-27 | 360
3A | ULE90130-03-UTL-00118 | 18 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-27 | 360
3A | ULE90130-03-UTL-00218 | 18 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-27 | 360
3A | ULE90130-03-UTL-00318 | 18 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-06 | 2007-04-19 | [6 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-27 | 360
3A | ULE90130-03-UTL-00418 | 18 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-27 | 360
3A | ULE90130-03-UTL-00518 | 18 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-27 | 360
3A | ULE90130-03-UTL-00618 | 18 | 06 - Verizon | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-27 | 360
3A | ULE90130-03-UTL-00718 | 18 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-27 | 360
3A | ULE90130-03-UTL-00818 | 18 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-27 | 360
3A | ULE90130-03-UTL-00918 | 18 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-10-27 | 360
3A | ULE90130-03-UTL-00019 | 19 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-03 | 367
3A | ULE90130-03-UTL-00119 | 19 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-03 | 367
3A | ULE90130-03-UTL-00219 | 19 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-03 | 367
3A | ULE90130-03-UTL-00319 | 19 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-06 | 2007-04-19 | [6 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-03 | 367
3A | ULE90130-03-UTL-00419 | 19 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-03 | 367
3A | ULE90130-03-UTL-00519 | 19 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-03 | 367
3A | ULE90130-03-UTL-00619 | 19 | 06 - Verizon | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-03 | 367
3A | ULE90130-03-UTL-00719 | 19 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-03 | 367
3A | ULE90130-03-UTL-00819 | 19 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-03 | 367
3A | ULE90130-03-UTL-00919 | 19 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-03 | 367
3A | ULE90130-03-UTL-00020 | 20 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-03 | 367
3A | ULE90130-03-UTL-00120 | 20 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-03 | 367
3A | ULE90130-03-UTL-00220 | 20 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-03 | 367
3A | ULE90130-03-UTL-00320 | 20 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-06 | 2007-04-19 | [6 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-03 | 367
3A | ULE90130-03-UTL-00420 | 20 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-03 | 367
3A | ULE90130-03-UTL-00520 | 20 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-03 | 367
3A | ULE90130-03-UTL-00620 | 20 | 06 - Verizon | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-03 | 367
3A | ULE90130-03-UTL-00720 | 20 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-03 | 367
3A | ULE90130-03-UTL-00820 | 20 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-03 | 367
3A | ULE90130-03-UTL-00920 | 20 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-03 | 367
3A | ULE90130-03-UTL-00021 | 21 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-10 | 374
3A | ULE90130-03-UTL-00121 | 21 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-10 | 374
3A | ULE90130-03-UTL-00221 | 21 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-10 | 374
3A | ULE90130-03-UTL-00321 | 21 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-06 | 2007-04-19 | [6 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-10 | 374
3A | ULE90130-03-UTL-00421 | 21 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-10 | 374
3A | ULE90130-03-UTL-00521 | 21 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-10 | 374
3A | ULE90130-03-UTL-00621 | 21 | 06 - Verizon | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-10 | 374
3A | ULE90130-03-UTL-00721 | 21 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-10 | 374
3A | ULE90130-03-UTL-00821 | 21 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-10 | 374
3A | ULE90130-03-UTL-00921 | 21 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-10 | 374
3A | ULE90130-03-UTL-00022 | 22 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3A | ULE90130-03-UTL-00122 | 22 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3A | ULE90130-03-UTL-00222 | 22 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3A | ULE90130-03-UTL-00322 | 22 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-06 | 2007-04-19 | [6 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3A | ULE90130-03-UTL-00422 | 22 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3A | ULE90130-03-UTL-00522 | 22 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3A | ULE90130-03-UTL-00622 | 22 | 06 - Verizon | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3A | ULE90130-03-UTL-00722 | 22 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3A | ULE90130-03-UTL-00822 | 22 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3A | ULE90130-03-UTL-00922 | 22 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3A | ULE90130-03-UTL-00023 | 23 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3A | ULE90130-03-UTL-00123 | 23 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3A | ULE90130-03-UTL-00223 | 23 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3A | ULE90130-03-UTL-00323 | 23 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-06 | 2007-04-19 | [6 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3A | ULE90130-03-UTL-00423 | 23 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3A | ULE90130-03-UTL-00523 | 23 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3A | ULE90130-03-UTL-00623 | 23 | 06 - Verizon | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3A | ULE90130-03-UTL-00723 | 23 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3A | ULE90130-03-UTL-00823 | 23 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3A | ULE90130-03-UTL-00923 | 23 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3B | ULE90130-03-UTL-00024 | 24 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3B | ULE90130-03-UTL-00124 | 24 | 01 - Scotland Gas Networks | Conflict | Programmed | 2007-09-06 | 2007-05-21 | 2007-09-20 | 2007-05-21 | 2007-09-21 | 2007-05-23 | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3B | ULE90130-03-UTL-00224 | 24 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 | 2007-02-18 | Written | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3B | ULE90130-03-UTL-00324 | 24 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-09-06 | 2007-04-19 | 2007-09-20 | 2007-06-05 | 2007-09-21 | 2007-06-07 |  |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3B | ULE90130-03-UTL-00424 | 24 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3B | ULE90130-03-UTL-00524 | 24 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3B | ULE90130-03-UTL-00724 | 24 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3B | ULE90130-03-UTL-00824 | 24 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3B | ULE90130-03-UTL-00924 | 24 | 09 - Thus | Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-17 | 381
3B | ULE90130-03-UTL-00025 | 25 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00125 | 25 | 01 - Scotland Gas Networks | Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00225 | 25 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 | 2007-02-18 | Written | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00325 | 25 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-09-06 | 2007-04-19 | 2007-09-20 |  | 2007-09-21 |  |  |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00425 | 25 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00525 | 25 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00725 | 25 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00825 | 25 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00925 | 25 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00026 | 26 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00126 | 26 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00226 | 26 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 | 2007-02-18 | Written | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00326 | 26 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-06 | 2007-04-19 | [6 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00426 | 26 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00526 | 26 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00726 | 26 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00826 | 26 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00926 | 26 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00027 | 27 | 00 - Composite | No Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00127 | 27 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00227 | 27 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 | 2007-02-18 | Written | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00327 | 27 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-06 | 2007-04-19 | [6 empty] | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00427 | 27 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00527 | 27 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00727 | 27 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00827 | 27 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00927 | 27 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-14 |  | 2007-07-27 | 2007-10-05 |  | 2007-10-19 |  |  | 2007-10-26 |  | 2007-10-30 |  | 2007-11-02 |  | 2008-11-24 | 388
3B | ULE90130-03-UTL-00028 | 28 | 00 - Composite |  | Programmed | [8 empty] | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00128 | 28 | 01 - Scotland Gas Networks |  | Programmed | 2007-09-20 | 2007-04-02 | 2007-10-04 | 2007-04-02 | 2007-10-05 | 2007-04-02 | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00228 | 28 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 | 2007-05-01 | 2007-11-02 | 2007-02-18 | Written | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00328 | 28 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-20 | 2006-12-22 |  |  | 2007-10-05 | 2007-04-02 |  |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00428 | 28 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00528 | 28 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00728 | 28 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00828 | 28 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00928 | 28 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00029 | 29 | 00 - Composite |  | Programmed | [8 empty] | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00129 | 29 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00229 | 29 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 | 2007-05-01 | 2007-11-02 | 2007-02-18 | Written | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00329 | 29 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-20 | 2006-12-22 | [6 empty] | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00429 | 29 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00529 | 29 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00729 | 29 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00829 | 29 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00929 | 29 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00030 | 30 | 00 - Composite |  | Programmed | [8 empty] | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00130 | 30 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00230 | 30 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 | 2007-05-01 | 2007-11-02 | 2007-02-18 | Written | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00330 | 30 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-20 | 2006-12-22 | [6 empty] | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00430 | 30 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00530 | 30 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00730 | 30 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00830 | 30 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00930 | 30 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00031 | 31 | 00 - Composite |  | Programmed | [8 empty] | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00131 | 31 | 01 - Scotland Gas Networks | Conflict | Programmed | 2007-09-20 | 2007-05-21 | 2007-10-04 | 2007-05-21 | 2007-10-05 | 2007-05-23 | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00231 | 31 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 | 2007-05-01 | 2007-11-02 | 2007-02-18 | Written | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00331 | 31 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-09-20 | 2006-12-22 | 2007-10-04 | 2007-06-05 | 2007-10-05 | 2007-06-07 |  |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00431 | 31 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00531 | 31 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00731 | 31 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00831 | 31 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3B | ULE90130-03-UTL-00931 | 31 | 09 - Thus | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00037 | 37 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00137 | 37 | 01 - Scotland Gas Networks | No Conflict | Programmed | 2007-09-20 | 2007-04-02 | 2007-10-04 | 2007-04-02 | 2007-10-05 | 2007-04-02 | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00237 | 37 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00337 | 37 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-09-20 | 2007-02-22 | 2007-10-04 | 2007-06-12 | 2007-10-05 | 2007-06-13 |  |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00437 | 37 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00537 | 37 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00737 | 37 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00837 | 37 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00937 | 37 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00038 | 38 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00138 | 38 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00238 | 38 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00338 | 38 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-09-20 | 2007-02-22 | 2007-10-04 | 2007-06-12 | 2007-10-05 | 2007-06-13 |  |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00438 | 38 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00538 | 38 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00738 | 38 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00838 | 38 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00938 | 38 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00039 | 39 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00139 | 39 | 01 - Scotland Gas Networks | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00239 | 39 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00339 | 39 | 03 - Scottish Water - Clean | No Conflict | Programmed | 2007-09-20 | 2007-02-22 | [6 empty] | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00439 | 39 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00539 | 39 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00739 | 39 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00839 | 39 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00939 | 39 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2008-12-01 | 381
3C | ULE90130-03-UTL-00040 | 40 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-05 | 416
3C | ULE90130-03-UTL-00140 | 40 | 01 - Scotland Gas Networks | Conflict | Programmed | 2007-09-20 | 2007-05-24 | 2007-10-04 | 2007-05-24 |  |  | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-05 | 416
3C | ULE90130-03-UTL-00240 | 40 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-05 | 416
3C | ULE90130-03-UTL-00340 | 40 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-09-20 | 2007-02-22 | 2007-10-04 |  | 2007-10-05 |  |  |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-05 | 416
3C | ULE90130-03-UTL-00440 | 40 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-05 | 416
3C | ULE90130-03-UTL-00540 | 40 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-05 | 416
3C | ULE90130-03-UTL-00740 | 40 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-05 | 416
3C | ULE90130-03-UTL-00840 | 40 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-05 | 416
3C | ULE90130-03-UTL-00940 | 40 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-05 | 416
3B | ULE90130-03-UTL-00032 | 32 | 00 - Composite |  | Programmed | [8 empty] | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3B | ULE90130-03-UTL-00132 | 32 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3B | ULE90130-03-UTL-00232 | 32 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 | 2007-05-01 | 2007-11-02 | 2007-02-18 | Written | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3B | ULE90130-03-UTL-00332 | 32 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-09-20 | 2006-12-22 | 2007-10-04 | 2007-06-05 | 2007-10-05 | 2007-06-07 |  |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3B | ULE90130-03-UTL-00432 | 32 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3B | ULE90130-03-UTL-00532 | 32 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3B | ULE90130-03-UTL-00732 | 32 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3B | ULE90130-03-UTL-00832 | 32 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3B | ULE90130-03-UTL-00932 | 32 | 09 - Thus | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3B | ULE90130-03-UTL-00033 | 33 | 00 - Composite |  | Programmed | [8 empty] | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3B | ULE90130-03-UTL-00133 | 33 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3B | ULE90130-03-UTL-00233 | 33 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 | 2007-05-01 | 2007-11-02 | 2007-02-18 | Written | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3B | ULE90130-03-UTL-00333 | 33 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-09-20 | 2006-12-22 | 2007-10-04 | 2007-06-05 | 2007-10-05 | 2007-06-07 |  |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3B | ULE90130-03-UTL-00433 | 33 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3B | ULE90130-03-UTL-00533 | 33 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3B | ULE90130-03-UTL-00733 | 33 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3B | ULE90130-03-UTL-00833 | 33 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3B | ULE90130-03-UTL-00933 | 33 | 09 - Thus | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3C | ULE90130-03-UTL-00034 | 34 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3C | ULE90130-03-UTL-00134 | 34 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3C | ULE90130-03-UTL-00234 | 34 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 | 2007-05-01 | 2007-11-02 | 2007-05-10 | Written | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3C | ULE90130-03-UTL-00334 | 34 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-09-20 | 2006-12-22 | 2007-10-04 | 2007-06-08 | 2007-10-05 | 2007-06-11 |  |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3C | ULE90130-03-UTL-00434 | 34 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3C | ULE90130-03-UTL-00534 | 34 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3C | ULE90130-03-UTL-00734 | 34 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3C | ULE90130-03-UTL-00834 | 34 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3C | ULE90130-03-UTL-00934 | 34 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3C | ULE90130-03-UTL-00035 | 35 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3C | ULE90130-03-UTL-00135 | 35 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3C | ULE90130-03-UTL-00235 | 35 | 02 - Scottish Power | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 | 2007-05-01 | 2007-11-02 | 2007-05-10 | Written | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3C | ULE90130-03-UTL-00335 | 35 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-09-20 | 2006-12-22 | 2007-10-04 | 2007-06-08 | 2007-10-05 | 2007-06-11 |  |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3C | ULE90130-03-UTL-00435 | 35 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3C | ULE90130-03-UTL-00535 | 35 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3C | ULE90130-03-UTL-00735 | 35 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3C | ULE90130-03-UTL-00835 | 35 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3C | ULE90130-03-UTL-00935 | 35 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-01-12 | 423
3C | ULE90130-03-UTL-00036 | 36 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-02-02 | 444
3C | ULE90130-03-UTL-00136 | 36 | 01 - Scotland Gas Networks | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-02-02 | 444
3C | ULE90130-03-UTL-00236 | 36 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 | 2007-05-01 | 2007-11-02 | 2007-05-10 | Written | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-02-02 | 444
3C | ULE90130-03-UTL-00336 | 36 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-09-20 | 2006-12-22 | 2007-10-04 | 2007-06-12 | 2007-10-05 | 2007-06-13 |  |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-02-02 | 444
3C | ULE90130-03-UTL-00436 | 36 | 04 - Scottish Water - Foul | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-02-02 | 444
3C | ULE90130-03-UTL-00536 | 36 | 05 - BT Openreach | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-02-02 | 444
3C | ULE90130-03-UTL-00736 | 36 | 07 - Virgin Media | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-02-02 | 444
3C | ULE90130-03-UTL-00836 | 36 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-02-02 | 444
3C | ULE90130-03-UTL-00936 | 36 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-09-28 |  | 2007-07-27 | 2007-10-19 |  | 2007-11-02 |  |  | 2007-11-09 |  | 2007-11-13 |  | 2007-11-16 |  | 2009-02-02 | 444
3C | ULE90130-03-UTL-00041 | 41 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00141 | 41 | 01 - Scotland Gas Networks | Conflict | Programmed | 2007-10-04 | 2007-05-24 | 2007-10-18 | 2007-05-24 |  |  | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00241 | 41 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00341 | 41 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-10-04 | 2007-02-22 | 2007-10-18 | 2007-06-12 | 2007-10-19 | 2007-06-13 |  |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00441 | 41 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00541 | 41 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00741 | 41 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00841 | 41 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00941 | 41 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00042 | 42 | 00 - Composite | Conflict | Programmed | [8 empty] | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00142 | 42 | 01 - Scotland Gas Networks | Conflict | Programmed | 2007-10-04 | 2007-05-24 | 2007-10-18 | 2007-05-24 |  |  | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00242 | 42 | 02 - Scottish Power | Conflict | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00342 | 42 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-10-04 | 2007-02-22 | 2007-10-18 | 2007-06-12 | 2007-10-19 | 2007-06-13 |  |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00442 | 42 | 04 - Scottish Water - Foul | Conflict | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00542 | 42 | 05 - BT Openreach | Conflict | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00742 | 42 | 07 - Virgin Media | Conflict | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00842 | 42 | 08 - Cable & Wireless | No Conflict | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00942 | 42 | 09 - Thus | No Conflict | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00043 | 43 | 00 - Composite |  | Programmed | [8 empty] | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00143 | 43 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00243 | 43 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00343 | 43 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-10-04 | 2007-02-22 | 2007-10-18 |  | 2007-10-19 |  |  |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00443 | 43 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00543 | 43 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00743 | 43 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00843 | 43 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00943 | 43 | 09 - Thus |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00044 | 44 | 00 - Composite |  | Programmed | [8 empty] | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00144 | 44 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00244 | 44 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00344 | 44 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-10-04 | 2007-02-22 | 2007-10-18 |  | 2007-10-19 |  |  |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00444 | 44 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00544 | 44 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00744 | 44 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00844 | 44 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00944 | 44 | 09 - Thus |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-02 | 458
3C | ULE90130-03-UTL-00045 | 45 | 00 - Composite |  | Programmed | [8 empty] | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-16 | 472
3C | ULE90130-03-UTL-00145 | 45 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-16 | 472
3C | ULE90130-03-UTL-00245 | 45 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-16 | 472
3C | ULE90130-03-UTL-00345 | 45 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-10-04 | 2007-02-22 | 2007-10-18 |  | 2007-10-19 |  |  |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-16 | 472
3C | ULE90130-03-UTL-00445 | 45 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-16 | 472
3C | ULE90130-03-UTL-00545 | 45 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-16 | 472
3C | ULE90130-03-UTL-00745 | 45 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-16 | 472
3C | ULE90130-03-UTL-00845 | 45 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-16 | 472
3C | ULE90130-03-UTL-00945 | 45 | 09 - Thus |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-16 | 472
3C | ULE90130-03-UTL-00046 | 46 | 00 - Composite |  | Programmed | [8 empty] | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00146 | 46 | 01 - Scotland Gas Networks |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00246 | 46 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00346 | 46 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-10-04 | 2007-02-22 | 2007-10-18 |  | 2007-10-19 |  |  |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00446 | 46 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00546 | 46 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00746 | 46 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00846 | 46 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00946 | 46 | 09 - Thus |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00047 | 47 | 00 - Composite |  | Programmed | [8 empty] | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00147 | 47 | 01 - Scotland Gas Networks |  | Programmed | 2007-10-04 | 2007-04-02 | 2007-10-18 | 2007-04-02 | 2007-10-19 | 2007-04-02 | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00247 | 47 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00347 | 47 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-10-04 | 2007-02-22 | 2007-10-18 |  | 2007-10-19 | 2007-04-02 |  |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00447 | 47 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00547 | 47 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00747 | 47 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00847 | 47 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00947 | 47 | 09 - Thus |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00048 | 48 | 00 - Composite |  | Programmed | [8 empty] | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00148 | 48 | 01 - Scotland Gas Networks |  | Programmed | 2007-10-04 | 2007-04-02 | 2007-10-18 | 2007-04-02 | 2007-10-19 | 2007-04-02 | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00248 | 48 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00348 | 48 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-10-04 | 2007-02-22 | 2007-10-18 |  | 2007-10-19 | 2007-04-02 |  |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00448 | 48 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00548 | 48 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00748 | 48 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00848 | 48 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00948 | 48 | 09 - Thus |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-03-23 | 479
3C | ULE90130-03-UTL-00049 | 49 | 00 - Composite |  | Programmed | [8 empty] | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-04-06 | 493
3C | ULE90130-03-UTL-00149 | 49 | 01 - Scotland Gas Networks |  | Programmed | 2007-10-04 | 2007-04-02 | 2007-10-18 | 2007-04-02 | 2007-10-19 | 2007-04-02 | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-04-06 | 493
3C | ULE90130-03-UTL-00249 | 49 | 02 - Scottish Power |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-04-06 | 493
3C | ULE90130-03-UTL-00349 | 49 | 03 - Scottish Water - Clean | Conflict | Programmed | 2007-10-04 | 2007-02-22 | 2007-10-18 |  | 2007-10-19 | 2007-04-02 |  |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-04-06 | 493
3C | ULE90130-03-UTL-00449 | 49 | 04 - Scottish Water - Foul |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-04-06 | 493
3C | ULE90130-03-UTL-00549 | 49 | 05 - BT Openreach |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-04-06 | 493
3C | ULE90130-03-UTL-00749 | 49 | 07 - Virgin Media |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-04-06 | 493
3C | ULE90130-03-UTL-00849 | 49 | 08 - Cable & Wireless |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-04-06 | 493
3C | ULE90130-03-UTL-00949 | 49 | 09 - Thus |  | Programmed | [6 empty] | 2007-10-12 |  | 2007-07-27 | 2007-11-02 |  | 2007-11-16 |  |  | 2007-11-23 |  | 2007-11-27 |  | 2007-11-30 |  | 2009-04-06 | 493
Note on L299: JMcAloon: Previously Issued to SDS on 10-May-07.

## Plates and Worksites
Section | Sub-Section | Work Site Reference | Worksite Location From | Worksite Location To | New Worksite Location From | New Worksite Location To | Plate No's | AMIS Rev 05 Construction Start Dates | Design Issue Order No
1 | 1A1 | 1AWSI003/000 | Casino Square | Casino Square | Casino Square | Casino Square | 15 | 2007-04-02 | 1 | ULE90130-01-UTL-00015 | ULE90130-01-UTL-000
1 | 1A1 | 1AWSI005/000 | Ocean Terminal Advance Works | Ocean Terminal Advance Works | Ocean Terminal Advance Works | Ocean Terminal Advance Works | 6,7,8 | 2007-05-28 | 2 | ULE90130-01-UTL-0006, | ULE90130-01-UTL-000,8
1 | 1A1 | 1AWSI003/001 | Tower Street | Tower Wharf | Tower Street | Tower Wharf | 15 | 2007-07-02 | 3 | ULE90130-01-UTL-00015 | ULE90130-01-UTL-000
1 | 1A1 | 1AWSI003/002 | Tower Wharf | Tower Place Roundabout | Tower Wharf | Tower Place Roundabout | 13,14,15 | 2007-07-02 | 3 | ULE90130-01-UTL-00013
1 | 1A1 | 1AWSI004/001 | Tower Place Roundabout | Commercial Wharf | Tower Place Roundabout | Commercial Wharf | 13 | 2007-07-02 | 3 | ULE90130-01-UTL-00013 | ULE90130-01-UTL-000
1 | 1B | 1BWSI001/001 | Croall Place | Croall Place | Croall Place | Croall Place | 31 | 2007-08-06 | 4 | ULE90130-01-UTL-00031
1 | 1B | 1BWSI001/002 | Croall Place | Pilrig Place | Croall Place | Pilrig Place | 29,30,31 | 2007-08-13 | 5 | ULE90130-01-UTL-00029 | ULE90130-01-UTL-00030
5 | 5A | 5WSI009/001 | Murrayfield Tram Stop | Roseburn Rail Junction | Murrayfield Tram Stop | Roseburn Rail Junction | 1,2 | 2007-08-20 | 6 | ULE90130-05-UTL-0001,
5 | 5A | 5WSI009/002 | Roseburn Rail Junction | Russell Road | Roseburn Rail Junction | Russell Road | 1 | 2007-08-20 | 6
6 | 6A | 6WSI001/001/WP1 | Gogarburn Tram Depot | Gogarburn Tram Depot | Gogarburn Tram Depot | Gogarburn Tram Depot | 1,2 | 2007-08-20 | 6 | ULE90130-06-UTL-0001,
6 | 6A | 6WSI001/002/WP1 | Gogarburn Tram Depot | Gogarburn Tram Depot | Gogarburn Tram Depot | Gogarburn Tram Depot | 1,2 | 2007-08-20 | 6 | ULE90130-06-UTL-0001,
6 | 6A | 6WSI001/002/WP2 | Gogarburn Tram Depot | Gogarburn Tram Depot | Gogarburn Tram Depot | Gogarburn Tram Depot | 1,2 | 2007-08-20 | 6 | ULE90130-06-UTL-0001, | ULE90130-06-UTL-000 | ULE90130-06-UTL-000
5 | 5A | 5WSI008/002 | Roseburn Street | Murrayfield Tram Stop | Roseburn Street | Murrayfield Tram Stop | 2,3 | 2007-08-27 | 7 | ULE90130-05-UTL-0002,
1 | 1A1 | 1AWSI002/005 | Constitution Street | Elbe Street | Constitution Street | Elbe Street | nop | 2007-09-10 | 8 | ULE90130-01-UTL-000no | ULE90130-01-UTL-000
1 | 1A1 | 1AWSI004/002 | Commercial Wharf | Pennies Isle Bridge RHS | Commercial Wharf | Victoria Dock Entrance Bridge RHS | 11,12 | 2007-09-10 | 8 | ULE90130-01-UTL-00001 | ULE90130-01-UTL-0000, | ULE90130-01-UTL-00002
1 | 1A1 | 1AWSI005/001 | Pennies Isle Bridge RHS | Ocean Terminal RHS | Victoria Dock Entrance Bridge RHS | Ocean Terminal RHS | 9,10,11 | 2007-10-01 | 9 | ULE90130-01-UTL-00009 | ULE90130-01-UTL-00010 | ULE90130-01-UTL-00011
7 | 7B | 7BWSI001/002 | Edinburgh Airport Terminal | Gogar Bridge Road (North) | Edinburgh Airport Terminal | Gogar Bridge Road (North) | 8 | 2007-10-01 | 9 | ULE90130-07-UTL-00008 | ULE90130-07-UTL-0000 | ULE90130-07-UTL-0000
7 | 7B | 7BWSI001/004 | Edinburgh Hilton Hotel | Gogar Mains Opening | Edinburgh Hilton Hotel | Gogar Mains Opening | 7 | 2007-10-01 | 9 | ULE90130-07-UTL-00007 | ULE90130-07-UTL-0000
5 | 5C | 5WSI001/001 | Gogarburn Tram Stop | Gogarburn A8 Roundabout | Gogarburn Tram Stop | Gogarburn A8 Roundabout | 24,25,26 | 2007-10-15 | 10 | ULE90130-05-UTL-00002 | ULE90130-05-UTL-0000,
5 | 5B | 5WSI005/001 | Edinburgh Park Train Stop | South Gyle Access Tram Stop | Edinburgh Park Train Stop | South Gyle Access Tram Stop | 16,17,18 | 2007-10-15 | 10 | ULE90130-05-UTL-00001 | ULE90130-05-UTL-0000, | ULE90130-05-UTL-00007
5 | 5B | 5WSI006/002 | Forrester High School (West) | Saughton Road North Tram Stop | Forrester High School (West) | Saughton Road North Tram Stop | 11,12,13,14 | 2007-10-15 | 10 | ULE90130-05-UTL-00001
6 | 6A | 6WSI001/001/WP2 | Gogarburn Tram Depot | Gogarburn Tram Depot | Gogarburn Tram Depot | Gogarburn Tram Depot | 1,2 | 2007-10-15 | 10 | ULE90130-06-UTL-00001 | ULE90130-06-UTL-00002
7 | 7B | 7BWSI001/003 | Gogar Bridge Road (North) | Edinburgh Hilton Hotel | Gogar Bridge Road (North) | Edinburgh Hilton Hotel | 8 | 2007-10-15 | 10 | ULE90130-07-UTL-00008 | ULE90130-07-UTL-0000
1 | 1B | 1BWSI001/003 | Pilrig Place | Iona Street | Pilrig Place | Iona Street | 28,29 | 2007-10-22 | 11 | ULE90130-01-UTL-00028
5 | 5B | 5WSI007/001 | Saughton Road North Tram Stop | Carrick Knowe Avenue | Saughton Road North Tram Stop | Carrick Knowe Avenue | 9,10,11 | 2007-10-22 | 11 | ULE90130-05-UTL-0009, | ULE90130-05-UTL-0000, | ULE90130-05-UTL-0001
1 | 1B | 1BWSI001/004 | Iona Street | Balfour Place | Iona Street | Balfour Street | 26,27,28 | 2007-10-29 | 12 | ULE90130-01-UTL-00026 | ULE90130-01-UTL-00027
1 | 1C2 | 1CWSI002/002 | South St. David Street | South St. Andrew Street (Low End) | The Mound | Waverley Bridge | 42,43,44 | 2007-10-29 | 12 | ULE90130-01-UTL-00042 | ULE90130-01-UTL-00043 | ULE90130-01-UTL-00044
5 | 5B | 5WSI007/002 | Carrick Knowe Avenue | Balgreen Road Tram Stop | Carrick Knowe Avenue | Balgreen Road Tram Stop | 6,7,8,9 | 2007-10-29 | 12 | ULE90130-05-UTL-0006,
5 | 5A | 5WSI008/001 | Balgreen Road Tram Stop | Roseburn Street | Balgreen Road Tram Stop | Roseburn Street | 3,4,5,6 | 2007-10-29 | 12 | ULE90130-05-UTL-0003, | ULE90130-05-UTL-000,5
1 | 1A2 | 1AWSI001/001 | Duke Street Junction | Duke Street Junction | Duke Street Junction | Duke Street Junction | 21,22 | 2007-11-05 | 13 | ULE90130-01-UTL-00021 | ULE90130-01-UTL-00022
1 | 1A2 | 1AWSI001/003 | Laurie Andrews Street | Coatfield Lane | Laurie Street | Coatfield Lane | 18,19 | 2007-11-05 | 13 | ULE90130-01-UTL-00018
1 | 1A2 | 1AWSI001/002 | Duke Street Junction | Laurie Andrews Street | Duke Street Junction | Laurie Street | 20,21 | 2007-11-12 | 14 | ULE90130-01-UTL-00020
1 | 1C2 | 1CWSI002/001 | The Mound | South St. Davids Street | The Mound | The Mound | 44 | 2007-11-19 | 15 | ULE90130-01-UTL-00044 | ULE90130-01-UTL-000
2 | 2 | 2WSI001/003 | Easter Dalry Road | Haymarket Train Station | Easter Dalry Road | Haymarket Train Station | 1 | 2007-11-26 | 16 | ULE90130-02-UTL-0001
5 | 5B | 5WSI004/001 | Edinburgh Park Tram Stop | Edinburgh Park Train Stop | Edinburgh Park Tram Stop | Edinburgh Park Train Stop | 18,19,20 | 2007-12-03 | 17 | ULE90130-05-UTL-00018 | ULE90130-05-UTL-00019 | ULE90130-05-UTL-00020
1 | 1A2 | 1AWSI001/004 | Coatfield Lane | Constitution Street South | Coatfield Lane | Queen Charlotte Street Junction | 18 | 2007-12-10 | 18 | ULE90130-01-UTL-00018
5 | 5C | 5WSI003/001 | The Gyle Tram Stop | Edinburgh Park Tram Stop | The Gyle Tram Stop | Edinburgh Park Tram Stop | 20,21,22,23 | 2007-12-10 | 18 | ULE90130-05-UTL-00020 | ULE90130-05-UTL-00021 | ULE90130-05-UTL-00022
1 | 1D | 1DWSI004/001 | Lothian Road Junction | Lothian Road Junction | Lothian Road Junction | Lothian Road Junction | 50 | 2008-01-04 | 19 | ULE90130-01-UTL-00050
1 | 1C2 | 1CWSI001/001 | The Mound | The Mound | No. 110 Princes Street | The Mound | 44,45,46 | 2008-01-07 | 20 | ULE90130-01-UTL-00044 | ULE90130-01-UTL-00045
5 | 5C | 5WSI001/002/Verizon | Gogarburn A8 Roundabout | The Gyle Tram Stop | Gogarburn A8 Roundabout | The Gyle Tram Stop | 23,24,25 | 2008-01-07 | 20 | ULE90130-05-UTL-00023
5 | 5B | 5WSI006/001 | South Gyle Access Tram Stop | Forrester High School (West) | South Gyle Access Tram Stop | Forrester High School (West) | 14,15,16 | 2008-01-07 | 20 | ULE90130-05-UTL-00014
5 | 5C | 5WSI007/002/Verizon | Gogarburn A8 Roundabout | The Gyle Tram Stop | Gogarburn A8 Roundabout | The Gyle Tram Stop | 23,24,25 | 2008-01-14 | 21 | ULE90130-05-UTL-00023 | ULE90130-05-UTL-00024
7 | 7B | 7BWSI001/001/WP1 | Edinburgh Airport Terminal | Edinburgh Airport Terminal | Edinburgh Airport Terminal | Edinburgh Airport Terminal | 9 | 2008-01-14 | 21 | ULE90130-07-UTL-0009
7 | 7B | 7BWSI001/001/WP2 | Edinburgh Airport Terminal | Edinburgh Airport Terminal | Edinburgh Airport Terminal | Edinburgh Airport Terminal | 9 | 2008-01-14 | 21 | ULE90130-07-UTL-0009 | ULE90130-07-UTL-000
1 | 1B | 1BWSI002/001 | Balfour Place | Orchardfield Road | Balfour Street | Orchardfield Lane | 26 | 2008-01-21 | 22 | ULE90130-01-UTL-00026 | ULE90130-01-UTL-000
5 | 5C | 5WSI008/001/Verizon | The Gyle Tram Stop | Edinburgh Park Tram Stop | The Gyle Tram Stop | Edinburgh Park Tram Stop | 20,21,22,23 | 2008-01-21 | 22 | ULE90130-05-UTL-00020 | ULE90130-05-UTL-00021
|  | Scottish Power 2*132kV | Cutins Road | Cutins Road | Cutins Road | Cutins Road | ??? | 2008-01-21 | 22 | ULE90130-0-UTL-000?? | ULE90130-0-UTL-000
|  | Scottish Power 2*132kV | The Gyle Tram Stop | Edinburgh Park Tram Stop | The Gyle Tram Stop | Edinburgh Park Tram Stop | ??? | 2008-01-21 | 22 | ULE90130-0-UTL-000?? | ULE90130-0-UTL-000
1 | 1B | 1BWSI002/002 | Orchardfield Road | Springfield Street | Orchardfield Lane | Springfield Street | 25,26 | 2008-01-28 | 23 | ULE90130-01-UTL-00025 | ULE90130-01-UTL-00026
1 | 1A2 | 1AWSI002/002 | Queen Charlotte Street | Baltic Street Junction | Maritime Lane | Bernard Street Junction | 17 | 2008-02-04 | 24 | ULE90130-01-UTL-00017 | ULE90130-01-UTL-000
1 | 1A1 | 1AWSI005/002 | Ocean Terminal RHS | Ocean Terminal LHS | Ocean Terminal RHS | Ocean Terminal LHS | 7,8,9 | 2008-02-04 | 24 | ULE90130-01-UTL-0007, | ULE90130-01-UTL-000,9
1 | 1A1 | 1AWSI006/001 | Ocean Terminal LHS | Britannia Yacht Road | Ocean Terminal LHS | Britannia Yacht Road | 6,7 | 2008-02-04 | 24 | ULE90130-01-UTL-0006,
1 | 1D | 1DWSI005/003 | Castle Street | South Lane | Castle Street | No. 110 Princes Street | 47 | 2008-02-04 | 24 | ULE90130-01-UTL-00047 | ULE90130-01-UTL-000
1 | 1A2 | 1AWSI002/001 | Constitution Street South | Queen Charlotte Street | Queen Charlotte Street Junction | Maritime Lane | 17,18 | 2008-02-11 | 25 | ULE90130-01-UTL-00017 | ULE90130-01-UTL-00018
1 | 1D | 1DWSI005/002 | South Charlotte Street East | Castle Street | South Charlotte Street East | Castle Street | 48 | 2008-02-11 | 25 | ULE90130-01-UTL-00048
1 | 1D | 1DWSI004/002 | Lothian Road Junction | South Charlotte Street West | Lothian Road Junction | South Charlotte Street West | 49 | 2008-02-18 | 26 | ULE90130-01-UTL-00049 | ULE90130-01-UTL-000
1 | 1D | 1DWSI005/001 | South Charlotte Street Junction | South Charlotte Street Junction | South Charlotte Street Junction | South Charlotte Street Junction | 49 | 2008-02-18 | 26 | ULE90130-01-UTL-00049 | ULE90130-01-UTL-000
1 | 1B | 1BWSI003/001 | Springfield Street | Stead's Place | Springfield Street | Stead's Place | 24,25 | 2008-03-03 | 27 | ULE90130-01-UTL-00024 | ULE90130-01-UTL-00025
2 | 2 | 2WSI001/001 | Roseburn Sub-Station | Dalry Terrace | Roseburn Sub-Station | Dalry Terrace | 2,3 | 2008-03-03 | 27 | ULE90130-02-UTL-0002, | ULE90130-02-UTL-000
2 | 2 | 2WSI001/002 | Dalry Terrace | Easter Dalry Road | Dalry Terrace | Easter Dalry Road | 1,2 | 2008-03-03 | 27 | ULE90130-02-UTL-0001,
1 | 1B | 1BWSI003/002 | Stead's Place | Jane Street | Stead's Place | Jane Street | 24 | 2008-03-10 | 28 | ULE90130-01-UTL-00024
1 | 1D | 1DWSI003/002 | Shandwick Place East End | Princes Street West End | Shandwick Place East End | Princes Street West End | 50,51 | 2008-03-10 | 28 | ULE90130-01-UTL-00050
5 | 5C | 5WSI002/001 | Gogarburn A8 Roundabout | The Gyle Tram Stop | Gogarburn A8 Roundabout | The Gyle Tram Stop | 23,24 | 2008-03-10 | 28 | ULE90130-05-UTL-00023
7 | 7A | 7AWSE003/002 | Gogar Mains Farm Road | Gogarburn Tram Stop | Gogar Mains Farm Road | Gogarburn Tram Stop | 1,2,3 | 2008-03-10 | 28 | ULE90130-07-UTL-0001,
7 | 7A | 7AWSE003/001 | Gogar Mains Farm Road | Gogar Mains Farm Road | Gogar Mains Farm Road | Gogar Mains Farm Road | 3 | 2008-03-17 | 29 | ULE90130-07-UTL-00003 | ULE90130-07-UTL-0000
1 | 1A2 | 1AWSI002/003 | Leith Assembly Rooms | Maritime Street Junction | Bernard Street Junction | Bernard Street Junction | 16,17 | 2008-03-24 | 30 | ULE90130-01-UTL-00001 | ULE90130-01-UTL-0000,
7 | 7A | 7AWSI002/001 | Gogar Mains Opening | Ingliston Park & Ride | Gogar Mains Opening | Ingliston Park & Ride | 6,7 | 2008-03-24 | 30 | ULE90130-07-UTL-00006
7 | 7A | 7AWSI002/003 | Gogarstone Road | Gogar Mains | Gogarstone Road | Gogar Mains | 5 | 2008-03-24 | 30 | ULE90130-07-UTL-00005 | ULE90130-07-UTL-0000 | ULE90130-07-UTL-0000 | ULE90130-07-UTL-0000 | ULE90130-07-UTL-0000
7 | 7B | 7BWSI001/001/WP6 | Edinburgh Airport Terminal | Edinburgh Airport Terminal | Edinburgh Airport Terminal | Edinburgh Airport Terminal | 9 | 2008-03-24 | 30 | ULE90130-07-UTL-00009 | ULE90130-07-UTL-0000
1 | 1C2 | 1CWSI002/003 | South St. Andrew Street (Low End) | South St. Andrew St (Top End) | Waverley Bridge Junction | Waverley Bridge Junction | 42 | 2008-03-31 | 31 | ULE90130-01-UTL-00004 | ULE90130-01-UTL-0000 | ULE90130-01-UTL-0000 | ULE90130-01-UTL-0000
7 | 7A | 7AWSI002/004 | Gogar Mains | Gogar Mains Farm Road | Gogar Mains | Gogar Mains Farm Road | 3,4,5 | 2008-03-31 | 31 | ULE90130-07-UTL-00003 | ULE90130-07-UTL-0004, | ULE90130-07-UTL-000
7 | 7B | 7BWSI001/001/WP3 | Edinburgh Airport Terminal | Edinburgh Airport Terminal | Edinburgh Airport Terminal | Edinburgh Airport Terminal | 9 | 2008-03-31 | 31 | ULE90130-07-UTL-0009 | ULE90130-07-UTL-000 | ULE90130-07-UTL-000
1 | 1A2 | 1AWSI002/004 | Maritime Street Junction | Tower Street | Bernard Street Junction | Tower Street | 16 | 2008-04-07 | 32 | ULE90130-01-UTL-00016
1 | 1A1 | 1AWSI006/002 | Britannia Yacht Road | North Leith Sands | Britannia Yacht Road | North Leith Sands | 5,6 | 2008-04-07 | 32 | ULE90130-01-UTL-0005,
1 | 1A1 | 1AWSI007/001 | North Leith Sands | Anchor Fields | North Leith Sands | MUDFA Entrance | 3,4,5 | 2008-04-07 | 32 | ULE90130-01-UTL-0003, | ULE90130-01-UTL-000,5
1 | 1B | 1BWSI003/004 | Manor Gordon Street | Crown Place | Crown Street | Crown Place | 22,23 | 2008-04-07 | 32 | ULE90130-01-UTL-00022 | ULE90130-01-UTL-00023 | ULE90130-01-UTL-000
1 | 1D | 1CWSI007/001 | Gayfield Street South | Gayfield Street North | Gayfield Square South | Annandale Street | 33,34 | 2008-04-07 | 32 | ULE90130-01-UTL-00033 | ULE90130-01-UTL-00034 | ULE90130-01-UTL-000
1 | 1D | 1CWSI008/001 | Gayfield Street North | Brunswick Street | Annandale Street | Brunswick Street | 32,33 | 2008-04-07 | 32 | ULE90130-01-UTL-00032 | ULE90130-01-UTL-00033
7 | 7B | 7BWSI001/001/WP7 | Edinburgh Airport Terminal | Edinburgh Airport Terminal | Edinburgh Airport Terminal | Edinburgh Airport Terminal | 9 | 2008-04-07 | 32 | ULE90130-07-UTL-0009 | ULE90130-07-UTL-000 | ULE90130-07-UTL-000 | ULE90130-07-UTL-000
1 | 1B | 1BWSI003/003 | Jane Street | Manor Gordon Street | Jane Street | Crown Street | 23 | 2008-04-21 | 33 | ULE90130-01-UTL-00023 | ULE90130-01-UTL-000 | ULE90130-01-UTL-000 | ULE90130-01-UTL-000
1 | 1C2 | 1CWSI003/001 | South St. Andrew St (Top End) | St. Andrew Square Central | South St. Andrew Street | St. Andrew Square Central | 41 | 2008-04-21 | 33 | ULE90130-01-UTL-00041 | ULE90130-01-UTL-000 | ULE90130-01-UTL-000 | ULE90130-01-UTL-000
1 | 1B | 1BWSI003/005 | Crown Place | Duke Street Junction | Crown Place | Duke Street Junction | 22 | 2008-04-28 | 34 | ULE90130-01-UTL-00022 | ULE90130-01-UTL-000 | ULE90130-01-UTL-000 | ULE90130-01-UTL-000
1 | 1C2 | 1CWSI003/002 | St. Andrew Square Central | St. Andrew Square Central | St. Andrew Square Central | St. Andrew Square Central | 40 | 2008-05-05 | 35 | ULE90130-01-UTL-00040 | ULE90130-01-UTL-000 | ULE90130-01-UTL-000
1 | 1A1 | 1AWSI008/001 | Hawthornvale | Newhaven Roundabout | Hawthornvale | Newhaven Roundabout | 1,2 | 2008-05-26 | 36 | ULE90130-01-UTL-0001, | ULE90130-01-UTL-000 | ULE90130-01-UTL-000
1 | 1C2 | 1CWSI002/004 | South St. Andrews Street (Closed) | South St. Andrew Street (Closed) | Waverley Bridge | South St. Andrew Street | 41,42 | 2008-05-26 | 36 | ULE90130-01-UTL-00041
1 | 1C2 | 1CWSI003/003 | St. Andrew Square Central | North St. Andrew Street | St. Andrew Square Central | North St. Andrew Street | 39,40 | 2008-06-09 | 37 | ULE90130-01-UTL-00039 | ULE90130-01-UTL-00040 | ULE90130-01-UTL-000 | ULE90130-01-UTL-000
1 | 1C1 | 1CWSI006/001 | Union Street | Gayfield Street South | Union Street | Gayfield Square South | 34,35 | 2008-06-09 | 37 | ULE90130-01-UTL-00034 | ULE90130-01-UTL-00035
1 | 1C1 | 1CWSI005/001 | Picardy Place | Union Street | Picardy Place | Union Street | 35,36 | 2008-06-16 | 38 | ULE90130-01-UTL-00035 | ULE90130-01-UTL-00036 | ULE90130-01-UTL-000 | ULE90130-01-UTL-000
1 | 1A1 | 1AWSI007/002 | Anchor Fields | Lindsay Road Junction | MUDFA Entrance | Lindsay Road Junction | 3 | 2008-06-23 | 39 | ULE90130-01-UTL-0003 | ULE90130-01-UTL-000
1 | 1D | 1DWSI003/001 | Canning Street | Stafford Street | Canning Street | Stafford Street | 51,52 | 2008-06-23 | 39 | ULE90130-01-UTL-00051 | ULE90130-01-UTL-00052 | ULE90130-01-UTL-000
1 | 1C2 | 1CWSI003/004 | North St. Andrew Street | York Place West End | North St. Andrew Street | York Place West End | 39 | 2008-06-30 | 40 | ULE90130-01-UTL-00039 | ULE90130-01-UTL-000 | ULE90130-01-UTL-000
1 | 1A1 | 1AWSI007/003 | Lindsay Road Junction | Hawthornvale | Lindsay Road Junction | Hawthornvale | 2,3 | 2008-07-02 | 41 | ULE90130-01-UTL-0002, | ULE90130-01-UTL-000
1 | 1D | 1DWSI002/001 | West Maitland Street | Canning Street | West Maitland Street | Canning Street | 52,53 | 2008-07-07 | 42 | ULE90130-01-UTL-00052 | ULE90130-01-UTL-00053 | ULE90130-01-UTL-000 | ULE90130-01-UTL-000
1 | 1C1 | 1CWSI004/004 | Broughton Street Junction | Picardy Place | Broughton Street Junction | Picardy Place | 36,37 | 2008-07-21 | 43 | ULE90130-01-UTL-00036 | ULE90130-01-UTL-00037 | ULE90130-01-UTL-000
1 | 1D | 1DWSI001/005 | Manor Place Junction | Manor Place Junction | Manor Place Junction | Manor Place Junction | 53,54 | 2008-07-21 | 43 | ULE90130-01-UTL-00053 | ULE90130-01-UTL-00054 | ULE90130-01-UTL-000
1 | 1C1 | 1CWSI004/003 | Broughton Street | Broughton Street Junction | Broughton Street Junction | Broughton Street Junction | 36,37 | 2008-07-28 | 44 | ULE90130-01-UTL-00036 | ULE90130-01-UTL-00037 | ULE90130-01-UTL-000
3 | 3A | 3AWSI001/001 | Roseburn Sub-Station | Water of Leith Bridge | Roseburn Sub-Station | Water of Leith Bridge | 1,2,3,4,5 | 2008-08-18 | 45 | ULE90130-03-UTL-0001, | ULE90130-03-UTL-000,3 | ULE90130-03-UTL-0004, | ULE90130-03-UTL-000
3 | 3A | 3AWSI002/001 | Water of Leith Bridge | Water of Leith Bridge | Water of Leith Bridge | Water of Leith Bridge | 5,6 | 2008-08-25 | 46 | ULE90130-03-UTL-00005 | ULE90130-03-UTL-0006 | ULE90130-03-UTL-000
3 | 3A | 3AWSI002/002 | Water of Leith Bridge | Ravelston Dykes Tram Stop | Water of Leith Bridge | Ravelston Dykes Tram Stop | 6,7,8,9 | 2008-09-01 | 47 | ULE90130-03-UTL-00006 | ULE90130-03-UTL-00007 | ULE90130-03-UTL-00008 | ULE90130-03-UTL-00009
1 | 1C2 | 1CWSI004/001 | York Place West End | Elder Street East | York Place West End | Elder Street East | 38,39 | 2008-09-08 | 48 | ULE90130-01-UTL-00038 | ULE90130-01-UTL-00039 | ULE90130-01-UTL-000
1 | 1C2 | 1CWSI004/002 | Elder Street East | Broughton Street | Elder Street East | Broughton Street | 37,38 | 2008-09-08 | 48 | ULE90130-01-UTL-00003 | ULE90130-01-UTL-0000, | ULE90130-01-UTL-00008 | ULE90130-01-UTL-0000
1 | 1D | 1DWSI001/004 | Palmerston Place | Torpichen Street | Palmerston Place | Torpichen Street | 54 | 2008-09-15 | 49 | ULE90130-01-UTL-00054 | ULE90130-01-UTL-000 | ULE90130-01-UTL-000 | ULE90130-01-UTL-000
3 | 3A | 3AWSI003/001 | Upper Colt Bridge | Craigleith Drive | Upper Colt Bridge | Craigleith Drive | 9,10,11 | 2008-09-15 | 49 | ULE90130-03-UTL-00009 | ULE90130-03-UTL-00001
1 | 1D | 1DWSI001/003 | Grosvener Street | Palmerston Place | Grosvener Street | Palmerston Place | 54,55 | 2008-09-29 | 50 | ULE90130-01-UTL-00005 | ULE90130-01-UTL-0000,
3 | 3A | 3AWSI003/002 | Craigleith Drive | Blinkbonny Road | Craigleith Drive | Blinkbonny Road | 12,13,14 | 2008-09-29 | 50 | ULE90130-03-UTL-00001
3 | 3A | 3AWSI003/003/WP1 | Blinkbonny Crescent Bridge | Blinkbonny Crescent Bridge | Blinkbonny Crescent Bridge | Blinkbonny Crescent Bridge | 14 | 2008-10-06 | 51 | ULE90130-03-UTL-00001 | ULE90130-03-UTL-0000
1 | 1D | 1DWSI001/002 | Dalry Road Junction | Grosvener Street | Dalry Road Junction | Grosvener Street | 55,56 | 2008-10-13 | 52 | ULE90130-01-UTL-00005 | ULE90130-01-UTL-0000,
3 | 3A | 3AWSI003/003/WP2 | Queensferry Road | Queensferry Road | Queensferry Road | Queensferry Road | 15 | 2008-10-13 | 52 | ULE90130-03-UTL-00001 | ULE90130-03-UTL-0000
3 | 3A | 3AWSI003/004 | Queensferry Road North Side | Craigleith Tram Stop | Queensferry Road North Side | Craigleith Tram Stop | 15,16 | 2008-10-20 | 53 | ULE90130-03-UTL-00001 | ULE90130-03-UTL-0000,
1 | 1D | 1DWSI001/001 | Haymarket Station | Dalry Road Junction | Haymarket Station | Dalry Road Junction | 56 | 2008-10-27 | 54 | ULE90130-01-UTL-00005
3 | 3A | 3AWSI004/001 | Craigleith Tram Stop | Groathill Road | Craigleith Tram Stop | Groathill Road | 16,17,18 | 2008-10-27 | 54 | ULE90130-03-UTL-00001 | ULE90130-03-UTL-0000, | ULE90130-03-UTL-00007
3 | 3A | 3AWSI004/002 | Groathill Road | Telford Way South Side | Groathill Road | Telford Way South Side | 18,19,20 | 2008-11-03 | 55 | ULE90130-03-UTL-00001 | ULE90130-03-UTL-0000,
3 | 3A | 3AWSI004/003 | Telford Way South Side | Telford Way Tram Stop | Telford Way South Side | Telford Way Tram Stop | 20,21 | 2008-11-10 | 56 | ULE90130-03-UTL-00002 | ULE90130-03-UTL-0000,
3 | 3A | 3AWSI005/001 | Telford Way Tram Stop | Wt'n General Hosp.Tram Stop | Telford Way Tram Stop | Wt'n General Hosp.Tram Stop | 21,22,23,24 | 2008-11-17 | 57 | ULE90130-03-UTL-00002
3 | 3A | 3AWSI006/001 | Wt'n General Hosp.Tram Stop | Crewe Toll Tram Stop | Wt'n General Hosp.Tram Stop | Crewe Toll Tram Stop | 24,25,26,27 | 2008-11-24 | 58 | ULE90130-03-UTL-00002 | ULE90130-03-UTL-0000, | ULE90130-03-UTL-00005
3 | 3B | 3BWSI001/001 | Crewe Toll Tram Stop | West Pilton Place | Crewe Toll Tram Stop | West Pilton Place | 28,29,30,31 | 2008-12-01 | 59 | ULE90130-03-UTL-00002
3 | 3C | 3BWSI002/002 | Granton Road | Granton Road | Granton Road | Granton Road | 37,38,39 | 2008-12-01 | 59 | ULE90130-03-UTL-00003
3 | 3C | 3BWSI002/003 | Granton Road | Caroline Park Tram Stop | Granton Road | Caroline Park Tram Stop | 40 | 2009-01-05 | 60 | ULE90130-03-UTL-00004
3 | 3B | 3BWSI001/002/WP1 | West Pilton Place | Wt. Granton Access Tram Stop | West Pilton Place | Wt. Granton Access Tram Stop | 32,33,34,35 | 2009-01-12 | 61 | ULE90130-03-UTL-00003
3 | 3B | 3BWSI002/001 | Wt. Granton Access Tram Stop | Granton Road | Wt. Granton Access Tram Stop | Granton Road | 35,36,37 | 2009-02-02 | 62 | ULE90130-03-UTL-00003
3 | 3C | 3CWSI001/001 | Caroline Park Tram Stop | Granton Waterfront Tram Stop | Caroline Park Tram Stop | Granton Waterfront Tram Stop | 41,42,43,44 | 2009-03-02 | 63 | ULE90130-03-UTL-00004
3 | 3C | 3CWSI002/001 | Granton Waterfront Tram Stop | Chestnut Street | Granton Waterfront Tram Stop | Chestnut Street | 44,45 | 2009-03-16 | 64 | ULE90130-03-UTL-00004
3 | 3C | 3CWSI002/002 | Chestnut Street | West Harbour Road | Chestnut Street | West Harbour Road | 45,46,47,48 | 2009-03-23 | 65 | ULE90130-03-UTL-00004
3 | 3C | 3CWSI002/003 | West Harbour Road | Granton Square Tram Stop | West Harbour Road | Granton Square Tram Stop | 48,49 | 2009-04-06 | 66 | ULE90130-03-UTL-00004
7 | 7A | 7AWSI002/002 | Ingliston Park & Ride | Gogarstone Road | Ingliston Park & Ride | Gogarstone Road | 5,6 |  |  | ULE90130-07-UTL-00005
7 | 7A | 7AWSI004/001 | Ingliston Car Park Phase 2 | Ingliston Car Park Phase 2 | Ingliston Car Park Phase 2 | Ingliston Car Park Phase 2 | 6 |  |  | ULE90130-07-UTL-00006
7 | 7B | 7BWSI001/001/WP4 | Edinburgh Airport Terminal | Edinburgh Airport Terminal | Edinburgh Airport Terminal | Edinburgh Airport Terminal | 9 |  |  | ULE90130-07-UTL-00009
7 | 7B | 7BWSI001/001/WP5 | Edinburgh Airport Terminal | Edinburgh Airport Terminal | Edinburgh Airport Terminal | Edinburgh Airport Terminal | 9
7 | 7B | 7BWSI001/003 Bridge | Eastfield Bridge | Eastfield Bridge | Eastfield Bridge | Eastfield Bridge | 8
|  | Direct Labour | St. Andrew Square Central | St. Andrew Square Central | St. Andrew Square Central | St. Andrew Square Central | ???
|  | Scottish Power 275kV | Tunnel Crossing | Tunnel Crossing | Tunnel Crossing | Tunnel Crossing | ???
|  | Telecom Subcontractor | St. Andrew Square (North Side) | St. Andrew Square Central | St. Andrew Square (North Side) | St. Andrew Square Central | ???

## Chart Data
|  | Buildability Thumbnail Sketches Prepared by AMIS for Scottish Water |  |  |  | SUC Approval - Scotland Gas Networks |  |  |  | SUC Approval - Scottish Power |  |  |  | SUC Approval - Scottish Water (Clean) |  |  |  | SUC Approval - Scottish Water (Foul) |  |  |  | SUC Approval - BT Openreach |  |  |  | SUC Approval - Verizon |  |  |  | SUC Approval - Virgin Media |  |  |  | SUC Approval - Cable & Wireless |  |  |  | SUC Approval - Thus |  |  |  | SUC Approval - Easynet |  |  |  | SUC Approval - Forth Ports |  |  |  | Issue Approved IFC to tie
Week Starting | Week Ending | PLANNED | PLANNED CUM | ACTUAL | ACTUAL CUM | PLANNED | PLANNED CUM | ACTUAL | ACTUAL CUM | PLANNED | PLANNED CUM | ACTUAL | ACTUAL CUM | PLANNED | PLANNED CUM | ACTUAL | ACTUAL CUM | PLANNED | PLANNED CUM | ACTUAL | ACTUAL CUM | PLANNED | PLANNED CUM | ACTUAL | ACTUAL CUM | PLANNED | PLANNED CUM | ACTUAL | ACTUAL CUM | PLANNED | PLANNED CUM | ACTUAL | ACTUAL CUM | PLANNED | PLANNED CUM | ACTUAL | ACTUAL CUM | PLANNED | PLANNED CUM | ACTUAL | ACTUAL CUM | PLANNED | PLANNED CUM | ACTUAL | ACTUAL CUM | PLANNED | PLANNED CUM | ACTUAL | ACTUAL CUM | PLANNED | PLANNED CUM | ACTUAL | ACTUAL CUM
2006-12-30 | 2007-01-05 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0
2007-01-06 | 2007-01-12 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0
2007-01-13 | 2007-01-19 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0
2007-01-20 | 2007-01-26 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0
2007-01-27 | 2007-02-02 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0
2007-02-03 | 2007-02-09 | 0 | 0 |  | 0 | 1 | 1 |  | 0 | 1 | 1 |  | 0 | 1 | 1 |  | 0 |  | 0 |  | 0 | 1 | 1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0
2007-02-10 | 2007-02-16 | 0 | 0 |  | 0 |  | 1 |  | 0 |  | 1 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0
2007-02-17 | 2007-02-23 | 0 | 0 |  | 0 |  | 1 |  | 0 |  | 1 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0
2007-02-24 | 2007-03-02 | 1 | 1 | 1 | 1 |  | 1 |  | 0 |  | 1 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0
2007-03-03 | 2007-03-09 | 0 | 1 |  | 1 |  | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 0 |  | 0 |  | 1 | 1 | 1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0
2007-03-10 | 2007-03-16 | 0 | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 0 |  | 0 |  | 1 |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 1 | 1 | 1
2007-03-17 | 2007-03-23 | 0 | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 0 |  | 0 |  | 1 |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 1 |  | 1
2007-03-24 | 2007-03-30 | 0 | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 0 |  | 0 |  | 1 |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 1 |  | 1
2007-03-31 | 2007-04-06 | 0 | 1 | 3 | 4 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 0 |  | 0 |  | 1 |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 1 |  | 1
2007-04-07 | 2007-04-13 | 0 | 1 |  | 4 | 1 | 2 |  | 1 | 1 | 2 |  | 1 | 1 | 2 |  | 1 | 1 | 1 |  | 0 | 1 | 2 |  | 1 |  | 0 |  | 0 | 1 | 1 |  | 0 | 1 | 1 |  | 0 | 1 | 1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 1 |  | 1
2007-04-14 | 2007-04-20 | 3 | 4 |  | 4 |  | 2 |  | 1 |  | 2 |  | 1 |  | 2 |  | 1 |  | 1 |  | 0 |  | 2 |  | 1 |  | 0 |  | 0 |  | 1 | 6 | 6 |  | 1 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 1 |  | 1
2007-04-21 | 2007-04-27 | 0 | 4 |  | 4 |  | 2 |  | 1 |  | 2 |  | 1 |  | 2 |  | 1 |  | 1 |  | 0 |  | 2 |  | 1 |  | 0 |  | 0 |  | 1 |  | 6 |  | 1 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 | 1 | 1 |  | 0 | 0 | 1 |  | 1
2007-04-28 | 2007-05-04 | 0 | 4 | 7 | 11 | 6 | 8 |  | 1 | 6 | 8 |  | 1 | 6 | 8 |  | 1 | 6 | 7 |  | 0 | 6 | 8 |  | 1 |  | 0 |  | 0 | 6 | 7 |  | 6 | 6 | 7 |  | 0 | 6 | 7 |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 | 1 | 2 |  | 1
2007-05-05 | 2007-05-11 | 0 | 4 | 3 | 14 |  | 8 |  | 1 |  | 8 | 42 | 43 |  | 8 |  | 1 |  | 7 |  | 0 |  | 8 |  | 1 |  | 0 |  | 0 |  | 7 |  | 6 |  | 7 |  | 0 |  | 7 |  | 0 |  | 0 |  | 0 | 3 | 4 |  | 0 | 0 | 2 |  | 1
2007-05-12 | 2007-05-18 | 3 | 7 | 2 | 16 |  | 8 |  | 1 |  | 8 |  | 43 |  | 8 |  | 1 |  | 7 |  | 0 |  | 8 |  | 1 |  | 0 |  | 0 |  | 7 |  | 6 |  | 7 |  | 0 |  | 7 |  | 0 |  | 0 |  | 0 | 3 | 7 |  | 0 | 0 | 2 |  | 1
2007-05-19 | 2007-05-25 | 9 | 16 | 5 | 21 |  | 8 |  | 1 |  | 8 |  | 43 |  | 8 |  | 1 |  | 7 |  | 0 |  | 8 |  | 1 |  | 0 |  | 0 |  | 7 |  | 6 |  | 7 |  | 0 |  | 7 |  | 0 |  | 0 |  | 0 |  | 7 | 3 | 3 | 0 | 2 |  | 1
2007-05-26 | 2007-06-01 | 0 | 16 |  | 21 | 5 | 13 |  | 1 | 5 | 13 |  | 43 | 5 | 13 |  | 1 | 5 | 12 |  | 0 | 5 | 13 |  | 1 | 1 | 1 |  | 0 | 5 | 12 |  | 6 | 5 | 12 |  | 0 | 5 | 12 |  | 0 |  | 0 |  | 0 |  | 7 |  | 3 | 6 | 8 |  | 1
2007-06-02 | 2007-06-08 | 2 | 18 | 9 | 30 | 10 | 23 | 3 | 4 | 10 | 23 |  | 43 | 10 | 23 |  | 1 | 10 | 22 |  | 0 | 10 | 23 | 11 | 12 |  | 1 |  | 0 | 10 | 22 | 22 | 28 | 10 | 22 | 3 | 3 | 10 | 22 |  | 0 | 2 | 2 |  | 0 |  | 7 |  | 3 | 0 | 8 |  | 1
2007-06-09 | 2007-06-15 | 3 | 21 | 8 | 38 | 3 | 26 |  | 4 | 3 | 26 |  | 43 | 3 | 26 | 3 | 4 | 3 | 25 |  | 0 | 3 | 26 |  | 12 |  | 1 |  | 0 | 3 | 25 |  | 28 | 3 | 25 | 5 | 8 | 3 | 25 |  | 0 |  | 2 |  | 0 |  | 7 |  | 3 | 0 | 8 |  | 1
2007-06-16 | 2007-06-22 | 6 | 27 | 0 | 38 | 9 | 35 |  | 4 | 9 | 35 | 17 | 60 | 9 | 35 | 0 | 4 | 9 | 34 | 0 | 0 | 9 | 35 | 0 | 12 |  | 1 | 0 | 0 | 9 | 34 | 0 | 28 | 9 | 34 | 0 | 8 | 9 | 34 | 3 | 3 |  | 2 | 0 | 0 |  | 7 | 0 | 3 | 0 | 8 |  | 1
2007-06-23 | 2007-06-29 | 2 | 29 |  |  | 5 | 40 |  |  | 5 | 40 |  |  | 5 | 40 |  |  | 5 | 39 |  |  | 5 | 40 |  |  |  | 1 |  |  | 5 | 39 |  |  | 5 | 39 |  |  | 5 | 39 |  |  |  | 2 |  |  | 3 | 10 |  |  | 8 | 16
2007-06-30 | 2007-07-06 | 4 | 33 |  |  | 11 | 51 |  |  | 11 | 51 |  |  | 11 | 51 |  |  | 11 | 50 |  |  | 11 | 51 |  |  |  | 1 |  |  | 11 | 50 |  |  | 11 | 50 |  |  | 11 | 50 |  |  |  | 2 |  |  |  | 10 |  |  | 7 | 23
2007-07-07 | 2007-07-13 | 0 | 33 |  |  | 6 | 57 |  |  | 6 | 57 |  |  | 6 | 57 |  |  | 6 | 56 |  |  | 6 | 57 |  |  |  | 1 |  |  | 6 | 56 |  |  | 6 | 56 |  |  | 6 | 56 |  |  | 1 | 3 |  |  | 2 | 12 |  |  | 3 | 26
2007-07-14 | 2007-07-20 | 5 | 38 |  |  | 6 | 63 |  |  | 6 | 63 |  |  | 6 | 63 |  |  | 6 | 62 |  |  | 6 | 63 |  |  |  | 1 |  |  | 6 | 62 |  |  | 6 | 62 |  |  | 6 | 62 |  |  |  | 3 |  |  | 2 | 14 |  |  | 9 | 35
2007-07-21 | 2007-07-27 | 0 | 38 |  |  |  | 63 |  |  |  | 63 |  |  |  | 63 |  |  |  | 62 |  |  |  | 63 |  |  |  | 1 |  |  |  | 62 |  |  |  | 62 |  |  |  | 62 |  |  |  | 3 |  |  | 1 | 15 |  |  | 5 | 40
2007-07-28 | 2007-08-03 | 3 | 41 |  |  | 5 | 68 |  |  | 5 | 68 |  |  | 5 | 68 |  |  | 5 | 67 |  |  | 5 | 68 |  |  |  | 1 |  |  | 5 | 67 |  |  | 5 | 67 |  |  | 5 | 67 |  |  |  | 3 |  |  |  | 15 |  |  | 11 | 51
2007-08-04 | 2007-08-10 | 2 | 43 |  |  | 3 | 71 |  |  | 3 | 71 |  |  | 3 | 71 |  |  | 3 | 70 |  |  | 3 | 71 |  |  |  | 1 |  |  | 3 | 70 |  |  | 3 | 70 |  |  | 3 | 70 |  |  |  | 3 |  |  |  | 15 |  |  | 6 | 57
2007-08-11 | 2007-08-17 | 5 | 48 |  |  | 3 | 74 |  |  | 3 | 74 |  |  | 3 | 74 |  |  | 3 | 73 |  |  | 3 | 74 |  |  |  | 1 |  |  | 3 | 73 |  |  | 3 | 73 |  |  | 3 | 73 |  |  |  | 3 |  |  |  | 15 |  |  | 6 | 63
2007-08-18 | 2007-08-24 | 0 | 48 |  |  | 6 | 80 |  |  | 6 | 80 |  |  | 6 | 80 |  |  | 6 | 79 |  |  | 6 | 80 |  |  |  | 1 |  |  | 6 | 79 |  |  | 6 | 79 |  |  | 6 | 79 |  |  |  | 3 |  |  |  | 15 |  |  | 0 | 63
2007-08-25 | 2007-08-31 | 3 | 51 |  |  | 5 | 85 |  |  | 5 | 85 |  |  | 5 | 85 |  |  | 5 | 84 |  |  | 5 | 85 |  |  |  | 1 |  |  | 5 | 84 |  |  | 5 | 84 |  |  | 5 | 84 |  |  |  | 3 |  |  |  | 15 |  |  | 5 | 68
2007-09-01 | 2007-09-07 | 0 | 51 |  |  |  | 85 |  |  |  | 85 |  |  |  | 85 |  |  |  | 84 |  |  |  | 85 |  |  |  | 1 |  |  |  | 84 |  |  |  | 84 |  |  |  | 84 |  |  |  | 3 |  |  |  | 15 |  |  | 3 | 71
2007-09-08 | 2007-09-14 | 7 | 58 |  |  | 3 | 88 |  |  | 3 | 88 |  |  | 3 | 88 |  |  | 3 | 87 |  |  | 3 | 88 |  |  |  | 1 |  |  | 3 | 87 |  |  | 3 | 87 |  |  | 3 | 87 |  |  |  | 3 |  |  |  | 15 |  |  | 3 | 74
2007-09-15 | 2007-09-21 | 2 | 60 |  |  |  | 88 |  |  |  | 88 |  |  |  | 88 |  |  |  | 87 |  |  |  | 88 |  |  |  | 1 |  |  |  | 87 |  |  |  | 87 |  |  |  | 87 |  |  |  | 3 |  |  |  | 15 |  |  | 6 | 80
2007-09-22 | 2007-09-28 | 0 | 60 |  |  | 7 | 95 |  |  | 7 | 95 |  |  | 7 | 95 |  |  | 7 | 94 |  |  | 7 | 95 |  |  |  | 1 |  |  | 7 | 94 |  |  | 7 | 94 |  |  | 7 | 94 |  |  |  | 3 |  |  |  | 15 |  |  | 5 | 85
2007-09-29 | 2007-10-05 | 9 | 69 |  |  | 27 | 122 |  |  | 27 | 122 |  |  | 27 | 122 |  |  | 27 | 121 |  |  | 27 | 122 |  |  | 23 | 24 |  |  | 27 | 121 |  |  | 27 | 121 |  |  | 27 | 121 |  |  |  | 3 |  |  |  | 15 |  |  | 0 | 85
2007-10-06 | 2007-10-12 | 0 | 69 |  |  |  | 122 |  |  |  | 122 |  |  |  | 122 |  |  |  | 121 |  |  |  | 122 |  |  |  | 24 |  |  |  | 121 |  |  |  | 121 |  |  |  | 121 |  |  |  | 3 |  |  |  | 15 |  |  | 3 | 88
2007-10-13 | 2007-10-19 | 9 | 78 |  |  | 13 | 135 |  |  | 13 | 135 |  |  | 13 | 135 |  |  | 13 | 134 |  |  | 13 | 135 |  |  |  | 24 |  |  | 13 | 134 |  |  | 13 | 134 |  |  | 13 | 134 |  |  |  | 3 |  |  |  | 15 |  |  | 0 | 88
2007-10-20 | 2007-10-26 | 0 | 78 |  |  |  | 135 |  |  |  | 135 |  |  |  | 135 |  |  |  | 134 |  |  |  | 135 |  |  |  | 24 |  |  |  | 134 |  |  |  | 134 |  |  |  | 134 |  |  |  | 3 |  |  |  | 15 |  |  | 7 | 95
2007-10-27 | 2007-11-02 | 0 | 78 |  |  | 9 | 144 |  |  | 9 | 144 |  |  | 9 | 144 |  |  | 9 | 143 |  |  | 9 | 144 |  |  |  | 24 |  |  | 9 | 143 |  |  | 9 | 143 |  |  | 9 | 143 |  |  |  | 3 |  |  |  | 15 |  |  | 27 | 122
2007-11-03 | 2007-11-09 | 0 | 78 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 122
2007-11-10 | 2007-11-16 | 0 | 78 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 13 | 135
2007-11-17 | 2007-11-23 | 0 | 78 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 135
2007-11-24 | 2007-11-30 | 0 | 78 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 9 | 144
2007-12-01 | 2007-12-07 | 0 | 78 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2007-12-08 | 2007-12-14 | 0 | 78 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2007-12-15 | 2007-12-21 | 0 | 78 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2007-12-22 | 2007-12-28 | 0 | 78 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2007-12-29 | 2008-01-04 | 0 | 78 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-01-05 | 2008-01-11 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-01-12 | 2008-01-18 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-01-19 | 2008-01-25 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-01-26 | 2008-02-01 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-02-02 | 2008-02-08 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-02-09 | 2008-02-15 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-02-16 | 2008-02-22 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-02-23 | 2008-02-29 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-03-01 | 2008-03-07 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-03-08 | 2008-03-14 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-03-15 | 2008-03-21 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-03-22 | 2008-03-28 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-03-29 | 2008-04-04 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-04-05 | 2008-04-11 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-04-12 | 2008-04-18 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-04-19 | 2008-04-25 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-04-26 | 2008-05-02 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-05-03 | 2008-05-09 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-05-10 | 2008-05-16 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-05-17 | 2008-05-23 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-05-24 | 2008-05-30 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-05-31 | 2008-06-06 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-06-07 | 2008-06-13 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-06-14 | 2008-06-20 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-06-21 | 2008-06-27 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-06-28 | 2008-07-04 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-07-05 | 2008-07-11 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-07-12 | 2008-07-18 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-07-19 | 2008-07-25 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-07-26 | 2008-08-01 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-08-02 | 2008-08-08 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-08-09 | 2008-08-15 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-08-16 | 2008-08-22 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-08-23 | 2008-08-29 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-08-30 | 2008-09-05 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-09-06 | 2008-09-12 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-09-13 | 2008-09-19 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-09-20 | 2008-09-26 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-09-27 | 2008-10-03 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-10-04 | 2008-10-10 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-10-11 | 2008-10-17 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-10-18 | 2008-10-24 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-10-25 | 2008-10-31 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-11-01 | 2008-11-07 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-11-08 | 2008-11-14 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-11-15 | 2008-11-21 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-11-22 | 2008-11-28 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-11-29 | 2008-12-05 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-12-06 | 2008-12-12 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-12-13 | 2008-12-19 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-12-20 | 2008-12-26 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144
2008-12-27 | 2009-01-02 |  |  |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 144 |  |  | 0 | 143 |  |  | 0 | 144 |  |  | 0 | 24 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 143 |  |  | 0 | 3 |  |  | 0 | 15 |  |  | 0 | 144

## Thumbnail Sketch Data PvA
Status | Programmed
Service Conflict | Conflict
AMIS Thumbnail Sketches Planned
Utility | Data | 2007-03-02 | 2007-04-19 | 2007-05-17 | 2007-05-22 | 2007-05-24 | 2007-06-07 | 2007-06-14 | 2007-06-21 | 2007-06-28 | 2007-07-05 | 2007-07-19 | 2007-08-02 | 2007-08-09 | 2007-08-16 | 2007-08-30 | 2007-09-13 | 2007-09-20 | 2007-10-04 | 2007-10-18 | Grand Total
03 - Scottish Water - Clean | PLANNED AMIS Thumbnail Sketches | 1 | 3 | 3 | 6 | 3 | 2 | 3 | 6 | 2 | 4 | 5 | 3 | 2 | 5 | 3 | 7 | 2 | 9 | 9 | 78
| ACTUAL AMIS Thumbnail Sketches | 1 | 3 | 3 | 6 | 3 | 2 |  | 5 | 2 |  |  |  | 2 |  |  |  | 1 | 8 | 2 | 38
Total PLANNED AMIS Thumbnail Sketches |  | 1 | 3 | 3 | 6 | 3 | 2 | 3 | 6 | 2 | 4 | 5 | 3 | 2 | 5 | 3 | 7 | 2 | 9 | 9 | 78
Total ACTUAL AMIS Thumbnail Sketches |  | 1 | 3 | 3 | 6 | 3 | 2 |  | 5 | 2 |  |  |  | 2 |  |  |  | 1 | 8 | 2 | 38
|  | 02-Mar-07 | 19-Apr-07 | 17-May-07 | 22-May-07 | 24-May-07 | 07-Jun-07 | 14-Jun-07 | 21-Jun-07 | 28-Jun-07 | 05-Jul-07 | 19-Jul-07 | 02-Aug-07 | 09-Aug-07 | 16-Aug-07 | 30-Aug-07 | 13-Sep-07 | 20-Sep-07 | 04-Oct-07 | 18-Oct-07
| Data | 02-Mar-07 | 19-Apr-07 | 17-May-07 | 22-May-07 | 24-May-07 | 07-Jun-07 | 14-Jun-07 | 21-Jun-07 | 28-Jun-07 | 05-Jul-07 | 19-Jul-07 | 02-Aug-07 | 09-Aug-07 | 16-Aug-07 | 30-Aug-07 | 13-Sep-07 | 20-Sep-07 | 04-Oct-07 | 18-Oct-07
| PLANNED AMIS Thumbnail Sketches | 1 | 3 | 3 | 6 | 3 | 2 | 3 | 6 | 2 | 4 | 5 | 3 | 2 | 5 | 3 | 7 | 2 | 9 | 9
| ACTUAL AMIS Thumbnail Sketches | 1 | 3 | 3 | 6 | 3 | 2 |  | 5 | 2 |  |  |  | 2 |  |  |  | 1 | 8 | 2

## Pivot - SUC Approvals
Status | Programmed
|  |  | 1A1 - 13,14,15 | 5A - 1,2,3 & 6A - 1,2 | 1B - 29,30,31 | 1B - 26,27,28 | 5C - 24,25,26,27
SUC Approval Planned Date
Utility | Data | 2007-03-09 | 2007-05-11 | 2007-06-15 | 2007-06-18 | 2007-06-20 | 2007-06-22 | 2007-07-06 | 2007-07-13 | 2007-07-20 | 2007-07-27 | 2007-08-03 | 2007-08-17 | 2007-08-24 | 2007-08-31 | 2007-09-07 | 2007-09-14 | 2007-09-28 | 2007-10-12 | 2007-10-19 | 2007-11-02 | 2007-11-16 | Grand Total
00 - Composite | Planned SUC Approvals | 1 | 3 | 5 | 3 | 3 | 4 | 9 | 3 | 9 | 5 | 6 | 5 | 3 | 3 | 6 | 5 | 3 | 7 | 27 | 13 | 9 | 132
| Actual SUC Approvals | [21 empty] | 1 | bar: 2007-03-09
01 - Scotland Gas Networks | Planned SUC Approvals | 1 | 3 | 5 | 3 | 3 | 4 | 9 | 3 | 9 | 5 | 6 | 5 | 3 | 3 | 6 | 5 | 3 | 7 | 27 | 13 | 9 | 132
| Actual SUC Approvals | 2007-03-09: 1; 2007-05-11: 3 | 4
02 - Scottish Power | Planned SUC Approvals | 1 | 3 | 5 | 3 | 3 | 4 | 9 | 3 | 9 | 5 | 6 | 5 | 3 | 3 | 6 | 5 | 3 | 7 | 27 | 13 | 9 | 132
| Actual SUC Approvals | 2007-03-09: 1; 2007-05-11: 3; 2007-06-15: 5; 2007-06-18: 3; 2007-06-20: 3; 2007-07-06: 9; 2007-07-20: 8; 2007-07-27: 2; 2007-08-03: 2; 2007-10-12: 6; 2007-10-19: 4; 2007-11-02: 9 | 55
03 - Scottish Water - Clean | Planned SUC Approvals | 1 | 3 | 5 | 3 | 3 | 4 | 9 | 3 | 9 | 5 | 6 | 5 | 3 | 3 | 6 | 5 | 3 | 7 | 27 | 13 | 9 | 132
| Actual SUC Approvals | 2007-03-09: 1; 2007-05-11: 3 | 4
04 - Scottish Water - Foul | Planned SUC Approvals |  | 3 | 5 | 3 | 3 | 4 | 9 | 3 | 9 | 5 | 6 | 5 | 3 | 3 | 6 | 5 | 3 | 7 | 27 | 13 | 9 | 131
Actual SUC Approvals
05 - BT Openreach | Planned SUC Approvals | 1 | 3 | 5 | 3 | 3 | 4 | 9 | 3 | 9 | 5 | 6 | 5 | 3 | 3 | 6 | 5 | 3 | 7 | 27 | 13 | 9 | 132
| Actual SUC Approvals | 2007-03-09: 1; 2007-05-11: 3; 2007-06-15: 2; 2007-09-07: 6 | 12
06 - Verizon | Planned SUC Approvals | 2007-06-15: 1; 2007-10-19: 23 | 24
Actual SUC Approvals
07 - Virgin Media | Planned SUC Approvals |  | 3 | 5 | 3 | 3 | 4 | 9 | 3 | 9 | 5 | 6 | 5 | 3 | 3 | 6 | 5 | 3 | 7 | 27 | 13 | 9 | 131
| Actual SUC Approvals | 2007-05-11: 3; 2007-06-15: 5; 2007-07-06: 9; 2007-07-20: 3; 2007-07-27: 1; 2007-08-03: 1; 2007-09-07: 6 | 28
08 - Cable & Wireless | Planned SUC Approvals |  | 3 | 5 | 3 | 3 | 4 | 9 | 3 | 9 | 5 | 6 | 5 | 3 | 3 | 6 | 5 | 3 | 7 | 27 | 13 | 9 | 131
| Actual SUC Approvals | 2007-05-11: 3; 2007-06-18: 3; 2007-06-20: 2 | 8
09 - Thus | Planned SUC Approvals |  | 3 | 5 | 3 | 3 | 4 | 9 | 3 | 9 | 5 | 6 | 5 | 3 | 3 | 6 | 5 | 3 | 7 | 27 | 13 | 9 | 131
| Actual SUC Approvals | 2007-05-11: 3 | 3
10 - Easynet | Planned SUC Approvals | 2007-06-22: 2; 2007-07-27: 1 | 3
Actual SUC Approvals
17 - Forth Ports | Planned SUC Approvals | 2007-05-11: 3 | 3
| Actual SUC Approvals | 2007-05-11: 3 | 3
Total Planned SUC Approvals |  | 5 | 30 | 46 | 27 | 27 | 38 | 81 | 27 | 81 | 46 | 54 | 45 | 27 | 27 | 54 | 45 | 27 | 63 | 266 | 117 | 81 | 1214
Total Actual SUC Approvals |  | 5 | 24 | 12 | 6 | 5 |  | 18 |  | 11 | 3 | 3 |  |  |  | 12 |  |  | 6 | 4 | 9 |  | 118