## Risk
ETP - PHASE 1A COSTS AND FUNDING REVIEW - RISK ALLOWANCE
Categ | Risk ID | Cause | Risk Event | Effect | Prob | Min | Likely | Max | P10 PM Reports | Revised Estimate | Approved Budget | Change | Bal
1 GENERAL/OVERALL | 169 | Concurrent major projects in Edinburgh | Other major projects in Edinburgh interface with Tram | Delay in sequence in certain areas, Additional interface project management costs. | 50 | 100 | 300 | 500 | 151.5052 | 151.5052 | 165.11 | -13.6048
1 GENERAL/OVERALL | 343 | General delay to programme with various causes e.g. failure to obtain approvals on time; parliamentary processes, delays due to lack of prioritisation of BAA agreement with new owners | Delay to completion of project | Inflation at 5% causes increased out-turn cost due to delay plus revenue loss | 40 | 6000 | 12000 | 19000 | 5047.6326 | 10000 | 5342 | 4658
7.3 Infraco | 994 | The design for the lighting has yet to be approved by CECs Street Lighting section | Additional time or cost could be incurred in relation to the street lighting works | Compliance with their requirements may incur abortive works resulting in additional cost and delay to programme | 17.5 |  | 12.5 |  | 2.2169 | 2.2169 | 2.4 | -0.18306 |  | Previously Design
7.3 Infraco | 44 | SDS contractor does not deliver the required prior approval consents before novation | Delay to IFCs beyond V31 Programme | Delay to programme with additional resource costs and delay to Infraco. procurement. Impact upon risk balance. | 50 | 900 | 1800 | 2700 | 1024.0643 | 1024.0643 | 1114.41 | -90.3457 |  | Previously Design
7.3 Infraco | 336 | Adequate scope and extent of noise and vibration prevention measures/requirements are not provided to SDS; Specifications relating o Tram noise provided by Tramco are optimistic. | Design assumptions lead to Tram noise and vibration measures being inadequate during operation | Tram design requires to be re-worked; Post construction elements need to be adjusted or re-constructed or additional noise and vibration measures need to be incorporated. | 10 | 100 |  | 1000 | 56.4709 | 56.4709 | 60.58 | -4.1091 |  | Previously Design
7.3 Infraco | 271 | Inadequate quality of submission of approval. Partial submission of package. Programme compression. Lack of CEC resources. CEC does not follow agreed process. | Failure to process prior approvals applications within 8 weeks | Delay and disruption to Infraco programme | 80 | 750 | 750 | 1000 | 844.4393 | 844.4393 | 914.79 | -70.3507 |  | Previously Design
7.3 Infraco | 279 |  | Third party consents including Network Rail consents are denied or delayed | Delay to programme; Risk transfer response by bidders is to return risk to tie; Increased out-turn cost if transferred and also as a result of any delay due to inflation. | 50 |  | 1250 |  | 712.5874 | 712.5874 | 772.82 | -60.2326 |  | Previously Design
7.3 Infraco | 974 | Inaccurate Topo Survey results | Increase in levels of Spoil Excavation | Increased Cost & Programme extension | 80 | 300 | 400 | 500 | 405.2828 | 405.2828 | 102.87 | 302.4128
7.3 Infraco | 952 | Scope of works relating to Wide Area Modelling (WAM) have not been agreed with SDS because they consider this to be out with the scope of their contract. | Uncertainty about extent of construction works required on road network relating to Wide Area Modelling issues. | Potential claim from SDS to deal with additional design work; Potential construction costs to deal with WAM issues (difficult to quantify without design) over and above those already included. | 95 | 0 |  | 3000 | 1802.4692 | 1802.4692 | 1958.78 | -156.3108
7.3 Infraco | 931 | Utilities assets uncovered during construction that were not previously accounted for; unidentified abandoned utilities assets; known redundant utilities; unknown live utilities; unknown redundant utilities. | Unknown or abandoned assets impacts scope of Infraco work | Re-design and delay as investigation takes place and solution implemented; Increase in Capex cost as a result of additional works. | 90 | 500 |  | 1000 | 684.0757 | 684.0757 | 742.96 | -58.8843
7.3 Infraco | 172 | Area of possible contamination and unstable ground (unlicensed tip) has been highlighted during desk study immediately to east of Gogar Burn - investigation for CERT project indicates that this consists of building rubble and domestic waste. | Tramway runs through area of possible contamination and special foundation is required to cope with unstable ground | Increase in costs to provide special foundation solution | 95 | 900 | 1000 | 1100 | 1203.5169 | 1203.5169 | 261.18 | 942.3369
7.3 Infraco | 105 | Encountering archaeological finds/burials/munitions during construction | Exhumation of archaeological finds/burials | Delay in construction programme | 85 | 0 | 150 | 500 | 210.2111 | 210.2111 | 228.43 | -18.2189
7.3 Infraco | 318 | Failure to make arrangements with Utilities for the phasing of necessary connections; Utility Company operational constraints | Utility connections cannot proceed as planned | Potential delay to start of Infraco works in certain sections | 50 | 100 |  | 500 | 152.3765 | 152.3765 | 167.18 | -14.8035
7.3 Infraco | 173 | Uncertainty over extent of contaminated land/hazardous materials on route | Tramway runs through area of previously unidentified contamination/hazardous materials and material requires to be removed and replaced (dig and dump). | Increase in costs to remove material to special and other tip. | 50 | 1500 | 6000 | 8000 | 2940.1042 | 2940.1042 | 3176.7 | -236.5958
7.3 Infraco | 865 | Buildings contain asbestos that was not uncovered during surveys | Asbestos found during demolition works and excavations for construction | Cost and delay during investigation and removal | 90 | 60 |  | 150 | 95.7361 | 95.7361 | 103.87 | -8.1339
7.3 Infraco | 911 | Scottish Power own and maintain a cable tunnel in the vicinity of Leith Walk that may or may not interfere with Tram construction and operation; exact location and depth of tunnel is unknown; condition of tunnel is unknown. | Presence of Scottish Power tunnel in Leith Walk requires radical solution | Tunnel may have to be decommissioned and re-laid in a more suitable location; tram alignment may require to be adjusted; special foundation solution e.g. cantilever may be required; increased capex; potential for tunnel collapse during operation and | 80 | 400 | 500 | 600 | 506.9719 | 506.9719 | 549.55 | -42.5781
7.3 Infraco | 932 | Information handed over in draft format as part of continual design development; Downstream Tram design change that impacts on requirements; Zone of interference not defined adequately. | SDS gives wrong or insufficient information to Network Rail | Network Rail design their works inappropriately for final Tram requirements; Network Rail are unable to complete their design in time to meet programme; Cost to change design; Delay during redesign; Final works are not suitable and consequently Tram canno | 5 | 100 | 300 | 500 | 19.1818 | 19.1818 | 20.58 | -1.3982
7.3 Infraco | 134 | Network Rail possessions over and above that estimate are required | Compensation paid to Train Operating Companies | Increased compensation paid to Train Operating Companies | 5 | 500 | 2000 | 4000 | 139.376 | 139.376 | 146.17 | -6.794
7.3 Infraco | 115 | Network Rail cancels planned possessions | Planned work at interface with Network Rail is delayed | Time delay and resulting cost increase | 10 | 350 | 750 | 2000 | 134.6005 | 134.6005 | 140.69 | -6.0895
7.3 Infraco | 993 | Due to a terrorism event relating to Edinburgh Airport or due to the mitigation of the risk of such an event occurring traffic restrictions introduced in the vicinity of the airport cause unacceptable delays for vehicles accessing and exiting from the sit | Free access cannot be guaranteed to the P&R site | Delays to construction vehicles could have impact on completion date and cost of construction, delays for car park users or buses could detract from usefulness and viability of facility | 2.5 |  | 12.5 |  | 0.39588 | 0.39588 | 0.43 | -0.034118
7.3 Infraco | 58 | Poor performance (quality) by Infraco during construction; poor materials; latent defects | Infraco fails to deliver construction quality; latent defects occur during or after Infraco maintenance period | Rework, stakeholder criticism, negative PR, programme delay if quality issue occurs during construction, operations affected by rework, project management costs to deal with issues | 10 | 25 | 62.5 | 100 | 6.3645 | 6.3645 | 6.82 | -0.45547
7.3 Infraco | 104 | Delay in design information release from specialist tram manufacturer | Delay in detailing of stops, trackway, OLE etc for Phase 1B | Time delay and consequent costs | 15 | 0 | 25 | 83 | 0 | 0 | 0 | 0
7.3 Infraco | 162 | Land is not acquired yet | Gaining access to land prior to purchase for advanced works | Increased management costs and delays to design | 10 | 0 |  | 30 | 1.4773 | 1.4773 | 1.6 | -0.12268
7.3 Infraco | 5 |  | Over excavation at depot - impact on cost and programme issues still to be finalised and agreed with Tramworks | Additional cost to provide suitable formation. Programme delay. | 80 | 300 | 350 | 400 | 354.7582 | 354.7582 | 0 | 354.7582
7.3 Infraco | 16 | De-watering of Gogar Depot | Movement below track support zone | Costs to NR for track monitoring and any track defects arising | 100 | 50 | 75 | 150 | 116.1253 | 116.1253 | 0 | 116.1253
7.3 Infraco | 35 |  | Roads throughout works require full depth reconstruction | Programme impact plus additional costs. £1.5m cap applies to only 4 areas. Total exposure estimated at £3m | 80 | 2000 | 2250 | 2500 | 2280.8208 | 2280.8208 | 0 | 2280.8208
7.3 Infraco | 49 | Lack of visibility of design changes between November 2007 and May 2008 and in general | Tramworks price based on a design which may have been altered. Unclear who authorised design changes from 25/11/07 onwards.. (ARM ID 1077) | Additional cost from Tramworks to meet revised design. | 80 | 5500 | 6000 | 6500 | 6081.9571 | 6081.9571 | 0 | 6081.9571
|  | QRA Total | [6 empty] | 24974.7184 | 29927.0858 | 15979.92 | 13947.1658
|  | 7.3 Infraco | [6 empty] | 19775.5806 | 19775.5806 | 10472.81 | 9302.7706
|  | 7.2 MUDFA/Utilities | [6 empty] | 0 | 0 | 0 | 0
|  | 5 PARLIAMENTARY PROCESS/ APPROVALS | [6 empty] | 0 | 0 | 0 | 0
|  | 3 Design | [6 empty] | 0 | 0 | 0 | 0
|  | 1.1 Land & Property | [6 empty] | 0 | 0 | 0 | 0
|  | 1 GENERAL/OVERALL | [6 empty] | 5199.1378 | 10151.5052 | 5507.11 | 4644.3952
|  | Other | [6 empty] | 0 | 0 | 0 | 0
|  | QRA by Category | [6 empty] | 24974.7184 | 29927.0858 | 15979.92 | 13947.1658
|  | Non-delivery of VE included in Infraco price | [6 empty] | 2000 | 4290 | 2000 | 2290
|  | Extent of Road Reinstatement | [6 empty] | 1500 | 1500 | 1500 | 0
|  | Risk Allowance Total | [6 empty] | 28474.7184 | 35717.0858 | 19479.92 | 16237.1658 | 0