## Sheet1
Edinburgh Tram Project
Review of SGN Contribution as at 18th August 2008
|  | Reductions £ | Additions £ | Contribution £
Extract from SGN - tie agreement on costs November 2007:
Total SGN Contribution - tie @ 25% Prime Cost O/H @ 9% & Design 2% |  |  |  | 1200379
tie's estimate of SGN Regulatory Income |  |  | 247269 | 1447648
Changes since agreement:
Contribution for MP diversion at Jane Street as diversion now considered to be required |  |  | 9144 | 1456792
SGN request to change pipe diameter in York Place |  | 10454 |  | 1446338
Additional requested works at London Rd junction with Leith Walk CMIS 16833 |  |  | 43286 | 1489624
SGN reinforcement works at Shandwick Place - Queensferry St SCT21602 |  |  | 71611 | 1561235
Section 3b deferred by tie |  | 8458 |  | 1552777
Section 3c deferred by tie |  | 30778 |  | 1521999
Policy related service renewals in Constitution Street and Leith Walk to be undertaken now by SGN |  | 267696 |  | 1254303
| sub totals | 317386 | 124041
Revised SGN contribution |  |  |  | 1254303
Notes:
Changes to replacement lengths in Leith Walk had already been taken into account by November 2007
SGN contribution as at November 2007 did not include the road crossing at Morrison Street.
SGN contribution as at November 2007 included a sum of £267,696 for policy service renewals in Constitution Street and Leith Walk. This work is now assumed to be undertaken by SGN, at SGN's cost.