## Summary 141207
INFRACO NEGOTIATION SUMMARY POSITION
Date:- 18/12/07
| Current |  | Comments
£m
Fixed Elements |  |  | See Appendix A2 for further details
Core contract sum - firm price | 213910342
Provisional elements taken into firm | 0 |  | All previously provisional items taken to firm
VE taken into firm price | -83000
VE taken into firm price - but conditional | -11065006 |  | See conditions referred to in Appendix A3
Premium for current provisional items | 8000000 |  | Negotiated sum for firming up all elements
Total firm price | 210762336 | 95.4%
Provisional Sums | 10170090.2178 |  | Previous normalisations which are still relevant - See Appendix A4
Total Provisional | 10170090.2178
Sub total | 220932426.2178
Remaining Identified VE | -2670000 |  | To be stated in contract with rules for adjustment of price and commitments for both parties work to deliver these items
Anticipated Infraco Contract Sum (Final Deal) | 218262426.2178

## Negotiation Detailed Summary
Item | Prelims | Trackform - System | Depot | Structures - Superstructure | Highways | Tramstops | Buildings | Supervisory & Comms | OLE | Tramstop Equipment | Trams | Reduction as BBS letter 11/10/07 | Reduction for taking CAF into BBS Consortia | Traction Power | Power for commissioning | System Wide | Network Rail | Total
Base
Firm | 75437757 | 43918161 | 18686351 | 31415121 | 11893955 | 3270376 | 3275180 | 5296482 | 14974462 | 1513587 | 1018910 | -1000000 |  |  | 1330000 | -120000 | 3000000 | 213910342
Provisional | [17 empty] | 0
Firm price addition | [15 empty] | 8000000 |  | 8000000
Sub-total Base | 75437757 | 43918161 | 18686351 | 31415121 | 11893955 | 3270376 | 3275180 | 5296482 | 14974462 | 1513587 | 1018910 | -1000000 | 0 | 0 | 1330000 | 7880000 | 3000000 | 221910342
Provisional (See Appendix A4 for details)
Provision of pumped surface water outfall system at A8 underpass |  |  | 100000 | [14 empty] | 100000
Spares not included in Price | [8 empty] | 174762 | [8 empty] | 174762
Scottish Power Connections to Depot and IPR | [8 empty] | 750000 | [8 empty] | 750000
Relocation of Ancient Monuments | 53700 | [16 empty] | 53700
Allowance for minor utility diversions |  | 750000 | [15 empty] | 750000
Archaeological Officer - impact on productivity |  | 405754.5495 | [15 empty] | 405754.5495
Ballast |  | 300000 | [15 empty] | 300000
Piccardy Place, York Place and London Road junction |  |  |  |  | 6340324.3822 | [12 empty] | 6340324.3822
E/O Shell Grip |  |  |  |  | 319343.2872 | [12 empty] | 319343.2872
Mains Power Connection to street lights and traffic signals |  |  |  |  | 115287.2177 | [12 empty] | 115287.2177
Adjust for Network Rail Possessions support |  |  |  | 755307 | [13 empty] | 755307
Leith Walk substation demolition |  |  |  | 55661.7812 | [13 empty] | 55661.7812
Additional Crew Relief Facilities at Haymarket |  |  |  | 49950 | [13 empty] | 49950
Sub-total - Provisional Normalisation | 53700 | 1455754.5495 | 100000 | 860918.7812 | 6774954.8871 | 0 | 0 | 0 | 924762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10170090.2178
Value Engineering
Firm
NR Immunisation. NOW IN FIRM PRICE - SEE ABOVE | [17 empty] | 0
Signalling & Comms - fewer CCTV cameras . Reduced to 55Nr . (Tramstops 45Nr, Depot 10Nr) | [7 empty] | -33000 | [9 empty] | -33000
UPS - reduce capacity from 4hrs to 3hrs | [7 empty] | -50000 | [9 empty] | -50000
0
Sub-total - Firm Value Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -83000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -83000
Firm with conditions
Delete depot pumping station/storm tanks by utilising existing gravity system. |  |  | -193526 | [14 empty] | -193526
Depot - Build part now with provision to expand in the future/reduce size of car park facilities |  |  | -230000 | [14 empty] | -230000
Delete under floor lift plant and utilise mobile jacks. Incl mobile future proofing. |  |  | -250000 | [14 empty] | -250000
Depot - delet split vehicle accommodation system - requirement dependant on tram vehicle selection |  |  | -27500 | [14 empty] | -27500
Depot - Track Maintenance Equipment - rationalise scope requirement and consider renting. |  |  | -27500 | [14 empty] | -27500
Depot - deletion of one pavement (inner) . |  |  | -36000 | [14 empty] | -36000
Depot - delete requirement for concrete apron to security fence |  |  | -6080 | [14 empty] | -6080
Depot - delete compressed air system, utilise 1 or 2 local /mobile compressors |  |  | -54400 | [14 empty] | -54400
Consolidated VE items 7, 10, 11, 19 which results from changes to initial Depot design driven by proximity to BAA runway and EARL decision. |  |  | -2200000 | [14 empty] | -2200000
Delete standby generator and substitute with hardstanding and power connection for portable generator. |  |  | -150000 | [14 empty] | -150000
Material recovery and reprocessing (Infraco); 2 options - reconstituted planings & Type 1R |  |  |  |  | -500000 | [12 empty] | -500000
Reduce Kerb and associated re-instatement of pavement |  |  |  |  | -100000 | [12 empty] | -100000
Reduce drainage run from guideway |  |  |  |  | -100000 | [12 empty] | -100000
Overhead Contact system - Switchgear - rationalise specification - considered "quite onerous" | [8 empty] | -160000 | [8 empty] | -160000
Edinburgh Park Bridge - 7 span to 2 , utilise steel beams in lieu of concrete Edinburgh Park Viaduct |  |  |  | -1470000 | [13 empty] | -1470000
Carricknowe Bridge Parapet - down grade from P6 / P5 to N2 (reduced cost of parapet plus knock on effect on deck design/cost) |  |  |  | -85000 | [13 empty] | -85000
A8 Underpass various initiatives |  |  |  | -850000 | [13 empty] | -850000
Roseburn Street viaduct various initiatives |  |  |  | -1375000 | [13 empty] | -1375000
Water of Leith various intiatives |  |  |  | -150000 | [13 empty] | -150000
Eight maintenance walkway structures - delete or reduce |  |  |  | -250000 | [13 empty] | -250000
Class 7 material conversion - |  |  |  | -300000 | [13 empty] | -300000
Optimise the work site lengths wherever practical to ensure efficient construction outputs | [15 empty] | -300000 |  | -300000
Accept more disruption over shorter period to maximise efficiency of construction operations - | [15 empty] | -100000 |  | -100000
Option to lease UPS provision from Supplier rather than purchase | [15 empty] | -300000 |  | -300000
Rationalising spares supplied with the Infraco bid | [15 empty] | -300000 |  | -300000
PM Integration including shared resources and co-location. | [15 empty] | -1000000 |  | -1000000
Noise attenuation (outside of Roseburn Corridor) 3,650m of fencing |  | -50000 | [15 empty] | -50000
Reduce ballasted track thickness from 300 to 200mm |  | -200000 | [15 empty] | -200000
Power Supply (up to passenger operation) - possible over allowance in DFBC | [13 empty] | -300000 |  |  |  | -300000
Sub-total - Provisional Value Engineering | 0 | -250000 | -3175006 | -4480000 | -700000 | 0 | 0 | 0 | -160000 | 0 | 0 | 0 | 0 | -300000 | 0 | -2000000 | 0 | -11065006
Further project management integration over 3 years | [15 empty] | -500000 |  | -500000
SDS design scope economy, variation and reduction | [15 empty] | -500000 |  | -500000
Tramstops, standard finishes to circa 20-30% of stops | [9 empty] | -500000 | [7 empty] | -500000
Picardy place level flexing - MUDFA savings |  |  |  |  | -500000 | [12 empty] | -500000
Picardy place level flexing - construction savings |  |  |  |  | -500000 | [12 empty] | -500000
Siemens agreement to reduce fixed price on item 49 above by £10,000. Now included in item 49 above. | [17 empty] | 0
Siemens agreement to reduce fixed price on item 145 above by £200,000. Now included in item 145 above. | [17 empty] | 0
Value engineer finishes on EPV and other structures |  |  |  | -170000 | [13 empty] | -170000
Other unidentified VE items | [15 empty] | 0 |  | 0
Sub-total - Provisional Value Engineering | 0 | 0 | 0 | -170000 | -1000000 | 0 | 0 | 0 | 0 | -500000 | 0 | 0 | 0 | 0 | 0 | -1000000 | 0 | -2670000
Total Anticipated Value | 75491457 | 45123915.5495 | 15611345 | 27626039.7812 | 16968909.8871 | 3270376 | 3275180 | 5213482 | 15739224 | 1013587 | 1018910 | -1000000 | 0 | -300000 | 1330000 | 4880000 | 3000000 | 218262426.2178
-13818006
Note on Q5: Geoff Gilbert: BBS reduction on firm price oferred 13/12/07

## Infraco Normalisations
|  | Description | Synopsis | Estimating Notes | SCOOP 1 |  |  | SCOOP 2 |  |  | SCOOP 3 |  |  | ROLEY 1 |  |  | ROLEY 2 |  |  | BBS 3 |  |  | Elemental tag |  |  | Escalation Spread |  | Escalation factor | Comments from Meeting on 22 Aug 2007 |  | Section A | Section B | Section C | Section D | System Wide 1A | System Wide 1B
[5 empty] | 1A | 1B | Total | 1A | 1B | Total | 1A | 1B | Total | 1A | 1B | Total | 1A | 1B | Total | 1A | 1B | Total |  | Section | Base Date | Start | End
inf | 7 | Provide depot plant | Original bids did not include depot plant, latest submissions contain. | N/A |  |  | 0 |  |  | 0 |  |  | 0 | 2458117 |  | 2458117 |  |  | 0 |  |  | 0 | Depot |  | N/A | N/A | N/A |  |  | a
inf | 15 | Depot Drainage System | Value removed as per query response RF005 | N/A |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1283341 |  | 1283341 |  |  | 0 | Depot |  | N/A | N/A | N/A |  |  | a
inf | 24 | Depot - Ground Water Control | Bidder has suggested a reduced value of £80k. - Included |  |  |  | 0 | 250000 |  | 250000 |  |  | 0 | 288000 |  | 288000 | 288000 |  | 288000 |  |  | 0 | Depot | Depot | 2Q06 | 2008-05-01 | 2009-05-01 | 1.1196 | ● tie to review allowance | a
inf | 33 | Depot - add back 100,000m3 exc and disp | For Normalisation purposes, claim back as part of V.E. | Based on a rate |  |  | 0 | 597000 |  | 597000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Depot |  | N/A | N/A | N/A |  |  | a
inf | 34 | Provision of pumped surface water outfall system at A8 underpass |  |  | 500000 |  | 500000 | 500000 |  | 500000 | 100000 |  | 100000 |  |  | 0 |  |  | 0 | 100000 |  | 100000 | Depot | 5C | 2Q06 | 2008-05-01 | 2009-05-01 |  | ● Bidder accepts normalisation value. | a | 100000
inf | 49 | Raise level of Depot | Part of V.E, £1m banked, remainder as V.E saving |  | -1000000 |  | -1000000 |  |  | 0 | -1000000 |  | -1000000 | -1000000 |  | -1000000 |  |  | 0 |  |  | 0 | Depot |  | escalated | N/A | N/A |  | ● Bidder accepts normalisation value. | a
inf | 65 | Depot material disposal | SCOOP are proposing to incorporate material excavated at the Depot into adjacent landscape areas, ROLEY have priced 90,000m3 disposal off-site | [7 empty] | 900000 |  | 900000 | [8 empty] | 0 | Depot |  | escalated | N/A | N/A |  |  | a
inf | 66 | Inflation | Bid for systems element (c£109m) is at base date Q1 2007. Inflated using T. S indices to reflect program completion of Q1 2011. - Included in bid | Calculation based on Transport scotland indices and ROLEY 2 price split, insufficient detail in ROLEY 3 to undertake inflation calculation. |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 11933019 | 1633626 | 13566645 |  |  | 0 | Inflation |  | escalated | N/A | N/A |  | ● Bidder to provide fixed price for systems by 24th Aug 2007. | b
inf | 18 | Add anticipated additional Substation | Closing the loop Granton Square to Newhaven. Bidder stated that this is not necessary due to power distribution. - Included in bid | From contractor submissions | 1593034 |  | 1593034 | 887669 |  | 887669 |  |  | 0 | 1593034 |  | 1593034 | 887669 |  | 887669 |  |  | 0 | OLE |  | escalated | N/A | N/A |  | ● Bidder confirmed additional substation will not be required, remove from Normalisation | c
inf | 35 | 11kv Connections | SCOOP have included in Provisional Sums, ROLEY has included in main bid | From SCOOP submission |  |  | 0 | 500000 |  | 500000 | 500000 |  | 500000 |  |  | 0 |  |  | 0 |  |  | 0 | OLE |  | N/A | N/A | N/A |  |  | c
inf | 46 | Allow for Pantographs | Pantograph now part of Tram supply | Price based on £1200 escalated to out-turn | 1345648 | 363763 | 1709411 |  |  | 0 |  |  | 0 | 1345648 | 363763 | 1709411 |  |  | 0 |  |  | 0 | OLE |  | N/A | N/A | N/A |  |  | c
inf | 53 | Scottish Power connections included as part of NW reinforcement | see "Power - 11kv connections" | N/A | -500000 |  | -500000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | OLE |  | N/A | N/A | N/A |  |  | c
inf | 60 | Bid errors | Relates to the Substation price element within the SCOOP 2 bid | Value comes from SCOOP May 2007 submission |  |  | 0 |  | 698862 | 698862 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | OLE |  | escalated | N/A | N/A |  |  | c
inf | 62 | Spares not included in Price | Bidder has included in the Maintenance budget | Spares cost moved from maintenance to CAPEX for comparison | [8 empty] | 0 | [6 empty] | 174762 | 100000 | 274762 | OLE |  | escalated | N/A | N/A |  | ● Bidder agreed to transfer initial spares from OPEX to CAPEX. | c |  |  |  |  | 174762 | 100000
inf | 70 | Scottish Power Connections to Depot and IPR | Refer to letter from Scottish Power | [16 empty] | 750000 |  | 750000 | OLE | [6 empty] | c | 750000
inf | 1 | Omit allowance for SDS design |  | From ROLEY submission | 0 |  | 0 |  |  | 0 |  |  | 0 | -2000000 |  | -2000000 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 29 | Efficiency saving undertaking 1A & 1B concurrently | SCOOPs 2nd bid included a £25m premium for delaying start of Phase 1B, ROLEY offered a £5M saving for concurrent working | From bid submissions |  |  | 0 |  |  |  | 0 |  | 0 |  |  | 0 | [5 empty] | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 36 | Allowance for market price change on key commodities | Represents the cost of price volatile materials (Copper, aluminium and steel) | £379k included in Tramlines "Schedule of Provisional Activities not included in Core Price" for May submission, increased for Aug submission |  |  | 0 | 379000 |  | 379000 | 824188 |  | 824188 |  |  | 0 |  |  | 0 |  |  | 0 | Prelims |  | escalated | N/A | N/A |  |  | d
inf | 38 | Market Price fluctuation | Included in base estimate above (£14.6m) plus £1m in core price for fluctuations on metals | N/A |  |  | 0 |  |  | 0 |  |  | 0 | 6600000 |  | 6600000 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 41 | Omit allowance for invasive species removal (funded by others) - No item identified - what level of allowance should be deleted??? | see description | N/A |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 42 | Allowance for Due Diligence on detailed designs | Historic normalisations for bids 1 and 2, not required for latest bids | N/A | 1000000 |  | 1000000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 45 | SDS Design costs post novation | Historic normalisations for bids 1 and 2, not required for latest bids | N/A |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 51 | Allowance for delayed start to Project |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 6252443 | 1302936 | 7555379 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 54 | Tram Vehicle Discount - to Tramco | N/A | N/A |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 55 | Adjustment for Accommodation Works | Included in bids | N/A | 1000000 |  | 1000000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 56 | Allowance for Third Party Works | Stanley casino etc. £1M provisional sum included for accommodation works will cover | N/A | 115468 |  | 115468 |  |  | 0 |  |  | 0 | 115468 |  | 115468 |  |  | 0 |  |  | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 67 | Stakeholder management | ROLEY have not included in their latest bid for managing stakeholders ie, public consultation, SCOOP have included | [9 empty] | 0 | [8 empty] | 0 | Prelims |  | N/A | N/A | N/A |  |  | d
inf | 71 | Relocation of Ancient Monuments | Relocation of minor monuments | [16 empty] | 53700 |  | 53700 | Prelims | [6 empty] | d |  | 53700
inf | 25 | Tram on-board S&C equipment | Included within latest submissions | N/A |  |  | 0 |  |  | 0 |  |  | 0 | 1399594 | 207347 | 1606941 |  |  | 0 |  |  | 0 | Supervisory&Comms |  | N/A | N/A | N/A |  |  | e
inf | 63 | CCTV cameras |  | Cost taken from SCOOP Aug 07 submission | [8 empty] | 0 | [7 empty] | 312861 | 312861 | Supervisory&Comms - Removed under VE |  | escalated | N/A | N/A |  | ● tie stated that this was for normalisation purposes and is subject to V.E. | e |  |  |  |  | 0 | 312861
inf | 8 | E/O carrier drains | Included in BBS firm price bid | Number taken from SCOOP submission and applied to ROLEY Normalisation |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 2769914 | 1644578 | 4414492 |  | 1644578 | 1644578 | Track & Form | All | escalated | N/A | N/A |  | ● Bidder has calculated cost of additional drainage in 1A to £2.25m and accepts normalisation value until further information is available. | f |  |  | 822289 | 822289
inf | 16 | Allowance for minor utility diversions | Minor utilities relate to utilities at OLE foundations etc. not being undertaken by MUDFA. |  | 750000 | 250000 | 1000000 | 750000 | 250000 | 1000000 | 750000 | 250000 | 1000000 | 750000 | 250000 | 1000000 | 750000 | 250000 | 1000000 | 750000 | 250000 | 1000000 | Track & Form | All |  | 2008-07-01 | 2010-05-01 |  | ● Bidder accepts normalisation value. | f |  |  |  |  | 750000 | 250000
inf | 17 | Allow for finished surface between tracks | Bidder suggested a sum of £250k. - Included |  |  |  | 0 |  |  | 0 |  |  | 0 | 757947 |  | 757947 | 907158 |  | 907158 | 0 |  | 0 | Track & Form | All | escalated | 2008-07-01 | 2010-05-01 |  | ● Bidder confirmed item is within core price, remove from Normalisation. | f
inf | 23 | Archaeological Officer - impact on productivity |  | R.O.M |  |  | 0 | 350000 |  | 350000 | 405754.5495 |  | 405754.5495 |  |  | 0 | 350000 |  | 350000 | 405754.5495 |  | 405754.5495 | Track & Form | All | 2Q06 | 2008-07-01 | 2010-05-01 | 1.1593 | ● Bidder suggested any delay would be dealt with under compensation agreement. | f |  |  |  |  | 405754.5495
inf | 40 | Adjust track drainage allowances - if ITN pricing document used for base quantities then new carrier drains will have been priced where required (Roseburn) - No adjust reqd |  |  | 541223 | 274984 | 816207 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Track & Form |  | N/A | N/A | N/A |  |  | f
inf | 43 | Allow for reduced excavation - thinner track slab | Historic normalisations for bids 1 and 2, not required for latest bids | N/A |  |  | 0 |  |  | 0 |  |  | 0 | -571874 | -44429 | -616303 |  |  | 0 |  |  | 0 | Track & Form |  | N/A | N/A | N/A |  |  | f
inf | 44 | Reduced base plate spacing on curves | Historic normalisations for bids 1 and 2, not required for latest bids | N/A | 100000 |  | 100000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Track & Form |  | N/A | N/A | N/A |  |  | f
inf | 57 | Adjust track drainage allowances - Scoop allow connection every 50m Roley every 25m - adjust Scoop | Covered above in Normalisation 8. | N/A |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Track & Form |  | N/A | N/A | N/A |  |  | f
inf | 59 | Old Tramway workings | It is foreseen that old tramway workings will be encountered during excavation works | Is this covered under "Unforeseen Ground conditions" risk? |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Track & Form |  | N/A | N/A | N/A |  |  | f
inf | 64 | Ballast | Bidder included for non NR compliant ballast, addition of £300k as indicated by Bidder for the use of NR compliant ballast. Include in V.E list ref. RF006 | £300k given verbally by ROLEY as the extra cost of using compliant ballast | [8 empty] | 0 | [6 empty] | 300000 |  | 300000 | Track & Form |  | escalated | N/A | N/A |  | ● Bidder accepted value. | f | 300000
inf | 68 | Stray Current monitoring | Bidder has included for current monitoring only which does not comply with the E.R. - Included (See separate proposals) | [9 empty] | 0 | [8 empty] | 0 | Track & Form |  | escalated | N/A | N/A |  | ● Bidders stray current proposals non compliant and drainage issues* | f
inf | 50 | Gogarburn Tram Stop By RBS | The additional cost of finishes and shelters etc for this tramstop are to be funded by RBS | Rates used from bid submissions | -171008 |  | -171008 | -167557 |  | -167557 | -167557 |  | -167557 | -132412 |  | -132412 | -184900 |  | -184900 |  |  | 0 | Tramstops - additional funding not construction cost saving |  | escalated | N/A | N/A |  | ● tie commented this is not a reduction in scope. Funding mechanism to be agreed. | g | 0
inf | 2 | Potential VE savings | From SCOOP Jan 07 submission | From SCOOP Jan 07 submission | -10000000 |  | -10000000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | V.E Opportunities |  | N/A | N/A | N/A |  |  | h
inf | 52 | Potential VE savings | Numbers included below the Normalisation totals | N/A |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | V.E Opportunities |  | N/A | N/A | N/A |  |  | h
| Sub Total Infraco Normalisation exc. Highways & Structures | [18 empty] | 2534216.5495 | 2307439 | 4841655.5495 | [8 empty] | 1150000 | 53700 | 822289 | 822289 | 1330516.5495 | 662861 | 0
inf | 3 | Piccardy Place, York Place and London Road junction | Additional cost over and above the base alignment scope - Includes £3,000,0000 in respect of Utilities Diversions | Breakdown available, £3m included for service diversions, not part of current MUDFA scope. | 5379599 |  | 5379599 | 5379599 |  | 5379599 | 6340324.3822 |  | 6340324.3822 | 5379599 |  | 5379599 | 5379599 |  | 5379599 | 6340324.3822 |  | 6340324.3822 | Highways | 1C | 2Q06 | 2008-03-01 | 2010-06-01 | 1.1325 | ● BBS to remeasure and provide value based on latest information by 24th Aug 07. For the interim value reduced to £2m, escalation applied. | i |  | 6340324.3822
inf | 4 | Extent of road refinishing in critical on street areas | Allowance for "kerb to kerb" finishes in selected areas. Not now required as is included in adjustment for firm price | Siemens have suggested a value of £1m would be sufficient | 5210041 |  | 5210041 |  |  | 0 |  |  | 0 | 5210041 |  | 5210041 | 5210041 |  | 5210041 |  |  | 0 | Highways - all additional costs included in firm price | 1D, 1B, 1C |  | 2008-03-01 | 2010-06-01 | 1.1325 | ● Bidder to provide commentary based on drawings and their assumptions for the demarcation of finishes, by 31st Aug 07. | i |  | 0
inf | 5 | Allowance for surface finishes on Leith walk and princess street areas | Enhanced finished required (i.e. cobbles etc.). Lack of assurance of scope coverage within "Highways" section of the bids |  |  |  | 0 | 2000000 |  | 2000000 | 2000000 |  | 2000000 |  |  | 0 |  |  | 0 |  |  | 0 | Highways | 1C |  | 2008-03-01 | 2010-06-01 |  |  | i
inf | 21 | Adjust for natural stone paving in Princess Street in lieu of asphalt | Bidders have priced a like-for-like replacement, where it is anticipated CEC would require an enhanced finish, betterment?. Covered in normalisation 4 and 5. | N/A |  |  | 0 |  |  | 0 |  |  | 0 | 589112 |  | 589112 | 589112 |  | 589112 |  |  | 0 | Highways |  | N/A | N/A | N/A |  |  | i
inf | 22 | E/O Shell Grip | Shell grip at junctions | Estimated using £9.16 / m2, backup available |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 276998 | 108821 | 385819 | 319343.2872 | 125663.0672 | 445006.3544 | Highways | All | 2Q06 | 2008-03-01 | 2011-02-01 | 1.1529 |  | i |  |  |  |  | 319343.2872 | 125663.0672
inf | 27 | Mains Power Connection to street lights and traffic signals | Allowance for connections to be undertaken by Scottish Power | Price agreed with bidders |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 100000 | 25000 | 125000 | 115287.2177 | 28821.8044 | 144109.0221 | Highways | All | 2Q06 | 2008-03-01 | 2011-02-01 | 1.1529 | ● Bidder accepts normalisation value. | i |  |  |  |  | 115287.2177 | 28821.8044
inf | 39 | Allowance for landscaping (included) | ROLEY original bid contained no allowance for landscaping, subsequently included | N/A |  |  | 0 |  |  | 0 |  |  | 0 | 88500 | 40500 | 129000 |  |  | 0 |  |  | 0 | Highways |  | N/A | N/A | N/A |  |  | i
inf | 48 | Reduction in sub-base rate | Rate within SCOOP May 07 submission looked to be a mistake due to its magnitude | Revised rate applied consistent with other areas of the scheme |  |  | 0 | -72000 |  | -72000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Highways |  | N/A | N/A | N/A |  |  | i
inf | 10 | A8 Underpass piling | Originally thought bid excluded piling, however further to recent information piling is included | N/A |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 3267590 |  | 3267590 | 0 |  | 0 | Structures |  | N/A | N/A | N/A |  |  | j
inf | 13 | Crewe Gardens Bridge - Contiguous piling | Bidder not included piling. - Included | Taken from SCOOP bid |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 1825000 | 1825000 |  |  | 0 | Structures | 3A | escalated | 2009-07-01 | 2011-01-01 |  | ● Bidder to re-check estimate and provide comment by 24th Aug 07. | j
| Sub Total Highways | [18 empty] | 6774954.8871 | 154484.8717 | 6929439.7587 | [8 empty] | 0 | 6340324.3822 | 0 | 0 | 434630.5048 | 154484.8717
inf | 19 | Adjust for Network Rail Possessions support | Costs for PICOPS / COSS when undertaking works adjacent / over the railway. |  | 755307 |  | 755307 | 755307 |  | 755307 | 755307 |  | 755307 | 755307 |  | 755307 | 755307 |  | 755307 | 755307 |  | 755307 | Structures | 7A, 5C, 5B, 5A |  | 2008-03-01 | 2009-11-01 |  | ● Bidder suggests reduction to £50k for track safety only personnel, not allowance has been made within bid for design interface. | j | 755307
inf | 20 | Balgreen Road - new structure reqd | It is anticipated that a new structure will be required. Bidder suggested that £600k would be sufficient based on £2,500/m2 + £100k for removal of old deck |  | 500000 |  | 500000 | 750000 |  | 750000 | 750000 |  | 750000 | 500000 |  | 500000 | 750000 |  | 750000 |  |  | 0 | Structures - all additional costs taken into account in firming up price | 5A | escalated | 2008-03-01 | 2009-09-01 |  | ● Bidder has received most recent information and is in agreement with normalisation value. | j | 0
inf | 26 | S23 Carrick Knowe Widening | Allowance to increase deck to accommodate cycleway. Bidder has suggested a cost of £125k based on a widening rate of £2.5k for 50m2 | As per ROLEY rates |  |  | 0 |  |  | 0 | 139955.9189 |  | 139955.9189 |  |  | 0 | 250000 |  | 250000 |  |  | 0 | Structures - all additional costs taken into account in firming up price | 5B | 2Q06 | 2008-04-01 | 2009-11-01 | 1.1196 | ● Bidder accepts normalisation value. | j | 0
inf | 28 | Leith Walk substation demolition | Potential requirement to demolish existing structure. |  |  |  | 0 | 50000 |  | 50000 | 55661.7812 |  | 55661.7812 |  |  | 0 | 50000 |  | 50000 | 55661.7812 |  | 55661.7812 | Structures | 1B | 2Q06 | 2008-06-01 | 2008-12-01 | 1.1132 | ● Bidder queried level of contamination around buried tanks, tie to investigate. | j |  | 55661.7812
inf | 30 | Roseburn Corridor Drainage Pumps | Anticipation for pumping to outfalls, cost captured under Normalisation 61 | N/A |  |  | 0 |  | 50000 | 50000 |  |  | 0 |  |  | 0 |  | 50000 | 50000 |  |  | 0 | Structures |  | N/A | N/A | N/A |  |  | j
inf | 31 | Additional Crew Relief Facilities at Haymarket | Late addition to scheme, facility to be located under span of proposed Haymarket Viaduct (5-span) | From SCOOP submission for Granton Square facilities |  |  | 0 | 49950 |  | 49950 | 49950 |  | 49950 |  |  | 0 | 49950 |  | 49950 | 49950 |  | 49950 | Structures |  | escalated | N/A | N/A |  | ● Bidder accepts normalisation value. | j | 49950
inf | 32 | Structure S18 allowance for anticipated works | Minimal works required at this location. | SCOOP included £277,500 in bid and ROLEY did not price. Minimal works likely so align values to equal £27.5k |  |  | 0 | -250000 |  | -250000 | -250000 |  | -250000 |  |  | 0 | 27500 |  | 27500 |  |  | 0 | Structures - all additional costs taken into account in firming up price | 1B | escalated | 2009-02-01 | 2009-08-01 |  | ● Bidder accepts normalisation value. | j |  | 0
inf | 37 | Murrayfield Tram Stop Lift and Steps | Installation of staircase and lift at Murrayfield Tramstop. ROLEY have captured within main bid, SCOOP have not. | £40k - Provision and installation of staircase to North West corner of Murrayfield Tramstop retaining wall £60k - Provision, installation and commissioning to lift to North West corner of Murrayfield Tramstop retaining wall. |  |  | 0 | 100000 |  | 100000 | 100000 |  | 100000 |  |  | 0 |  |  | 0 |  |  | 0 | Structures | 5A | escalated | 2008-05-01 | 2009-09-01 |  |  | j
inf | 47 | Delete Crew Relief Facilities at Granton Sqr | No longer required, operators will be directed to use public facilities | From bid submissions |  |  | 0 |  | -49950 | -49950 |  | -49950 | -49950 |  |  | 0 |  |  | 0 |  |  | 0 | Structures |  | escalated | N/A | N/A |  |  | j
inf | 58 | Landfill Tax Post 2008 +33% | Marker | is this applicable, can spoil be reused around the network? |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Structures |  | N/A | N/A | N/A |  |  | j
inf | 61 | Roseburn corridor retaining wall align assumptions | Design not developed in this area, bidder has made his own assumptions | Values aligned due to vastly differing assumptions, Mean value used and Normalised accordingly | [7 empty] | -2008445 | -2008445 | [7 empty] | 3228456 | 3228456 | Structures |  | escalated | N/A | N/A |  | ● Bidder accepts normalisation value, level of design information available leaves this area uncertain. | j |  |  | 3228456
| Sub Total Structures | [18 empty] | 860918.7812 | 3228456 | 4089374.7812 | [8 empty] | 805257 | 55661.7812 | 3228456 | 0 | 0 | 0
| Total | [18 empty] | 10170090.2178 | 5690379.8717 | 15860470.0894
|  |  | Current Normalisation Total (24 August 2007) |  | 7119312 | 888747 | 8008059 | 12808968 | 948912 | 13757880 | 12253584.6318 | -1808395 | 10445189.6318 | 30378524 | 2120117 | 32498641 | 35690298 | 5537025 | 41227323 | 30510270.6533 | 17071139.615 | 47581410.2683
|  |  | Normalisation at 23 August 2007 | [16 empty] | 53822000 | 8619000 | 62441000
|  |  | Variance | [16 empty] | -23311729.3467 | 8452139.615 | -14859589.7317
Note on X1: terramic: Filters through to main summary sheets
Note on AC1: terramic: Using Average multiplier across duration
Note on AD5: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Groundwater control: o AMIS to control water until Infraco takes over. o BBS to take temp pumping into their bid. o Normalisation to be removed
Note on AD7: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Agreed.
Note on AD8: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Agreed – Allowance common to both bidders.
Note on AD10: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Inflation for systems. BBS to reconsider. Tie are willing to consider arrangements for pre purchase/commitment to price volatile metals or indexation arrangements for such materials. Tie are not willing for the systems price generally to be fluctuating price.
Note on AD11: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 BBS view is that the additional sub-station is not required and that system will comply with Employer’s Requirements with 1a operating on a standalone basis. Agreed to remove.
Note on AD16: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Spares. Agreed.
Note on AD32: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Agreed.
Note on AD33: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Carrier Drains: o BBS’s view is that this allowance for Phase 1a should be 2.25m. o Leave 1b as is for the moment.
Note on AD34: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Minor Utility Diversion – Common allowance for both bidders
Note on AD35: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Allowance for refinishing roads between tracks. BBS confirmed that they have allowed for surface finishes between the tracks within their bids. Normalisation to be removed.
Note on AD36: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Archeological Officer – Allowance agreed
Note on AD42: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Ballast. Allowance agreed.
Note on AD43: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Stray current monitoring – BBS to consider taking this risk into their bid. BBS to review allowances for trackform drainage within their bid following the Trackform review meeting with tie.
Note on AD44: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Agreed – Funding adjustment common to both bidders.
Note on AD50: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 BBS to review Picardy Place allowance and advise their view on 24/8/07.
Note on AD51: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 BBS have based their pricing on the indicative roads and pavings drawings and have allowed for the finishes indicated on the basis of like for like reinstatement. However, full paving reinstatements are only included where this is shown on the drawings. Unless otherwise shown on the drawings issued BBS have included for reinstatement to match existing e.g. York stone finishes are not allowed in Princes St except where existing finishes are York stone. For the whole of the on street alignment BBS have allowed for resurfacing the roads with a new surface coat, but have not allowed for extensive full reinstatement of roads and sub base. Need to have a clear definition of requirement. For clarity BBS will provide details of the scope of work that they have allowed for each section of the alignment. This will be provided for 24/08/07
Note on AD54: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 E/O shell grip. Allowance agreed
Note on AD55: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Agreed.
Note on AD59: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Crewe Gardens Bridge – BBS to consider appropriate allowance
Note on AD63: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Additional Network Rail Possession Support. o Costs for possessions included in bid. o BBS assume SDS will gain NWR approval of design including getting Form C approval. o tie to review and remove normalisation.
Note on AD64: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Balgreen Road. New Structure – Allowance of £750k agreed
Note on AD65: terramic: From GG minutes of meeting with BBS on 23 Aug 2007
Note on AD66: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Leith Walk Substation – Allowance agreed.
Note on AD68: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Agreed – BBS to check not duplicated
Note on AD69: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Agreed.
Note on AD73: terramic: From GG minutes of meeting with BBS on 23 Aug 2007 Roseburn Corridor retaining walls. Agreed.

## VE Agreed with BBS
EDINBURGH TRAM PROJECT - PHASE 1A | [9 empty] | 71214 Single VE List v31 agreed bbs tie v1
VALUE ENGINEERING OPPORTUNITIES REGISTER
REF | ITEM | FILTER | [8 empty] | VALUE |  | NOTES | [13 empty] | Key Qualifications
[11 empty] | Target | Agreed BBS position |  |  | 1569000
BUILDINGS
The 2 sub-station items have been rejected by BBS.
| BUILDINGS TOTAL | [9 empty] | 0 | 0
DEPOT
8 | Delete depot pumping station/storm tanks by utilising existing gravity system. | Depot | PD |  |  |  | 0 | 0 | 0 | 193526 | 193526 | 193526 | tie may need to add in cost of a small pump | Further impact on operating costs to be investigated Not a VE issue but on-going design of depot drainage. |  |  |  |  | #N/A |  |  |  |  | SDS to confirm final arrangement and requirements as a part of revised design. Updated design from SDS awaited. SDS are required to cost new layout. When available tie will require to review cost estimate to extract final VE savings and change to Risk All |  |  | tie's carries specification/acceptance risk and cost of additional pump
9 | Depot - Build part now with provision to expand in the future/reduce size of car park facilities | Depot | SDS |  |  |  | 0 | 0 | 0 | 230000 | 230000 | 230000 | Initial supply of 100 car park places agreed. | Confirmed stabling requirements: Short term 27 tram fleet - 24 in sidings balance in shed. In addition to items 4, 5 & 6? False economy? Revisit esti mate for full dig for 35 tram fleet (8 sidings) but infrastructure installed for 27 tram fleet (6 siding | [9 empty] | Incremental construction of buildings rejected. Sidings and car park to be done stages. SDS instructed accordingly. Updated design from SDS awaited. SDS are required to cost new layout. When available tie will require to review cost estimate to extract fi |  |  | tie's carries specification/acceptance risk
14 | Delete under floor lift plant and utilise mobile jacks. Incl mobile future proofing. | Depot |  | - | - | - | 0 | 0 | 0 |  | 250000 | 250000 |  | See "SCOOP" email received from BD 100407 Rejected - complicates operations and negative impact on Health & Safety |  | - | - | - | - | - | - | - | - |  |  |  | tie's carries specification/acceptance risk
16 | Depot - delet split vehicle accommodation system - requirement dependant on tram vehicle selection | Depot |  |  |  |  | 0 | 27500 | 0 | 27500 | 27500 | 27500 | Accomodation bogies are in CAF offer | See "SCOOP" email received from BD 100407 AR - Not good in the long run really from reliability. Underfoot jacks are generally more reliable and, in conjunction with under floor body stands, safer. Scoop 3 - no savings offered. Tram choice dependent - Nee | [9 empty] | Technical team do not have visibility of either Tramlines of Roley pricing for this particualr item. Will be procured from Tramco. Therefore there may be "saving" on either Infraco but not on project overall |  |  | tie's carries specification/acceptance risk
17 | Depot - Track Maintenance Equipment - rationalise scope requirement and consider renting. | Depot |  |  |  |  | 0 | 27500 | 0 | 27500 | 27500 | 27500 |  | See "SCOOP" email received from BD 100407 | [9 empty] | AR can confirm if Scoop have delivered promised clear statement of equipment not required or which they propose to hire when required. Roley initially asked for both additional building and mobile plant. Understand now withdrawn. AR to advise if full lis |  |  | tie's carries specification/acceptance risk
20 | Depot - deletion of one pavement (inner) . | Depot |  | - | - | - | 0 | 36000 | 0 | 36000 | 36000 | 36000 | Shown on latest site plan drawings. | May not be realised as a saving due to requirement to feed water main under footway |  | - | - | - | - | - | - | - | - | Directly associated with utility diversion and removal of A8 retaining wall. Updated design from SDS awaited. SDS are required to cost new layout. When available tie will require to review cost estimate to extract final VE savings and change to Risk Alloc |  |  | tie's carries specification/acceptance risk
24 | Depot - delete requirement for concrete apron to security fence | Depot |  |  |  |  | 0 | 6080 | 0 | 6080 | 6080 | 6080 | [11 empty] | SDS have been instructed to revise design. Updated design from SDS awaited. SDS are required to cost new layout. When available tie will require to review cost estimate to extract final VE savings and change to Risk Allocation. Revised design to Preferred |  |  | tie's carries specification/acceptance risk
129 | Depot - delete compressed air system, utilise 1 or 2 local /mobile compressors | Depot |  |  |  |  | 0 | 54400 | 0 | 54400 | 54400 | 54400 | [11 empty] | Is already "banked" as VE saving at this price! VE register 129 How are Tramlines shown at same price? Minor ER change if not already done. | ER already modified I believe. CAF have expressed preference for power operated tools. Half-way house maybe to fit pipework and then decide on fixed compressor and reservoir at a later date but provide space for them. | Need to cnfirm woth Tramco the detailed proposals. Otherwise thought already agreed. | tie's carries specification/acceptance risk
145 | Consolidated VE items 7, 10, 11, 19 which results from changes to initial Depot design driven by proximity to BAA runway and EARL decision. | Depot |  |  |  |  | 821264 | 1200000 | 0 | 3321264 | 3181264 | 2000000 | Includes rreductions in structural loadings (gantry crane reduced in capacity and size impacting on building frame and envelope), reductions in staff accommodation provision (reduced operational workforce reducing messing facilities, changing rooms, locke | [10 empty] | SDS have been instructed to revise design. Accomodation numbers provided by TEL. Updated design from SDS awaited. SDS are required to cost new layout. When available tie will require to review cost estimate to extract final VE savings and change to Risk A |  |  | DTC but compliant with current technical /design info. Subsequent saving of £200,000 added see below.
New | Delete standby generator and substitute with hardstanding and power connection for portable generator. | Depot | [8 empty] | 250000 | 150000 | [14 empty] | tie's carries specification/acceptance risk
| DEPOT TOTAL |  |  | 0 | 7700000 | 0 | 13090006.4 | 5131477 | 875000 | 21566321 | 4256270 | 2975006 |  |  |  | 0 | 1742562.1 | 0 | #N/A | 5878809 | 5878809 | 0 | 0
HIGHWAYS
36b | Material recovery and reprocessing (Infraco); 2 options - reconstituted planings & Type 1R | Highways | [8 empty] | 500000 | 500000 | [14 empty] | Subject to confirmation from SDS; level of saving subject to adjustment of quantity of this item based on the final design
152 | Reduce Kerb and associated re-instatement of pavement | Highways | [8 empty] | 100000 | 100000 | [11 empty] | CEC planning issue? Does the Street/highway demarcation agreement help? |  | Cannot comment without more information; happening in detailed design in any case? Design has probably not yet reached the stage of establishing exactly what is required in any case. | Subject to confirmation from SDS; level of saving subject to adjustment of quantity of this item based on the final design
153 | Reduce drainage run from guideway | Highways | [8 empty] | 100000 | 100000 | [11 empty] | Presumably refers to the Fastlink takeover? Would need further evaluation once existing drainage is understood. |  | Cannot comment without more information. | Subject to confirmation from SDS; level of saving subject to adjustment of quantity of this item based on the final design
| HIGHWAYS TOTAL |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 700000 | 700000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NETWORK RAIL
42 | NR Immunisation - ensure design of immunisation is based on minimum safe propagation distance (e.g. <100m). Project budget previously very conservative. | NR | SB |  | 7700000 |  | 2800000 | 0 | 0 | 2800000 | 4700000 | 4700000 | Original proposal work by BBS suggests a target of less <50m may be achievable. | [13 empty] | Terms remain as BBS letter; particularly that tie carries NR cost risk | 1
| NETWORK RAIL TOTAL |  |  | 0 | 7700000 |  | 2800000 | 0 | 0 | 2800000 | 4700000 | 4700000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OLE
49 | Overhead Contact system - Switchgear - rationalise specification - considered "quite onerous" | OLE |  |  |  |  | 0 | 336000 | 0 | 336000 | 336000 | 150000 | Price change requested for manual, three position cubicle mounted line islators throughout, with the exception of the depot where they can be pole mounted. Status of isolator to be shown via SCADA. Sub-station bypasses to remain motorised. | See "SCOOP" email received from BD 100407 Scoop 3 - rational discussion with Transdev reqd (ASt). | [5 empty] | 336000 | 336000 |  |  | BBS originally offered pole mounted (motorised) everywhere. Provision of latter rejected by tie. Agreed to offer cabinet mounted but did not offer any reduction for manual (see RT12, RT30 and RT98). Stated would be extra cost. Not visible to technical |  |  | Siemens commitment related to non specific items
135 | OLE - Catenary opportunity in Sections 5 to 7 - replace trolley wire with catenary on segregated sections. | OLE |  |  |  |  | 0 |  | 0 |  |  | 0 | Detailed price change requested for: catenary with 3-step poles Haymarket Yard-Russell Road (Russell Road-Airport already catenary); fixed termination Haymarket Yards-Newhaven; Tapered Poles Haymarket-Newhaven. | Use of messenger wire as current carrying conductor may reduce need for parallel feeders. In theory, fewer supports required. | [9 empty] | Roley bid currently offers this. Scoop offers trolley wire. No incremental price variation for alternative available from either. Immediate issue for Preferred Bidder. Should have no illusions that CEC Planning will require considerable convincing to acce |  |  | No net savings. All in price. Assumes fully compliant with planning and technical requirements but excludes tapered poles.
149 | Provision of combined incoming and return cabinet. | OLE | [8 empty] | 42000 | 0 | [11 empty] | Do not totally understand what this means. As it is labelled OLE assume it is something to do with the feeds to and from the OLE at sub-stations. Might be quite sensible and could be what BW are already proposing for Tramlines. Immediate preferred bidder | Seems ok on the face of it. | Cannot comment without more information. | tie proven to be incompatible with SP feeder arrangements.
| OLE TOTAL |  |  | 0 | 0 |  | 0 | 336000 | 0 | 336000 | 378000 | 150000 |  |  |  | 0 | 0 | 0 | 0 | 336000 | 336000 | 0 | 0
STRUCTURES
54 | Value Engineering/ de-risked pricing approach developed for the final designs for all structures, particularly substructures and foundations (where not covered below) | Structures | SDS |  |  |  | 8000000 | 0 | 0 | 8000000 | 2000000 | 0 |  | Initial bids based on Prelim Design. Both bidders have stated that they anticipate savings will be generated through co-operative detailed design. There has already been co-operative design Scoop 3 -Subject of separate discussions with bidder (ASt) | [5 empty] | 4000000 | 4000000 | [5 empty] | Unable to commit
55 | Edinburgh Park Viaduct various savings including use of cross heads to eliminate temp works, steel or concrete beams. | Structures |  |  |  |  | 0 | 0 | 500000 | 850000 | 1470000 | 1470000 | This assumes continuation with 7 span structure. | Higher initial construction cost but through use of weathering steel can achieve lifetime savings in not maintaining paint system. CEC approval required | [12 empty] | Subject to approval of design by NEL/ CEC and subject to SDS designing to cost
56 | Carricknowe Bridge Parapet - down grade from P6 / P5 to N2 (reduced cost of parapet plus knock on effect on deck design/cost) | Structures | SDS (TK)/JP |  |  |  | 0 | 0 | 0 | 85000 | 85000 | 85000 |  | Requirement for N2 protection - bids to be checked to establish if P6/P5 costed |  |  | 90015.18 |  | 88908.5577 | [7 empty] | Subject to approval of design by Network Rail
57 | A8 Underpass various initiatives | Structures | SDS |  |  |  | 0 | 0 | 0 |  | 850000 | 850000 | Changing to a contiguous piled wall/ leaner designs | Key issue is precise location and depth of a bank of ducts containing fibre optic cables | [12 empty] | Subject to being able to design to cost
New | Roseburn Street viaduct various initiatives | Structures | [8 empty] | 1375000 | 1375000 | [14 empty] | Subject to approval by stakeholders - SRU and Network Rail
New | Water of Leith various intiatives | Structures | [8 empty] | 150000 | 150000 | [14 empty] | Subject to being able to design to cost
New | Eight maintenance walkway structures - delete or reduce | Structures | [8 empty] | 250000 | 250000 | Unlikely to yield net savings unless structure needs to be redesigned for other purposes. | [13 empty] | Subject to being able to design to cost; and tie taking approvals risk
New | Russel rd Bridge piling changes | Structures | [8 empty] | 100000 | 0 | [14 empty] | Subject to being able to design to cost
154 | Class 7 material conversion - | Structures | [8 empty] | 300000 | 300000 | [11 empty] | Please refer to the latest update on the VE structures for current proposal for these structures. Also ensure that VE structures team are aware of these latest proposals as they may be different from that proposed earlier by BBS. |  | Is this already included in bids? No problem in principle. | Subject to confirmation of SDS agreeing to principle; level of saving subject to adjustment of quantity of fill required by the final design
| STRUCTURES TOTAL |  |  | 0 | 0 |  | 8000000 | 0 | 500000 | 8935000 | 6580000 | 4480000 |  |  |  | 0 | 90015.18 | 0 | 88908.5577 | 4000000 | 4000000 | 0 | 0
SUPERVISORY & COMMS
65 | Signalling & Comms - fewer CCTV cameras . Reduced to 55Nr . (Tramstops 45Nr, Depot 10Nr) | Supervisory & Comms |  |  |  |  | 0 | 266000 | 0 | 266000 | 100000 | 33000 | Price requested for 55 off for Phase 1a | See "SCOOP" email received from BD 100407 Both bidders have priced cameras in excess of operational requirements (ITN pricing document quotes excessive qty) Scoop3 - unclear what fig is based on. Maybe technical team fig of 90 (Ast) |  |  | 1312860.92 |  | 0 | 266000 | 266000 |  |  | Tramlines have offered similar proposal and near identical price. Suggest this is because both bidders have responded to the AS/RJ revised CCTV headcount of c90 cameras. The ER may have been tidied up already to reflect this (can TK comment) | Agreed | Agreed
69 | Signalling & Comms - rationalise fibre optic ring. More economic architecture that performs the same function could be employed | Supervisory & Comms |  |  |  |  | 0 |  | 0 |  | 100000 | 0 | Ensure separation 1a and 1b costs | See "SCOOP" email received from BD 100407 Essentially requires Phase 1b to be in place to be practical. No savings at this time. Scoop3 - fig of £270k quoted but applies if 1a & 1b built simultaneously. (ASt) | [9 empty] | BBS currently comply with tie requirements. Could do the same but the saving may be different. However only relevant if 1a and 1b are built simultaneously.
73 | Signalling & Comms - Current requirement for location and interface of the SCADA and Points controllers etc is unnecessarily complex. | Supervisory & Comms |  |  |  |  | 0 | 13000 | 0 | 13000 | 50000 | 0 | A simpler solution e.g. as in Nottingham, would be cheaper and more user friendly. | See "SCOOP" email received from BD 100407 Proposal in principle acceptable to TEL/Transdev | [5 empty] | 13000 | 13000 |  |  | BBS have same potential point mechanism supplier. Therefore could do the same but the saving may be different.
74 | Signalling & Comms - rationalise loop quantities by combining some loop functions | Supervisory & Comms |  |  |  |  | 0 | 87500 | 0 | 87500 | 87500 | 0 |  | See "SCOOP" email received from BD 100407 Essentially one of detail design and not VE. Scoop 3 - provided £33k VE however this cannot happen if item 133 taken. (ASt) | [9 empty] | Tramlines have offered similar proposal but with less savings. Essentially this will be the final development of the SDS design Not an ER issue. Agree with TEL comment Preferred Bidder issue | If no reduction in ultimate system performance then fine, but performance risk remains with Infraco. | Agreed; rationalisation would always be part of detailed design in any case
75 | Signalling & Comms - Remove ambient noise sensing on the passenger announcement system | Supervisory & Comms |  |  |  |  | 0 | 7000 | 0 | 7000 | 7000 | 0 | Price change requested. | See "SCOOP" email received from BD 100407 Proposal in principle acceptable to TEL/Transdev |  |  | 339686 |  |  | 7000 | 7000 |  |  | Tramlines have offered similar proposal and near identical price. Still require night/day changeover Simple change to ER | Agreed | Agreed
163 | UPS - reduce capacity from 4hrs to 3hrs | Supervisory & Comms | [8 empty] | 50000 | 50000 | Would be included in financial advantage for proposal to outsource UPS provision to Chloride.
165 | Reduce nr of Signalised Pedestrian Xings. | Supervisory & Comms | [8 empty] | ? | 0 | From review of latest road layouts there is a signifcant increase in qtys. May need to challenge CEC (c.£50k/ crossing)
| SUPERVISORY & COMMS TOTAL |  |  | 0 | 0 |  | 0 | 373500 | 0 | 373500 | 394500 | 83000 | BBS have agreed to review Phase 1a/1b split. Still outstanding. |  |  | 0 | 1652546.92 | 0 | 0 | 286000 | 286000 | 0 | 0
SYSTEM WIDE
77 | Optimise the work site lengths wherever practical to ensure efficient construction outputs | System Wide |  |  |  |  | 0 | 0 | 225000 | 300000 | 300000 | 300000 | Linked to other discussions e.g. Rhaeda City trackform (see 138 too) | Resolve with bidder/CEC methodology reviews. Roley 3 - 10, 15 & 20 % efficiency range taken on Roley bid info (Plant & labour only). Await Scoop3 details - JP | [5 empty] | Stakeholder Agreement needed | [6 empty] | Subject to further Programme development with CEC, confirm by 9th January.
80 | Accept more disruption over shorter period to maximise efficiency of construction operations - | System Wide | SC/AH/KR |  |  |  | 0 | 0 | 150000 | 100000 | 100000 | 100000 | Intitial discussions suggests CEC are likely to be flexible | Roley 3 - full weekend working (+ 1.5 days) - saved 16% on trackform programme durations. This will increase local disruption ie traffic/shopping - JP | [12 empty] | Subject to further Programme development with CEC, confirm by 9th January.
148 | Remove spare capacity from OTN (linked to item 69) | System Wide | [8 empty] | 180000 | 0 | [11 empty] | This appears to suggest reducing the capacity of the OTN fibre-optic cables rather than a re-configuration as was proposed by Tramlines. Would need to see revised OTN architecture to give view. Is essentially a question of the extent to which tie wish to | Await further info. Need to check what the cost of running 1b at a later date was versus this saving. | Cannot comment without more information.
150 | Option to lease UPS provision from Supplier rather than purchase | System Wide | [8 empty] | 300000 | 300000 | Originally BBS proposal | [10 empty] | This might be worth looking at commercially However how does it relate to the proposal at 3 above? Would require overall review of total UPS requirements across the system. | Await commerical details. | Cannot comment without more information. | Subject to agreement of operator
151 | Rationalising spares supplied with the Infraco bid | System Wide | [8 empty] | 300000 | 300000 | Originally BBS proposal | [10 empty] | The Midland Metro Concessionaire made last minute "savings" by removing spares other than consumable from the supply (both infrastructure and trams). The operator ending up buying later at a premium with system availbility compromised in the process. In t | Personally consider that the design is too insufficiently developed for anyone to take a safe-bet on spares requirements. Insufficient spares is of no use to anyone, regardless of contractual responsibility. Reputationally if the tram system is not reliab | Agree with TEL. | Subject to agreement of operator
160 | PM Integration including shared resources and co-location. | System wide | [8 empty] | 1000000 | 1000000 | Late BBS VE proposal | [13 empty] | Subject to BBS /tie agreeing savings in resources and facilites items from BBS and tie costs
| SYSTEM WIDE TOTAL |  |  | 0 | 0 |  | 0 | 0 | 375000 | 400000 | 2180000 | 2000000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRACK FORM
100 | Noise attenuation (outside of Roseburn Corridor) 3,650m of fencing | Trackform |  |  |  |  | 0 | 13688 | 0 |  | 50000 | 50000 | Also a timing issue, because we would not necessarily install during construction but await reaction if any. | Noise barriers | [12 empty] | Subject to property owner claims
138 | Trackform - changing embedded to ballast rail. Ballasted track adjacent to NwkRail | Trackform | [5 empty] | 3000000 | 0 | 3000000 | 2000000 | 0 | Awaiting a formal technical and financial proposal for Rhaeda City trackform for both embedded and grass and a validated construction programme. | Scoop 3 - Difficult due to ballast not acceptable in ares prposed by Scoop (ASt) | [5 empty] | 1200000 | 1200000 |  |  | Surely this is the same as their Ref 8 above? See previous comments | Consistent position has been that there is not ballast in certain locations for good reasons. TEL do not see merit in pursuing this. | Agreed that this is repetition. | Unlikely to yield savings because of short distance. Plus maintenance implications.
156 | Track installation install in strips. | Trackform | [8 empty] | 0 | 0 | Would need v strong justification. | [10 empty] | This has never been formally raised by the BBS track team (Bilfinger or Siemens) Therefore it is surprising to see it appear like this especially with such a large figure associated with it. It has certainly been done elsewhere but there still has to be t |  | Cannot comment without more information; feel very nervous. | Unacceptable
164 | Reduce ballasted track thickness from 300 to 200mm | Trackform | [8 empty] | 300000 | 200000 | [14 empty] | Design to cost.
| TRACK FORM TOTAL |  |  | 0 | 0 |  | 0 | 3013688 | 0 | 3000000 | 2350000 | 250000 |  |  |  | 0 | 0 | 0 | 0 | 1200000 | 1200000 | 0 | 0
TRACTION POWER
103 | 11Kv Traction Power feeds to sub stations including any network reinforcement required (separate VE 104). | Traction Power | TK |  |  |  | 1468742.4 | 0 | 0 | 1468742 | ? | 0 | Dialogue needed with tie to incorporate SP negotiated savings into BBS proposal. | SDS allowance £302k per feed. Discussions suggest that £130k per feed more appropriate. Investigate CEC ability to lever price from DNO. Will Power Supply need to be tendered? | 1569000 | [8 empty] | Meeting held with SP. Update awaited |  |  | Defer until SP current phase of negotiations is complete.
109 | Power supply - Russell Rd TPH - equipment for future upgrade to substation to be supplied when needed i.e. don't supply transformer rectifier now. | Traction Power |  |  |  |  | 0 | 56809 | 0 | 56809 | ? | 0 | BBS have been instructed to assume that for Ph 1a on its own nothing at all will be required at Russell Road. Separate discussion re Phase 1b still continuing. | See "SCOOP" email received from BD 100407 Agreed in principle. Tie requires to make final decision. | [5 empty] | 56809 | 56809 | [5 empty] | BBS to check equipment included and advise. ASAP
158 | Power Supply (up to passenger operation) - possible over allowance in DFBC | Traction Power | [7 empty] | 300000 | 300000 | 300000 | [14 empty] | Subject to tie demonstrating evidence.
| TRACTION POWER TOTAL |  |  | 0 | 0 |  | 1468742.4 | 56809 | 0 | 1825551 | 300000 | 300000 |  |  |  | 0 | 0 | 0 | 0 | 56809 | 56809 | 0 | 0
New | Other unidentified VE items | Other | [8 empty] | 1000000 | 0 | [14 empty] | Need specifics for BBS commitment therefore zero.
| UNIDENTIFIED VE TOTAL | [9 empty] | 1000000 | 0
[12 empty] | 0 | [14 empty] | Need specifics for BBS commitment therefore zero.
NEW INITIATIVES AGREED AFTER MAIN MEETING
New | Further project management integration over 3 years | [10 empty] | 500000 | [14 empty] | Joint target
New | SDS design scope economy, variation and reduction | [10 empty] | 500000 | [14 empty] | Joint target
New | Tramstops, standard finishes to circa 20-30% of stops | [10 empty] | 500000 | [14 empty] | Joint target
New | Picardy place level flexing - MUDFA savings | [10 empty] | 500000 | [14 empty] | tie led initiative
New | Picardy place level flexing - construction savings | [10 empty] | 500000 | [14 empty] | Joint target
NOTE | BB agreement to reduce fixed price £120,000 | [10 empty] | 120000 | for the record only (not part of VE savings) | [13 empty] | BB risk
NOTE | Siemens agreement to reduce fixed price on item 49 above by £10,000 | [10 empty] | 10000 | [14 empty] | Siemens risk
NOTE | Siemens agreement to reduce fixed price on item 145 above by £200,000 | [10 empty] | 200000 | [14 empty] | Siemens risk
New | Value engineer finishes on EPV and other structures | Structures | [9 empty] | 170000 | [14 empty] | Subject to approval by NEL/CEC
| NEW VE INITIATIVES TOTAL | [9 empty] | 0 | 3000000
DEFINITIONS
| BANKED' | Items offered by bidders or developed by project team.
| IN PROGRESS' | Potential for further saving (undisclosed)
| CLOSED' | No Value / Dead
| REJECTED' | Value exists but not attainable
| OPEN' | Active Item under review
Rev 27_11.10.7 - updated to include Geoff's assessemnt of category 1s
| TOTAL | [10 empty] | 18638006
[12 empty] | -4700000 | Less NR Immunisation (net Client side cost of £3m in bid)
[12 empty] | -120000 | Less item above included for info only
13818006