## COST SUMMARY_Level 3
Edinburgh Tram Network
PROJECT COST SUMMARY - LEVEL 3
A | B | C | D | E | F | G | H | E | F | G
Line 1a & 1b Airport to Newhaven and Roseburn to Granton SQR |  |  |  | Previous Budget (TS Aug 06 Report) |  | Latest Budget
LEVEL 1 Ref | Fin Code | Work Package | Funding | Line 1a & 1b | Line 1b | Line 1a & 1b | Line 1b | Line 1a | Line 1b | Line 1a & 1b
Proj Mgnt etc |  | tie Project Management |  | 18694000 |  | 64698032 | 2398894 | 62299138 | 2398894 | 64698032
Design |  | Design |  | 22266484 | 2000000 | 26084976 | 1832985 | 24251991 | 1832985 | 26084976
Land & Property |  | L&P/TRO's LEGALS |  | 45335654 | 3901996 | 25528917 | 3873000 | 21655917 | 3873000 | 25528917
Proj Mgnt etc |  | COMMS/MKTG |  | 3559004 |  | 3170324 | 134028 | 3036296 | 134028 | 3170324
Proj Mgnt etc |  | INSURANCE |  | 6949380 |  | 1982298.68 | 218210.1182 | 1764088.5618 | 218210.1182 | 1982298.68
Utilities |  | UTILITIES - MUDFA |  | 52538000 | 5181783 | 47125000 | 5458204 | 41666796 | 5458204 | 47125000
Utilities |  | UTILITIES - Ancillary |  | 6271835 |  | 11500000 | 1512449.3528 | 9987550.6472 | 1512449.3528 | 11500000
Infrastructure |  | INFRACO # |  | 271641775 | 47478544
|  | Prelims |  |  |  | 36971233 | 7339241 | 29631992 | 7339241 | 36971233
|  | A - Trams |  |  |  | 1239314 | 244550 | 994764 | 244550 | 1239314
|  | B1 - Track & Formation |  |  |  | 75129134 | 17886406 | 57242728 | 17886406 | 75129134
|  | B2 - Tram Stops |  |  |  | 4613698 | 1395735 | 3217963 | 1395735 | 4613698
|  | B3 - Depot |  |  |  | 21162690 |  | 21162690 | 0 | 21162690
|  | B4 - Highways |  |  |  | 18230701 | 3199818 | 15030883 | 3199818 | 18230701
|  | B5 - Buildings |  |  |  | 1779773 | 325973 | 1453800 | 325973 | 1779773
|  | B6 - Structures |  |  |  | 27280042 | 6073196 | 21206846 | 6073196 | 27280042
|  | C - Supervisory & Comms |  |  |  | 14293349 | 2985522 | 11307827 | 2985522 | 14293349
|  | D - E&P |  |  |  | 26329682 | 5061093 | 21268589 | 5061093 | 26329682
Infrastructure |  | Advance Work Packages |  | 5000000 |  | 3214147 | 38642 | 3175505 | 38642 | 3214147
Tram Vehicles |  | TRAMCO |  | 75640000 | 9760000 | 57173572 | 7441751.2258 | 49731820.7742 | 7441751.2258 | 57173572
Other Third Party Wks |  | THIRD PARTY AGREEMENTS |  |  |  | 8647139 | 499140 | 8147999 | 499140 | 8647139
Proj Mgnt etc |  | OTHER |  |  |  | 3768454 |  | 3768454 | 0 | 3768454
|  | Miscellaneous |  | 352569 |  |  | 0 | 0 | 0 | 0
|  | OCIP deduction only Infraco and Tramco |  | -6761835 |  |  |  | 0 | 0 | 0
|  | Pre March 05 Costs |  | 3093000 |  |  |  | 0 | 0 | 0
|  | RISK Specified Contingency P90 (Including OB) |  | 87134948 | 8671175 | 57400000 | 5000000 | 52400000 | 5000000 | 57400000
|  | SUB TOTAL IMPLEMENTATION COSTS | 545000000 | 591714814 | 76993498 | 537322475.68 | 72918837.6968 | 464403637.9832 | 72918837.6968 | 537322475.68
|  | Inflation | INC |  |  | 55086347.7335 | 7263595.5472 | 47822752.1863 | 7263595.5472 | 55086347.7335
|  | TOTAL PROJECT COSTS | 545000000 | 591714814 | 76993498 | 592408823.4135 | 80182433.244 | 512226390.1695 | 80182433.244 | 592408823.4135
Opportunities:-
Reversion to 6/12 service pattern (reduction in trams)
Omit Section from Ocean Terminal to Newhaven
Depot - moving existing runway
[6 empty] | 0 | 0
# Includes INFRACO Adjustments