## Contract Change Order
tie CHANGE ORDER
Project: | Infraco
Date: | 6th August 2012
Change Estimate No: | Refer to TNC 539
Change Order No: | 529 Rev A
Change Description: | Rev 3A to Rev 4 - Delay Costs September 2011 and Completion Date 8 July 2014
Change Value | £4,541,161.00*
Scope of Works:- | This tie change order is issued to give a point of reference per the Infraco / T&T / CEC meeting of 11th July 2012. This change order is supplementary to Change Order No. 529, which provided affect and recognised the Independent Certifier's Opinion regarding the Rev 3A Rev 4 programme, dated 21 December 2011. In particular this changer order requests that the aspect of agreeing and implementing milestones should be enacted. Milestone values and dates should be agreed no later than 24th August 2012. *The milestones and values should be assessed, calculated and agreed to ensure a nett single allowance, taking into account any recovery made under other events or change instructions, all as detailed in the Certifier's Opinion of 21st December 2011.
Relief required from compliance with Infraco obligations under the contract:- | To Be Assessed
Programme impact and required Extension of Time:- | To Be Assessed
Impact on Performance:- | None
Any additional Consents, Land Consents and/or Traffic Regulation Orders:- | To Be Assessed
Any amendment or revision required to existing Consents, Land Consents and/or Traffic Regulation Orders:- | To Be Assessed
Any new agreements with third parties:- | To Be Assessed
Any amendment required to the Agreement or the Key Subcontracts as a result of this Change:- | To Be Assessed
Proposed Method of Delivery of this Change:- | As Approved Infraco Proposals and Method Statements
Any Changes required to the terms of the Agreement and/or the SDS Contract:- | None
Effect on Milestone Payments:- | To Be Assessed
Authorised: |  | Date:
Title/Name: Julian Weatherley |  | Signature:
Received: |  | Date:
Name: |  | Signature:

## Explanatory Notes
CONTRACT CHANGE ORDER
Definitions
1 | Contract Change Order:A Change Request and Estimate (when applicable) which have been approved by The Change Owner.
2 | Change Originator:-is the originator of a Change Request. A change originator submits a change request to a change owner .
3 | Change owneris Project Manager, who is accountable for the inclusion of all change impacts and other relevant necessary information in the preparation of the required change forms and tracking the progress of a change request through the entire change process.
4 | Scope-as contained in a Contract.
5 | Order Value-the value agreed.
Distribution
the Originalis to the Change Originator.
One Copyis to the Change Owner.