## Status Papers
This document is prepared for the purposes of assisting negotiations between CEC and Scottish Water and is subject to further detailed development and subsequent final agreement between CEC and Scottish Water. This document or any of its terms are not intended to have any legally binding effect whatsover and for the avoidance of doubt, this document or any of its terms, does not constitute an agreement between the parties.
Status Papers grouped by issue | Update as at 20 January 2014
Primary Issue | Secondary Issue | Tertiary Issue | Quaternary Issue | CEC Progress Update as at 20 January 2014
1A Buildovers | 2A Deeds of servitude |  |  | CEC to advise. CEC to secure private landowner's agreement.
| 19A Scope drawings |  |  | CEC to confirm that designs are compliant or request derogation. [NB: Are CEC happy to take on this design risk?]
| 35A Haymarket Viaduct |  |  | CEC to secure access agreement with Network Rail
| 49A Haymarket Yards pipe under kerb and in DKE |  |  | CEC to pay "extra over" costs in the event of failure of buried infrastructure. Subject to extent and duration of "extra over" cost liability being agreed.
34A Cost Neutrality | DKE+2 |  |  | In the event that infrastructure is not moved, CEC to pay extra over. Not consequential costs. Subject to extent and duration of "extra over" cost liability being agreed.
| 10A Dublin Street Steps |  |  | In the event that infrastructure is not moved, CEC to pay extra over. Not consequential costs. Subject to extent and duration of "extra over" cost liability being agreed.
| 22A Section 7 Private supply pipe |  |  | CEC to provide agreement referred to by T&T
| 27A York Place Piling |  |  | CEC to pay "extra over" costs in the event of failure of buried infrastructure. Subject to extent and duration of "extra over" cost liability being agreed.
| 54A Site wide derogations | 11A Princes Street Derogations | 56A Jenners MH | Princes Street gardens (11A) and Jenners (56A) as per 49A above (otherwise file note attached to 11A is dealt with on a case by case basis). Subject to extent and duration of "extra over" cost liability being agreed.
Non Compliant Works | 3A Fire Hydrants |  |  | 100 Hydrant caps to be supplied. T&T have stated hydrants to be BS5750. CEC to ensure stand pipe can be fitted. Replace Shandwick Place hydrant. Ensure Broughton hydrant is operational. Subject to extent of this obligation being clearly defined within any final agreement.
| 9A Lead Replacement |  |  | Lead replacement in Leith re-visited and insofar as possible replaced in 2013. In the event of further excavations then opportunistic replacement will be executed. CEC to provide works information to assist cost recovery for Scottish Water. Subject to extent of this obligation being clearly defined within any final agreement.
| 14A Defects - general | 13A York Place Leaking Couplers 40A York Pl power ducts 41A Leaking Dav at Gogar depot 42A York Pl Section of main in concrete 43A York Pl junc SAS 125mm under ducts 50A Seized bypass Palmerston Pl 52A Carrick Knowle displaced joint |  | Defects liability period - 2 years
| 15A West Register Street |  |  | Leave asset in situ; CEC offering new berth.
| 16A Gogar Landfill sewers |  |  | CEC to offer final draft of agreement to Scottish Water.
| 17A 450 Thrust block |  |  | SW to build at market rates. CEC to reimburse. Subject to extent and duration of "extra over" cost liability being agreed.
| 24A St Andrews Sq drainage | 51A SAS MH North FIM 71-75 |  | Infraco to complete snagging. T&T to sign off.
| 25A Site wide drainage connections | 23A A8 drainage adoption 31A Bankhead drainage connection 32A Carrick Knowle footpath flooding |  | A8 adoption documents to be issued by CEC. T&T to provide list of drainage connections
| 29A Elder Street Sewer |  |  | No action
| 30A Water of Leith Manhole |  |  | No action
| 44A repairs to Crawley Tunnel |  |  | No action
| 55A Generic Water gas separation |  |  | No action
Safety/Handover | 4A Legacy Handoverpacks |  |  | CEC to cover reasonable cost for SW to carry out completion survey works. SW to provide cost estimate. Subject to extent and duration of "extra over" cost liability being agreed.
| 5A Post September 11 Handover Packs |  |  | Confirmation from SW that T&T have issued all information packages.
| 18A Stray Current |  |  | CEC to share information from Operator on stray current monitoring in accordance with obligations of Infraco to share relevant information under the Infraco Contract.
| 20A CCTV |  |  | No action
| 33A Bylaws |  |  | Complete
| 36A Health & Safety CDM |  |  | T&T to issue final package
| 37A Training |  |  | Complete
| 60 Transfer of assets |  |  | CEC to provide back to back defects liability per Infraco and McNicholas contract
Commercial | 6A Legacy Costs |  |  | CEC offer to settle by payment to SW of £700,000. Payment of the settlement sum will be in full and final settlement of all claims, past, present or future, arising from or related to any SW Assets, subject to CEC's obligations to make payment of certain extra over costs isfofar as CEC/SW agree.
| 7A Post September 11 Costs |  |  | SW only to recover TQ costs on close out actions (in addition to 6A and 4A). Subject to extent and duration of TQ cost liability being agreed.
| 8A Staff Resourcing |  |  | As per 7A. Subject to extent and duration of TQ cost liability being agreed.
| 39A Grosvenor St sewer collapse |  |  | SW to recover from insurance
12A Leith Walk |  |  |  | See points agreed generally - item (9)
Closed | 26A Russel Rd Sevice |  |  | Closed
| 45A steel place b'twn gas and water |  |  | Closed
| 46A service crossing to St Johns Church |  |  | Closed
| 47A Mound 315mm crossing close to gas |  |  | Closed
| 13A Leaking couplers |  |  | SW to check failure position
| 31A Bankhead Drive |  |  | No action
| 32A Carrick Knowe |  |  | Report to be prepared by T&T to confirm no issue
| 44A Crawley Tunnel |  |  | No action
| 51A Manhole - St Andrew Square |  |  | No action
| 52A Carrick Knowe joint |  |  | Corrective action proposal by T&T from CEC to SW

## General Points
This document is prepared for the purposes of assisting negotiations between CEC and Scottish Water and is subject to further detailed development and subsequent final agreement between CEC and Scottish Water. This document or any of its terms are not intended to have any legally binding effect whatsover and for the avoidance of doubt, this document or any of its terms, does not constitute an agreement between the parties.
Scottish Water / City of Edinburgh Council
Points Agreed Generally
1. | Settlement Sum: CEC to make payment of cash settlement of the sum of £700k in full and final settlement of all claims, past, present, or future, arising from or related to any SW Assets, subject to CEC's obligations to make payment of certain extra over costs (with the extent and duration of such obligations to be agreed between SW and CEC).
2. | Scottish Water Entitlement: SW will have no entitlement to payment beyond those amounts paid up to Autumn 2013, subject to an entitlement to payment for certain "extra-over" costs and an entitlement to payment for certain TQ Costs (subject to CEC and SW agreeing: (i) the specific items in respect of which SW is entitled to these payments; and (ii) the extent and duration of CEC's obligation to make payment of these costs).
3. | SW Remedial Work: Scottish Water to execute work to Thrust Block to existing 450mm diameter ductile iron water main at Bankhead Drive to be carried out at market rates. CEC will be liable for the reasonable cost of this work, subject to point 2, above
4. | CEC Remedial Work: Leith (Picardy to Granton) - CEC to remediate work commenced by MUDFA and not completed to prevailing (2007-2009) standard on opening up the apparatus at the time of executing Leith tram line extension, or within 10 years; or in the event of failure (EO cost only), whichever is the earlier.
5. | Access: SW will be entitled to gain access to its entire infrastructure, in accordance with relevant statutory provisions. Cost of obtaining access should be agreed between parties on an item by item basis.
6. | Deliverables – Stray Current: CEC to share all information on stray currents, in line with the information which it receives from Infraco on stray currents, under the Infraco Contract.
7. | Deliverables – MUDFA/H&S: CEC to provide confirmation of, and record, the known position of MUDFA (including Health and Safety packages).
8. | Deliverables - Health and Safety: All works Health and Safety files executed by McNicholas to be forwarded to SW.
9. | Entire Agreement: Parties acknowledge that the draft "TEL Agreement" and the draft "Derogations Agreement" were never entered into or executed by either Party and therefore have no legal binding effect of any kind whatsoever. Any future settlement agreement entered into between the parties will constitute the entire agreement between the parties and will supersede and extinguish all previous agreements, promises, assurances, warranties, representations and understandings between them, whether written or oral, relating to its subject matter.
10. | Non-Interference: CEC and SW agree, working collaboratively, not to interfere with, or deprive, the rights of the other relating to each parties respective infrastructure.