## Scoring sheet
tie Draft Tram line 1, 2 and [3] |  | 2003-07-31 |  |  | Appendix 1
Scorer name | puk, FM, Motts, GT DLA
PROCUREMENT STRATEGY INFRACO
SCORING SHEET | combine
Procurement Options
CRITERIA | MEASURES | Full PFI, 100% availability payment | Hybrid PFI, mix availability / milestone payment | DBFM, tie Buy Trams | DBFM, tie Lease Trams | Public Sector Procurement
Cost and Affordability | Total Capital Cost Limit | 3 | 3.4 | 3 | 3.8 | 1.75
| Operating Cost | 3.4 | 3.2 | 3 | 3.4 | 2
| Affordability | 2.8 | 3.4 | 2.8 | 3.1 | 2.75
System Integration | Network benefits | 3.2 | 3.6 | 3.3 | 3.2 | 3.25
Interface issues | Performance | 3.6 | 4 | 2.4 | 2.8 | 2.5
Deliverability | Overall timescale | 2.2 | 2.6 | 3 | 3.2 | 3.5
| Implication on other interested third parties | 2.2 | 2.4 | 2.6 | 2.4 | 3.25
| Fundability | 3.2 | 4.2 | 3.6 | 3.6 | 2
| Practicality | 2.6 | 3.2 | 2.8 | 3 | 3.5
Risk transfer and Value for Money | Risk transfer | 3.4 | 3.8 | 2.6 | 3.2 | 1
| Impact on City of Edinburgh Council | 4 | 3.5 | 2.8 | 3.2 | 1.5
| Extensions | 2.4 | 2.8 | 3.1 | 3.3 | 4.25
TOTAL |  | 36 | 40.1 | 35 | 38.2 | 31.25
Excludes Motts as no response received to date
Over arching concepts
Partnering / framework arrangement
Advantages | If lines procured incrementally, allows for potential retention of same infraco partner. This may be one
means of avoiding the system integration risk of a new infraco partner. Also allows for potential sharing
of knowledge/value engineering on later lines.
Risk sharing
open book
greater opportunity to share benefits /savings
Agreed rates, better defined, less opportunity for change
Diadvantages | Lack of competition for later lines - potential difficulty in demonstrating vfm
Contractual arrangements
tie retain greater share of risk
higher risk of cost escalation
greater inflationary elements
Setting schedule now and less able to deal with future change
more complex contract structure
Utilities in / out
Advantages | in
| better integration with alignment design | [5 empty] | If out. potential time saving, but cost/risk for tie.
programme risk and cost with contractor
reduces direct claim issues
gives contractor management control
out
benefit from 7.5% tax discount
better contractual terms between public sector and utility companies
ability to commence works early, reducing programme
no charge by contractor for management of works
Disadvantages | in
stats may not accept working with contractor (or may charge a premium cost)
loss of discount
contractor will charge a management cost
possible lengthening of programme particularly if long lead times required
out
responsibility for programme rests with tie
any alignment change could incur cost
less optimistic with overall design
upfront payment by public sector