## Summary
Current
Project |  | Budget
|  | Total Value at Phoenix | Change Since Phoenix Date | Draft Final Account | Based on B & S Payment Certificate No 78 | Difference | Current Budget | Reported. (Based on AfP 78 to 1st Feb 2014) | Draft final account application at 22/7 | Difference reported - final account | Difference | Comments
|  | a | b |  |  |  | c
90A | Design Core Scope & Design Change | 6613362 | 1349254.51 | 7962616.51 | 7907826.99 | 54789.52 | 7929647.26 | 8022241.31 | 7962616.51 | -59624.8 | -92594.05 | Reduction in value of change register £30,300. Does not include Changes on account £62,294.
91A | PH 4 - Construction Support (TQ's / As-Builts) | 1104688 | -50000 | 1054688 | 989323.78 | 65364.22 | 989323.78 | 1104688 | 1054688 | -50000 | -115364.22 | Assumed as lump sum
92A | ECS | 3439542 | -145305.44 | 3294236.56 | 3294236.56 | 0 | 3294237 | 3294237 | 3294236.56 | -0.44 | 0
93A | Design Support | 1077656 | -8139 | 1069517 | 1069517 | 0 | 1069517 | 1069517 | 1069517 | 0 | 0
90485A | Design Completion | 459643 | 0 | 459643 | 459643 | 0 | 459643 | 459643 | 459643 | 0 | 0
74A | Prolongation | 907593 | 0 | 907593 | 907593 | 0 | 907593 | 907593 | 907593 | 0 | 0
42A | Direct Sell |  |  | 281743 | 281743 | 0 | 281743 | 281743 | 281743 | 0 | 0
| Contra Charge to B & S |  | -656727.96 | -656727.96 | -609227.96 | -47500 | -609227.96 | -589227.96 | -656727.96 | -67500 | -20000
|  | 13602484 | 489082.11 | 14373309.11 | 14300655.37 | 72653.74 | 14322476.08 | 14550434.35 | 14373309.11 | -177125.24 | -227958.27

## Change Register
Edinburgh Tram Network
Design Change Register
|  |  |  | By B&S |  | By SDS |  |  |  | By B&S | [5 empty] | By B&S | By SDS - to 07 Dec 13 |  |  | Bilfinger & Siemens
Index | INTC/PMC | Short Title | Full Description | Change Notification |  | Change Estimate | Date | Standard | Value | Change Order | Date | Value | Change Status | Completion | August Application BBS comment | Previously Certified | Application Value | Current Variance/Application | Current SDS Comment | Assessment Value | Assessment Period | Assessment Variance | Assessment Comments
DCR0001 | 30 | IDC Gogarburn Bridge | Additional IDC required to maintain programme for Gogarburn Bridge |  |  | DCR0001 | 2008-05-22 | 0 | 0 |  |  |  | Withdrawn | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0002 | 31 | Telford Road Bridge - Single Handrail Detail | CEC have asked for a single handrail detail drawing at the stepped access. This is additional to Employers Requirements | RDC029 | 2008-09-01 |  |  |  | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0003 |  | Design Review Process | Content and Expectations of Design Review process as tie see it | [5 empty] | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0004 | 103 | Saltire Square Tramstop | Planning Application required for DDA compliant access requires retaining walls extending outwith the LoD |  |  | DCR0004 | 2008-05-29 | 0 | 0 |  |  |  | Withdrawn | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0005 | 42 | Ravelston Tramstop Landscaping | CEC have instructed PB verbally to provide area of ground cover pending and relocate tree. Already received planning and IFC sent | RDC040 | 2008-09-01 | DCR0005 | 2008-10-03 | 0 | 2052 | DCO043 | 2009-06-05 | 2052 | Completed | 100% |  | 2052 | 2052 | 0 |  | 2052 | 0 | 0
DCR0006 | 93 | Lindsay Rd, Ocean Drive, Ocean Terminal and Tower Place Planning Permissions | CEC request for full Planning Applications and subsequent Prior Approvals required |  |  | DCR0006 | 0 | 0 | 0 |  |  |  | Withdrawn | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0007 | ATR | Murrayfield Stadium Retaining Wall technical meeting | Request from David Taylor design change. Meeting arranged for Tuesday 17th June | [5 empty] | 0 |  |  |  | Superseded |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0008 | 325 | Advertisement Consents | CEC have intimated at meetings that Advertisements and PID's may require to be relocated. This change for consent work only | RDC048 | 2008-09-01 | DCR0008 | 2009-02-02 | 0 | 0 |  |  |  | Withdrawn | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0009 | 94 | Hilton Hotel Full Planning | Planning Application required as work design lies outwith the LoD | RDC049 | 2008-09-01 | DCR0009 | 2008-06-17 | 0 | 0 |  |  |  | Withdrawn | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0010 | 95 | Additional Depot Prior Approvals | CEC have instructed SDS to submit 3nr Prior Approvals in lieu of 1nr |  |  | DCR0010 | 2008-06-17 | 0 | 0 |  |  |  | Withdrawn | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0011 | 96/43 | Shandwick Place CEC preferential Treatments | CEC request relocation of tramstop, change position of street lighting | RDC006, RDC032, RDC037, RDC041 | 2008-09-01 | DCR0011 | 2008-09-02 | 0 | 48087 | DCO030 | 2009-04-23 | 48087 | Completed | 100% |  | 48087 | 48087 | 0 |  | 48087 | 0 | 0
DCR0011a | 96/43 | Shandwick Place CEC preferential Treatments Preliminary Design |  | letter | 2008-10-02 | DCR0011a | 2008-10-16 | 0 | 12788 | DCI007 | 2008-11-20 | 12788 | Completed | 100% |  | 12788 | 12788 | 0 |  | 12788 | 0 | 0
DCR0012 | NA | Gogar Interchange Options | Optioneering at Gogar Interchange - 11 nr different options | [5 empty] | 0 |  |  |  | Superseded |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0013 | NA | Disability Consultation Group Barcelona | TEL/tie consultation of tram mock up in Barcelona | RDC047 | 2008-09-01 |  |  |  | 0 |  |  |  | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0014 | 48 | Additional Copy TRO Drawing | Request from tie on 17/06 for additional copy of TRO Drawing | RDC046 | 2008-09-01 | DCR0014 | 2008-07-04 | 0 | 3128 | DCO010 | 2009-02-06 | 3128 | Completed | 100% |  | 3128 | 3128 | 0 |  | 3128 | 0 | 0
DCR0015 | 78 | Redesign Gogarburn Retaining Wall | Alterations to Retaining Wall design along Gogarburn and Airport Kiosk | RDC018 & RDC055 | 2008-08-22 | DCR0015 | 2008-08-20 | 0 | 41414 | DCO015 | 2009-02-06 | 41414 | Completed | 100% |  | 41414 | 41414 | 0 |  | 41414 | 0 | 0
DCR0016 | 97 | Balgreen Road Bridge Amending Technical Design | During the CEC meeting on 29/05 instruction given for additional work |  |  | DCR0016 | 2008-09-03 | 0 | 2085 | DCO037 | 2009-05-15 | 2085 | Completed | 100% |  | 2085 | 2085 | 0 |  | 2085 | 0 | 0
DCR0017 | 84 | Burnside Road Diversion | Design Fee only required for the design of Burnside Road Diversion including a like for like replacement of the existing Burnside Road | RDC016 | 2008-08-04 | DCR0017 | 2008-08-26 | 0 | 0 |  |  |  | Withdrawn | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0018 | 65 | Murrayfield Stadium Retaining Wall Patterned Finish | CEC Planning asked for patterned finish | RDC007 | 2008-07-28 | DCR0018 | 2008-08-18 | 0 | 2382.5 | DCO024 | 2009-04-01 | 2382.5 | Completed | 100% |  | 2382.5 | 2382.5 | 0 |  | 2382.5 | 0 | 0
DCR0019 | 67 | Murrayfield Tram Stop Design Change | Design Change - architectural, structural and landscaping design | RDC008 | 2008-07-28 | DCR0019 | 2008-08-18 | 0 | 27809.5 | DCO016 | 2009-02-06 | 27809.5 | Completed | 100% |  | 27809.5 | 27809.5 | 0 |  | 27809.5 | 0 | 0
DCR0020 | VE | Delete Depot pumping Station/ Storm Tanks | Delete Depot pumping Station/ Storm Tanks | RDC001 | 2008-07-28 | DCR0020 | 2008-08-20 | 0 | 0 |  |  |  | Closed | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0021 | VE | Depot Future Expansion | Build Depot now with future expansion and reduce car park | RDC002 | 2008-07-28 | DCR0021 | 2008-09-15 | 380 | 0 |  |  | 0 | Completed | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0022 | VE | Delete one pavement at Depot | Delete one pavement at Depot | RDC003 | 2008-07-28 | DCR0022 | 2008-08-18 | 0 | 0 |  |  |  | Closed | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0023 | VE | Delete Concrete Apron to Security Fence at Depot | Delete Concrete Apron to Security Fence at Depot | RDC004 | 2008-07-28 | DCR0023 | 2008-08-18 | 0 | 0 |  |  |  | Closed | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0024 | VE | Roseburn Street Viaduct VE |  | RDC021 | 2008-08-29 | DCR0024 | 2008-09-03 | 0 | 316619 | DCO011 (was DCI005) | 2009-02-06 | 316619 | Completed | 100% |  | 316619 | 316619 | 0 |  | 316619 | 0 | 0
DCR0024a | VE | Roseburn Street Viaduct VE Preliminary design |  | letter | 2008-10-03 | DCR0024a | 2008-10-22 | 0 | 25773 | DCI006 | 2008-11-20 | 25773 | Completed | 100% |  | 25773 | 25773 | 0 |  | 25773 | 0 | 0
DCR0025 | 17 | South Gyle Access Road | South Gyle Access Road: New Bridge foundations and piling not to clash with sewer | RDC005 | 2008-07-28 | DCR0025 | 2008-08-05 | 0 | 0 |  |  |  | Superseded | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0026 | VE | Change Initial Depot Design VE | [6 empty] | 0 | DCI004 | 2008-10-13 | 0 | Withdrawn | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0027 | VE | Edinburgh Park Viaduct VE | [6 empty] | 0 | DCI002 | 2008-10-13 | 0 | Withdrawn | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0028 | VE | A8 Underpass VE | [6 empty] | 0 | DCI003 | 2008-10-13 | 0 | Withdrawn | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0029 | VE | Water of Leith VE | [6 empty] | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0030 | VE | Maintenance Walkway Structures VE | [6 empty] | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0031 | VE | Split Vehicle Accommodation Bogies VE | [6 empty] | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0032 | VE | RationaliseTrack Maintenance Equipment VE | [6 empty] | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0033 | VE | Carricknowe Bridge Parapet VE |  | RDC022 | 2008-08-27 |  |  |  | 0 |  |  |  | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0034 | VE | Reduce Kerb and Associated Re-instatement of Pavement VE | [6 empty] | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0035 | VE | Reduce Drainage Run form Guideway VE | [6 empty] | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0036 | VE | Reconstituted Planing VE |  |  |  | DCR0036 | 2011-06-15 | 0 | 0 |  |  | 0 | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0037 | 32 | IFC South Gyle Access Road Bridge and Bankhead Retaining Wall | Delay in IFC due to CEC not logging application | RDC030 | 2008-08-27 | DCR0037 |  |  | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0038 | 36 | IFC Crewe Road Gardens Bridge | IFC Crewe Road Gardens Bridge revised priority to Haymarket Tramstop | RDC034 | 2008-09-01 | DCR0038 |  |  | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0039 |  | IFC Caroline Park Tramstop | Design Changes requested by CEC | [5 empty] | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0040 | 46 | IFC Murrayfield Tramstop and Retaining Wall | Delay by CEC validating approval | [5 empty] | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0041 | 28 | IFC Balfour Street, 1B Roads, etc | IFC Balfour Street, 1B Roads, Street Lighting, Landscape and Drainage CEC late in response | RDC026 | 2008-09-01 | DCR0041 |  |  | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0042 | 27/ 34/ 39 | IFC Shandwick Place Tramstop, 1D Roads, etc | IFC Shandwick Place Tramstop, 1D Roads, Street Lighting, Landscape and Drainage - late formal comments by CEC | RDC025 | 2008-09-01 | DCR0042 |  |  | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0043 | 37 | IFC Roseburn Terrace Bridge, Roseburn Tramstop, Roseburn Retaining Wall | IFC Roseburn Terrace Bridge, Roseburn Tramstop, Roseburn Retaining Wall - CEC request design change | RDC035 | 2008-09-01 | DCR0043 |  |  | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0044 | 33 | IFC Balgreen and Baird Drive Structures | IFC Balgreen and Baird Drive Structures - late comments from Network Rail and changes from CEC | RDC031 | 2008-08-27 |  |  |  | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0045 | 41 | IFC Ravelston Tramstop, Ravelston Dykes Bridge, Roseburn Retaining Walls | IFC Ravelston Tramstop, Ravelston Dykes Bridge, Roseburn Retaining Walls - CEC request reprioritisation | RDC039 | 2008-09-01 | DCR0045 |  |  | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0046 | NA | IFC 3C Roads, Street Lighting, Landscape and Drainage | IFC 3C Roads, Street Lighting, Landscape and Drainage late comments by CEC | [5 empty] | 0 |  |  |  | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0047 | 35 | Bernard Street Tramstop - Extend CEC Public Realm | Bernard Street Tramstop - Extend CEC Public Realm | RDC033 | 2008-09-01 |  |  |  | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0048 | 122 | IFC Foot of the Walk Tram Stop | IFC Foot of the Walk Tram Stop - late Prior Approval by CEC | RDC043 | 2008-09-01 | DCR0048 |  |  | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0049 | 78 | IFC 7A Roads, Airport Tram Stop and Gogarburn Retaining Walls | IFC 7A Roads, Airport Tram Stop and Gogarburn Retaining Walls - Delayed due to impending changes | [5 empty] | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0050 | BSC | BB Information for Building Warrants Section 1 | BB Information for Building Warrants Section 1 | [5 empty] | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0051 | BSC | BB Information for Building Warrants Line 2 | BB Information for Building Warrants Line 2 | [5 empty] | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0052 | 57 | IFC Section 1D | IFC Section 1D no formal comments received | RDC044 | 2008-09-01 | DCR0052 |  |  | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0053 | 55 | IFC 3C Roads, Street Lighting, Landscape and Drainage | IFC Section 3C Roads Street Lighting Landscape and Drainage no formal comments received | RDC042 | 2008-09-01 | DCR0053 |  |  | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0054 | 65 | Roseburn Street Viaduct and Murrayfield Stadium Retaining Wall | Roseburn Street Viaduct and Murrayfield Stadium Retaining Wall - CEC blockwork changes | [5 empty] | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0055 | 100 | IFC Sections 5B & 5C | IFC Sections 5B & 5C - no formal comments | [5 empty] | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0056 | 60 | RBS Bunded Material | RBS Bunded Material - response to tie correspondence | RDC012 | 2008-08-04 |  |  |  | 0 |  |  |  | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0057 | 26 | Picardy Place Delay of Issue to CEC for Prior Approval | Picardy Place Delay of Issue to CEC for Prior Approval - change instructed at Novation | RDC024 | 2008-09-01 | DCR0057 |  |  | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0058 | 29 | Haymarket Station Car Park TQ | Haymarket Station Car Park TQ - in response to tie correospondence | RDC027 | 2008-09-01 |  |  |  | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0059 | BSC | Protocol Relating to Issue of design Information | Production of dwg's for BSC |  |  | DCR0059 | 2009-12-17 | 0 | 18751 | DCO113 | 2010-01-20 | 18751 | Completed | 100% |  | 18751 | 18751 | 0 |  | 18751 | 0 | 0
DCR0060 | BSC | IFC S22B Balgreen Road Access Road Bridge | IFC S22B Balgreen Road Access Road Bridge - no access to Network Rail land | [5 empty] | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0061 | 90 | Attending Workshops | Attending Workshop for VE exercise | [5 empty] | 0 |  |  |  | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0062 | 61 | Gogar Surcharge Utilisation | Feasibility of using material temporary stockpiled within Gogarburn Embankment | RDC050 | 2008-09-01 | DCR0062 | 2008-08-01 | 0 | 0 |  |  | 0 | Completed | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0063 | 79 | Design Alternative to Haymarket Junction | Design Alternative to Haymarket Junction | RDC045 | 2008-08-28 | DCR0063 | 2008-08-20 | 0 | 44056 | DCO021 | 2009-02-26 | 44056 | Completed | 100% |  | 44056 | 44056 | 0 |  | 44056 | 0 | 0
DCR0064 | 89 | Balfour Street Crossing | Additional Pedestrian Crossing at signalled junction (Balfour Street) | RDC069 | 2008-12-15 | DCR0064 | 2009-02-23 | 0 | 7492 | DCO032 | 2009-04-23 | 7492 | Completed | 100% |  | 7492 | 7492 | 0 |  | 7492 | 0 | 0
DCR0065 | VE | Delete Noise Attenuation VE |  | RDC014 | 2008-08-04 | DCR0065 | 2008-10-16 | 0 | 0 |  |  |  | Closed | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0066 | VE | Reduced Ballasted Track thickness VE |  | RDC015 | 2008-08-04 | DCR0066 | 2008-10-16 | 0 | 0 |  |  |  | Closed | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0067 | 279 | West Pilton Tram Stop retaining wall Annotated drawings | Note be added to the PA drawings indicating where a wall/railing arrangement will go and that it's form is to be determined in consultation with CEC | RDC085 |  | DCR0067 | 2009-06-24 | 0 | 732 | DCO065 | 2009-08-04 | 732 | Completed | 100% |  | 732 | 732 | 0 |  | 732 | 0 | 0
DCR0068 | 92 | Russell Road Retaining Wall Sewer | Russell Road Retaining Wall Sewer: existing sewer impacts on proposed piled retaining wall | RDC010 | 2008-08-01 | DCR0068 | 2009-03-26 | 0 | 0 |  |  |  | Withdrawn | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0069 | 60 | Gogarburn Bridge Sewer Diversion | Gogarburn Bridge Sewer Diversion clashes with new concrete piles | RDC009 | 2008-07-25 | DCR0069 | 2008-08-06 | 0 | 8553.25 | DCI001 | 2008-10-10 | 8553.25 | Completed | 100% |  | 8553.25 | 8553.25 | 0 |  | 8553.25 | 0 | 0
DCR0070 | 77 | Section 5C Hedge North of Tramway | Include a hedge to north of Tramway along toe of the embankment | RDC011 | 2008-08-04 | DCR0070 | 2008-08-18 | 0 | 2197.5 | DCO036 | 2009-05-14 | 2197.5 | Completed | 100% |  | 2197.5 | 2197.5 | 0 |  | 2197.5 | 0 | 0
DCR0071 | NA | Design Temporary Protection to Water Main. | Temporary Protection to allow Bulk Excavation | RDC013 | 2008-08-04 |  |  |  | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0072 | 100 | IFC Section 2A Track OLE Street Lighting Landscaping and Drainage | IFC Section 2A Track OLE Street Lighting Landscaping and Drainage: delayed - no formal comments | [5 empty] | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0073 | 33 | IFC Section 3B Roads Street Lighting Landscape and Drainage | IFC Section 3B Roads Street Lighting Landscape and Drainage no formal comments received | [5 empty] | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0074 |  | Section 1A Tower Place Bridge Parapets | CEC wish parapet design to be reviewed on Tower Place Bridge | [5 empty] | 0 |  |  |  | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0075 | 163 | Section 1D Haymarket Taxi Stance | CEC require area in front of Haymarket Railway Station to revert back to taxi stance in lieu of bus stop | RDC063 | 2008-11-11 | DCR0075 | 2008-11-19 | 0 | 22300 | DCO027 | 2009-04-14 | 22300 | Completed | 100% |  | 22300 | 22300 | 0 |  | 22300 | 0 | 0
DCR0076 |  | IFC Section 1A Victoria Docks Entrance Bridge | IFC Section 1A Victoria Docks Entrance Bridge - ongoing changes in line with Forth Ports Agreements means no defined scope | [5 empty] | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0077 | 123 | Section 1A3 Ocean Terminal By Pass Road | Section 1A3 Ocean Terminal By Pass Road: revised Forth Ports Agreement will affect the by pass road thus having an impact on TRO's Prior and Technical Approvals | [5 empty] | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0078 | 138 | Water of Leith Bridge Sewer/Foundation Conflict | Water of Leith Bridge Sewer/Foundation Conflict: design piled foundations to avoid sewer | RDC017 | 2008-08-12 | DCR0078 | 2008-11-19 | 0 | 27315.5 | DCO052 | 2009-06-08 | 27315.5 | Completed | 100% |  | 27315.5 | 27315.5 | 0 |  | 27315.5 | 0 | 0
DCR0079 | 130 | IFC Ingliston Park and Ride Tram Stop | IFC Ingliston Park and Ride Tram Stop: no formal change order | [5 empty] | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0080 |  | Tower Place Bridge Parapets | CEC wish parapet design to be reviewed on Tower Place Bridge |  |  | DCR0080 | 2009-09-04 | 0 | 0 |  |  |  | Withdrawn | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0081 | 76 | Gogar Additional Tramstop - Preliminary Design | TNC015 from tie to BSC Gogar interim report on GRIP | RDC092 (was RDC019) | 2009-02-04 | DCR0081 | 2009-03-11 | 380 | 0 |  |  |  | Superseded | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0082 | 76 | Gogar Additional Tramstop - Detailed Design | TNC015 from tie to BSC Gogar interim report on GRIP, Option 4BB | RDC092 (was RDC020) | 2009-02-04 | DCR0082 | 2009-03-11 | 0 | 340938 | DCO055 | 2009-06-16 | 340938 | Completed |  | Agreed | 340938 | 340938 | 0 |  | 340938 | 0 | 0
DCR0082A |  | Gogar Additional Tramstop - Further requirements | As per meetings post Instruction |  |  | DCR0082A | 2010-03-25 | 0 | 100876.85 | DCO121 | 2010-06-24 | 100876.85 | Completed |  | agree | 100876.85 | 100876.85 | 0 |  | 100876.85 | 0 | 0
DCR0083 | 242 | TRO Informal Consultation Plans (1) | CEC & tie changed format | RDC093 | 2009-02-06 | DCR0083 | 2009-02-25 | 0 | 20000 | DCO077 | 2009-11-09 | 20000 | Completed | 100% |  | 20000 | 20000 | 0 |  | 20000 | 0 | 0
DCR0084 | DCO013 | Q8110043292 Information for Tarmac | Carrick Knowe and Edinburgh Park beam design |  |  | DCR0084 | 2008-10-14 | 0 | 11212.5 | DCO013 | 2009-01-06 | 11212.5 | Completed | 100% |  | 11212.5 | 11212.5 | 0 |  | 11212.5 | 0 | 0
DCR0085 | 86 | Transfer of Utilities Diversions | Transfer of Utilities Diversions from MUDFA to Infraco | RDC023 | 2008-08-27 | DCR0085 | 2011-06-15 | 0 | 0 |  |  | 0 | Closed | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0086 | 172 | TAL 5/05 Pedestrian Crossing Timings | Change in Standards for Pedestrian Crossing Timings | RDC051 | 2008-08-29 | DCR0086 | 2008-10-14 | 0 | 36494 | DCO028 | 2009-04-07 | 36494 | Completed | 100% |  | 36494 | 36494 | 0 |  | 36494 | 0 | 0
DCR0087 |  | Section 1D Shandwick Place Trees | Section 1D Shandwick Place Trees, CEC interim solution for removal of trees requires additional time for CEC | [5 empty] | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0088 | 40 | Ground Investigations in Section 1A | Organisation of three sets of ground investigation surveys | RDC038 | 2008-08-27 | DCR0088 |  |  | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0089 | 126 | 1B Headspan OLE & Lighting arrangement | CEC comments dictate change from 2 centre to headspan poles | RDC087 | 2009-02-04 |  |  |  | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0090 | 81 | Environmentally friendly lighting | 5B TAA for lighting request bat friendly lighting along cycleways | RDC052 | 2008-09-09 | DCR0090 | 2008-09-30 | 0 | 8998 | DCO063 | 2009-07-28 | 8998 | Completed | 100% |  | 8998 | 8998 | 0 |  | 8998 | 0 | 0
DCR0091 | 80 | Gogarburn Retaining Wall Finish | At Prior Approval consultation CEC asked for 2nd change of finish to wall for vertical relief | RDC053 | 2008-09-09 | DCR0091 | 2008-10-09 | 0 | 4258 | DCO012 | 2009-01-20 | 4258 | Completed | 100% |  | 4258 | 4258 | 0 |  | 4258 | 0 | 0
DCR0092 | 259 | Cycleway design at Edinburgh Park Station | 5B TAA for Roads meeting request design change and Edinburgh Park Interchange | RDC088 | 2009-02-05 | DCR0092 | 2009-04-03 | 0 | 11486.5 | DCO034 | 2009-05-12 | 11486.5 | Completed | 100% |  | 11486.5 | 11486.5 | 0 |  | 11486.5 | 0 | 0
DCR0093 | 38 | RSA - Road Safety Audit Delay | RSA - Road Safety Audit Delay due to procedure - delays roads design | RDC036 | 2008-08-27 |  |  |  | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0094 | 122 | IFC Sections 1A1 and 1A2 | IFC Sections 1A1 and 1A2 Port of Leith, Bernard Street, Foot of the Walk, 1A1 & 1A2 roads Street Lighting, Landscape and Drainage: No comments from CEC | [5 empty] | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0095 | 182 | Design Changes to Airport Kiosk | As per tie letter INF_CORR.122 | RDC054 | 2008-09-25 | DCR0095 | 2008-10-23 | 0 | 11222 | DCO029 | 2009-04-16 | 11222 | Completed | 100% |  | 11222 | 11222 | 0 |  | 11222 | 0 | 0
DCR0096 | 127 | Split S16 PA from Batch 1/02 | As per TQ 160 split PA packages for strucutres Victoria Dock and Tower Place bridges to avoid IFC delay | RDC056 | 2008-09-29 | DCR0096 | 2008-10-23 | 0 | 4272 | DCO008 | 2009-01-06 | 4272 | Completed | 100% |  | 4272 | 4272 | 0 |  | 4272 | 0 | 0
DCR0097 | 129 | Request for Extension of time by CEC for PA batches 1/01a,b,c | Extension of time to determine application Newhaven Tram Stop, Lindsay Road retaining walls, Ocean Drive retaining walls | [5 empty] | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0098 | 137 | Removal of trees to create continuous layby - Constitution St | CEC Transport want to remove tree/build outs to create a continuous lay-by. This will require an amendment to the Prior Approval and CEC Planning consent | RDC089 | 2009-02-05 | DCR0098 | 2009-04-03 | 0 | 0 | DCO091 | 2010-01-06 | 0 | Withdrawn | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0099 | 136 | Picardy Place re-design | [6 empty] | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0100 | 123 | Forth Ports Section 1A3 Ocean Terminal By Pass Road | Section 1A3 Ocean Terminal By Pass Road: revised Forth Ports Agreement will affect the by pass road thus having an impact on TRO's Prior and Technical Approvals | RDC057 & RDC058 | 2008-10-10 | DCR0100 | 2008-11-06 | 0 | 47565.5 | DCO009 | 2009-01-20 | 47565.5 | Completed | 100% |  | 47565.5 | 47565.5 | 0 |  | 47565.5 | 0 | 0
DCR0101 | 278 | Wider Area Modelling | Linsig2 Modelling of Fast Answers Junctions and Optional Surveys |  |  | DCR0101 | 2008-09-23 | 0 | 6460 | DCO092A | 2010-01-06 | 6460 | Completed | 100% |  | 6460 | 6460 | 0 |  | 6460 | 0 | 0
DCR0102 | 145 | 5C Transdev comments | Transdev gave additional comments on design through Edinburgh Park - CEC forwarded letter as part of the TAA comments | RDC090 | 2009-02-04 | DCR0102 | 2009-02-27 | 380 | 0 | DCO093 | 2010-01-06 | 0 | Withdrawn | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0103 | 139 | Relocation of 5 OLE Poles to North at Tower Place Junction | OLE poles relocation requuested by CEC Transport which is different to previously approved PA via TAA comment | RDC060 | 2008-11-03 | DCR0103 | 2008-11-19 | 0 | 3935.5 | DCO094A | 2010-01-25 | 3935.5 | Completed | 100% |  | 3935.5 | 3935.5 | 0 |  | 3935.5 | 0 | 0
DCR0104 | 143 | 5C CEC comment to make Lochside up to adoptable standards | 5C CEC wish to make Lochside AVe up to adoptable standards - not previously advised to SDS | RDC062 | 2008-11-07 | DCR0104 | 2009-07-10 | 0 | 34132 | DCO071 | 2009-09-23 | 34132 | Completed | 100% |  | 34132 | 34132 | 0 |  | 34132 | 0 | 0
DCR0105 | 141 | West End Tramstop review | Review 9 options as per CEC email and tie informal request for estimate |  |  | DCR0105 | 2008-10-30 | 0 | 14170.5 | DCO031 | 2009-04-23 | 14170.5 | Completed | 100% |  | 14170.5 | 14170.5 | 0 |  | 14170.5 | 0 | 0
DCR0106 | 196 | Little King Street revisions 1C | CEC requirement to change street outwith LoD | RDC065 | 2008-11-11 | DCR0106 | 2009-01-28 | 0 | 879 | DCO025A | 2009-04-08 | 879 | Completed | 100% |  | 879 | 879 | 0 |  | 879 | 0 | 0
DCR0107 | 197 | Gyle Stop Cycleway widening | CEC requirement to widen cycleway outwith loD | RDC066 | 2008-11-11 | DCR0107 | 2009-01-28 | 0 | 9966 | DCO022 | 2009-02-26 | 9966 | Completed | 100% |  | 9966 | 9966 | 0 |  | 9966 | 0 | 0
DCR0108 | 198 | Gogar Roundabout lighting | CEC requirement to light entire roundabout portions of which go outwith outwith LoD | RDC067 | 2008-11-11 | DCR0108 | 2008-12-17 | 0 | 3866.5 | DCO026 | 2009-04-14 | 3866.5 | Completed | 100% |  | 3866.5 | 3866.5 | 0 |  | 3866.5 | 0 | 0
DCR0109 | 425 | Bernard Street Revisions outwith LOD | [6 empty] | 0 |  |  |  | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0110 | 242 | Updates to TRO drawings | Updates to drawings based on markups received from tie / CEC (K. Rimmer / A. Conway) |  |  | DCR0110 | 2008-11-21 | 0 | 0 |  |  |  | Withdrawn | 98% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0111 | 243 | Forth Ports Substation | Forth Ports have constructed a new substation on the site of the tram substation. No as-built information forthcoming. |  |  | DCR0111 | 2008-11-21 | 0 | 6664.5 | DCO054 | 2009-06-12 | 6664.5 | Completed | 100% |  | 6664.5 | 6664.5 | 0 |  | 6664.5 | 0 | 0
DCR0112 | 242 | TRO Exhibition Review | Interim presectation required | RDC093 | 2009-02-06 | DCR0112 | 2009-02-25 | 0 | 0 |  |  |  | Withdrawn | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0113 | 125 | Haymarket Internal retaining wall | additional design of wall due to unforeseen ground conditions |  |  | DCR0113 | 2008-11-19 | 0 | 12102.5 | DCO056 | 2009-06-16 | 12102.5 | Completed | 100% |  | 12102.5 | 12102.5 | 0 |  | 12102.5 | 0 | 0
DCR0114 | 179 | SRU/ Murrayfield Accomodation works | Revsion of accomodation works inc Gatehouse to comply with Final SRU agreement | RDC068 & RDC074 | 2008-11-11 | DCR0114 | 2009-02-11 | 0 | 92178.5 | DCO035 | 2009-05-14 | 92178.5 | Ongoing |  |  | 92178.5 | 92178.5 | 0 |  | 92178.5 | 0 | 0
DCR0115 | 167 | Wanderers Clubhouse alterations | Issue of detailed drawings required | RDC064 | 2008-11-11 |  |  |  | 0 |  |  |  | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0116 | BSC | A8 Underpass piling operations | Optioneering with Expanded for Piling operations | RDC061 | 2008-11-18 | DCR0116 | 2008-12-17 | 0 | 12140 | DCO023 | 2009-03-25 | 12140 | Completed | 100% |  | 12140 | 12140 | 0 |  | 12140 | 0 | 0
DCR0117 | 74 | Gogar Landfill embankment erosion | details of protection measures req for MH7601 to prevent furtehr scouring | RDC059 | 2008-10-29 |  |  |  | 0 |  |  |  | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0118 | 100 | Delay to IFC Section 1A4 | Delay of Roads, Street Lighting, Landscape and Drainage | [5 empty] | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0119 | 242 | TRO Informal Consultation Plans (2) | From comments provided from tie and CEC as outcomes of the informal exhibitions | RDC094 | 2009-02-06 | DCR0119 | 2009-02-25 | 0 | 0 |  |  |  | Withdrawn | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0120 | 228 | Bus Stop to be relocated outwith LoD | Bus Stop outside princes st mall to be relocated outwith LoD | RDC091 | 2009-02-04 | DCR0120 | 2009-04-24 | 0 | 0 |  |  |  | Withdrawn | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0121 |  | Review of Siemens documentation to asses impact on planning approvals and consents | See DC traction study, Harmonic Study, Principle Overall System Description, Control and Protection Concept incl Emergency Trip system | [5 empty] | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0122 |  | Review of Siemens OLE design to asses impact on planning approvals and consents | See SPM-REL-OCL.0320 Rev A | [5 empty] | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0123 |  | Shandwick Place change Signage Markings |  |  |  | DCR0123 |  |  | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0124 |  | South Gyle Access Road sewer change | [6 empty] | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0125 | 269 | Trackform - ground improvement and vibration mitigation |  | RDC076 | 2009-01-08 | DCR0125 | 2009-01-29 | 0 | 316075.5 | DCO018 | 2009-02-23 | 316075 | Completed | 100% | Agree [complete] | 316075 | 316075 | 0 |  | 316075 | 0 | 0 | Refer DCO 018 and Phoenix Agreement
DCR0126 | 271 | Roads construction Details methodology | Pavement methodology and pavement assessment. Price per package only. | RDC075 | 2009-01-08 | DCR0126 | 2009-01-29 | 0 | 17125.5 | DCO019 | 2009-02-23 | 17125.5 | Completed | 100% |  | 17125.5 | 17125.5 | 0 |  | 17125.5 | 0 | 0
DCR0127 | 244 | Building Fixing Owner Agreements | SDS provide a completed proforma to support their works to obtain owner agreements for OLE Building Fixings. | RDC095 | 2009-02-06 | DCR0127 | 2009-01-29 | 0 | 14265 | DCO080 | 2009-12-09 | 14265 | Closed | 100% | Agree [complete] | 14265 | 14265 | 0 |  | 14265 | 0 | 0
DCR0128 |  | Trackform structures review | [6 empty] | 0 |  |  |  | Superseded |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0129 | 273 | W14 Gogarburn retaining wall to accommodate utilities |  | RDC081 | 2009-01-19 | DCR0129 | 2009-02-25 | 0 | 0 |  |  | 0 | Withdrawn | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0130 | 375 | Redesign of OLE pole foundations in Section 1c, 1b, 1d, 1a | Section 1 Generic | RDC083 | 2009-01-29 | DCR0130 | 2009-02-09 | 0 | 48438 | DCO045 | 2009-06-08 | 48438 | Completed | 100% |  | 48438 | 48438 | 0 |  | 48438 | 0 | 0
DCR0131 | 257 | Feasibility Study Forth Ports Access to ADM Milling |  | RDC072 | 2008-12-16 | DCR0131 | 2009-02-10 | 0 | 1384 | DCO033 | 2009-04-23 | 1384 | Completed | 100% |  | 1384 | 1384 | 0 |  | 1384 | 0 | 0
DCR0132 | 501 | RBS / Gogarburn tramstop upgrade |  | RDC070 RDC148 | 15/12/2008 29/10/2009 | DCR0132 | 2009-02-13 | 0 | 7248 | DCO090A | 2009-12-10 | 7248 | Completed | 100% |  | 7248 | 7248 | 0 |  | 7248 | 0 | 0
DCR0133 | 17a | South Gyle Access Bridge Option 4 Preliminary Design |  | RDC071 | 2008-12-15 | DCR0133 | 2009-02-10 | 0 | 61463 | DCO039 | 2009-05-15 | 61463 | Completed | 100% |  | 61463 | 61463 | 0 |  | 61463 | 0 | 0
DCR0134 | 258 | NIL further future proofing |  | RDC073 | 2008-12-16 | DCR0134 | 2009-02-24 | 0 | 40541.5 | DCO059 | 2009-07-02 | 40541.5 | Completed | 100% |  | 40541.5 | 40541.5 | 0 |  | 40541.5 | 0 | 0
DCR0134A | 258 | NIL further future proofing - OLE changes | New ple, move 4-5 poles and gain approvals and consents | RDC073A | 2010-06-24 | DCR0134A | 2010-07-20 | 0 | 4378 | DCO126 | 2010-09-28 | 4378 | Completed | 100% |  | 4378 | 4378 | 0 |  | 4378 | 0 | 0
DCR0135 | 275 | Airport Tramstop interface with CCRC scheme |  | RDC082 | 2009-01-20 | DCR0135 | 2009-02-20 | 0 | 5432 | DCO040 | 2009-05-28 | 5432 | Completed | 100% |  | 5432 | 5432 | 0 |  | 5432 | 0 | 0
DCR0136 | 320 | Demarcation requirements |  | RDC100 | 2009-02-24 | DCR0136 | 2009-02-26 | 0 | 0 |  |  |  | Withdrawn | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0137 |  | Check of Banagher Concrete revised design for pre-cast beams | [6 empty] | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0138 |  | Depot and Workshop Equipment - Under-floor Lifting Plant | [6 empty] | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0139 |  | TQ452 - A8 Underpass – Modification of permanent works to facilitate Phase 3 Temporary Works |  | RDC099 | 2009-02-13 | DCR0139 | 2009-02-25 | 0 | 1910 | DCO066 | 2009-08-07 | 1910 | Completed | 100% |  | 1910 | 1910 | 0 |  | 1910 | 0 | 0
DCR0140 | 271 | Roads construction analysis of results | Requested to price at meeting with CB & SR on 270109 | RDC076 | 2009-01-08 | DCR0140 | 2009-01-29 | 0 | 98815.2 | DCO020 | 2009-02-23 | 98815.2 | Completed | 100% |  | 98815.2 | 98815.2 | 0 |  | 98815.2 | 0 | 0
DCR0141 | 289 | Hawthorne Vale cycleway connection |  | RDC097 | 2009-02-13 | DCR0141 | 2009-09-11 | 0 | 4800 | DCO081A | 2009-12-10 | 4800 | Completed | 100% |  | 4800 | 4800 | 0 |  | 4800 | 0 | 0
DCR0142 | 292 | Lindsay road retaining wall step/ramp access |  | RDC098 | 2009-02-13 |  |  |  | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0143 | 281 | Cathedral Lane Substation | Request to Hold Building Warrant | [5 empty] | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0144 |  | Stage E Landscape Drawings | As per CEC Informative and meeting Sept 09 |  |  | DCR0144 | 2009-02-27 | 0 | 0 |  |  |  | Withdrawn | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0145 |  | Section 6 turning Head | Incorporating a turning head at the access gate to the depot |  |  | DCR0145 | 2009-09-01 | 0 | 0 | DCO096 | 2010-01-06 | 0 | Withdrawn | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0146 | 277 | Design of Canopy and boundary treatment at Airport Kiosk |  | RDC084 | 2009-01-30 | DCR0146 | 2009-02-25 | 0 | 42574 | DCO038 | 2009-05-15 | 42574 | Completed | 100% | Agree [complete] | 42574 | 42574 | 0 |  | 42574 | 0 | 0
DCR0147 | 287 | Forth Ports Access rd traffic signal | CEC requested tram update substatndard Forth Ports design currently shown in Section 4 - outwith SDS scope. | RDC096 | 2009-02-11 | DCR0147 | 2009-02-26 | 0 | 7778 | DCO062 | 2009-07-28 | 7778 | Completed | 100% |  | 7778 | 7778 | 0 |  | 7778 | 0 | 0
DCR0148 | 343 | Section 6A/ Depot Access Road street lighting | CEC preferential treatment for design |  |  | DCR0148 | 2009-02-23 | 0 | 1745 | DCO067 | 2009-08-17 | 1745 | Completed | 100% |  | 1745 | 1745 | 0 |  | 1745 | 0 | 0
DCR0149 | 319 | Shandwick Place TRO Signage |  |  |  | DCR0149 | 2009-02-09 | 0 | 6763 | DCO075 | 2009-10-05 | 6763 | Completed | 100% |  | 6763 | 6763 | 0 |  | 6763 | 0 | 0
DCR0150 | BSC | Edinburgh Park Station Bridge U12 Beams |  | RDC086 | 2009-02-05 | DCR0150 | 2009-02-04 | 0 | 25902 | DCO017 | 2009-02-10 | 25902 | Completed | 100% |  | 25902 | 25902 | 0 |  | 25902 | 0 | 0
DCR0151 |  | West Depot Turnout Revision |  |  |  | DCR0151 | 2009-07-10 | 0 | 3204.5 | DCO079 | 2009-12-03 | 3204.5 | Completed | 100% |  | 3204.5 | 3204.5 | 0 |  | 3204.5 | 0 | 0
DCR0152 | 375 | Redesign of OLE pole foundations in Section 1a | Section 1a specific | RDC080 | 2009-01-29 | DCR0152 | 2009-02-09 | 0 | 6363 | DCO046 | 2009-06-08 | 6363 | Completed | 100% |  | 6363 | 6363 | 0 |  | 6363 | 0 | 0
DCR0153 | 375 | Redesign of OLE pole foundations in Section 1b | Section 1b specific | RDC078 | 2009-01-29 | DCR0152 | 2009-02-09 | 0 | 1862 | DCO047 | 2009-06-08 | 1862 | Completed | 100% |  | 1862 | 1862 | 0 |  | 1862 | 0 | 0
DCR0154 | 375 | Redesign of OLE pole foundations in Section 1c | Section 1c specific | RDC077 | 2009-01-29 | DCR0152 | 2009-02-09 | 0 | 4104 | DCO048 | 2009-06-08 | 4104 | Completed | 100% |  | 4104 | 4104 | 0 |  | 4104 | 0 | 0
DCR0155 | 375 | Redesign of OLE pole foundations in Section 1d | Section 1d specific | RDC079 | 2009-01-29 | DCR0152 | 2009-02-09 | 0 | 1862 | DCO049 | 2009-06-08 | 1862 | Completed | 100% |  | 1862 | 1862 | 0 |  | 1862 | 0 | 0
DCR0156 | BSC | Update Cable Route and Ducting Layouts for 1B | Amend drawings ULE90130-01-DCT-00010, 00011, 00012, 00013 as per meeting 20/01/09 | [5 empty] | 0 | DCO014 | 2009-02-05 | 0 | Completed | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0157 | BSC | Murrayfield GI | Requested by Jhi to put on Change instead of ATR |  |  | DCR0152 | 2009-06-30 | 0 | 14000 | DCO060 | 2009-07-09 | 14000 | Completed | 100% |  | 14000 | 14000 | 0 |  | 14000 | 0 | 0
DCR0158 |  | Meeting between BSC & Halcrow | Visit by BSC to Halcrow office in Glasgow | [5 empty] | 0 |  |  |  | Superseded |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0159 |  | Response to TQBBS529 | Response to TQBBS529 | [5 empty] | 0 |  |  |  | Superseded |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0160 |  | Existing Batter to North of Gogar Depot - Earthworks | Investigate the stability of the exisintg batters to North of Gogar Depot Site, as per walk out 060209. Earthworks | RDC101 | 2009-03-02 | DCR0160 | 2009-04-17 | 0 | 14632 | DCO058 | 2009-06-17 | 14632 | Completed | 100% |  | 14632 | 14632 | 0 |  | 14632 | 0 | 0
DCR0161 |  | Tower Place Bridge Section | [6 empty] | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0162 | 226 | Reduction to drawings with deliverables | Reduce number from 5 A1 to 3A1 and 2A3 | RDC103 | 2009-03-17 | DCR0162 | 2010-07-29 | 0 | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0163 | 227 | Operational Design review of Depot - Section 6 | see letter and minutes | RDC104 | 2009-03-17 | DCR0163 | 2009-07-10 | 0 | 0 | DCO097 | 2010-01-06 | 0 | Withdrawn | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0164 |  | Delay to Listed Building consents | see letter and change notice | RDC102 | 2009-03-17 | DCR0164 | 2010-07-16 | 0 | 0 |  |  |  | EOT |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0165 | 365 | Wider Area Fly P&R Survey and Proposals | Preliminary review of the roads and junctions adjacent to the out of city tram stops with a view to pre empting the use of these roads as unofficial park and ride sites once the tram is operational. | [5 empty] | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0166 | 409 | Forth Ports new Construction @ Ocean Drive | Revised planning drawings for bypass Rd based on new CEC requirements |  |  | DCR0166 | 2009-04-24 | 0 | 2400 | DCO041 | 2009-05-29 | 2400 | Completed | 100% |  | 2400 | 2400 | 0 |  | 2400 | 0 | 0
DCR0167 | 281 | Cathedral Lane substation alternative design - Henderson Global Concept | Alternative proposal with respect to Henderson Global and St. James centre power supplies | RDC105 | 2009-03-16 | DCR0167 | 2009-10-30 | 0 | 1584.97 | DCO084 DCO132 | 10/12/2009 04/11/2010 | 0 | Superseded | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0168 |  | Re-design WEBS trackform and drainage | as per request from Colin Brady to AD and CR | RDC108 | 2009-04-03 | DCR0168 | 2009-04-23 | 0 | 41304 | DCO044 | 2009-06-09 | 41304 | Completed | 100% |  | 41304 | 41304 | 0 |  | 41304 | 0 | 0
DCR0169 | 400 | Bicycle Provision at Haymarket Steps | CEC have requested that a cycle channle/ provision be added to the proposed steps at Haymarket Viaduct |  |  | DCR0169 | 2009-04-22 | 0 | 380 | DCO098A | 2010-01-06 | 380 | Closed | 100% |  | 380 | 380 | 0 |  | 380 | 0 | 0
DCR0170 | 270 | RBS Tramstop Existing Utility Services | RBS Tramstop Existing Utility Services | RDC110 |  | DCR0170 | 2009-09-02 | 0 | 1665 | DCO078 | 2009-12-03 | 1665 | Closed | 100% | Agree [complete] | 1665 | 1665 | 0 |  | 1665 | 0 | 0
DCR0171 |  | Siemens Cable Pulling Pits |  | RDC106 | 2009-03-30 | DCR0171 | 2009-05-05 | 0 | 1836 | DCO042 | 2009-06-05 | 1836 | Completed | 100% |  | 1836 | 1836 | 0 |  | 1836 | 0 | 0
DCR0172 | 306 | Leith Walk Underground Structure |  | RDC107 | 2009-03-30 | DCR0172 | 2010-10-21 | 0 | 7500 | DCO099 | 2010-01-06 | 7500 | Completed | 100% |  | 7500 | 7500 | 0 |  | 7500 | 0 | 0
DCR0173 | 321 | Picardy Place, York Place and London Road Junctions - revised alignment |  | RDC109 | 2009-04-24 | DCR0173 | 2009-07-10 | 0 | 59834.5 | DCO076 | 2009-10-23 | 59834.5 | Completed | 100% |  | 59834.5 | 59834.5 | 0 |  | 59834.5 | 0 | 0
DCR0174 |  | A8 Underpass VE Reduction in height |  | RDC111 | 2009-04-24 | DCR0174 | 2010-07-16 | 0 | 0 |  |  |  | Superseded | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0175 | 360 | Forth Ports Road 8 - Design Alteration |  | RDC112 | 2009-04-27 | DCR0175 | 2009-05-11 | 0 | 10164 | DCO053 | 2009-06-12 | 10164 | Completed | 100% |  | 10164 | 10164 | 0 |  | 10164 | 0 | 0
DCR0176 | 376 | OLE development workshop | Redesign of OLE poles foundation Line 2 and layout drawings to show actual pole locations and where necessary obtain approval for the revised locations | RDC113 | 2009-04-23 | DCR0176 | 2009-05-01 | 0 | 73018 | DCO050 | 2009-06-08 | 73018 | Completed | 100% |  | 73018 | 73018 | 0 |  | 73018 | 0 | 0
DCR0177 | 377 | OLE development workshop | Amend OLE System design documents as identified as misalignment in the OLE development workshop | RDC114 | 2009-04-23 | DCR0177 | 2009-05-01 | 0 | 6511 | DCO073 | 2009-08-28 | 6511 | Completed | 100% | Agree [complete] | 6511 | 6511 | 0 |  | 6511 | 0 | 0
DCR0178 | 378 | OLE development workshop | Amend OLE Building Fixing Loads and layout drawings to show actual building fixings and where necessary obtain approval for the revised locations. | RDC115 | 2009-04-23 | DCR0178 | 2009-05-01 | 0 | 6260 | DCO051 | 2009-06-08 | 6260 | Completed | 100% | Agree [complete] | 6260 | 6260 | 0 |  | 6260 | 0 | 0
DCR0179 | 379 | OLE development workshop | Design Provision of alternative lighting where OLE Poles are not provided, possibly in a form similar to OLE Poles for Planning Consent Reasons. Design the Lighting System to take account of any relevant aspects of the OLE System (eg Tensioning Equipment) which was not part of the reference design. Design revised earthing bonding and insulation requirements for lighting. | RDC116 | 2009-04-23 | DCR0179 | 2009-05-01 | 0 | 47262 | DCO074 | 2009-08-28 | 47262 | Completed | 100% | Agree [complete] | 47262 | 47262 | 0 |  | 47262 | 0 | 0
DCR0180 | 380 | OLE development workshop | Amend OHLE Fixings at Depot Access Bridge to incorporate requirements for direct fixed catenary on low headroom span | RDC117 | 2009-04-23 | DCR0180 | 2009-05-01 | 0 | 20028 | DCO082 | 2009-12-10 | 20028 | Completed | 100% |  | 20028 | 20028 | 0 |  | 20028 | 0 | 0
DCR0181 | 203 | Depot Additional Design | Various design as request from BSC or suppliers |  |  | DCR0181 | 2009-06-09 | 0 | 46851 | DCO0100 | 2010-01-06 | 46851 | Completed | 100% |  | 46851 | 46851 | 0 |  | 46851 | 0 | 0
DCR0182 |  | WEBS vertical alignment change due to Direct Fix | Siemens request to alter vertical alignment | RDC118 | 2009-05-01 | DCR0182 | 2009-05-14 | 0 | 0 |  |  | 0 | Withdrawn | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0183 |  | Taxi Rank at George Street | Construction of off-peak taxi rank at outside Dome hotel on George St | RDC119 | 2009-05-07 |  |  |  | 0 |  |  |  | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0184 | 406 | Existing Batter to North of Gogar Depot - Drainage | Investigate the stability of the exisintg batters to North of Gogar Depot Site, as per walk out 060209 - Drainagw only | RDC101 | 2009-03-02 | DCR0184 | 2009-04-17 | 0 | 6306 | DCO057 | 2009-06-17 | 6306 | Completed | 100% |  | 6306 | 6306 | 0 |  | 6306 | 0 | 0
DCR0185 |  | WEBS Reinstatement Design for Guided Busway post GI | provide details of permanent reinstatement works afer GI | RDC120 | 2009-05-18 | DCR0185 | 2009-06-02 | 0 | 1472 | DCO115 | 2010-03-12 | 1472 | Completed | 100% |  | 1472 | 1472 | 0 |  | 1472 | 0 | 0
DCR0186 | 415 | 5C Pumping Station at Depot | Design a Pumping station and manhole and rising main | RDC124 | 2009-06-09 |  |  |  | 0 |  |  |  | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0187 |  | Provision of Combined Services Drawings | Composite plans inc Track OLE Drinage Lighting ducts | RDC123 | 2009-06-08 |  |  |  | 0 |  |  |  | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0188 | 412 | Depot Floor - Pit for a manual bogie turntable | Design of Depot Floor to incorporate Manual Bogie Turntable | RDC121 | 2009-05-22 | DCR0188 | 2009-06-18 | 0 | 7593 | DCO068 | 2009-08-17 | 7593 | Completed | 100% |  | 7593 | 7593 | 0 |  | 7593 | 0 | 0
DCR0189 | 305 | Special track slab for Rheda for Princes St and Leith. Priority Crawley Tunnel | Underground Chamber and Services: Special track slab for Rheda for Princes St and Leith. Prority Crawley Tunnel | RDC122 | 2009-06-16 |  |  |  | 0 |  |  |  | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0190 |  | Carrick Knowe Underbridge Beams |  |  |  | DCR0190 | 2009-07-01 | 0 | 19262 | DCO061 | 2009-07-21 | 19262 | Completed | 100% |  | 19262 | 19262 | 0 |  | 19262 | 0 | 0
DCR0191 | 310 | Gogar Landfill Scottish Water Utility Diversion | Review CCTV video and redesign | RDC126 | 2009-07-07 | DCR0191 | 2009-08-05 | 0 | 16284 | DCO083 | 2009-12-10 | 16284 | Completed | 100% |  | 16284 | 16284 | 0 |  | 16284 | 0 | 0
DCR0192 |  | Phase 1a/1b Split | Phase 1a to meet the Employer's Requirements | RDC125 | 2009-06-16 |  |  |  | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0193 |  | Street Lighting Haymarket Terrace | Comment 7507 1D TAA comments, move column to Haymarket Terrace parapet |  |  | DCR0193 | 2009-12-09 | 0 | 380 | DCO105A | 2010-01-06 | 380 | Closed | 100% |  | 380 | 380 | 0 |  | 380 | 0 | 0
DCR0194 | 179 | SRU/ Murrayfield Accommodation works - Additional design | Additional to DCR0114 |  |  | DCR0194 | 2009-07-21 | 0 | 29668 | DCO069 | 2009-08-17 | 29668 | Completed | 100% |  | 29668 | 29668 | 0 |  | 29668 | 0 | 0
DCR0195 | 439 | Office Move | SDS move wholly to Edinburgh park as requested by tie |  |  | DCR0195 | 2009-07-30 | 0 | 17984.07 | DCO064 | 2009-07-30 | 17984.07 | Completed | 100% |  | 17984.07 | 17984.07 | 0 |  | 17984.07 | 0 | 0
DCR0196 | 459 | Informal Consultation TRO Changes |  |  |  | DCR0196 | 2009-07-31 | 0 | 38970 | Ph |  | 38970 | Completed | 100% |  | 38970 | 38970 | 0 |  | 38970 | 0 | 0
DCR0197 |  | TRO affect on IFCs |  |  |  | DCR0197 | 2009-07-31 | 0 | 0 |  |  |  | Withdrawn | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0198 | 417 | BAA Dualling Future proofing - Eastfield Avenue | Design dualling future proofing inc Siemens components | RDC129 | 2009-07-22 | DCR0198 | 2009-08-27 | 0 | 1112 | DCO088 | 2009-12-10 | 1112 | Completed | 100% |  | 1112 | 1112 | 0 |  | 1112 | 0 | 0
DCR0199 | 446 | Roseburn Delta junction landscaping | Amended species to show low level planting | RDC130 | 2009-07-22 |  |  |  | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0200 | 450 | BAA New Burnside Road Alignment | Incorporate new Burnside Road alignment, update signage and roads drawings | RDC131 | 2009-07-22 | DCR0200 | 2009-10-01 | 0 | 6818.5 | DCO089 | 2009-12-10 | 6818.5 | Completed | 100% |  | 6818.5 | 6818.5 | 0 |  | 6818.5 | 0 | 0
DCR0201 |  | Network Rail Turning Head Lighting | Light turning head at new access road and tram crossing as per Transdev comments |  |  | DCR0201 | 2011-06-15 | 0 | 0 | DCO106 | 2010-01-06 | 0 | Withdrawn | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0202 | 463 | Forth Ports Drainage Approvals | FP approval of drinage (inc Sliemens track drainaage box) due to fact that CEC did not adopt road as per Agreement | RDC143 | 2009-10-05 | DCR0202 | 2009-12-10 | 0 | 5000 | DCO085 | 2009-12-10 | 5000 | Completed | 100% |  | 5000 | 5000 | 0 |  | 5000 | 0 | 0
DCR0203 | 461 | Forth Ports substation re-design | Re-design required after survey received for DCR0111 | RDC137 | 2009-10-05 | DCR0203 | 2009-12-10 | 0 | 10000 | DCO086 | 2009-12-10 | 10000 | Completed | 100% |  | 10000 | 10000 | 0 |  | 10000 | 0 | 0
DCR0204 | 467 | Drainage at Depot - BAA run off | Further to DCR0184 additional drainage is required |  |  | DCR0204 | 2011-06-15 | 0 | 3750 | DCO107 | 2010-01-06 | 3750 | Completed | 100% |  | 3750 | 3750 | 0 |  | 3750 | 0 | 0
DCR0205 | 465 | Redesign of drainage and slope due to BAA/CCRC interface | Further to DCR0135 - redesign of drainage and retaining slope | RDC144 | 2009-10-05 | DCR0205 | 2009-12-10 | 0 | 3219 | DCO087A | 2009-12-10 | 3219 | Completed | 100% |  | 3219 | 3219 | 0 |  | 3219 | 0 | 0
DCR0206 | 472 | DKE checks against CAF Tram | Review of CAF DKE swept path taking on board all known Client Design amendments and utilising CAF DKE Information baselined 01/08/09 |  |  | DCR0206 | 2009-08-07 | 0 | 12878 | DCO070 | 2009-09-07 | 12878 | Completed | 100% |  | 12878 | 12878 | 0 |  | 12878 | 0 | 0
DCR0207 |  | Changes to TRO 1 drawings | The changes that have been requested by Duncan Fraser at the TRO Review meeting are 1.The title block be revised to include an appropriate road name reference along with the drawing number and 2. A key plan | [5 empty] | 0 |  |  |  | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0208 |  | Review of Track Drainage at Eastfield Avenue | Alteration to drainage to avoid clash with the utilities crossing tram works as per tie letter | RDC128 | 2009-08-07 |  |  |  | 0 |  |  |  | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0209 | 305 | Crawley Tunnel Underground Chamber and Services | Design of Special trackslab for Rheda City Trackform suitable to span shallow underground Crawley tunnel | RDC132 | 2009-08-07 | DCR0209 | 2010-03-05 | 0 | 20164 | DCO101A | 06/01/2010 12/08/2010 | 20164 | Completed | 100% |  | 20164 | 20164 | 0 |  | 20164 | 0 | 0
DCR0210 |  | Underground Chamber - Clifton Terrace |  | RDC134 | 2009-08-24 |  |  |  | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0211 | 468 | Underground Chamber - West Maitland Street & Clifton Terrace |  | RDC133 & RDC134 | 2009-08-24 | DCR0211 | 2009-10-30 | 0 | 0 | DCO102 | 2010-01-06 | 0 | Withdrawn | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0212A | 476 | Tram Stops Development Workshop - All works | Scope determines as per misalignment workshops - see minutes attached to RDC | RDC138 | 2009-09-07 | DCR0212A | 2010-02-22 | 0 | 108241 | DCO108 | 2010-01-06 | 108241 | Completed | 100% |  | 108241 | 108241 | 0 |  | 108241 | 0 | 0
DCR0212B |  | Tram Stops Development Workshop - Palette of finishes only | Scope determines as per misalignment workshops - see minutes attached to RDC | RDC138 | 2009-09-07 | DCR0212B |  |  | 0 |  |  |  | Superseded |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0213A | 477 | Substation Development Workshop - All works | Scope determines as per misalignment workshops - see minutes attached to RDC | RDC139 | 2009-09-07 | DCR0213A | 2009-11-13 | 0 | 84847 | DCO111 | 2010-01-15 | 84847 | Completed | 100% |  | 84847 | 84847 | 0 |  | 84847 | 0 | 0
DCR0213B |  | Substation Development Workshop - CAD Siemens mark ups only | Scope determines as per misalignment workshops - see minutes attached to RDC | RDC139 | 2009-09-07 | DCR0213B | 2009-11-13 | 0 | 0 |  |  |  | Superseded | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0214 |  | Provision of 110v Supply to Tramstops | See BSC letter ref: CS/3115 dated 22/07/09 |  |  | DCR0214 | 2009-09-11 | 0 | 8518 | DCO103 | 2010-01-06 | 8518 | Completed | 100% |  | 8518 | 8518 | 0 |  | 8518 | 0 | 0
DCR0215 | 486 | TRO Changes Sept 2009 | As per meeting with SDS and tie |  |  | DCR0215 | 2009-09-18 | 0 | 2922 | DCO072 | 2009-09-25 | 2922 | Completed | 100% |  | 2922 | 2922 | 0 |  | 2922 | 0 | 0
DCR0216 | 488 | Drainage Development Workshop | As per RDC | RDC142 |  | DCR0216 | 2009-12-21 | 0 | 36700 | DCO109A | 06/01/2010 30/07/2010 | 36700 | Completed | 100% |  | 36700 | 36700 | 0 |  | 36700 | 0 | 0
DCR0217 |  | Diversion of Cables at Tower Place Bridge | Design for the diversion of temporary cables on the north parapel into the new duct system into the south parapet | RDC145 | 2009-10-05 |  |  |  | 0 |  |  |  | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0218 |  | Princes St Arches - TQ1060 | Due to the undiscovered arches in Princes st. south carriageway, do an alternative carriageway design to accomodate them. | RDC146 | 2009-10-15 |  |  |  | 0 |  |  |  | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0219 | 499 | Frederick Street new crossing | CEC have identified 2 new comments (ID 9776, 9777) in their closeout responses related to a new pedestrian crossing along Frederick Street. | RDC150 | 2009-11-30 | DCR0219 | 2010-02-25 | 0 | 11250 | DCO110A | 2010-01-06 | 11250 | Completed | 100% |  | 11250 | 11250 | 0 |  | 11250 | 0 | 0
DCR0220 | 512 | Compressed Air Supply | See IF-114-SPS-CIV |  |  | DCR0220 | 2009-11-04 | 0 | 10007 | DCO104 | 2010-01-06 | 10007 | Completed | 100% |  | 10007 | 10007 | 0 |  | 10007 | 0 | 0
DCR0221 | 500 | Picardy Place incorporate 4th lane eastbound | Develop alternative design as per CEC comments by adding a 4th lane eastbound throught the junction. | RDC147 | 2009-10-23 | DCR0221 | 2010-02-08 | 0 | 28378 | DCO119/DCO227 | 2010-05-12 | 28378 | Completed | 100% |  | 28378 | 28378 | 0 |  | 28378 | 0 | 0 | Finalised in line with DCO 227
DCR0222 | 549 | Street Lighting new comment - conical aluminium | Comment 9878 Section 1D items should be conical aluminium and not steel and without 0.5m projection | RDC179 | 2010-11-08 | DCR0222 | 2010-12-21 | 0 | 1895 | Ph | 2011-06-15 | 1895 | Completed | 100% |  | 1895 | 1895 | 0 |  | 1895 | 0 | 0
DCR0223 |  | Additional Footway Across Depot Access Bridge | CEC comment on Section 6A due to Gogar Interchange. | [5 empty] | 0 |  |  |  | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0224 |  | Drawing Register | Updating format for BSC |  |  | DCR0224 | 2009-10-29 | 0 | 12500 | DCO095 | 2009-12-15 | 12500 | Completed | 100% |  | 12500 | 12500 | 0 |  | 12500 | 0 | 0
DCR0225 |  | Lindsay road retaining wall step/ramp access | As per tie letter INF CORR 2721/DS | RDC149 | 2009-11-11 | DCR0225 | 2009-12-10 | 0 | 0 |  |  |  | Withdrawn | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0226 | 277 | OLE Base Special - Airport | OLE Base special due to Siemens Layout change at Stop/Canopy | RDC156 | 2010-02-16 | DCR0226 | 2010-03-31 | 0 | 27890 | Ph | 2011-06-15 | 27890 | Completed | 100% |  | 27890 | 27890 | 0 |  | 27890 | 0 | 0
DCR0227 | 376 | Development Workshop Civils re-design to suit Siemens OLE design | Alignment of Siemens OLE Design with SDS Design | RDC113 | 2009-04-23 | DCR0227 | 2010-04-06 | 0 | 128974 | DCO114 | 2010-03-16 | 128974 | Completed | 100% | Agreed | 128974 | 128974 | 0 |  | 128974 | 0 | 0
DCR0228 |  | South Gyle Access Bridge Detailed Design | Changes in S26 and W11 detailed design as per DCR0133 feasibility report |  |  | DCR0228 | 2009-11-24 | 0 | 0 |  |  |  | Withdrawn | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0229 | 376 | OLE Plinths on Structures | Detailed Design of the OLE Plinths for system proposed by Siemens |  |  | DCR0229 | 2010-04-08 | 0 | 115525.75 | Ph | 2011-06-15 | 115525.75 | Completed | 100% |  | 115525.75 | 115525.75 | 0 |  | 115525.75 | 0 | 0
DCR0230 |  | Ducting inc on Structures | Misalignment Change and Siemens additional requirements | [5 empty] | 0 | Ph | 2011-06-15 |  | Superseded |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0231 | 525 | Earthing and Bonding Development Workshop Misalignment | Alignments for E&B on strucutres, equipment poles, Depot, substations, Voltage Limiting Devices... | RDC152 | 2010-01-15 | DCR0231 | 2010-07-30 | 0 | 71114 | Ph | 2011-06-15 | 71114 | Ongoing | 100% | 24,519 were to cover specialist SDS support on site. This has not been provided. Deduction under DCO271 | 71114 | 71114 | 0 | Accepted figure | 71114 | 0 | 0
DCR0231 | 525 | Earthing and Bonding Development Workshop Misalignment | Reduction on scope as agreed | [6 empty] | DCO271 | 2013-10-30 | -24519 | Ongoing | 100% |  | -24519 | -24519 | 0 | Accepted figure | -24519 | 0 | 0
DCR0232 |  | Tower Place Bridge - Remove Ramp, Remove concrete downstand, Revise OLE Baseplate | See RDC154 | RDC154 RDC154A | 21/01/2010 02/07/2010 | DCR0232 | 2011-06-15 | 0 | 7228 | Ph/DCO226 | 2011-06-15 | 8000 | Ongoing | suspended | Full scope of works not complete - assessment made on works complete | 8000 | 8000 | 0 |  | 8000 | 0 | 0 | Finalised in line with DCO 227
DCR0233 | 529 | Gogar Landfill profile re-design | Excavation of works for sewer has affected permanent civil design works | RDC153 | 2010-01-18 | DCR0233 | 2010-03-10 | 0 | 19411 | DCO124 | 2010-08-25 | 19411 | Completed | 100% |  | 19411 | 19411 | 0 |  | 19411 | 0 | 0
DCR0234 |  | Further Change to Airport (BAA) Canopy design as per CEC comments | See minute of meetign from 08/02/10 - CEC requirements and tie instructions | RDC157 | 2010-02-11 | DCR0234 | 2010-02-09 | 0 | 16983 | DCO117 | 2010-04-09 | 16983 | Completed | 100% |  | 16983 | 16983 | 0 |  | 16983 | 0 | 0
DCR0235 |  | Special Trackform on Leith Walk Railway Bridge | Design to achieve 120MPa | RDC151 | 2009-12-03 | DCR0235 | 2010-04-08 | 0 | 0 |  |  |  | Withdrawn | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0236 |  | S21B & S21D ground conditions | [6 empty] | 0 |  |  |  | Superseded |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0237 |  | Floating Track Design | See Siements letter ETN(BSC)SDS=TD&ABC#057137 | RDC155 | 2010-02-04 | DCR0237 | 2010-04-08 | 0 | 26000 | Ph | 2011-06-15 | 26000 | Completed | 100% | agreed | 26000 | 26000 | 0 |  | 26000 | 0 | 0
DCR0238 |  | Hydraulic Model of Gogarburn Retaining Walls |  |  |  | DCR0238 | 2010-03-10 | 0 | 0 |  |  | 0 | Completed | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0239 |  | Trackform Change Embedded to Ballasted Track | Letter from tie to BSC sent via email from Frank Wenzel | [5 empty] | 0 |  |  |  | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0240 |  | Forth Ports Section 1A - Fence Alterations | Additional constraints in Casino area |  |  | DCR0240 | 2011-06-15 | 0 | 11509 | PhDCO226 | 2011-06-15 | 20000 | Completed | suspended | agreed | 20000 | 20000 | 0 |  | 20000 | 0 | 0 | Finalised in line with DCO 227
DCR0240,0278,0309,0324,0325,0327,0355 | PMC084 | Ceasing any further works on the Secondary Phase 1a Design | Ceasing any further works on the Secondary Phase 1a Design | RDC225 | 2012-03-15 | DCR0355 | 2012-04-18 | 0 | 0 | DCO226 |  | -105760.07 | Completed | 100% | works not part of agreement of 19-july | -105760.07 | -105760.07 | 0 |  | -105760.07 | 0 | 0 | Refer DCO 226
DCR0241 | 568 | Topo Survey ScotRail Depot | ScotRail cannot provide sufficient As Builts for the DCR0024 change. Topo Survey needed |  |  | DCR0241 | 2010-03-02 | 0 | 1542.5 | DCO137 | 2011-02-11 | 1542.5 | Completed | 100% |  | 1542.5 | 1542.5 | 0 |  | 1542.5 | 0 | 0
DCR0242 | 167 | Changes to Murrayfield Accommodation Works - Wanderers Club House |  |  |  | DCR0242 | 2010-03-15 | 0 | 692 | Ph | 2011-06-15 | 692 | Completed | 100% |  | 692 | 692 | 0 |  | 692 | 0 | 0
DCR0243 |  | Advanced Directional Signing for Constitution St | New CEC comment related to the provision of additional signs, not previously discussed | [5 empty] | 0 |  |  |  | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0244 |  | Lindsay Rd phone mast | New phone mast construction conflicts with proposed/instructed design |  |  | DCR0244 | 2011-06-15 | 0 | 0 | Ph | 2011-06-15 | 0 | Completed | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0245 |  | OLE Special Foundations - Several |  |  |  | DCR0245 | 2011-06-15 | 0 | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0246 |  | Topo Survey WEBS | Procure Survey to resolve PGM discrepancies |  |  | DCR0246 | 2010-03-12 | 0 | 1584 | DCO116 | 2010-03-31 | 1584 | Completed | 100% |  | 1584 | 1584 | 0 |  | 1584 | 0 | 0
DCR0247 |  | Russell Road Retaining Wall unforeseen ground conditions W4 | Amend Piling Methodology based on new on-site information inc shear connection detail for W4 | RDC164 | 2010-03-31 | DCR0247 | 2010-03-30 | 0 | 9788 | DCO118 | 2010-04-26 | 9788 | Completed | 100% |  | 9788 | 9788 | 0 |  | 9788 | 0 | 0
DCR0248 | 588 | Special Trackform Construction at Shallow Depth obstructions | 1) Victoria Dock bridge 2) Tower Place Birdge 4) Leith Walk Bridge 5) 275kv cables Arthur St to Dalmeny St 6) Leith Walk Scottish Power Tunnel | RDC162 | 2010-03-30 | DCR0248 | 2010-05-14 | 0 | 7560.5 | Ph/DCO227 | 2011-06-15 | 15121 | Completed | suspended | agree | 15121 | 15121 | 0 |  | 15121 | 0 | 0 | Finalised in line with DCO 227
DCR0249 | 598 | Victoria Dock Entrance Bridge |  |  |  | DCR0249 | 2010-03-30 | 0 | 0 |  |  | 0 | Completed | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0250 | 630 | Further to DCR0113 amendments are required to Internal Retaining Wall for Haymarket Viaduct | Due to unforeseen site conditions | RDC161 | 2010-03-31 | DCR0250 | 2010-05-12 | 0 | 3606 | Ph | 2011-06-15 | 3606 | Completed | 100% |  | 3606 | 3606 | 0 |  | 3606 | 0 | 0
DCR0251 |  | Reinstate traffic island on Princes St | Design to provide reinstatement for island that has been moved by other prior to instruction | RDC160 | 2010-03-25 | DCR0251 | 2010-05-04 | 0 | 1140 | DCO122 | 2010-07-28 | 1140 | Completed | 100% |  | 1140 | 1140 | 0 |  | 1140 | 0 | 0
DCR0252 |  | Mounting of sign plates on buildings or railings | Letter request to review all possibilities | [5 empty] | 0 |  |  |  | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0253 |  | Russell Road Retaining Wall - Installation Error | Re-design due to error on site - TQ 1592 | RDC163 | 2010-04-12 | DCR0253 | 2010-05-24 | 0 | 22899 | DCO123 | 2010-07-30 | 22899 | Completed | 100% |  | 22899 | 22899 | 0 |  | 22899 | 0 | 0
DCR0254 |  | Radius Curve Containment on Gogarburn Bridge | Provide Design for reinforced concrete containment and centre beams |  |  |  | _ | 0 | 0 | DCO112 | 2010-01-14 | 0 | Completed | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0255 |  | Grosvenor Street 2 Way Change | Change from the previous agreed layout from one way entry from clifton terrace to 2 way |  |  | DCR0255 | 2010-05-04 | 0 | 26968 | Ph | 2011-06-15 | 26968 | Completed | 100% |  | 26968 | 26968 | 0 |  | 26968 | 0 | 0
DCR0256 | 477A | Cathedral Lane Substation Misalignment | See DCR0213 | RDC139 | 2010-04-07 | DCR0256 | 2010-05-25 | 0 | 18490 | Ph/DCO227 | 2011-06-15 | 23113.5 | Completed | 100% | Works put on Hold and not completed. | 23113.5 | 23113.5 | 0 |  | 23113.5 | 0 | 0 | Finalised in line with DCO 227
DCR0257 |  | Russell Road Retaining Wall unforeseen ground conditions W3 | Amend Piling Methodology based on new on-site information inc shear connection detail for W3 |  |  | DCR0257 | 2010-05-04 | 0 | 7313 | Ph | 2011-06-15 | 7313 | Completed | 100% |  | 7313 | 7313 | 0 |  | 7313 | 0 | 0
DCR0258 |  | Section 5B Busgate MP Gas Main | Provide design for permanent diversion of the MP gas main | RDC166 | 2010-04-22 | DCR0258 | 2010-09-23 | 0 | 5026 | DCO120A | 2010-05-18 | 5026 | Completed | 100% |  | 5026 | 5026 | 0 |  | 5026 | 0 | 0
DCR0259 | 588 | Special Trackform Construction at Shallow Depth obstructions | 3) Culvert North Const St | RDC162 | 2010-03-30 | DCR0259 | 2010-05-20 | 0 | 0 |  |  |  | Closed | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0260 |  | Road/Rail Interface | [6 empty] | 0 |  |  |  | Superseded |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0261 |  | Roseburn St Viaduct curtain walls | Design of curtain walls required at Roseburn St in lieu of current fencing proposals in the vicinity of each abutment | RDC167A | 2011-03-17 | DCR0261 | 2011-06-15 | 0 | 38800 | Ph | 2011-06-15 | 38800 | Ongoing |  |  | 38800 | 38800 | 0 |  | 38800 | 0 | 0
DCR0262 |  | Depot formation redesign | Additional Cross Sections for Depot Formation Design |  |  | DCR0262 | 2011-06-15 | 0 | 6000 | Ph | 2011-06-15 | 6000 | Completed | 100% |  | 6000 | 6000 | 0 |  | 6000 | 0 | 0
DCR0263 | 732 | TQ1853 - Update 5B MX file Trackform | The current Siemens Track Layout Design shows ballasted track in Section 5B between 522917 - 523695. In contrast to this the current mx trackform file ULE90130-05-Cal-00070v1 only shows ballasted track up to CH 523520 and then a track slab design. | RDC188 | 2011-03-10 | DCR0263 | 2011-06-15 | 0 | 5062 | DCO125 | 2010-09-10 | 5062 | Completed | 100% |  | 5062 | 5062 | 0 |  | 5062 | 0 | 0
DCR0264 |  | Listed Building Consents for Dublin St | Change to levels at York Place/Queens St/ Dublin St impacts listed building consent for two walls at Dublin St |  |  | DCR0264 | 2011-06-15 | 0 | 0 | Ph | 2011-06-15 | 0 | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0265 | 485 | Tram Turnback Strategy | Redsign of traffic signals required for tram turnback manoeurvres where police attendance is not an accrptable means of operation | RDC141 | 2009-09-28 | DCR0265 | 2011-06-15 | 0 | 39000 | Ph | 2011-06-15 | 39000 | Completed | 100% | agree | 39000 | 39000 | 0 |  | 39000 | 0 | 0
DCR0266 |  | Murrayfield Tramstop Layout Changes | Bollard, Fence and Turnstile Changes |  |  | DCR0266 | 2011-06-15 | 0 | 7000 | Ph | 2011-06-15 | 7000 | Completed | 100% |  | 7000 | 7000 | 0 |  | 7000 | 0 | 0
DCR0267 |  | Depot Tram Wash Equipment | Provide design for a revised civil design for tram wash | RDC168 | 2010-05-26 |  |  |  | 0 |  |  |  | Closed | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0268 |  | Depot Revised layout showing service requirements | [6 empty] | 0 |  |  |  | Closed | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0269 |  | Depot Earthing and Bonding and Special Sub-stations | [6 empty] | 0 |  |  |  | Closed | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0270 | 649 | Tramstop Layout Changes | Changes to TVM layout and dimensions and branding | RDC171 | 2010-07-13 | DCR0270 | 2010-08-23 | 0 | 40000 | Ph | 2011-06-15 | 40000 | Completed | 100% | agreed | 40000 | 40000 | 0 |  | 40000 | 0 | 0
DCR0271 |  | DKE review of CAF tram - Close out of DKE analysis and issue of final report | Revisions to report REP-00755 | [5 empty] | 0 | Ph | 2011-06-15 |  | Superseded |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0272 |  | Haymarket OLE Plinths | Amendement to loads | [5 empty] | 1594 | Ph | 2011-06-15 | 1594 | Completed | 100% |  | 1594 | 1594 | 0 |  | 1594 | 0 | 0
DCR0273 | 586 | Junction of the Mound, Princes St and Hanover St | Additional demarcation and markings | RDC169 | 2010-06-21 | DCR0273 | 2010-07-28 | 0 | 0 | Ph/DCO227 | 2011-06-15 | 6398 | Superseded | 0% |  | 6398 | 6398 | 0 |  | 6398 | 0 | 0 | Finalised in line with DCO 227
DCR0274 |  | Murrayfield Stadium Retaining Walls Ground Improvement Change | S21B, S21D, S21C, S505 changes to ground conditions due to further GI | RDC186 | 2011-02-22 | DCR0274 | 2011-06-15 | 0 | 30000 | Ph/DCO227 | 2011-06-15 | 70000 | Completed | 100% | Revised design estimate requested to reflect actual situation | 70000 | 70000 | 0 |  | 70000 | 0 | 0 | Finalised in line with DCO 227
DCR0275 |  | DWG files June '10 onwards as no ECS CAD | Produce dwg/dwf files for BSC | [5 empty] | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0276 | 642 | Elder Street Junction | Redesign Junction as requested by CEC | RDC170 | 2010-07-06 | DCR0276 | 2010-11-05 | 0 | 0 | Ph | 2011-06-15 | 0 | Superseded | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0277 | 554 | CCRC walkway Earthing and Bonding | Civil design for Siemens E&B design on CVI | RDC159 | 2010-02-25 | DCR0277 | 2010-09-21 | 0 | 5245 | DCO135 | 2011-01-21 | 5245 | Completed | 100% |  | 5245 | 5245 | 0 |  | 5245 | 0 | 0
DCR0278 |  | Picardy Place Detailed Design | Further to DCR0173 & DCR0221 |  |  | DCR0278 | 2011-06-15 | 0 | 299736 | DCO131/DCO226 | 2010-11-04 | 100000 | Completed | suspended | Agreed | 100000 | 100000 | 0 |  | 100000 | 0 | 0 | Finalised in line with DCO 226
DCR0278 |  | Picardy Place Detailed Design | Further to DCR0173 & DCR0221 |  |  | DCR0278 | 2011-06-15 | 0 | 299736 | DCO131/DCO226 | 2010-11-04 | 250000 | Completed | suspended | Agreed | 250000 | 250000 | 0 |  | 250000 | 0 | 0 | Finalised in line with DCO 226
DCR0279 |  | Special OLE Foundation Murrayfield Tramstop retaining wall | Change to the OLE location made by Siemens to avoid the pedestrian crossing of the tracks at the east end of the platforms | [5 empty] | 0 |  |  |  | Superseded |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0280 | 702 | Pedestrian Guardrail Change | Changes to design and spec as per CEC letter | RDC177 | 2010-10-28 | DCR0280 | 2010-08-27 | 0 | 1448 | Ph | 2011-06-15 | 1448 | Completed | 100% |  | 1448 | 1448 | 0 |  | 1448 | 0 | 0
DCR0281 | 654 | Gogar Interchange - Name Change | Change Tramstop Name to Edinburgh Gateway | RDC172 | 2010-07-20 | DCR0281 | 2010-08-19 | 0 | 1880 | DCO134 | 2010-11-30 | 1880 | Completed | 100% |  | 1880 | 1880 | 0 |  | 1880 | 0 | 0
DCR0282 | 665 | Edinburgh Gateway - A8 Drainage | Relocate the combined sewer in the original design solution for the A8 | RDC173 | 2010-07-21 | DCR0282 | 2010-08-04 | 0 | 22846 | DCO133 | 2010-11-05 | 22846 | Completed | 100% |  | 22846 | 22846 | 0 |  | 22846 | 0 | 0
DCR0283 |  | Re-Design due to OLE Rev F | Revision F submitted under cover letter | RDC181 | 2010-12-14 | DCR0283 | 2011-06-15 | 0 | 12895 | Ph | 2011-06-15 | 12895 | Completed | 100% |  | 12895 | 12895 | 0 |  | 12895 | 0 | 0
DCR0284 | 588 | Lit Signs Requirements from CEC | For Section 5C - Lochside Ave |  |  | DCR0284 | 2011-06-15 | 0 | 0 | Ph | 2011-06-15 | 0 | Completed | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0285 |  | Section 7A Special OLE Foundation Design due to Unforeseen Ground Conditions | TQ1989 - 2no. OLE Foundations | [5 empty] | 0 | Ph | 2011-06-15 |  | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0286 | 731 | Section 5A Special OLE Foundation Design Murrayfield TramStop retaining wall | Siements OLE pole position changes - Rev F - 2no. OLE Foundations | RDC187 | 2011-03-10 | DCR0286 | 2011-06-15 | 0 | 5000 | Ph | 2011-06-15 | 5000 | Completed | 100% |  | 5000 | 5000 | 0 |  | 5000 | 0 | 0
DCR0287 |  | Burnside Road Topo Survey | Survey required for intergration of new road into design |  |  | DCR0287 | 2010-07-29 | 0 | 2453 | DCO130 | 2010-10-22 | 2453 | Completed | 100% |  | 2453 | 2453 | 0 |  | 2453 | 0 | 0
DCR0288 |  | Visualisations and Options for Airport Canopy Design | Various Options for extension of canopy and 2no. Visualisations |  |  | DCR0288 | 2011-06-15 | 0 | 0 | Ph | 2011-06-15 | 0 | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0289 |  | Enhanced Road/ Trackform Design | Develop 2no. enhanced designs for Princes Street |  |  | DCR0289 | 2010-09-08 | 0 | 6460 | DCO127 | 2010-10-22 | 6460 | Completed | 100% |  | 6460 | 6460 | 0 |  | 6460 | 0 | 0
DCR0290 |  | Wooden Walkways in Depot | Concrete across track walkways in the Depot Stabling Area can now be changed to a wooden solution |  |  | DCR0290 | 2011-06-15 | 0 | 3000 | Ph | 2011-06-15 | 3000 | Completed | 100% |  | 3000 | 3000 | 0 |  | 3000 | 0 | 0
DCR0291 |  | Lighting Change for combined OLE/Lighting on Ocean Drive | Change due to height of pole |  |  | DCR0291 | 2011-06-15 | 0 | 0 | Ph | 2011-06-15 | 0 | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0292 |  | Section 2A Special OLE Foundation Design due to Unforeseen Ground Conditions | TQ2076 - 2no. OLE foundations |  |  | DCR0292 | 2011-06-15 | 0 | 13000 | Ph | 2011-06-15 | 13000 | Completed | 100% |  | 13000 | 13000 | 0 |  | 13000 | 0 | 0
DCR0293 |  | Enhanced Road/ Trackform Design - Option 2 design | As per SR email to JRC |  |  | DCR0293 | 2010-09-23 | 0 | 6460 | DCO128 | 2010-10-22 | 6460 | Completed | 100% |  | 6460 | 6460 | 0 |  | 6460 | 0 | 0
DCR0294 |  | SDS Interface design to suit direct Fixation Track for Turnouts/Crossovers | TQ2133 & details provided under Siemens submission 0306 |  |  | DCR0294 | 2011-06-15 | 0 | 10000 | Ph | 2011-06-15 | 10000 | Completed | 100% | agree | 10000 | 10000 | 0 |  | 10000 | 0 | 0
DCR0295 |  | OLE Planning Line 2 | SDS to provide technical and planning liasion support to BSC and support BSC to secure the Approvals and Consents for the Client design |  |  | DCR0295 | 2010-09-29 | 0 | 0 | Ph | 2011-06-15 | 0 | Withdrawn | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0296 |  | Main Diversion at Gogar Roundabout | 5C letter from tie | [5 empty] | 0 |  |  |  | Superseded |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0297 |  | Hydraulic Model of Gogarburn Retaining Walls (2) | Further modelling and changes to kiosk due to straightening of wall outwith LoD |  |  | DCR0297 | 2011-06-15 | 0 | 40000 | Ph | 2011-06-15 | 40000 | Completed | 100% |  | 40000 | 40000 | 0 |  | 40000 | 0 | 0
DCR0298 |  | Enhanced Road/ Trackform Design - Generic | As per Damian Wheeler email to JRC |  |  | DCR0298 | 2010-10-11 | 0 | 2375 | DCO129 | 2010-10-22 | 2375 | Completed | 100% |  | 2375 | 2375 | 0 |  | 2375 | 0 | 0
DCR0299 | 676 | TAA for NIL Crossing 1 & 2 | CEC advised at informal consultation meeting that TAA is required for Crossing 1 and Crossing 2 | RDC176 | 2010-10-13 | DCR0299 | 2010-11-04 | 0 | 2185 | Ph | 2011-03-28 | 2185 | Completed | 100% |  | 2185 | 2185 | 0 |  | 2185 | 0 | 0
DCR0300 |  | New access road to the Forth Ports cruise liner area | Full Planning Permission Required |  |  | DCR0300 | 2011-06-15 | 0 | 0 | Ph | 2011-03-28 | 0 | Closed | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0301 | 690 | Tower Place Bridge East Approach Embankment | Revise design of foundation due to archealogical discovery | RDC178 | 2010-10-27 | DCR0301 | 2010-11-09 | 0 | 1460 | Ph | 2011-03-28 | 1460 | Completed | 100% |  | 1460 | 1460 | 0 |  | 1460 | 0 | 0
DCR0302 | 722 | Murrayfield Accommodation TV Duct | Design for the necessary cast in situ sections | RDC180 | 2010-11-30 | DCR0302 | 2010-12-16 | 0 | 4990 | DCO136 | 2011-01-24 | 4990 | Completed | 100% |  | 4990 | 4990 | 0 |  | 4990 | 0 | 0
DCR0303 | 550 | Trackform Change from Direct Fix, Rheda C/D/Green to Ballast | See tie letter INFCORR4099/WB | RDC158 | 2010-11-08 |  |  |  | 0 |  |  |  | Withdrawn | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0304 |  | Lindsay Road temporary tie in | See TNC 121 | RDC182 | 2011-01-21 | DCR0304 | 2011-06-15 | 0 | 16000 | Ph | 2011-04-04 | 16000 | Completed | 100% |  | 16000 | 16000 | 0 |  | 16000 | 0 | 0
DCR0305 | 723 | Incorporation of Murrayfield Accommodation works as built documentation/information | SDS to review and incorporate As Built data into the over all 'TRAM' As built | RDC181 | 2011-01-21 | DCR0305 | 2011-03-29 | 0 | 3893 | Ph | 2011-04-04 | 3893 | Completed | 100% |  | 3893 | 3893 | 0 |  | 3893 | 0 | 0
DCR0306 |  | Constitution St/Laurie St HGV turning | Option 3 of design sketches to be incorporated with TRO & Planning impacts |  |  | DCR0306 | 2011-06-15 | 0 | 0 | Ph | 2011-04-04 | 0 | Completed | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0307 | [8 empty] | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0308A |  | Lindsay Road retaining Wall footpath | Review AECOM design - and design footpath/cycleway to link Ocean Drive/Ocean Drive Link Road | RDC183 | 2011-02-08 | DCR0308A | 2011-06-15 | 0 | 0 | Ph/DCO227 | 2011-04-04 | 20000 | Superseded | 0% |  | 20000 | 20000 | 0 |  | 20000 | 0 | 0 | Finalised in line with DCO 227
DCR0308B | PMC001 | Hawthorne Vale cycleway connection (2) |  | RDC193 | 2011-07-06 | DCR0308B | 2011-07-18 | 0 | 15000 | Ph/DCO227 | 2011-12-16 | 15000 | Completed | 100% | Agree | 15000 | 15000 | 0 |  | 15000 | 0 | 0 | Finalised in line with DCO 227
DCR0308B | PMC001 | Hawthorne Vale cycleway connection (2) |  | RDC193 | 2011-07-06 | DCR0308B | 2011-07-18 | 0 | 7414 | DCO204 | 2011-12-16 | 7414 | Completed | 100% | Agree | 7414 | 7414 | 0 |  | 7414 | 0 | 0 | Finalised in line with DCO 241
DCR0308B | PMC001 | Hawthorne Vale cycleway connection (2) |  | RDC193 | 2011-07-06 | DCR0308B | 2011-07-18 | 0 | 7414 | DCO241 | 2012-12-13 | -7414 | Completed | 100% | Agree | -7414 | -7414 | 0 |  | -7414 | 0 | 0
DCR0309 |  | Revised Finishes to Ocean Terminal | As per drawings enclosed TNC009.1 | RDC184 | 2011-02-14 | DCR0309 | 2011-06-15 | 0 | 6300 | Ph/DCO226 | 2011-04-04 | 7000 | Completed | suspended | Full scope of works not complete - assessment made on works complete | 7000 | 7000 | 0 |  | 7000 | 0 | 0 | Finalised in line with DCO 226
DCR0310 | 76b | Edinburgh Gateway - OLE Backstay Arrangements | See tie letter with RDC | RDC185 | 2011-02-15 | DCR0310 | 2011-06-15 | 0 | 0 | Ph/DCO227 | 2011-04-04 | 5000 | Withdrawn | 0% | This change was not taken forward with SDS - no SDS costs | 5000 | 5000 | 0 |  | 5000 | 0 | 0 | Finalised in line with DCO 227
DCR0311 |  | Rail Expansion/Movement Joints | Coordination with Siemens (BAM) for Rail Expansion Joints on Structures |  |  | DCR0311 | 2011-06-15 | 0 | 35000 | Ph | 2011-04-04 | 35000 | Completed | 100% | Agree | 35000 | 35000 | 0 |  | 35000 | 0 | 0
DCR0312 | PMC023 | Depot Access Road Hammer head | Relocation of Turning Head to Option 2 | RDC191 | 2011-03-21 | DCR0312 | 2011-06-15 | 0 | 29250 | Ph/DCO227 | 2012-05-01 | 29250 | Completed | 100% | Agree | 29250 | 29250 | 0 |  | 29250 | 0 | 0 | Finalised in line with DCO 227
DCR0312 | PMC023 | Depot Access Road Hammer head | Relocation of Turning Head to Option 2 | RDC191 | 2011-03-21 | DCR0312 | 2011-06-15 | 0 | 22578.5 | DCO214 | 2012-05-01 | 22578.5 | Completed | 100% | Agree | 22578.5 | 22578.5 | 0 |  | 22578.5 | 0 | 0
DCR0312 | PMC023 | Depot Access Road Hammer head | Relocation of Turning Head to Option 2 | RDC191 | 2011-03-21 | DCR0312 | 2011-06-15 | 0 | 22578.5 | DCO241 | 2012-12-13 | -22578.5 | Completed | 100% | Agree | -22578.5 | -22578.5 | 0 |  | -22578.5 | 0 | 0
DCR0313 | PMC022 | Gogar Castle Access Road | Seek approval for tram crossing and approaches within CEC land | RDC190 | 2011-03-21 | DCR0313 | 2011-06-15 | 0 | 23208.2 | Ph/DCO227 | 2012-05-01 | 23400 | Completed | 100% | Agree | 23400 | 23400 | 0 |  | 23400 | 0 | 0 | Finalised in line with DCO 227
DCR0314 |  | Section 5B - OLE Busgate - OLE Pile Clash | Design of the OLE/Utilities clash solution | RDC189 | 2011-03-22 | DCR0314 | 2011-06-15 | 0 | 7500 | Ph | 2011-04-04 | 7500 | Completed | 100% |  | 7500 | 7500 | 0 |  | 7500 | 0 | 0
DCR0315 |  | Gyle Tramstop Cycleway | [6 empty] | 0 |  |  |  | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0316 |  | Grosvenor St OLE Change | [6 empty] | 0 |  |  | 0 | Completed | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0317 |  | Rheda Open on Structures | Review the listed structures listed int eh RDC to detemine the feas and impacts of changing trackform from direct to rheda open | RDC192 | 2011-10-17 | DCR0317 |  |  | 45370.64 | DCO260 | 2013-06-13 | 11250 | Ongoing | 100% |  | 11250 | 11250 | 0 | Costs Submitted for works done , payment now due | 11250 | 0 | 0 | -
DCR0318 |  | Further change to SDS Interface design to suit direct Fixation Track for Turnouts/Crossovers | Further changes to DCR0294 | [5 empty] | 0 |  |  |  | Superseded |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0313 | PMC022 | Gogar Castle Access Road | Seek approval for tram crossing and approaches within CEC land | RDC190 | 2011-03-21 | DCR0313 | 2011-06-15 | 0 | 23208.2 | DCO213 | 2012-05-01 | 23208.2 | Completed | 100% | Agree | 23208.2 | 23208.2 | 0 |  | 23208.2 | 0 | 0
DCR0313 | PMC022 | Gogar Castle Access Road | Seek approval for tram crossing and approaches within CEC land | RDC190 | 2011-03-21 | DCR0313 | 2011-06-15 | 0 | 23208.2 | DCO241 | 2012-12-13 | -23208.2 | Completed | 100% | Agree | -23208.2 | -23208.2 | 0 |  | -23208.2 | 0 | 0
DCR0319 | PMC008 | St James Substation (Cathedral Lane Substation) | Refers back to DCR0167 (see RDC for new scope) | RDC200 | 2011-07-18 | DCR0319 | 2011-11-02 |  | 173162.1 | DCO210 | 2012-04-27 | 173162.1 | Completed | 100% | Agree | 173162.1 | 173162.1 | 0 |  | 173162.1 | 0 | 0
DCR0320 | PMC007 | St Andrew Square inc Position Statement | See RDC197 | RDC197 | 2011-07-05 | DCR0320 | 2011-08-10 | 0 | 98647.5 | DCO203 | 2011-11-09 | 98647.5 | Ongoing | 100% | agreed | 98647.5 | 98647.5 | 0 |  | 98647.5 | 0 | 0 | Refer DCO 203
DCR0321 | PMC005 | York Place Terminal Point | Prelimary Design | RDC203 | 2011-07-05 | DCR0321 | 2011-07-08 | 0 | 169498 | DCO205 | 2011-12-16 | 169498 | Completed | 100% | Agree | 169498 | 169498 | 0 |  | 169498 | 0 | 0
DCR0322 | PMC010 | Water connection Gogar Lodge to Landowners Septic tank |  | RDC198 | 2011-07-07 | DCR0322 | 2011-08-03 | 0 | 3440 | DCO207 | 2011-12-16 | 3440 | Completed | 100% |  | 3440 | 3440 | 0 |  | 3440 | 0 | 0
DCR0323 | PMC006 | Mound Cycleway (2) | Split into 2 changes | RDC196 | 2011-07-04 | DCR0323 | 2011-08-03 | 0 | 7933 | DCO206 | 2011-12-16 | 7932.5 | Completed | 100% |  | 7932.5 | 7932.5 | 0 |  | 7932.5 | 0 | 0
DCR0324 | PMC004 | Blenheim Place review of existing design |  | RDC195 | 2011-07-04 | DCR0324 | 2011-08-05 | 0 | 1714.6 | DCO202/DCO226 | 2011-11-09 | 34282.5 | Completed | suspended | Full scope of works not complete - assessment made on works complete | 34282.5 | 34282.5 | 0 |  | 34282.5 | 0 | 0 | Finalised in line with DCO 226
DCR0325 | PMC002 | Provision of Footpath at Ocean Drive | Now Verge - and amendment to Landscaping | RDC194 | 2011-07-04 | DCR0325 | 2011-08-09 | 0 | 2579 | DCO201/DCO226 | 2011-11-09 | 7584 | Completed | suspended | Design only taken to IFEA Status - payment in line with Estimate | 7584 | 7584 | 0 |  | 7584 | 0 | 0 | Finalised in line with DCO 226
DCR0326 | PMC013 | Eastfield Avenue Tram Crossing | Verification of Design and Approval from BAA | RDC199 | 2011-07-14 | DCR0326 | 2011-08-03 | 0 | 7295.5 | DCO209 | 2011-12-16 | 7281.5 | Completed | 100% | Agree | 7281.5 | 7281.5 | 0 |  | 7281.5 | 0 | 0 | Updated in line with DCO 209
DCR0327 | PMC012 | Ocean Terminal By Pass Road | Carry Out redesign of OCT By Pass road, incorporating the AECOM design | RDC201 | 2011-07-18 | DCR0327 | 2011-08-10 | 0 | 31837.6 | DCO208/DCO226 | 2011-12-16 | 39797 | Completed | suspended | agreed | 39797 | 39797 | 0 |  | 39797 | 0 | 0 | Finalised in line with DCO 226
DCR0328a | PMC015 | Revised Design to minimise Utility Diversions | 6no. Poles | RDC202 | 2011-07-26 | DCR0328a | 2011-10-28 | 0 | 45270.9 | DCO212 | 2012-08-28 | 46042.9 | Completed |  | agree with reduction of 771.90 | 46042.9 | 46042.9 | 0 |  | 46042.9 | 0 | 0 | Finalised in line with DCO 271
DCR0328a | PMC015 | Revised Design to minimise Utility Diversions | Reduction of scope | [6 empty] | DCO271 | 2013-10-30 | -721.9 | Completed |  |  | -721.9 | -721.9 | 0 |  | -721.9 | 0 | 0 | Finalised in line with DCO 271
DCR0328b | PMC015 | Revised Design to minimise Utility Diversions | IMPC 13A & 13B | RDC202 | 2011-07-26 | DCR0328b | 2011-10-28 | 0 | 32281 | DCO212 | 2012-08-28 | 32281 | Completed |  | agreed | 32281 | 32281 | 0 |  | 32281 | 0 | 0 | Finalised in line with DCO 271
DCR0328b | PMC015 | Revised Design to minimise Utility Diversions | Reduction of design change fee | [6 empty] | DCO271 | 2013-10-30 | -380 | Completed |  |  | -380 | -380 | 0 |  | -380 | 0 | 0
DCR0328c | PMC015 | Revised Design to minimise Utility Diversions | IMPC 13C & 13D | RDC202 | 2011-07-26 | DCR0328c | 2011-12-14 | 0 | 37962.6 | DCO212 | 2012-08-28 | 37962.6 | Completed |  | agreed | 37962.6 | 37962.6 | 0 |  | 37962.6 | 0 | 0 | Amended as per DCO 212
DCR0329 |  | Constitution Street Cemetery Wall - Interface with Tram | Special OLE foundation | [5 empty] | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0330 |  | Tower Place Bridge Steps Updated | Alternative proposal to shift the current design for the steps westwards | [5 empty] | 0 |  |  |  | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0331 | PMC024 | Old Port Cycleway - RW1A Footpath at toe of wall ADM to Ocean Drive Link Road | Review AECOM design - and design footpath/cycleway to link Ocean Drive/Ocean Drive Link Road |  |  | DCR0331 | 2011-10-03 | 0 | 0 |  |  |  | Withdrawn | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0332 | PMC019 | NIL Design Finalisation | Design Changes to crossings | RDC204 | 2011-10-19 | DCR0332 | 2012-12-01 |  | 3784.5 | DCO218 | 2012-08-28 | 3784.5 | Completed | 100% | agreed | 3784.5 | 3784.5 | 0 |  | 3784.5 | 0 | 0
DCR0333 |  | Dublin St Steps re-Design |  |  |  | DCR0333 | 2012-01-25 | 0 | 0 |  |  |  | Withdrawn |  | Principle of Change not agreed | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0334 | PMC038 | Revised Design to minimise Utility Diversions | OLE Princes St - St. Johns church | RDC206 | 2011-12-05 | DCR0334 | 2012-01-27 | 0 | 7249 | DCO221 | 2012-08-28 | 7249.3 | Ongoing |  | Agree | 7249.3 | 7249.3 | 0 |  | 7249.3 | 0 | 0 | Amended as per DCO 221
DCR0335 | PMC039 | Revised Design to minimise Utility Diversions | Shandwick OLE & landscape design | RDC213 | 2012-01-06 | DCR0335 | 2012-01-27 | 0 | 14476.8 | DCO219 | 2012-08-28 | 14476.8 | Ongoing |  | Agree | 14476.8 | 14476.8 | 0 |  | 14476.8 | 0 | 0 | Amended as per DCO 219
DCR0336 | PMC048 | Matt Fell T&T support | Utilities support to T&T | RDC210 | 2011-12-13 | DCR0336 | 2011-12-14 | 0 | 95826 | DCO216/ DCO258 | 27/04/2012 09/05/2013 | 97541.15 | Ongoing |  | M&A % not accepted, Payment as per BBS assesment of Hours provided -refer time sheet mark up | 97541.15 | 97541.15 | 0 | ongoing "call off" order | 97541.15 | 0 | 0 | Payment as per B&S assesment of hours provided - refer time sheet mark ups. Slight reduction as hours split into other time sheet PMCs.
DCR0337 | - | Landscaping changes in Section 5B | Saughton Stenhouse and Carrick Knowe | RDC205 | 2011-12-05 | DCR0337 | 2012-01-17 | 0 | 10952 | DCO211 | 2012-04-27 | 10952 | Completed | 100% | Agree | 10952 | 10952 | 0 |  | 10952 | 0 | 0
DCR0338 | PMC042 | Revised Landscaping to accommodate new CEC for Plot 304 |  | RDC207 | 2011-12-05 | DCR0338 | 2012-01-17 | 0 | 3768 | DCO215 | 2012-05-01 | 3768 | Completed | 100% | Agree | 3768 | 3768 | 0 |  | 3768 | 0 | 0
DCR0339 |  | Review of track alignment against As Built structures |  | RDC208 | 2011-12-09 | DR0339 | 2012-01-27 | 0 | 30159 | DCO236 | 2012-11-21 | 30159 | Ongoing | 100% | Estimate Under review-final figure to be agreed 50% payment to date. Aim to resolve period 5.8 | 30159 | 30159 | 0 |  | 30159 | 0 | 0
DCR0340 |  | S26 Ground Improvement |  | RDC209 | 2011-12-12 |  |  |  | 0 |  |  |  | Withdrawn | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0341 | PMC054 | Edinburgh Gateway - Initial Feasibility Study | do minimum' alignment | RDC211 | 2012-01-23 | DCR0341 |  |  | 13455 | DCO233 | 2012-10-31 | 13455 | Ongoing | 100% | Agreed | 13455 | 13455 | 0 |  | 13455 | 0 | 0
DCR0342 | PMC053 | York Place Terminal Point | Detailed Design | RDC212 | 2012-01-06 | DCR0342 | 2012-01-20 | 0 | 41837 | DCO217 | 2012-05-01 | 41837 | Ongoing | 100% | Not Complete -CEC approval still to brequired 90% payment to reflect progress | 41837 | 41837 | 0 | IFCs issued and agreed with CEC , but SDS await outstanding formal CEC approval | 41837 | 0 | 0
DCR0343 | PMC056 | OLE Circular Pile Cap Design |  | RDC214 | 2012-01-06 | DCR0343 | 2012-01-27 | 0 | 15316.3 | DCO220 | 2012-08-28 | 15316.3 | Completed | 100% |  | 15316.3 | 15316.3 | 0 |  | 15316.3 | 0 | 0
DCR0344 | PMC014 | Edinburgh Gateway - retaining wall - new slope | Option 5 | RDC227a | 2012-04-03 | DCO228 |  |  | 66770 | DCO228 | 2012-09-07 | 66770 | Ongoing |  | Still not complete await landsacpe design design.updated design issued by SDS due to errors and omission in initial IFC design, | 66770 | 66770 | 0 | complete | 66770 | 0 | 0
DCR0345 | PMC061 | Roseburn Non DDA compliant footpath | Explore alternative solutions at Roseburn corridor | RDC220 | 2012-01-25 | DCR0345 | 2012-02-22 | 0 | 0 |  |  |  | Withdrawn | 0% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0346 | PMC062 | Cathedral Lane substation new retaining wall |  | RDC219 | 2012-01-26 | DCR0346 | 2012-03-02 | 0 | 25544 | DCO222 | 2012-08-28 | 25544 | Completed | 100% | agree | 25544 | 25544 | 0 |  | 25544 | 0 | 0
DCR0347 | PMC021 | Communication Connection between ETN ODN & City Chambers UTC Integration |  | RDC221 | 2012-01-26 | DCR0347 | 2012-04-18 | 0 | 0 | DCO246 | 2013-04-11 | 0 | Completed | 100% |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0348 | PMC045 | Revised Design to minimise Utility Diversions - OLE | Call Off Order | RDC217 | 2012-01-23 | DCR0348 | 2012-01-26 |  | 32153 | DCO257 | 09/05/2013 26/01/2012 | 26238.5 | Ongoing |  | Refer BBS mark up of PMC Timesheets | 26238.5 | 26238.5 | 0 | ongoing "call off" order, Certification breakdown required | 26238.5 | 0 | 0 | Payment as per B&S assesment of hours provided - refer time sheet mark ups.
DCR0349 | PMC046 | Revised Design to minimise Utility Diversions - Ducting | Call Off Order | RDC216 | 2012-01-23 | DCR0349 | 2012-01-26 |  | 29918 | DCO268 | 26/01/2012 16/10/13 | 35447 | Ongoing |  | Refer BBS mark up of PMC Timesheets | 35447 | 35447 | 0 | ongoing "call off" order, Certification breakdown required | 35447 | 0 | 0 | Payment as per B&S assesment of hours provided - refer time sheet mark ups.
DCR0350 | PMC047 | Revised Design to minimise Utility Diversions - Trackform | Call Off Order | RDC215 | 2012-01-23 | DCR0350 | 2012-01-26 |  | 8054 | DCO261 | 27/06/2013 26/01/2012 | 5829.91 | Ongoing |  | Refer BBS mark up of PMC Timesheets | 5829.91 | 5829.91 | 0 | ongoing "call off" order, Certification breakdown required | 5829.91 | 0 | 0 | Payment as per BBS assesment of hours provided - refer time sheet mark ups.
DCR0351 | PMC050 | Revised Design to minimise Utility Diversions - Drainage | Call Off Order | RDC218 | 2012-01-23 | DCR0351 | 2012-01-26 |  | 84802 | DCO269 | 26/01/2012 16/10/13 | 91213 | Ongoing |  | Refer BBS mark up of PMC Timesheets | 91213 | 91213 | 0 | ongoing "call off" order, Certification breakdown required | 91213 | 0 | 0 | Payment as per B&S assesment of hours provided - refer time sheet mark ups.
DCR0352 |  | S21D Ground Improvement | As per TQ2856 | [5 empty] | 0 |  |  |  | Withdrawn |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0353 | PMC070 | St. Andrew Square - Value engineering design Changes | see TNC 586 | RDC224 | 2012-02-21 | DCR0353 | 2012-03-26 | 0 | 11288 | DCO223 | 2012-08-28 | 11288 | Ongoing | 100% | Not Complete -CEC approval still required 90% payment to reflect progress | 11288 | 11288 | 0 | CEC Approval Outstanding | 11288 | 0 | 0
DCR0354 | PMC071 | Granite Setts Design | Amend Design as oper TNC587 | RDC226 | 2012-03-15 | DCR0354 |  |  | 11499 | DCO231 | 2012-10-31 | 11499 | Ongoing | 100% | Not Complete -detailed setts layout required for st andrews square and discrepancies in section 1D HRL drawings to be resolved | 11499 | 11499 | 0 | complete , note ongoing discussions with CEC on detailed layouts but this is not specifically related to this change | 11499 | 0 | 0
DCR0355 | PMC084 | Cessation of Sec Phase 1a Design | [7 empty] | DCO226 | [6 empty] | 0 |  |  |  | 0 |  | DCO226
DCR0356 | PMC089 | Gogarburn Tramstop Shelters | Amend length of shelters | RDC228 | 2012-03-23 | DCR0356 | 2012-04-10 | 0 | 2671 | DCO224 | 2012-08-28 | 2671 | Completed | 100% | agreed | 2671 | 2671 | 0 | closed | 2671 | 0 | 0
DCR0357 | PMC60/63/ 65/92/170 | Crew Relief | Stairs/Parapet/wall/crew relief | RDC229 | 2012-04-03 | DCR0357 |  |  | 7010 | DCO272 | 2013-12-04 | 7010 | Ongoing | 100% | Estimate still under review with T&T.Aim to resolve period 5-7 | 7010 | 7010 | 0 | Complete issued on BIW 28/6, | 7010 | 0 | 0
DCR0358 | PMC093 | Network Rail encroachment into LoD ( Ducting and OLE) |  | RDC230 | 2012-04-04 | DCR0358 |  | 0 | 6819.65 | DCO238 | 2012-11-22 | 6819.65 | Ongoing | 100% | Estiamte under review with T&T.Balance of payment following approval from T&T.Aim to resolve in period 5-8 | 6819.65 | 6819.65 | 0 | completed within Period 5-3 | 6819.65 | 0 | 0
DCR0359 | PMC007 | St Andrew Square inc Position Statement | Addendum | RDC197Addendum | 2012-04-03 |  |  | 0 | 0 |  |  |  | Closed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0360 |  | RSA stage3 Gogar Lane & Depot Access road |  | RDC232 | 2012-05-18 | DCR0361 |  |  | 10212 | DCO239 | 2012-12-12 | 10212 | Ongoing |  | Estimate under review with T&T. Balance of payment following approval from T&T.Aim to resolve in period 5-6 | 10212 | 10212 | 0 | not 90% complete | 10212 | 0 | 0
DCR0361 | PMC115 | Edinburgh Airport Tramstop Design |  | RDC232 | 2012-05-18 | DCR0361 |  |  | 13183 | DCO230 | 2012-10-31 | 13183 | Ongoing | 100% | Design not complete -CCTV foundation, electrical abd drainage issues to be reolved by SDS | 13183 | 13183 | 0 | completed within Period 5-7 | 13183 | 0 | 0
DCR0362 | PMC064 | Hope Street/ Princes Street Junction |  | RDC234 RDC254 | 18/05/2012 03/10/2012 | DCR0362 |  |  | 8941 | DCO247 | 2013-04-11 | 8941 | Ongoing | 100% | Not coplete within period and estimaet still to be agreed with T7T | 8941 | 8941 | 0 | complete . | 8941 | 0 | 0
DCR0363 | PMC119 | St Johns Church - Pedestrian Guardrail |  | RDC233 | 2012-05-21 | DCR0363 |  |  | 0 | DCO225 | 2012-08-28 | 0 | Completed |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0364 | PMC124 | Twin water Crossing Lochside avenue. |  | RDC235 | 2012-05-29 | DCR0364 |  |  | 8266 | DCO248 | 2013-04-11 | 8266 | Ongoing | 100% | Estimate still under review with T&T.Aim to resolve period 5-8 | 8266 | 8266 | 0 | complete | 8266 | 0 | 0
DCR0365 | PMC014 | Gateway Slop Option-sewer/OLE Conflict |  | RDC236 | 2012-06-13 | DCO228 |  |  | 9580 | DCO228 | 2012-09-07 | 9580 | Completed | 100% | Agree | 9580 | 9580 | 0 | completed in Period 5-7 | 9580 | 0 | 0
DCR0365a | PMC014 | Gateway slope option sewer and track conflict |  | RDC231 | 2012-06-13 | DCR0365a |  |  | 15757 | DCO228 | 2012-09-07 | 15757 | Ongoing | 100% | Estiamte still under review with T&T 50% payment aim to resolve period 5.7 | 15757 | 15757 | 0 | complete | 15757 | 0 | 0
DCR0366 | PMC150 | St Andrews Square MX Cross sections stage 1/stage2 |  | RDC237a | 2012-06-19 | DCR0366 |  |  | 6587 | DCO242 | 2013-01-30 | 6587 | Ongoing | 100% | Estiamte still under review with T&T 50% payment aim to resolve period 5.7 | 6587 | 6587 | 0 | complete | 6587 | 0 | 0 | Closed at value of DCO.
DCR0367 | PMC151 | Lighting Cabinet Relocation Princes street |  | RDC238 | 2012-06-19 |  |  |  | 0 | DCO249 | 2013-04-11 | 0 | Completed | 100% |  | 0 |  | 0 |  | 0 | 0 | 0
DCR0368 |  | Road Safety Audit stage 3, remaining sections |  | RDC239 | 2012-06-19 | DCR0368 | [6 empty] | Ongoing |  |  | 0 |  | 0 |  | 0 | 0 | 0
DCR0369 | PMC155 | Princes st As-Built drainage drawing for Scottish water |  | RDC240 | 2012-06-26 | DCR0369 |  |  | 2425 | DCO245 | 2013-01-30 | 2425 | Ongoing |  | not complete | 1818.75 | 2425 | -606.25 | Complete | 1818.75 | 0 | -606.25 | Not complete - further update required once final drainage connection works completed - 75% payment to reflect works completed to date
DCR0370 |  | As built Survey Check -A8 underpass to depot road access bridge |  | RDC241 | 2012-07-27 | DCR0370 |  |  | 3357 | DCO232 | 2012-10-31 | 3003 | Ongoing |  |  | 3003 | 3003 | 0 | Complete | 3003 | 0 | 0 | Agreed as per DCO 232
DCR0371 | PMC169 | Eastfield Avenue Road and Pedestrian Crossing | Provide Composite Drawing | RDC242 | 2012-08-09 | DCR0371 |  |  | 1478 | DCO240 | 2012-12-13 | 1478 | Ongoing | 100% | Agree | 1478 | 1478 | 0 | Complete | 1478 | 0 | 0
DCR0372 |  | York Place Floating slab change request |  | RDC243 | 2012-08-09 | DCR0372 |  |  | 6986 | DCO234 | 2012-11-21 | 6986 | Ongoing |  |  | 6986 | 6986 | 0 | Complete | 6986 | 0 | 0
DCR0373 | PMC177 | Design response to Princes St road safety audit |  | RDC244 | 2012-08-13 | DCR0373 |  |  | 1194 | DCO237 | 2012-11-22 | 1194 | Ongoing |  |  | 1194 | 1194 | 0 | Complete | 1194 | 0 | 0
DCR0374 | PMC150 | On street works carriageway reconstruction-Design |  | RDC245 | 2012-08-20 | DCR0374 |  |  | 11597 | DCO243 | 2013-01-30 | 11120 | Ongoing |  |  | 11120 | 11120 | 0 | Complete | 11120 | 0 | 0 | Agreed as per DCO 238
DCR0375 | PMC172 | MUDFA as Built Drawings |  | RDC246 | 2012-08-20 | DCR0375 | [6 empty] | Ongoing |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
DCR0376 | PMC046 | Provide Drawing for Works at Lord Bodos Bar |  | RDC247 | 2012-08-27 | DCR0376 |  |  | 0 | DCO268 | 2013-10-16 | 0 | Ongoing |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | CLOSED - Works covered under PMC 045/046
DCR0377 |  | Revised Evaluation of Project Phoenix |  |  |  | N/a |  |  | 0 | DCO227 | 2012-08-28 | -103227 | Completed |  |  | -103227 | -103227 | 0 |  | -103227 | 0 | 0 | Refer DCO 227
DCR0378 | PMC207 | On Street Drainage Design |  | RDC248 | 2012-09-10 | DCR0378 |  |  | 5855 | DCO259 | 2013-05-16 | 13328.95 | Ongoing |  |  | 13132.62 | 13132.62 | 0 |  | 13132.62 | 0 | 0 | B&S assessed value based on time sheets submitted by SDS.
DCR0379 | PMC206 | Cathedral Lane Tram Substation |  | RDC249 | 2012-09-10 | DCR0379 |  |  |  | DCO250 | 2013-04-11 | 34521 | Ongoing |  |  | 34521 | 34521 | 0 | Refer time charge sheet | 34521 | 0 | 0
DCR0380 | PMC213 | On Street Basses-Ducting (type2's) |  | RDC250 | 2012-09-25 | DCR0380 |  |  | 16611 |  |  |  | Ongoing |  |  | 62293.81 | 62839.76 | -545.95 | Complete | 62293.81 | 0 | -545.95 | B&S assessed value based on time sheets submitted by SDS.
DCR0381 | PMC212 | St Andrew Square East Redesign |  | RDC251 | 2012-09-25 | DCR0381 |  |  |  | DCO251 | 2013-04-11 | 6825 | Ongoing |  |  | 6825 | 6825 | 0 |  | 6825 | 0 | 0
DCR0382 | PMC215 | Airport Interface Reinstatement |  | RDC252 | 2010-09-27 | DCR0382 |  |  | 29006 | DCO270 | 2013-10-16 | 25742 | Ongoing |  |  | 25742 | 25742 | 0 |  | 25742 | 0 | 0 | -
DCR0383 |  | Precast alterations |  | RDC253 | 2012-10-01 | DCR0383 |  |  | 2822 | DCO235 | 2012-11-21 | 2822 | Ongoing |  |  | 2822 | 2822 | 0 |  | 2822 | 0 | 0
DCR0385 | PMC170 | Call off change, network rail technical issues |  | RDC255 | 2012-10-09 | DCR0385 |  |  |  | DCO272 | 2013-12-04 | 3861 | Ongoing |  |  | 3861.22 | 3861.22 | 0 |  | 3861.22 | 0 | 0 | Agreed - reflects work carried out on call off (time sheet basis).
DCR0386 | PMC093 | W18 Wall / Drainage |  |  |  | DCR0386 |  |  | 2636 | DCO238 | 2012-11-22 | 2636.25 | Ongoing |  |  | 2636.25 | 2636.25 | 0 | Complete | 2636.25 | 0 | 0
DCR0387 | PMC226 | SGN Asbuilt drawings between Ingliston and Eastfield Avenue |  | RDC256 | 2012-10-15 | DCR0387 |  |  | 2531 | DCO256 | 2013-05-09 | 2531 | Ongoing |  |  | 2531 | 2531 | 0 |  | 2531 | 0 | 0 | Agreed
DCR0388 |  | Gas Governer House Works |  |  |  | DCR0388 | [9 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | Refer previous SN/GL discussion and agreement.
DCR0389 | PMC254 | Russell Road/ Haymarket Retaining Walls | Changes to Network Rail post Survey ,resulting in revised design |  |  | DCR0389 |  |  | 47153 | DCO267 | 2013-10-01 | 38256.98 |  |  |  | 45491.98 | 45491.98 | 0 |  | 45491.98 | 0 | 0 | Agreed as per DCO value.
Phase 3 (DCR 0390) |  | Revised Phase 3 | Revised Evaluation of Phase 3 Deliverables |  |  | DCR0390 |  |  | -30000 | DCO229 | 2012-10-31 | -30000 |  |  |  | -30000 | -30000 | 0 |  | -30000 | 0 | 0 | CLOSED
DCR0391 | PMC150 | SAS west side update of MX |  | RDC258 | 2012-11-15 | DCR0391 |  |  | 2810 | DCO244 | 2013-01-30 | 2810 |  |  |  | 2810 | 2810 | 0 |  | 2810 | 0 | 0
DCR0392 | PMC232 | Edinburgh Park Central Lighting |  | RDC257 | 2012-11-14 | DCR0392 |  |  | 2568 | DCO252 | 2013-04-11 | 2568 |  |  |  | 2568 | 2568 | 0 |  | 2568 | 0 | 0 | Agreed.
DCR0393 | PMC172 | Fare Collection Equipment |  | RDC260 | 2012-11-22 | DCR0393 |  |  | 10163 | DCO253 | 2013-04-11 | 10163 |  |  |  | 10163 | 10163 | 0 |  | 10163 | 0 | 0 | Agreed.
DCR0394 | PMC235 | Re-alignment of SW pipe at Murrayfield | Calculations for temporary case | RCD259 | 2012-11-22 | DCR0394 |  |  | 2421 | DCO254 | 2013-04-11 | 2421 |  |  |  | 2421 | 2421 | 0 |  | 2421 | 0 | 0
DCR0395 | - | Not Used | [14 empty] | 0 |  |  | 0 |  | 0
DCR0396 | PMC262 | Shandwick Place Bus Markings | Update to HRL drawings. | RDC262 | 2013-02-12 | DCR0396 |  |  | 4944 | DCO264 | 2013-09-10 | 3982.77 |  |  |  | 3982.77 | 3982.77 | 0 |  | 3982.77 | 0 | 0 | Agreed at reduced value as per SN/GL agreement
DCR0397 | - | TR2500s |  | RDC261 | 2013-01-29 | DCR0397 |  |  | 30000 | DCO255 | 2013-04-11 | 30000 |  |  |  | 30000 | 30000 | 0 |  | 30000 | 0 | 0 | Agreed - Works completed.
DCR0398 | - | Not Used | [14 empty] | 0 |  |  | 0 | 0 | 0
DCR0399 | PMC254 | ScotRail Gantry Foundation Support | Changes to Network Rail post Survey ,resulting in revised design | [6 empty] | DCO267 | 2013-10-01 | 7235 |  |  |  |  | 0 |  |  | 0 | 0 | 0
DCR0400 | PMC278 | ScotRail Gantry New Fence Design |  | RDC263 | [5 empty] | DCO273 | 2013-12-04 | 5828 |  |  |  | 5828 | 5828 |  |  | 5828 | 0 | 0 | Agreed
DCR0401 | PMC215 | Airport Interface Reinstatement | Further works - amended tNC issued. | RDC252 | 2013-05-02 |  |  |  |  | DCO270 | 2013-10-16 | 0 |  |  |  |  | 0 |  |  | 0 | 0 | 0 | Covered above under PMC 215 - DCR 0382
DCR0402 | PMC281 | Reduction in hard copy As-built drawings to be provided | SDS to provide 1 hard copy as-built in lieu of 5 number previously agreed | RDC264 | 2013-04-23 | [11 empty] | 0 |  |  | 0 | 0 | 0 | Withdrawn
DCR0403 | PMC283 | DKE Survey | Due to change in DKE ao CAF vehicle, SDS to re-run the DKE report | RDC265 | 2013-05-02 |  |  |  | 19120 | DCO265 | 2013-09-10 | 19120 |  |  |  | 9560 | 19120 |  |  | 9560 | 0 | -9560 | Report issued. 50% payment until verification of report is completed.
DCR0404 | - | Alternative parapet design check |  | RDC266 |  | RDC266 | 2013-06-11 |  | 1807 | DCO262 | 2013-06-27 | 1807 |  |  |  | 1807 | 1807 |  |  | 1807 | 0 | 0 | -
DCR0405 |  | On-Street Design Changes due to Track Form Conflicts | [14 empty] | 0 |  |  | 0 | 0 | 0 | CLOSED
DCR0406 | - | Re-design of power feed to ScotRail car park |  | RDC267 |  | RDC267 | 2013-06-20 |  | 2772 | DCO263 | 2013-06-27 | 2772 |  |  |  | 2772 | 2772 |  |  | 2772 | 0 | 0 | -
DCR0407 | - | OLE base re-design due to utility conflicts |  | - | - |  |  |  |  | - | - | - |  |  |  | 0 | 0 |  |  | 0 | 0 | 0 | -
DCR0408 | - | - |  | - | - |  |  |  |  | - | - | - |  |  |  | 0 | 0 |  |  | 0 | 0 | 0 | -
DCR0409 | PMC304 | Third Party works As-Builts |  | RDC270 | 2013-08-28 | [10 empty] | 0 | 22175 |  |  | 0 | 0 | -22175 | Estimate issued after application. Estimate to be agreed with client. Works still to be completed by SDS.
DCR0410 | PMC170 | ScotRail Depot Store Loading |  | - | - | [10 empty] | 0 | 0 |  |  | 0 | 0 | 0 | Covered under PMC 170 time sheet call off.
DCR0411 | PMC309 | Tram Weight Delta |  | RDC272 | 2013-09-11 |  |  |  |  | DCO275 | 2014-01-14 | 1074 |  |  |  | 0 | 1074 |  |  | 1074 | 1074 | 0 | Agreed
DCR0412 | PMC315 | Carrick Knowe Lighting |  | RDC273 | 2013-10-04 |  |  |  |  | DCO276 | 2014-01-14 | 628 |  |  |  | 0 | 0 |  |  | 0 | 0 | 0 | -
DCR0413 | PMC314 | Section B Lighting As-Builts update |  | RDC274 | 2013-10-04 |  |  |  |  | DCO277 | 2014-01-14 | 0 |  |  |  | 0 | 628 |  |  | 0 |  |  | Estimate issued after application. Estimate to be agreed with client. Works still to be completed by SDS.
DCR0414 | PMC290 | Broughton Street | Change in levels due to MUDFA | RDC268 | 2013-06-24 |  |  |  |  | DCO266 | 2013-10-01 | 1440 |  |  |  | 1440 | 1440 |  |  | 1440 | 0 | 0 | -
DCR0415 | PMC293 | ScotRail Timber Steps | ScotRail Timber Steps | RDC269 | 2013-09-05 |  |  |  |  | DCO274 | 2013-12-04 | 7589 |  |  |  | 0 | 7589 |  |  | 7589 | 7589 | 0 | Agreed
[16 empty] | 0 |  |  |  | 0 | 0 | 0
[11 empty] | Subtotal | 5673551.81 |  |  |  | 5716192.26 | 5758370.46 | -1152.2 |  | 5724855.26 | 8663 | -32887.2 | B&S Assessment - TOTAL
[11 empty] | Total | 5673551.81 |  |  |  | 5716192.26 | 5758370.46 | -1152.2 |  | 5724855.26 | 8663 | -32887.2
Note on J6: ShudallK: withdrawn as per meeting with Dennis Murray 04/02/09
Note on J10: ShudallK: revised 15/12/08
Note on J15: ShudallK: pro rata 2/3 as per meeting with Dennis Murray 04/02/09
Note on J16: ShudallK: revised 03/02/09 & 09/02/09
Note on J20: ShudallK: revised 03/02/09
Note on J21: ShudallK: revised 07/01/09
Note on J22: ShudallK: revised 03/02/09
Note on J23: ShudallK: was £25,080 but not needed by tie
Note on J24: ShudallK: revised 03/02/09
Note on J25: ShudallK: revised 07/01/09
Note on M33: ShudallK: Rescinded 03/12/09
Note on M34: ShudallK: Rescinded 03/12/09
Note on M35: ShudallK: Rescinded 03/12/09
Note on J69: shudallk: 30% of original estimate done only
Note on J70: ShudallK: revised 03/02/09 & 09/02/09
Note on J74: ShudallK: updated 23/06/09
Note on J75: ShudallK: reinstated 26/03/09. Was £79, 732 but withdrawn. Fully withdrawn 02/09/09
Note on J77: ShudallK: revised 03/02/09
Note on J82: ShudallK: revised 03/02/09 & 09/02/09
Note on J85: ShudallK: revised 03/02/09 & 09/02/09
Note on J87: shudallk: withdrawn 041110
Note on J88: ShudallK: Updated 11/03/09
Note on J89: ShudallK: Updated 11/03/09
Note on J91: ShudallK: Amended 081009
Note on J92: ShudallK: revised 15/12/08
Note on J94: ShudallK: revised 20/02/09
Note on J98: ShudallK: revised 03/02/09
Note on J99: ShudallK: revised 15/12/08
Note on J103: ShudallK: revised 03/02/09
Note on J104: ShudallK: revised 15/12/08
Note on J106: ShudallK: Withdrawn 24/02/10
Note on J108: ShudallK: revised 15/12/08
Note on J109: shudallk: updated 140910 & 091110. Amended to £3500 settlement 080211
Note on L109: shudallk: Amended 04/03/11
Note on J110: ShudallK: updated 18/03/09
Note on M110: ShudallK: Withdrawn by BSC 21/01/10
Note on J111: ShudallK: Updated 120110
Note on J112: ShudallK: Updated 30/07/09
Note on J113: ShudallK: revised 15/12/08
Note on J114: ShudallK: Abortive cost only - advised in letter 11/12/09
Note on L114: ShudallK: updated 160310
Note on J115: ShudallK: revised 09/02/09
Note on J116: ShudallK: revised 09/02/09
Note on J118: ShudallK: withdrawn 310709
Note on J119: ShudallK: revised 09/02/09
Note on J121: ShudallK: revised 09/02/09
Note on J122: ShudallK: Updated 05/05/09
Note on J124: ShudallK: revised 09/02/09
Note on J127: ShudallK: withdrawn 310709
Note on J133: shudallk: reduced as per vibration mitigation letter
Note on M133: shudallk: Reduced as per vobration mitigation letter. Updated again 110311 to add back in vibration
Note on J135: ShudallK: revised 09/02/09
Note on J137: ShudallK: withdrawn by BSC 12/05/09
Note on J138: ShudallK: Revsied 28/05/08
Note on J139: ShudallK updated 03/04/09
Note on J140: ShudallK: Updated 040210
Note on L140: shudallk: Updated 190810
Note on J141: ShudallK: Updated 08/05/09
Note on J142: ShudallK updated 24/04/09
Note on J145: ShudallK: withdrawn 21/12/09
Note on J150: ShudallK: updated 16/10/09 Abortive costs agreed at £4800
Note on L150: shudallk: Amened 131010
Note on M150: ShudallK: Abortive costs sent to BSC
Note on J153: ShudallK: Updated 261009
Note on J154: ShudallK: revised 28/09/09. Withdrawn 24/02/10
Note on J155: ShudallK: Updated 02 April 2009
Note on J156: ShudallK: updated 18/03/09
Note on J159: ShudallK: revised 06/02/09
Note on J166: ShudallK: Agreed at meeting on 300609 KS and JHi
Note on J169: ShudallK: Updated 04/06/09
Note on J172: ShudallK: Updated 300709
Note on M176: shudallk: £1585 ordered to date. £119171 overall estimate
Note on J178: ShudallK: Closed 190310 Abortuive costs sent to BSC
Note on L178: shudallk: Amended 141010
Note on J179: ShudallK: revised 28/09/09 Stage 1 only
Note on J180: ShudallK: Updated 05/05/09
Note on J181: shudallk: updated 051110
Note on J182: ShudallK: Stage 1 & 2 only All staged price was £254,081.25
Note on M182: ShudallK: Stage 1 & 2 only
Note on J185: ShudallK: Revsied 28/05/08
Note on J186: ShudallK: Revsied 28/05/08 See email AD to CB agreing v1 price
Note on J194: ShudallK: Amended 03/03/10
Note on J197: ShudallK: Updated 010709
Note on J200: ShudallK: updated 21/08/09
Note on E201: ShudallK: withdrawn 20/08/09 letter from BSC
Note on J202: ShudallK: Updated 110110
Note on L202: shudallk: Amended 131010
Note on J203: ShudallK: Updated 300709
Note on J204: shudallk: Final cost issued 150910
Note on J206: shudallk: Withdrawn 181010
Note on J207: ShudallK: amended 301009 Abortive costs submitted as not needed
Note on J209: ShudallK: Revised 241109
Note on M210: ShudallK: withdrawn 120310
Note on J211: ShudallK: updated 110110
Note on J212: ShudallK: Updated 1110110
Note on J214: ShudallK: Updated 110110
Note on L214: shudallk: Amended 271010
Note on J218: shudallk: Amended 25/03/10
Note on J220: ShudallK: Done at no cost 29/04/10
Note on J221: ShudallK: Updated 060410 & 200510 & 260810
Note on J223: shudallk: Updated 18/08/10
Note on J227: ShudallK: Updated 04/02/10
Note on J230: ShudallK: Updated 05/03/10 & 10/06/10
Note on L230: shudallk: updated 08/11/10
Note on J231: ShudallK: Updated 140110
Note on J232: ShudallK: Amended 12/02/10
Note on M232: Graham.Blades: ref DCO227
Note on J236: ShudallK: amended 12/02/10 Abortive costs
Note on J237: shudallk: Updated 140610
Note on J238: shudallk: Proforma update 230910
Note on J240: shudallk: updated 18/06/10
Note on J242: shudallk: Updated 010910
Note on M242: simon.nesbitt: Full scope of works not complete - as per Phoenix Agreement. Total amount due as per issue 5 of SDS Estimate (updated 26 Nov 2010). Additional monies within Phoenix for on site support that was not provided or requested.
Note on J243: shudallk: Updated 010910
Note on M243: simon.nesbitt: Full scope of works not complete - as per Phoenix Agreement. Total amount due as per issue 5 of SDS Estimate (updated 26 Nov 2010). Additional monies within Phoenix for on site support that was not provided or requested.
Note on J245: ShudallK: updated 060410
Note on J246: ShudallK: Updated 11/02/10
Note on J247: shudallk: not requried
Note on J249: shudallk: updated 12/05/10
Note on J252: Graham.Blades: £11509 agreed at commercial meeting 19/7/12
Note on R252: Graham.Blades: £11509 agreed at commercial meeting 19/7/12
Note on J260: ShudallK: amended 070410 & 160410
Note on M261: Graham.Blades: ref DCO227
Note on J263: shudallk: updated 20/05/10
Note on J266: shudallk: updated 050710
Note on J268: shudallk: Updated 110610 & 01/07/10
Note on J269: shudallk: updated 060710 reduced to 18490.80from 23114 to reflect HG Substation works not complete
Note on J270: shudallk: Updated 120710 & 140910
Note on L271: shudallk: Amended 08/10/10
Note on J272: shudallk: Asked to be split from DCR0248 19/05/10
Note on F278: shudallk: Final information not received until 160810
Note on J283: shudallk: updated 210910 & 180211
Note on J286: shudallk: updated 081110superseded by DCR0323
Note on M286: shudallk: superseded ref DCO227
Note on M287: Graham.Blades: refdco227 -30k
Note on J289: shudallk: updated 101110 & 280111
Note on J290: shudallk: updated 131010
Note on J291: Graham.Blades: 299,736 agreed at commercial meeting 19/7/12
Note on J292: Graham.Blades: 299,736 agreed at commercial meeting 19/7/12
Note on J294: shudallk: amended 081110
Note on J295: shudallk: Updated 270810
Note on J296: shudallk: Updated 270810
Note on J313: shudallk: updated 081110 & 030211
Note on J319: shudallk: updated 240511
Note on M322: shudallk: superseded
Note on J323: shudallk: 15.178.00 actual estimate - updated 270711
Note on J324: shudallk: 15.178.00 actual estimate - updated 270711
Note on J325: shudallk: 15.178.00 actual estimate - updated 270711
Note on J326: Graham.Blades: 6300 agreed at commercial meeting 19/7/12
Note on J329: shudallk: updated 061011
Note on J330: shudallk: updated 061011
Note on J331: shudallk: updated 061011
Note on J332: shudallk: updated 061011
Note on F336: shudallk: amended 171011
Note on J338: shudallk: updated 061011
Note on J339: shudallk: updated 061011
Note on J341: shudallk: udpated 061011
Note on J342: shudallk: amended 080911 & 061011
Note on J345: Graham.Blades: 1715 agreed at commercial 19/7/12
Note on M345: Graham.Blades: amended value as shutdown agreements
Note on M346: Graham.Blades: Vlaue amended as shutdown agreements
Note on J349: shudallk: revsied 141211
Note on M349: shudallk: revsied 141211
Note on U349: shudallk: revsied 141211
Note on J350: shudallk: revsied 141211
Note on M350: shudallk: revsied 141211
Note on U350: shudallk: revsied 141211
Note on J353: shudallk: updated 160112
Note on M353: shudallk: updated 160112
Note on H361: shudallk: amended 160112
Note on J364: shudallk: amended 100412
Note on J370: shudallk: amended 06/03/12
Note on J371: shudallk: amended 100412
Note on J378: shudallk: amended 170412
Note on J381: shudallk: issued 120412 no change
Note on K382: Constanze Gebauer - Bilfinger Construction UK: Main portion is with PMC170, waiting for final TCO
Note on M403: Graham.Blades: dcr-221-248-256-273-274-308a-308b-310-312-313.
Note on T405: simon.nesbitt: This is not a time sheet estimate.
Note on J408: simon.nesbitt: OLD VALUE - SUPERSEDED - NEW VALUE 25,455.00
Note on K410: Constanze Gebauer - Bilfinger Construction UK: Main portion is with PMC170, waiting for final TCO
Note on U410: Constanze Gebauer - Bilfinger Construction UK: plc check that the 7,010 from DCR0357 are not certified in hereagain
Note on K425: Constanze Gebauer - Bilfinger Construction UK: Main portion is with PMC170, waiting for final TCO
Note on K440: Constanze Gebauer - Bilfinger Construction UK: Main portion is with PMC170, waiting for final TCO